## Instructions and Descriptions
Project Elevation
High-Level Separation Workplan - Instructions, Descriptions, and Examples
Below are instructions for the high-level separation workplan template
This template comprises of three tabs: one focused a list of Day 1 projects, the second focused on capturing the tasks and milestones required to complete those projects, and final focused on capturing project-associated costs
1) Follow the directions in the light grey rows of example tables below. There is an example table for each of the three tabs; example line items are provided in italics.
2) This template is designed to be modular - if you need to create multiple Project Plan tabs to break up workplanning, please do so. Indicate your tab divisions by renaming the tab where it says "{Project}"
3) Please refer any questions to your separation counterpart or contact. Leverage your contact for help with submission and plan consolidation
| Day 1 Project List Tab | Orange fields due for completion by 4 December 2015
| Activity-Level Description | [14 empty] | Dependency Resolution Checklist
| Project ID (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | Day 1 Project Description | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with a workstream-defined three letter code for WS & SWS and a unique 3 digit code for the activity within | List the name of the Resource Unit, Function, or division acting as a workstream with the separation | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Provide a detailed description (what, why and where) of the Day 1 Project | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Provide the date by which this project must be completed | Provide an estimate of the number of calendar days it will take to complete the entire project | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the project is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
x | HRD-LRL-001 | Human Resources | Labor Relations | French Works Council Approval | Adjusting organizations in France requires gaining approval from the Works Council via a formal proposal | Both | 2016-06-01 | 132 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Will require input from X, Y, and Z | [27 empty] | 2016-01-15
| HRD-LRL-002 | Human Resources | Labor Relations | German Works Council Approval | Adjusting organizations in Germany requires gaining approval from the Works Council via a series of formal meetings | Both | 2016-06-01 | 102 | 2016-02-20 | 0% | FALSE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Will require input from X, Y, and Z | [27 empty] | 2015-10-31
| Project Plan Tab | Fields due for completion by 17 December 2015
| Task-Level Description | [14 empty] | Dependency Resolution Checklist
| Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with workstream-defined three letter code for SWS, the unique 3 digit code for the activity, and a two digit code for the task | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Identify the name of the task that must be done to complete the project. Only list one task per row | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Mark whether or not this task is a milestone for a project. Milestones are the most critical tasks within a project, which are often time-sensitive. | Provide the date by which this task must be completed | Provide an estimate of the number of calendar days it will take to complete the entire task | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the task is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, important subtasks that must be captured, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
| LRL-001-01 | Labor Relations | French Works Council Approval | -Draft Proposal | Both | FALSE | 2016-02-20 | 30 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-001-02 | Labor Relations | French Works Council Approval | -Submit Proposal | Both | TRUE | 2016-03-01 | 10 | 2016-02-20 | 0% | FALSE |  | Dominique Bordeaux | Not Started
| LRL-001-03 | Labor Relations | French Works Council Approval | -Follow up after 3 months | Both | FALSE | 2016-06-01 | 90 | 2016-03-03 | 0% | FALSE |  | Dominique Bordeaux | Not Started
x | LRL-002-01 | Labor Relations | German Works Council Approval | -Draft Proposal | Both | FALSE | 2016-03-20 | 30 | 2016-02-19 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-002-02 | Labor Relations | German Works Council Approval | -Submit Proposal | Both | TRUE | 2016-04-01 | 10 | 2016-03-22 | 0% | FALSE |  | Petra Schmidt | Not Started
| LRL-002-03 | Labor Relations | German Works Council Approval | -Follow up after 2 months | Both | FALSE | 2016-06-01 | 60 | 2016-04-02 | 0% | FALSE |  | Petra Schmidt | Not Started
Project Costs Tab
| Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale
| Provide the unique ID for the project defined on the Day 1 Projects tab | Provided the name of the Day 1 project defined on the Day 1 Projects tab | Provide a description of what the cost is and why it exists | Indicate if this cost is a dis-synergy (incl stranded cost) (True/False) | Indicate if this cost is a one-time cost (True/False) | Indicate who will own the plan to minimize and address this cost | Provide an estimated cost for all or part of this Day 1 Project | Briefly describe rationale (business case) for cost estimate
| HRD-LRL-002 | German Works Council Approval | Lobbying - Gaining approval often requires spending money to lobby key officials | No | Yes | Peter Schmidt | 10000 | Spending this money will reduce risk and speed transition for German Org
x
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Instructions and Descriptions'!$[Required Completion Date]),"",'Instructions and Descriptions'!$[Required Completion Date]-'Instructions and Descriptions'!$[Days to Accomplish])

## Day 1 Project List_IK
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Projects
| As Of | 2016-02-15 14:00
| Project-Level Description | [16 empty] | Dependency Resolution Checklist
Project Number | Project ID Blueprint # (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | In scope sub processes | Day 1 Project Description | Country of Service Delivery | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) PLEASE INSERT DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | Total # Tasks in Project | Start Date Review | Completion Date Review | % Complete Progression Review | % Tasks for Review | Off Track or at risk
EFAS01 | 2,19,38,44 | GSS | Istvan Katus_Finance | EFAS01_Accounts Payable | - Invoice entry, processing RDE failed resolution - Invoice Indexing - Statement Review - Account reconciliation for AP - Due and unpaid invoice report review - Payment processing, run payment cycles - Potential duplicate payment control - Subledger clos | Establish organization structure, establish IT systems (incl. IIPS (eFlow, Basware); Payload etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Australia, Europe, US, Russia | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system, infrastucture, applications, Alcoa Direct etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Procurement - purchase licenses by 3/1/2016; renew 3rd party contracts (DLM, Doqsys, ACS, Westnet, Ariba/B2B, Wallmedien, AP Recovery audit) by 6/30/2016, new postal boxes by 6/30/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - bank account openings, setting up approvers, register them in banks and get tokens, check setup by 4/30/2016 GSS - employee setups by 5/31/2016 | Anikó Krizsány | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 |  | 2016-05-31 |  | 2016-01-03 | [22 empty] | 29 | - | REVIEW | REVIEW | - | -
EFAS02 | 12, 46 | GSS | Istvan Katus_Finance | EFAS02_AR_CAN_USA | - Daily revenue control and reconciliation - Problem solving - Misc. Invoicing process - Create and post invoices - PC&E - AR reconciliation - Cash application - Reconciliation of Receivables Accounts | Establish organization structure, establish IT systems (incl. Oracle, JDE, Discoverer etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Canada, US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oarcle and JDE), infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - bank account openings, setting up approvers, register them in banks and get access to Locboxes by 4/30/2016 GSS - lockbox setups, etc. by 4/30/2016 GSS - close cooperation with Hank's and Alain's teams | Judit Antli | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 |  | 3/1/2016 | [24 empty] | 20 | - | REVIEW | REVIEW | - | -
EFAS03 | 21 | GSS | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | - Collection files, cash collection via draft and direct debit - Daily cash control & cash application - Control reports and AR sub-ledger closing - Process misdirected payments - Cross payment, customer refund - Manual invoicing - Daily revenue control and reconciliation - Problem solving - Reconciliation of Receivables Accounts | Establish organization structure, establish IT systems (incl. Oracle, Discoverer, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oarcle), infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - bank account openings, setting up approvers, register them in banks and get tokens by 4/30/2016 | Judit Antli | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 | [26 empty] | 21 | - | REVIEW | REVIEW | - | -
EFAS04 | 14, 26, 51 | GSS | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | - Compliance testing on behalf of location - ASAT management - Consultancy on compliance - Ensure SOX compliance of locations over thorough testing | Establish organization structure, establish IT systems (incl. copy Brazil tool, mailboxes, ASP system, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Canada, Europe, US | Both | 2016-07-31 | 60 | 2016-06-01 | 10% | TRUE | IT - ERP system, infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 ASP system - replicate system by 6/1/2016 Brazil tool - replicate the tool by 7/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Treasury - setting up approvers, register them in banks and get tokens by 4/30/2016 GSS - decisions on how the process will change for central CAN/US ASAT testings by 4/30/2016 | Ágota Vízkeleti | On Track |  |  |  | 2016-04-30 |  |  | 2016-01-01 |  | 2016-04-30 | [24 empty] | 31 | REVIEW | REVIEW | - | - | -
EFAS05 | 47 | GSS | Istvan Katus_Finance | EFAS05_Cost Accounting | - Monthly cost Build activities - Monthly inventory org maintenance activities - Accounting activities, cost rollup, analyse cost variance, inventory account reconciliation - Support plants in new process - Support plants in reconciliation annual physical inventory - Maintenance Setup in OPM - Maintaining procedures and performing ASAT processing and testing - Participating in all tests related to system upgrade/enhancements - Work with Locations on problem solving (onsite) - Expertise assistance (investigations) | Establish organization structure, establish IT systems (incl. Oacle, JDE, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | US | Both | 2016-07-31 | 90 | 2016-05-02 | 5% | TRUE | IT - ERP system ( Oracle, JDE) , infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 GSS - close cooperation with Hank's teams | Judit Antli | On Track |  | 2016-02-28 |  |  |  |  | 2016-01-01 |  | x | [25 empty] | REVIEW | REVIEW | - |  | -
EFAS06 | 3 | GSS | Istvan Katus_Finance | EFAS06_FAPA_AUS | - CWIP reporting, problem solving with locations - CWIP reconciliation - FA account reconciliation per fiscal - Depreciation forecast for locations - PPR, IR management - eRFA system support and helpdesk function - Sub-ledger closing - Asset categorization for capitalization - Inventory support - Year end tax reporting - Porcess JV special entries - Maintain assets as per US and Local Tax, Gaap | Establish organization structure, establish IT systems (incl. Oracle, Discoverer, eRFA, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Australia | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oracle), infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 eRFA system - ready by 3/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 GSS - close cooperation with Tonya's teams | Judit Antli | On Track |  | 2016-02-28 |  |  |  |  | 2016-01-01 |  | x | [24 empty] | 12 | - | REVIEW | REVIEW | - | -
EFAS07 | 11, 45 | GSS | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | - CWIP reporting, problem solving with locations - CWIP reconciliation - FA account reconciliation per fiscal - Depreciation forecast for locations - PPR, IR management - eRFA system support and helpdesk function - Sub-ledger closing - MRC transactions in two currencies - MRC reconciliation - Fair value maintenance - Asset categorization for capitalization - Maintain assets as per US and Local Tax, Gaap | Establish organization structure, establish IT systems (incl. Oracle, Discoverer, eRFA, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Canada, US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oracle) , infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 eRFA system - ready by 3/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 GSS - close cooperation with Hank's and Alain's teams | Judit Antli | On Track |  | 2016-02-28 |  |  |  |  | 2016-01-01 |  | x | [24 empty] | 17 | - | REVIEW | REVIEW | - | -
EFAS08 | 20, 39 | GSS | Istvan Katus_Finance | EFAS08_FAPA_EU | - CWIP reporting, problem solving with locations - CWIP reconciliation - FA account reconciliation per fiscal - Depreciation forecast for locations - PPR, IR management - eRFA system support and helpdesk function - Sub-ledger closing - Multi currency asset maintenance - Preparation of movement table - GPP step-up value maintenance - Inventory support - Year end tax reporting - Maintain assets as per US and Local Tax, Gaap | Establish organization structure, establish IT systems (incl. Oracle, Discoverer, eRFA, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe, Russia | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oracle), infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 eRFA system - ready by 3/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 | Judit Antli | On Track |  | 2016-02-28 |  |  |  |  | 2016-01-01 | [26 empty] | 18 | - | REVIEW | REVIEW | - | -
EFAS09 | 23 | GSS | Istvan Katus_Finance | EFAS09_Finance System Support | - Remedy ticket resolution (incl. problem resolution and/or acting as SPA if IT is resolving the problem) - BPO type of work: approvals, SOD, customization, enhancements) - Testing (dev or CRP) - Closing support - SR / Oracle coordination - Project type o | Establish organization structure, establish IT systems, replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system, infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Procurement - purchase licenses by 3/1/2016 | Ágota Vízkeleti | On Track |  |  | x |  |  |  | 2016-01-01 |  |  |  | 2016-03-01 | [20 empty] | x | Oracle, DLM, Doqsys, Banks | 23 | - | REVIEW | REVIEW | REVIEW | -
EFAS10 | 10, 43 | GSS | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | - Pre-closing activities - Manual Journal Entry creation ( recurring , accruals, other normal entries) - JE Review and posting - FET upload, Interface correction - Payroll posting - HC upload - Bad debt reserve calculation and booking - Period end closing - Budget reporting - Interco receiver offset coding - Location accountant type of activities - Account reconciliation, Review and Approval - BU accountant related tasks – taken over from SSC – value add activity | Establish organization structure, establish IT systems (incl. Oracle, Discoverer, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Canada, US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oracle), infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 GSS - close cooperation with Hank's and Alain's teams | Judit Antli | On Track |  | 2016-02-28 |  |  |  |  | 2016-01-01 |  | x | [24 empty] | 24 | - | REVIEW | REVIEW | - | -
EFAS11 | 18 | GSS | Istvan Katus_Finance | EFAS11_General Ledger_EU | - Rate upload - Book and reconcile bank entries - Book and reconcile Treasury transactions - Split, Book and reconcile zero balance transactions - Cash exposure reports for Treasury - US GAAP adjustments creation and postings - Pre-closing activities - Payroll Accounting - Manual Journal Entry creation ( recurring , accruals, other normal entries) - Payload entries - HC entries - JE Review and posting - Maintain fiscal mapping - FET upload, Interface correction - Bad debt reserve calculation and booking - Fiscal consolidation - Period end closing - Account reconciliation, Review and Approval - Year end closing - Execute tests ( Patch, upgrade, system changes) and evaluate test result | Establish organization structure, establish IT systems (incl. Oracle, Discoverer, etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system ( Oracle), infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - bank account openings, setting up approvers, register them in banks and get tokens by 4/30/2016 | Judit Antli | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 | [26 empty] | 19 | - | REVIEW | REVIEW | - | -
EFAS12 | 7, 33 | GSS | Istvan Katus_Finance | EFAS12_IICS | - control high value ledger to ledger Interco variances - Financial closing activities - Global AR & Global AP reconciliation, control - Supervision of Interco Cash clearing Account - Calculate and Book FX rate effect on Interco netting - on-board new implementations for acquired companies, manage divestiture related activities | Establish organization structure, establish IT systems, replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Australia, Europe | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system, infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - Sungard netting (Quantum) by 3/1/2016 GSS - close cooperation with all regional teams | Anikó Krizsány | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 |  | x | [24 empty] | 15 | - | REVIEW | REVIEW | - | -
EFAS13 | 5,8,16,31,35,36,41,53 | GSS | Istvan Katus_Finance | EFAS13_Master Data Management | - BPO responsibilities: Item, Vendor Master - Item set-up - Vendor set-up - Alcoa-direct administration - supplier type and SCO governance - administration of supplier risk management (TRACE project) - supplier safety qualification | Establish organization structure, establish IT systems (incl. VEAT, Keep it Common, AlcoaDirect, SRS etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Australia, Brazil, Canada, Europe,China, Mexico, Russia, US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system, infrastucture, applications, VEAT, Keep It Common, Alcoa Direct, SRS Tool etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 GSS - close cooperation with all regional teams | Nóra Lukács | On Track | [6 empty] | 2016-01-01 |  | x | [24 empty] | 28 | - | REVIEW | REVIEW | - | -
EFAS14 | 29,52 | GSS | Istvan Katus_Finance | EFAS14_Process Support | - process improvements - Payment related approvals - Operation Support (closing Support, Problem solving) - process ASATs testing | Establish organization structure, establish IT systems, replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe, US | Both | 2016-07-31 | 60 | 2016-06-01 | 15% | TRUE | IT - ERP system, infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Treasury - setting up approvers, register them in banks and get tokens by 4/30/2016 | Ágota Vízkeleti | On Track |  |  |  | 2016-04-30 |  |  | 2016-01-01 | [26 empty] | 3 | REVIEW | REVIEW | - | REVIEW | -
EFAS15 | 6, 32 | GSS | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | - Accounting activities of TBO - FX trxs with external partners, deal creation - complete Alcoa compensation process - Setup and maintenance of Quantum, netting center - Problem solving - Monitor Interco loans - Create and Monitor metal related and FX ccy hedging - daily Cash & liquidity management | Establish organization structure, establish IT systems, replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Australia, Europe | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | IT - ERP system, infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - bank account openings, setting up approvers, register them in banks and get tokens by 4/30/2016, Sungard netting (Quantum) by 3/1/2016 GSS - close cooperation with all regional teams | Anikó Krizsány | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 |  | x | [24 empty] | 17 | - | REVIEW | REVIEW | REVIEW | -
EFAS16 | 22, 48 | GSS | Istvan Katus_Procurement Services | EFAS16_PSC | - Purchase order processing - Change order processing - Purchase order maintenance - Purchase agreement maintenance - Delivery management/ expediting - Alloy planning activities - Alloy ordering administration - Prime metal purchasing Support - GRP scrap purchasing Support - EKAER control - Central IT leasing activities - GPP metal control administration | Establish organization structure, establish IT systems (incl. MSIS, B2B/Ariba etc), replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe, US | Both | 2016-07-31 | 120 | 2016-04-02 | 5% | TRUE | IT - ERP system, infrastucture, applications, VEAT, Keep It Common, MSIS, B2B/Ariba, Alcoa Mall, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 GSS - employee setups by 5/31/2016 | Nóra Lukács | On Track | [6 empty] | 2016-01-01 |  | 2016-05-31 | [24 empty] | 22 | REVIEW | REVIEW | - | - | -
EFAS17 | 25, 50 | GSS | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | - report design - run reports manually / automatically - report automation | Establish organization structure, establish IT systems, replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe, US | Both | 2016-07-31 | 90 | 2016-05-02 | 5% | TRUE | IT - ERP system, infrastucture, applications etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Procurement - purchase licenses (AutoMate, Visual Studio) by 3/1/2016 Treasury - setting up approvers, register them in banks and get tokens by 4/30/2016 | Ágota Vízkeleti | On Track |  |  |  | 2016-04-30 |  |  | 2016-01-01 |  |  |  | 2016-03-01 | [22 empty] | 21 | REVIEW | REVIEW | - | - | -
EFAS18 | 24, 49 | GSS | Istvan Katus_Finance | EFAS18_T&E | - Credit card administration - annual reconciliation - T&E audit - Customer service desk - Escalation management - LVP admin | Establish organization structure, establish IT systems, replicate processes to create a like for like service offering to both companies by creating procedures, renewing SLAs and training employees. Reassign responsibilities according to new roles. | Europe, US | Both | 2016-07-31 | 90 | 2016-05-02 | 5% | TRUE | IT - ERP system, infrastucture, applications, etc. - decision required by 1/1/2016, testing schedule to be provided by 1/31/2016, test environment ready by 3/1/2016, established live production system by 8/1/2016 GSS Mgmt - decision on communicating the new org structure to staff by 2/1/2016 Procurement - renew 3rd party contracts (Agencia, AMEX, Concur, Citibank, LVP, Meridian) by 6/30/2016 Finance - define/request new LBC structure by 2/28/2016 Treasury - bank account openings by 4/30/2016 GSS - employee setups by 5/31/2016 | Anikó Krizsány | On Track |  | 2016-02-28 |  | 2016-04-30 |  |  | 2016-01-01 |  | 2016-05-31 |  | 2016-06-30 | [22 empty] | 27 | REVIEW | REVIEW | - | - | -
EFAS19 | N/A | GSS | Transformation_Facilities | EFAS19_Shared Facilities | Physical location of office and all supporting infrastructure | Project to address all infrastructure to support both orgs | Europe | Both | 2016-07-31 | 120 | 2016-04-02 | 5% | TRUE | Facilities IT | Lisa Marie | <Select> | [6 empty] | 2/28/2016 | [8 empty] | 2016-01-31 | [18 empty] | REVIEW | REVIEW | - |  | -
[51 empty] | - | - |  |  | -
[51 empty] | - | - |  |  | -
[51 empty] | - | - |  |  | -
[51 empty] | - | - |  |  | -
[51 empty] | - | - |  |  | -
[51 empty] | - | - |  |  | -
[51 empty] | - | - |  |  | -
x
Formulas:
Start Date (Calculated) = IF(ISBLANK(ProjectsTable[[#This Row],[Required Completion Date]]),"",ProjectsTable[[#This Row],[Required Completion Date]]-ProjectsTable[[#This Row],[Days to Accomplish]])
Start Date Review = IFERROR(IF(ProjectsTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF(ProjectsTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")

## Risk Register_IK
To be filled out by Lisa in PMO
Date risk recorded | Project Number | Day 1 Project Name | Sub-Workstream (SWS) | Related project Task ID(s) | Risk Title | Mitigating Action(s) | Probability of occurance (0-100%) 0% being less probable | Degree of Impact (1-10) 1 being low impact | Risk rating (Probability x Impact) | For discussion in GSS PMO? (Y/N) | Status | Weekly Status Comments (enter date DD-MON-YYYY (06-JAN-2016) then comment) | Person recording risk (Last name, First name) | Date Reviewed in PMO DD-MON-YYYY (06-JAN-2016) | Track in Deloitte tool? | SPO escalation?
2016-01-14 | All | All | All | All | Risk of system clones not completing on time and delaying integrated functional testing (data, applications, interfaces) and remediation. | Participate with GIS, and deliver needed inputs and knowledge…prepare for timely and thorough testing. | 75% | 10 | 7.5 | Y | OnTrack |  | Vízkeleti, Ágota |  | <Select> | <Select>
2016-01-14 | All | All | All | All | Need to ensure sufficient testing resources are in place to support functional testing. Extra resources need to be brought with proper lead time so as to be productive during testing and remediation. | Resources for growth/sweeps need to be hired earlier so that we have resources freed up for testing. | 50% | 9 | 4.5 | Y | OnTrack |  | Vízkeleti, Ágota |  | Y | N
2016-01-18 | All | All | All | All | Risk of filling dis-synergie positions too late. There are a number of key open positions, where we need to start hiring asap. E.g. Payment team member, US-AUS-CAN AP Team Lead, Functional Support PO/Inv, TBO team members | Discuss whether we can start posting jobs and seeking for candidates. Need approval for these positions asap. | 50% | 9 | 4.5 | Y | OnTrack |  | Vízkeleti, Ágota |  | Y | N
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>

## Project Plan(s) - {IK}
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
|  | As Of | 2016-02-15 14:00
|  | Task-Level Description | [15 empty] | Dependency Resolution Checklist
| Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) PLEASE INSERTE DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours | Category | Jan | Feb | Mar | April | May | June | July | August | Sept | Oct | TOTAL | Start Date Review | Completion Date Review | % Complete Progression Review
5 | EFAS16 | EFAS16_EFAS16_PSC_5 | Istvan Katus_Procurement Services | EFAS16_PSC | Review knowledge base of the team members | Both | FALSE |  | 2016-01-31 | 27 | 2016-01-04 | 100% | FALSE |  | Nóra Lukács | Complete | [33 empty] | Review | 15 | PSC Team |  |  |  | Training | 15 | [9 empty] | 15 | - | - | REVIEW
6 | EFAS16 | EFAS16_EFAS16_PSC_6 | Istvan Katus_Procurement Services | EFAS16_PSC | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-01-31 | 27 | 2016-01-04 | 100% | FALSE |  | Nóra Lukács | Complete | [33 empty] | Review | 48 | PSC Team |  |  |  | Training | 48 | [9 empty] | 48 | - | - | REVIEW
8 | EFAS16 | EFAS16_EFAS16_PSC_8 | Istvan Katus_Procurement Services | EFAS16_PSC | Review existing documents and create new ones if needed (Procedures, Wis, SLAs) | Both | FALSE |  | 2016-03-31 | 87 | 2016-01-04 | 25% | FALSE |  | Nóra Lukács | On Track | [33 empty] | No Review | 80 | PSC Team |  |  |  | Training | 26 | 27 | 27 | [7 empty] | 80 | - | REVIEW | REVIEW
14 | EFAS16 | EFAS16_EFAS16_PSC_14 | Istvan Katus_Procurement Services | EFAS16_PSC | Create training plans (training materials) for each areas - who, whom, what, when | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 50% | FALSE |  | Nóra Lukács | On Track | [33 empty] | No Review | 8 | PSC Team |  |  |  | Training | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
16 | EFAS16 | EFAS16_EFAS16_PSC_16 | Istvan Katus_Procurement Services | EFAS16_PSC | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 2 | PSC Team |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
21 | EFAS16 | EFAS16_EFAS16_PSC_21 | Istvan Katus_Procurement Services | EFAS16_PSC | Review and finalize US PSC structure and responsibilities | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Cooperation with US Buy.Pay | Nóra Lukács | Not Started | [8 empty] | 2016-03-31 | [24 empty] | No Review | 4 | PSC Team |  |  |  | Training |  |  | 4 | [7 empty] | 4 | REVIEW | REVIEW | -
22 | EFAS16 | EFAS16_EFAS16_PSC_22 | Istvan Katus_Procurement Services | EFAS16_PSC | Start the hiring process based on approved future org charts, including approved dis-synergie positions and new positions due to scope add | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Nóra Lukács | Not Started | GSS management needs to approve | [7 empty] | 2016-02-15 | [24 empty] | Review | 8 | PSC Team |  |  |  | Training |  | 8 | [8 empty] | 8 | - | - | REVIEW
23 | EFAS16 | EFAS16_EFAS16_PSC_23 | Istvan Katus_Procurement Services | EFAS16_PSC | Request shared mailboxes | Up. Co. | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | TRUE | IT Infrastructure have to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-04-01 | [26 empty] | No Review | 8 | PSC Team |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
24 | EFAS16 | EFAS16_EFAS16_PSC_24 | Istvan Katus_Procurement Services | EFAS16_PSC | Training - CCM | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 40 | PSC Team |  |  |  | Training |  |  |  | 40 | [6 empty] | 40 | REVIEW | REVIEW | -
25 | EFAS16 | EFAS16_EFAS16_PSC_25 | Istvan Katus_Procurement Services | EFAS16_PSC | Training - Spec/Extra | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 270 | PSC Team |  |  |  | Training |  |  | 150 | 120 | [6 empty] | 270 | REVIEW | REVIEW | -
26 | EFAS16 | EFAS16_EFAS16_PSC_26 | Istvan Katus_Procurement Services | EFAS16_PSC | Training - US (CTT, OTD, PO) | Both | FALSE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 150 | PSC Team |  |  |  | Training |  |  |  | 70 | 80 | [5 empty] | 150 | REVIEW | REVIEW | -
27 | EFAS16 | EFAS16_EFAS16_PSC_27 | Istvan Katus_Procurement Services | EFAS16_PSC | Identify system testers | Both | FALSE |  | 2016-04-15 | 14 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 2 | PSC Team |  |  |  | Testing |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
28 | EFAS16 | EFAS16_EFAS16_PSC_28 | Istvan Katus_Procurement Services | EFAS16_PSC | Request responsibilities, accesses for the users | Both | FALSE |  | 2016-04-25 | 10 | 2016-04-15 | 0% | TRUE | Test systems have to be available | Nóra Lukács | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | 8 | PSC Team |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
29 | EFAS16 | EFAS16_EFAS16_PSC_29 | Istvan Katus_Procurement Services | EFAS16_PSC | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-05-27 | [26 empty] | No Review | 140 | PSC Team |  |  |  | Testing |  |  |  | 70 | 70 | [5 empty] | 140 | REVIEW | REVIEW | -
31 | EFAS16 | EFAS16_EFAS16_PSC_31 | Istvan Katus_Procurement Services | EFAS16_PSC | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 358 | PSC Team |  |  |  | Testing |  |  |  |  | 80 | 250 | 28 |  |  |  | 358 | REVIEW | REVIEW | -
32 | EFAS16 | EFAS16_EFAS16_PSC_32 | Istvan Katus_Procurement Services | EFAS16_PSC | Management Knowledge transfer (ASAT, approvals etc) | Both | FALSE |  | 2016-07-15 | 44 | 2016-06-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 48 | PSC Team |  |  |  | Training | [5 empty] | 35 | 13 |  |  |  | 48 | REVIEW | REVIEW | -
| EFAS16 | EFAS16_EFAS16_PSC_ | Istvan Katus_Procurement Services | EFAS16_PSC | CPA/BPA conversion in relation to the OU split in Italy | V-A Co. | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | TRUE | New OU needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-06-15 | [26 empty] | No Review | 56 | PSC Team |  |  |  | System config | [5 empty] | 56 |  |  |  |  | 56 | REVIEW | REVIEW | -
| EFAS16 | EFAS16_EFAS16_PSC_ | Istvan Katus_Procurement Services | EFAS16_PSC | Open Order conversion in relation to the OU split in Italy | V-A Co. | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | TRUE | New OU needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-06-15 | [26 empty] | No Review | 90 | PSC Team |  |  |  | System config | [5 empty] | 90 |  |  |  |  | 90 | REVIEW | REVIEW | -
33 | EFAS16 | EFAS16_EFAS16_PSC_33 | Istvan Katus_Procurement Services | EFAS16_PSC | Review responsibilites and accessses | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Production systems have to be available | Nóra Lukács | Not Started | [6 empty] | 2016-07-15 | [26 empty] | No Review | 8 | PSC Team |  |  |  | Training | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
| EFAS16 | EFAS16_EFAS16_PSC_ | Istvan Katus_Procurement Services | EFAS16_PSC | Duplicate shared drives and move historical data to the appropriate company | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT infrastructure needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-07-01 | [26 empty] | No Review | 80 | PSC Team |  |  |  | System config | [6 empty] | 80 |  |  |  | 80 | REVIEW | REVIEW | -
35 | EFAS16 | EFAS16_EFAS16_PSC_35 | Istvan Katus_Procurement Services | EFAS16_PSC | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | PSC Team |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
5 | EFAS13 | EFAS13_EFAS13_Master Data Management_5 | Istvan Katus_Finance | EFAS13_Master Data Management | Review knowledge base of the team members | Both | FALSE |  | 2016-01-31 | 27 | 2016-01-04 | 100% | FALSE |  | Nóra Lukács | Complete | [33 empty] | Review | 15 | MDM Team |  |  |  | Training | 15 | [9 empty] | 15 | - | - | REVIEW
6 | EFAS13 | EFAS13_EFAS13_Master Data Management_6 | Istvan Katus_Finance | EFAS13_Master Data Management | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-01-31 | 27 | 2016-01-04 | 100% | FALSE |  | Nóra Lukács | Complete | [33 empty] | Review | 36 | MDM Team |  |  |  | Training | 36 | [9 empty] | 36 | - | - | REVIEW
8 | EFAS13 | EFAS13_EFAS13_Master Data Management_8 | Istvan Katus_Finance | EFAS13_Master Data Management | Review existing documents and create new ones if needed (Procedures, WIs, SLAs) | Both | FALSE |  | 2016-03-31 | 87 | 2016-01-04 | 25% | FALSE |  | Nóra Lukács | On Track | [33 empty] | No Review | 80 | MDM Team |  |  |  | Training | 26 | 27 | 27 | [7 empty] | 80 | - | REVIEW | REVIEW
14 | EFAS13 | EFAS13_EFAS13_Master Data Management_14 | Istvan Katus_Finance | EFAS13_Master Data Management | Create training plans (training materials) for each areas - who, whom, what, when | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 50% | FALSE |  | Nóra Lukács | On Track | [33 empty] | No Review | 16 | MDM Team |  |  |  | Training | 8 | 8 | [8 empty] | 16 | - | - | REVIEW
16 | EFAS13 | EFAS13_EFAS13_Master Data Management_16 | Istvan Katus_Finance | EFAS13_Master Data Management | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 2 | MDM Team |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
19 | EFAS13 | EFAS13_EFAS13_Master Data Management_19 | Istvan Katus_Finance | EFAS13_Master Data Management | Integrate TRAC process into Upstream supplier maintenance process | Up. Co. | FALSE |  | 2016-02-29 | 28 | 2016-02-01 | 5% | FALSE |  | Nóra Lukács | On Track | [33 empty] | No Review | 32 | MDM Team |  |  |  | Training |  | 32 | [8 empty] | 32 | - | REVIEW | REVIEW
20 | EFAS13 | EFAS13_EFAS13_Master Data Management_20 | Istvan Katus_Finance | EFAS13_Master Data Management | Integrate VAT and TAX ID change process into Upsteam supplier maintenance process | Up. Co. | FALSE |  | 2016-02-29 | 28 | 2016-02-01 | 5% | FALSE |  | Nóra Lukács | On Track | [33 empty] | No Review | 32 | MDM Team |  |  |  | Training |  | 32 | [8 empty] | 32 | - | REVIEW | REVIEW
22 | EFAS13 | EFAS13_EFAS13_Master Data Management_22 | Istvan Katus_Finance | EFAS13_Master Data Management | Start the hiring process based on approved future org charts, including approved dis-synergie positions and new positions due to scope add | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Nóra Lukács | Not Started | GSS management needs to approve | [7 empty] | 2016-02-15 | [24 empty] | Review | 8 | MDM Team |  |  |  | Training |  | 8 | [8 empty] | 8 | - | - | REVIEW
24 | EFAS13 | EFAS13_EFAS13_Master Data Management_24 | Istvan Katus_Finance | EFAS13_Master Data Management | Identify system testers | Up. Co. | FALSE |  | 2016-04-15 | 14 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 2 | MDM Team |  |  |  | Testing |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
25 | EFAS13 | EFAS13_EFAS13_Master Data Management_25 | Istvan Katus_Finance | EFAS13_Master Data Management | Request shared mailboxes | Up. Co. | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | TRUE | IT Infrastructure have to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-04-01 | [26 empty] | No Review | 8 | MDM Team |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
26 | EFAS13 | EFAS13_EFAS13_Master Data Management_26 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - AU Supplier Maintenance | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 70 | MDM Team |  |  |  | Training |  |  |  | 70 | [6 empty] | 70 | REVIEW | REVIEW | -
27 | EFAS13 | EFAS13_EFAS13_Master Data Management_27 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - EU Customer Maintenance | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 96 | MDM Team |  |  |  | Training |  |  |  | 96 | [6 empty] | 96 | REVIEW | REVIEW | -
28 | EFAS13 | EFAS13_EFAS13_Master Data Management_28 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - AU Credit Limit Updates | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 32 | MDM Team |  |  |  | Training |  |  |  | 32 | [6 empty] | 32 | REVIEW | REVIEW | -
29 | EFAS13 | EFAS13_EFAS13_Master Data Management_29 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - SCO/Supplier Type assignment task | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 70 | MDM Team |  |  |  | Training |  |  |  | 70 | [6 empty] | 70 | REVIEW | REVIEW | -
30 | EFAS13 | EFAS13_EFAS13_Master Data Management_30 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - EHS Prequalification, Supplier Evaluation, Energy Certificates, Att. De Vigilance etc. Processes | Both | FALSE |  | 2016-04-30 | 29 | 2016-04-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 70 | MDM Team |  |  |  | Training |  |  |  | 70 | [6 empty] | 70 | REVIEW | REVIEW | -
31 | EFAS13 | EFAS13_EFAS13_Master Data Management_31 | Istvan Katus_Finance | EFAS13_Master Data Management | Request responsibilities, accesses for the users | Up. Co. | FALSE |  | 2016-04-25 | 10 | 2016-04-15 | 0% | TRUE | Test systems have to be available | Nóra Lukács | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | 8 | MDM Team |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
32 | EFAS13 | EFAS13_EFAS13_Master Data Management_32 | Istvan Katus_Finance | EFAS13_Master Data Management | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Nóra Lukács | Not Started | [33 empty] | No Review | 230 | MDM Team |  |  |  | Testing |  |  |  | 100 | 130 | [5 empty] | 230 | REVIEW | REVIEW | -
33 | EFAS13 | EFAS13_EFAS13_Master Data Management_33 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - EU Supplier Maintenance | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 100 | MDM Team |  |  |  | Training |  |  |  |  | 100 | [5 empty] | 100 | REVIEW | REVIEW | -
34 | EFAS13 | EFAS13_EFAS13_Master Data Management_34 | Istvan Katus_Finance | EFAS13_Master Data Management | Define employees according to new approval hierarchy | Up. Co. | FALSE |  | 2016-05-31 | 20 | 2016-05-11 | 0% | TRUE | Information required from new departments | Nóra Lukács | Not Started | [8 empty] | 2016-05-11 | [24 empty] | No Review | 100 | MDM Team |  |  |  | Training |  |  |  |  | 100 | [5 empty] | 100 | REVIEW | REVIEW | -
35 | EFAS13 | EFAS13_EFAS13_Master Data Management_35 | Istvan Katus_Finance | EFAS13_Master Data Management | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 358 | MDM Team |  |  |  | Testing |  |  |  |  | 80 | 250 | 28 |  |  |  | 358 | REVIEW | REVIEW | -
36 | EFAS13 | EFAS13_EFAS13_Master Data Management_36 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - EU Hierarchy Setups | Both | FALSE |  | 2016-06-30 | 29 | 2016-06-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 48 | MDM Team |  |  |  | Training | [5 empty] | 48 |  |  |  |  | 48 | REVIEW | REVIEW | -
37 | EFAS13 | EFAS13_EFAS13_Master Data Management_37 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - NA Hierarchy Setups | Both | FALSE |  | 2016-06-30 | 29 | 2016-06-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 32 | MDM Team |  |  |  | Training | [5 empty] | 32 |  |  |  |  | 32 | REVIEW | REVIEW | -
38 | EFAS13 | EFAS13_EFAS13_Master Data Management_38 | Istvan Katus_Finance | EFAS13_Master Data Management | Training - integrated TRAC Process | Both | FALSE |  | 2016-06-30 | 29 | 2016-06-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 48 | MDM Team |  |  |  | Training | [5 empty] | 48 |  |  |  |  | 48 | REVIEW | REVIEW | -
39 | EFAS13 | EFAS13_EFAS13_Master Data Management_39 | Istvan Katus_Finance | EFAS13_Master Data Management | Management Knowledge transfer (ASAT, approvals etc) | Both | FALSE |  | 2016-07-15 | 44 | 2016-06-01 | 0% | FALSE |  | Nóra Lukács | Not Started | [33 empty] | No Review | 36 | PSC Team |  |  |  | Training | [5 empty] | 25 | 11 |  |  |  | 36 | REVIEW | REVIEW | -
40 | EFAS13 | EFAS13_EFAS13_Master Data Management_40 | Istvan Katus_Finance | EFAS13_Master Data Management | Review responsibilites and accessses | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Production systems have to be available | Nóra Lukács | Not Started | [6 empty] | 2016-07-15 | [26 empty] | No Review | 8 | MDM Team |  |  |  | Training | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
41 | EFAS13 | EFAS13_EFAS13_Master Data Management_41 | Istvan Katus_Finance | EFAS13_Master Data Management | Communication to Suppliers/customers of new LE's (Bankaccount, VAT, New PO numbers, AlcoaDirect etc.) | Both | FALSE |  | 2016-09-15 | 5 | 2016-09-10 | 0% | TRUE | Procurement have to provide the information letter. | Nóra Lukács | Not Started | [10 empty] | 2016-07-10 | [22 empty] | No Review | 24 | MDM Team |  |  |  | Training | [8 empty] | 24 |  | 24 | REVIEW | REVIEW | -
42 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_42 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Define scope of transition (EUR) | Up. Co. | TRUE |  | 2016-01-31 | 15 | 2016-01-16 | 100% | FALSE |  | Anikó Krizsány | Complete | [33 empty] | Review | 1 | TBO |  |  |  | Training | 1 | [9 empty] | 1 | - | - | REVIEW
43 | EFAS13 | EFAS13_EFAS13_Master Data Management_43 | Istvan Katus_Finance | EFAS13_Master Data Management | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | MDM Team |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
2 | EFAS04 | EFAS04_EFAS04_Compliance_2 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Post compliance position (English/French or English/German knowledge) - 1 position is already approved - to be calculated how many more is needed | V-A Co. | FALSE |  | 2015-12-18 | 1 | 2015-12-17 | 100% | FALSE |  | Ágota Vízkeleti | Complete | [33 empty] | No Review | 1 | Compliance Team |  |  |  | Training | 1 | [9 empty] | 1 | - | - | REVIEW
3 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_3 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Define scope of transition (Brasil) | V-A Co. | TRUE |  | 2016-01-31 | 15 | 2016-01-16 | 100% | FALSE |  | Anikó Krizsány | Complete | [33 empty] | Review | 8 | TBO |  |  |  | Training | 8 | [9 empty] | 8 | - | - | REVIEW
6 | EFAS04 | EFAS04_EFAS04_Compliance_6 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Review knowledge base of the team members | Both | FALSE |  | 2016-01-31 | 18 | 2016-01-13 | 100% | FALSE |  | Ágota Vízkeleti | Complete | [33 empty] | Review | 4 | Compliance Team |  |  |  | Training | 4 | [9 empty] | 4 | - | - | REVIEW
10 | EFAS04 | EFAS04_EFAS04_Compliance_10 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Finalize org charts internally (changes) based on compliance strategy | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 90% | FALSE |  | Ágota Vízkeleti | On Track | 15-JAN-2016: It depends on the compliance strategy - GPP to BR; VA to HU? | [32 empty] | No Review | 8 | Compliance Team |  |  |  | Other | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
11 | EFAS04 | EFAS04_EFAS04_Compliance_11 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Start the hiring process based on approved future org charts, including approved dis-synergie positions and new positions due to scope add | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Ágota Vízkeleti | Not Started | GSS management needs to approve | [7 empty] | 2016-02-15 | [24 empty] | Review | 8 | Compliance Team |  |  |  | Other |  | 8 | [8 empty] | 8 | - | - | REVIEW
1 | EFAS14 | EFAS14_EFAS14_Process Support_1 | Istvan Katus_Finance | EFAS14_Process Support | Review knowledge base of the team members | Both | FALSE |  | 2016-02-28 | 18 | 2016-02-10 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 1 | Compliance Team |  |  |  | Training |  | 1 | [8 empty] | 1 | - | REVIEW | REVIEW
12 | EFAS04 | EFAS04_EFAS04_Compliance_12 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Interview people for the open compliance positions (dis-synergie and scope-add) | V-A Co. | FALSE |  | 2016-02-15 | 40 | 2016-01-06 | 20% | FALSE |  | Ágota Vízkeleti | On Track | 19-JAN-2016: 5 interviews completed until today. 09-JAN-2016: applicants were selected and requested for an interview. | [32 empty] | No Review | 30 | Compliance Team |  |  |  | Other | 20 | 10 | [8 empty] | 30 | - | - | REVIEW
2 | EFAS14 | EFAS14_EFAS14_Process Support_2 | Istvan Katus_Finance | EFAS14_Process Support | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 4 | Compliance Team |  |  |  | Training |  | 4 | [8 empty] | 4 | REVIEW | REVIEW | -
3 | EFAS14 | EFAS14_EFAS14_Process Support_3 | Istvan Katus_Finance | EFAS14_Process Support | Create training plans (incl. training materials) and substitution plan for each areas - who, whom, what, when will train | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 1 | Compliance Team |  |  |  | Training |  | 1 | [8 empty] | 1 | REVIEW | REVIEW | -
22 | EFAS04 | EFAS04_EFAS04_Compliance_22 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Create training plans (incl. training materials) and substitution plan for each areas - who, whom, what, when will train | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 4 | Compliance Team |  |  |  | Training |  | 4 | [8 empty] | 4 | REVIEW | REVIEW | -
24 | EFAS04 | EFAS04_EFAS04_Compliance_24 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 8 | Compliance Team |  |  |  | Training |  | 8 | [8 empty] | 8 | REVIEW | REVIEW | -
26 | EFAS04 | EFAS04_EFAS04_Compliance_26 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Identify how many IIPS licenses are needed - work with Procurement | Both | FALSE |  | 2016-04-30 | 20 | 2016-04-10 | 0% | TRUE | Procurement | Ágota Vízkeleti | Not Started | [10 empty] | 2016-03-01 | [22 empty] | No Review | 1 | Compliance Team |  |  |  | Other |  |  |  | 1 | [6 empty] | 1 | REVIEW | REVIEW | -
30 | EFAS04 | EFAS04_EFAS04_Compliance_30 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Identify who needs what responsibilities (req approver, OSF-17, OSF-18) | Both | FALSE |  | 2016-04-30 | 10 | 2016-04-20 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 3 | Compliance Team |  |  |  | Other |  |  |  | 3 | [6 empty] | 3 | REVIEW | REVIEW | -
1 | EFAS09 | EFAS09_EFAS09_Finance System Support _1 | Istvan Katus_Finance | EFAS09_Finance System Support | Post open Funct Support position | Up. Co. | FALSE |  | 2016-01-31 | 1 | 2016-01-30 | 100% | FALSE |  | Ágota Vízkeleti | Complete | [33 empty] | Review | 1 | Functional Support Team |  |  |  | Other | 1 | [9 empty] | 1 | - | - | REVIEW
1 | EFAS17 | EFAS17_EFAS17_Reporting_1 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Complete trainings as per trainings plans | Both | FALSE |  | 2016-05-15 | 80 | 2016-02-25 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 8 | DMR Team |  |  |  | Training |  | 8 | [8 empty] | 8 | REVIEW | REVIEW | -
30 | EFAS04 | EFAS04_EFAS04_Compliance_30 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | Compliance Team |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
33 | EFAS04 | EFAS04_EFAS04_Compliance_33 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Create Oracle system responsibilities for the team members | Both | FALSE |  | 2016-05-05 | 5 | 2016-04-30 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | Compliance Team |  |  |  | System config |  |  |  |  | 2 | [5 empty] | 2 | REVIEW | REVIEW | -
34 | EFAS04 | EFAS04_EFAS04_Compliance_34 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Complete trainings as per trainings plans | Both | FALSE |  | 2016-05-15 | 40 | 2016-04-05 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 40 | Compliance Team |  |  |  | Training |  |  |  | 25 | 15 | [5 empty] | 40 | REVIEW | REVIEW | -
35 | EFAS04 | EFAS04_EFAS04_Compliance_35 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Participate in EBS Oracle - CRP testing 4/18 - 5/20 if needed | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | 8 | Compliance Team |  |  |  | Testing |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
36 | EFAS04 | EFAS04_EFAS04_Compliance_36 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Modify SLAs with locations where necessary | Both | FALSE |  | 2016-05-28 | 20 | 2016-05-08 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 16 | Compliance Team |  |  |  | Other |  |  |  |  | 16 | [5 empty] | 16 | REVIEW | REVIEW | -
37 | EFAS04 | EFAS04_EFAS04_Compliance_37 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Archive information (archive pst, shared mailboxes) | Both | FALSE |  | 2016-07-31 | 20 | 2016-07-11 | 0% | TRUE | IT - what is the strategy? | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-31 | [26 empty] | No Review | 8 | Compliance Team |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
39 | EFAS04 | EFAS04_EFAS04_Compliance_39 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Copy Brazil tool in case it has to be duplicated for Upstream Co. | Up. Co. | FALSE |  | 2016-05-31 | 20 | 2016-05-11 | 0% | TRUE | Brazil GSS help is needed | Ágota Vízkeleti | Not Started | [8 empty] | 2016-05-31 | [24 empty] | No Review | 40 | Compliance Team |  |  |  | System config |  |  |  |  | 40 | [5 empty] | 40 | REVIEW | REVIEW | -
40 | EFAS04 | EFAS04_EFAS04_Compliance_40 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Test Brazil tool for Upstream Co. | Up. Co. | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 16 | Compliance Team |  |  |  | Testing | [5 empty] | 16 |  |  |  |  | 16 | REVIEW | REVIEW | -
41 | EFAS04 | EFAS04_EFAS04_Compliance_41 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Request/arrange bank approver responsibilities (Citi, BBVA, Landsbankinn, Quantum) for Compliance staff | Both | FALSE |  | 2016-07-01 | 60 | 2016-05-02 | 0% | TRUE | Treasury Front Office | Ágota Vízkeleti | Not Started | [8 empty] | 2016-07-01 | [24 empty] | No Review | 16 | Compliance Team |  |  |  | System config |  |  |  |  | 8 | 8 |  |  |  |  | 16 | REVIEW | REVIEW | -
42 | EFAS04 | EFAS04_EFAS04_Compliance_42 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 8 | Compliance Team |  |  |  | Testing |  |  |  |  | 4 | 4 |  |  |  |  | 8 | REVIEW | REVIEW | -
43 | EFAS04 | EFAS04_EFAS04_Compliance_43 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Request new shared mailboxes for Upstream | Up. Co. | FALSE |  | 2016-07-31 | 10 | 2016-07-21 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 8 | Compliance Team |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
44 | EFAS04 | EFAS04_EFAS04_Compliance_44 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Duplicate Sharepoint sites in case it is needed for Upstream | Up. Co. | FALSE |  | 2016-07-31 | 10 | 2016-07-21 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 16 | Compliance Team |  |  |  | System config | [6 empty] | 16 |  |  |  | 16 | REVIEW | REVIEW | -
45 | EFAS04 | EFAS04_EFAS04_Compliance_45 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Get eRFA responsibilities - send request to RfA support | Both | FALSE |  | 2016-07-31 | 10 | 2016-07-21 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 3 | Compliance Team |  |  |  | System config | [6 empty] | 3 |  |  |  | 3 | REVIEW | REVIEW | -
46 | EFAS04 | EFAS04_EFAS04_Compliance_46 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Get MSIS, ASP responsibilities - send request to MSIS/ASP support to get accounts | Both | FALSE |  | 2016-07-31 | 10 | 2016-07-21 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | Compliance Team |  |  |  | System config | [6 empty] | 2 |  |  |  | 2 | REVIEW | REVIEW | -
48 | EFAS04 | EFAS04_EFAS04_Compliance_48 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Request ASP Schedulers to reassign the objectives | Both | FALSE |  | 2016-07-31 | 15 | 2016-07-16 | 0% | TRUE | ASP Schedulers | Ágota Vízkeleti | Not Started | [31 empty] | 2016-07-31 | ASP Schedulers | No Review | N/A |  |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
50 | EFAS04 | EFAS04_EFAS04_Compliance_50 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Identify helpchain for KC staff (where / whom to turn to in various topics) - who in each company will be the main contacts e.g. For compliance escalation process, etc. | Both | FALSE |  | 2016-07-31 | 15 | 2016-07-16 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 1 | Compliance Team |  |  |  | Training | [6 empty] | 1 |  |  |  | 1 | REVIEW | REVIEW | -
51 | EFAS04 | EFAS04_EFAS04_Compliance_51 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Separate centralized / process ASATs / controls (who drives changes in system?) | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | IAD (Kyle Rush?) | Ágota Vízkeleti | Not Started | [24 empty] | 2016-08-01 | [8 empty] | No Review | N/A |  |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
52 | EFAS04 | EFAS04_EFAS04_Compliance_52 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Request ASP Support (HelpDesk) help - create different groups in ASP | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | Compliance Team |  |  |  | System config | [6 empty] | 2 |  |  |  | 2 | REVIEW | REVIEW | -
52 | EFAS04 |  | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Test ASP system | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 180 | Compliance Team |  |  |  | Testing | [5 empty] | 90 | 90 |  |  |  | 180 | REVIEW | REVIEW | -
5 | EFAS09 | EFAS09_EFAS09_Finance System Support _5 | Istvan Katus_Finance | EFAS09_Finance System Support | Start the hiring process based on approved future org charts, including approved dis-synergie positions. | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Ágota Vízkeleti | Not Started | GSS management needs to approve | [7 empty] | 2016-01-15 | [24 empty] | Review | N/A |  |  |  |  | Other | [10 empty] | 0 | - | - | REVIEW
6 | EFAS09 | EFAS09_EFAS09_Finance System Support _6 | Istvan Katus_Finance | EFAS09_Finance System Support | Review knowledge base of the team members | Both | FALSE |  | 2016-01-31 | 18 | 2016-01-13 | 100% | FALSE |  | Ágota Vízkeleti | Complete | [33 empty] | Review | 4 | Functional Support Team |  |  |  | Training | 4 | [9 empty] | 4 | - | - | REVIEW
7 | EFAS09 | EFAS09_EFAS09_Finance System Support _7 | Istvan Katus_Finance | EFAS09_Finance System Support | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 8 | Functional Support Team |  |  |  | Training |  | 8 | [8 empty] | 8 | REVIEW | REVIEW | -
9 | EFAS09 | EFAS09_EFAS09_Finance System Support _9 | Istvan Katus_Finance | EFAS09_Finance System Support | Create training plans (incl. training materials) and substitution plan for each areas - who, whom, what, when will train | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 5% | FALSE |  | Ágota Vízkeleti | On Track | [33 empty] | No Review | 4 | Functional Support Team |  |  |  | Training |  | 4 | [8 empty] | 4 | REVIEW | REVIEW | -
12 | EFAS09 | EFAS09_EFAS09_Finance System Support _12 | Istvan Katus_Finance | EFAS09_Finance System Support | Identify who needs what responsibilities (req approver, OSF-17, OSF-18) | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 3 | Functional Support Team |  |  |  | System config |  | 3 | [8 empty] | 3 | - | - | REVIEW
15 | EFAS09 | EFAS09_EFAS09_Finance System Support _15 | Istvan Katus_Finance | EFAS09_Finance System Support | Identify Functional Support team members' participation in the IT separation project: Data separation (e.g. POs, BPA/CPA, Assets, Projects, GL, etc. needs to be separated (before cloning?) and archiving. Establish structure - Legal entities, L-Parents, LBCs; configure/arrange new bank accounts; create hierarchies; interfaces to be identified and repointed to the appropriate new environment, etc. | Both | FALSE |  | 2016-02-15 | 20 | 2016-01-26 | 20% | TRUE | Who is going to lead the IT part, how do we cooperate, what tasks are to be done by our teams? | Ágota Vízkeleti | On Track | 15-JAN-2016: SPA names provided to Ricky Schoeffler | [5 empty] | 2016-02-15 | [26 empty] | No Review | 5 | Functional Support Team |  |  |  | Other | 5 | [9 empty] | 5 | - | - | REVIEW
16 | EFAS09 | EFAS09_EFAS09_Finance System Support _16 | Istvan Katus_Finance | EFAS09_Finance System Support | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | Functional Support Team |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
20 | EFAS09 | EFAS09_EFAS09_Finance System Support _20 | Istvan Katus_Finance | EFAS09_Finance System Support | Interview for open Funct Support positions | V-A Co. | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 10 | Functional Support Team |  |  |  | Other |  | 10 | [8 empty] | 10 | - | - | REVIEW
21 | EFAS09 | EFAS09_EFAS09_Finance System Support _21 | Istvan Katus_Finance | EFAS09_Finance System Support | Create test plans (how will KC Support staff be involved) | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | TRUE | IT will provide integrated test plans and schedules | Ágota Vízkeleti | Not Started | [6 empty] | 2016-02-15 | [26 empty] | Review | 1 | Functional Support Team |  |  |  | Training |  | 1 | [8 empty] | 1 | - | - | REVIEW
22 | EFAS09 | EFAS09_EFAS09_Finance System Support _22 | Istvan Katus_Finance | EFAS09_Finance System Support | Identify how many IIPS licenses are needed - work with Procurement | Both | FALSE |  | 2016-04-30 | 20 | 2016-04-10 | 0% | TRUE | Procurement and Legal need to negotiate with system providers for licenses, support, etc. for the two separate companies/systems. | Ágota Vízkeleti | Not Started | [6 empty] | 2016-04-30 | [26 empty] | No Review | 2 | Functional Support Team |  |  |  | Other |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
25 | EFAS09 | EFAS09_EFAS09_Finance System Support _25 | Istvan Katus_Finance | EFAS09_Finance System Support | Complete trainings as per trainings plans | Both | FALSE |  | 2016-05-15 | 80 | 2016-02-25 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 80 | Functional Support Team |  |  |  | Training |  | 5 | 35 | 35 | 5 | [5 empty] | 80 | REVIEW | REVIEW | -
26 | EFAS09 | EFAS09_EFAS09_Finance System Support _26 | Istvan Katus_Finance | EFAS09_Finance System Support | Create Oracle system responsibilities for the team members | Both | FALSE |  | 2016-05-05 | 5 | 2016-04-30 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 24 | Functional Support Team |  |  |  | System config |  |  |  |  | 24 | [5 empty] | 24 | REVIEW | REVIEW | -
27 | EFAS09 | EFAS09_EFAS09_Finance System Support _27 | Istvan Katus_Finance | EFAS09_Finance System Support | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | 450 | Functional Support Team | 390 | Project team |  | System config/Testing |  |  |  | 420 | 420 | [5 empty] | 840 | REVIEW | REVIEW | -
28 | EFAS09 | EFAS09_EFAS09_Finance System Support _28 | Istvan Katus_Finance | EFAS09_Finance System Support | Archive information (archive pst, shared mailboxes) | Both | FALSE |  | 2016-07-31 | 20 | 2016-07-11 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | 8 | Functional Support Team |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
30 | EFAS09 | EFAS09_EFAS09_Finance System Support _30 | Istvan Katus_Finance | EFAS09_Finance System Support | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 300 | Functional Support Team | 200 | Project team |  | Testing |  |  |  |  | 200 | 250 | 50 |  |  |  | 500 | REVIEW | REVIEW | -
31 | EFAS09 | EFAS09_EFAS09_Finance System Support _31 | Istvan Katus_Finance | EFAS09_Finance System Support | EBS Oracle, Wallmedien, B2B Quadrem/Ariba, Intelligent Invoice Processing System (IIPS, eFlow, Basware), Payload, Sharepoint, Alcoa Intranet, Banks (Citi, Landsbankinn, BBVA, Deutsche), RST, ARMP, Remedy system, ASP system, Fusion Middleware, Swift connection, Interconnect adapters, OSB, FTP communication, TOAD, SQL Developer, ODBC, DB Link, GASS, ITG etc. - anything to be done by our team? | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | IT | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | 750 | Functional Support Team |  |  |  | System config/Testing |  |  |  | 200 | 200 | 180 | 170 |  |  |  | 750 | REVIEW | REVIEW | -
35 | EFAS09 | EFAS09_EFAS09_Finance System Support _35 | Istvan Katus_Finance | EFAS09_Finance System Support | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | Functional Support Team |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
36 | EFAS09 | EFAS09_EFAS09_Finance System Support _36 | Istvan Katus_Finance | EFAS09_Finance System Support | Modify process documentation (SOP, WI etc) | Both | FALSE |  | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 40 | Functional Support Team |  |  |  | Training | [7 empty] | 20 | 20 |  | 40 | REVIEW | REVIEW | -
37 | EFAS09 | EFAS09_EFAS09_Finance System Support _37 | Istvan Katus_Finance | EFAS09_Finance System Support | Depending on the amount of work needed from the team, identify whether consultants/contractors are needed | Both | FALSE |  | 2016-02-15 | 5 | 2016-02-10 | 100% | TRUE | IT should provide info | Ágota Vízkeleti | Complete | 08-JAN-2016: Estimated that 4 external contractors are needed | [5 empty] | 2016-02-15 | [26 empty] | Review | 1 | Functional Support Team |  |  |  | Other |  | 1 | [8 empty] | 1 | - | - | -
| EFAS09 | EFAS09_EFAS09_Finance System Support _ | Istvan Katus_Finance | EFAS09_Finance System Support | Hire contractors once it is approved by GSS management | Both | FALSE |  | 2016-02-15 | 2 | 2016-02-13 | 0% | TRUE | IT should provide info | Ágota Vízkeleti | Not Started | [6 empty] | 2016-02-15 | [26 empty] | Review | 1 | Functional Support Team |  |  |  | Other |  | 1 | [8 empty] | 1 | - | - | REVIEW
55 | EFAS09 |  | Istvan Katus_Finance | EFAS09_Finance System Support | Participate (testing) in pre-projects of separation of commingled legal entities and OUs (US/EUR) | Both | TRUE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-31 | [26 empty] | No Review | 670 | Functional Support Team | 300 | Project team |  | System config/Testing |  |  |  | 500 | 470 | [5 empty] | 970 | REVIEW | REVIEW | -
56 | EFAS09 |  | Istvan Katus_Finance | EFAS09_Finance System Support | Participate (setups) in Alti Forge project | Both | TRUE |  | 2016-05-01 | 45 | 2016-03-17 | 0% | TRUE | Legal | Ágota Vízkeleti | Not Started | 21-JAN-2016: need to register legal entity by 17 March |  |  |  | 2016-03-17 |  | 2016-05-31 | [26 empty] | No Review | 144 | Functional Support Team |  |  |  | System config/Testing |  |  | 48 | 96 | [6 empty] | 144 | REVIEW | REVIEW | -
2 | EFAS17 | EFAS17_EFAS17_Reporting_2 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Identify shared reports and define what it takes to separate them | Both | FALSE |  | 2015-12-18 | 5 | 2015-12-13 | 100% | FALSE |  | Ágota Vízkeleti | Complete | [33 empty] | No Review | 2 | DMR Team |  |  |  | Training | 2 | [9 empty] | 2 | - | - | REVIEW
6 | EFAS17 | EFAS17_EFAS17_Reporting_6 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Review knowledge base of the team members | Both | FALSE |  | 2016-01-31 | 18 | 2016-01-13 | 100% | FALSE |  | Ágota Vízkeleti | Complete | [33 empty] | Review | 2 | DMR Team |  |  |  | Training | 2 | [9 empty] | 2 | - | - | REVIEW
7 | EFAS17 | EFAS17_EFAS17_Reporting_7 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 8 | DMR Team |  |  |  | Training |  | 8 | [8 empty] | 8 | REVIEW | REVIEW | -
9 | EFAS17 | EFAS17_EFAS17_Reporting_9 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Create training plans (incl. training materials) and substitution plan for each areas - who, whom, what, when will train | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 2 | DMR Team |  |  |  | Training |  | 2 | [8 empty] | 2 | REVIEW | REVIEW | -
12 | EFAS17 | EFAS17_EFAS17_Reporting_12 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | DMR Team |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
13 | EFAS17 | EFAS17_EFAS17_Reporting_13 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Identify who needs what responsibilities (req approver, OSF-17, OSF-18, bank approver responsibilities) | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | Review | 3 | DMR Team |  |  |  | Training |  | 3 | [8 empty] | 3 | - | - | REVIEW
16 | EFAS17 | EFAS17_EFAS17_Reporting_16 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Create test plans (how will KC Reporting/Project staff be involved) | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | TRUE | IT will provide integrated test plans and schedules | Ágota Vízkeleti | Not Started | [6 empty] | 2016-02-15 | [26 empty] | Review | 1 | DMR Team |  |  |  | Testing |  | 1 | [8 empty] | 1 | - | - | REVIEW
18 | EFAS17 | EFAS17_EFAS17_Reporting_18 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Create Oracle system responsibilities for the team members | Both | FALSE |  | 2016-05-05 | 5 | 2016-04-30 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | DMR Team |  |  |  | System config |  |  |  |  | 2 | [5 empty] | 2 | REVIEW | REVIEW | -
19 | EFAS17 | EFAS17_EFAS17_Reporting_19 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Participate in EBS Oracle - CRP testing 4/18 - 5/20 if needed | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | 8 | DMR Team |  |  |  | Testing |  |  |  | 4 | 4 | [5 empty] | 8 | REVIEW | REVIEW | -
20 | EFAS17 | EFAS17_EFAS17_Reporting_20 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Split Bad debt Tool / Modify Statement Service macro - we do the testing part only. Credit needs to test too. | Both | FALSE |  | 2016-05-30 | 20 | 2016-05-10 | 0% | FALSE | IT help is needed, Credit needs to test too. | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-30 |  | 2016-05-30 | [24 empty] | No Review | 16 | DMR Team |  |  |  | System config |  |  |  |  | 16 | [5 empty] | 16 | REVIEW | REVIEW | -
21 | EFAS17 | EFAS17_EFAS17_Reporting_21 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Split Timesheet | Both | FALSE |  | 2016-05-30 | 20 | 2016-05-10 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 4 | DMR Team |  |  |  | System config |  |  |  |  | 4 | [5 empty] | 4 | REVIEW | REVIEW | -
22 | EFAS17 | EFAS17_EFAS17_Reporting_22 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Split ARMP | Both | FALSE |  | 2016-05-30 | 20 | 2016-05-10 | 0% | FALSE | IT help is needed | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-30 | [26 empty] | No Review | 80 | DMR Team |  |  |  | System config |  |  |  |  | 80 | [5 empty] | 80 | REVIEW | REVIEW | -
23 | EFAS17 | EFAS17_EFAS17_Reporting_23 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Request/arrange bank approver responsibilities (Citi, BBVA, Landsbankinn, Quantum) | Both | FALSE |  | 2016-07-01 | 60 | 2016-05-02 | 0% | TRUE | Treasury Front Office | Ágota Vízkeleti | Not Started | [8 empty] | 2016-07-01 | [24 empty] | No Review | 16 | DMR Team |  |  |  | System config |  |  |  |  | 8 | 8 |  |  |  |  | 16 | REVIEW | REVIEW | -
24 | EFAS17 | EFAS17_EFAS17_Reporting_24 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 8 | DMR Team |  |  |  | Testing |  |  |  |  | 4 | 4 |  |  |  |  | 8 | REVIEW | REVIEW | -
24 | EFAS17 |  | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Remediate reports/macros after testing (CRP) | Both | FALSE |  | 2016-05-22 | 27 | 2016-04-25 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [6 empty] | 2016-05-22 | [26 empty] | No Review | 144 | DMR Team |  |  |  | System config |  |  |  |  | 144 | [5 empty] | 144 | REVIEW | REVIEW | -
25 | EFAS17 | EFAS17_EFAS17_Reporting_25 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Split shared reports (Shared 401; UpCo 29; ValueAdd 119; TSA 5) | Both | FALSE |  | 2016-07-15 | 90 | 2016-04-16 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 650 | DMR Team |  |  |  | System config |  |  |  | 130 | 150 | 250 | 120 |  |  |  | 650 | REVIEW | REVIEW | -
26 | EFAS17 | EFAS17_EFAS17_Reporting_26 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | EBS Oracle, Discoverer, Hyperion, Sharepoint, AutoMate, BU Legacy systems (IWAN, Flits, JD Edwards, PPM), Alcoa Intranet, Banks (Citi, Landsbankinn, BBVA, Deutsche), RST, ARMP, Bad Debt Management Tool - these systems should be ready for us - define if anything to be done by our team (testing, etc) | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | IT | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | 8 | DMR Team |  |  |  | Testing |  |  |  | 2 | 2 | 2 | 2 |  |  |  | 8 | REVIEW | REVIEW | -
30 | EFAS17 | EFAS17_EFAS17_Reporting_30 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Archive information (archive pst, shared mailboxes) | Both | FALSE |  | 2016-07-31 | 20 | 2016-07-11 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | 8 | DMR Team |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
32 | EFAS17 | EFAS17_EFAS17_Reporting_32 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | DMR Team |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
33 | EFAS17 | EFAS17_EFAS17_Reporting_33 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Modify process documentation (SOP, WI etc) | Both | FALSE |  | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 40 | DMR Team |  |  |  | Training | [7 empty] | 20 | 20 |  | 40 | REVIEW | REVIEW | -
3 | EFAS01 | EFAS01_EFAS01_Accounts Payable_3 | Istvan Katus_Finance | EFAS01_Accounts Payable | Create training plans ((incl. training materials) for each areas - who, whom, what, when | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 10% | FALSE |  | Anikó Krizsány | On Track | [33 empty] | No Review | 8 | AP teams |  |  |  | Training | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
4 | EFAS01 | EFAS01_EFAS01_Accounts Payable_4 | Istvan Katus_Finance | EFAS01_Accounts Payable | Review and create test script - EUR, NOA, CAN… | Both | FALSE |  | 2016-05-15 | 60 | 2016-03-16 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 16 | AP teams |  |  |  | Testing |  |  | 4 | 8 | 4 | [5 empty] | 16 | REVIEW | REVIEW | -
9 | EFAS01 | EFAS01_EFAS01_Accounts Payable_9 | Istvan Katus_Finance | EFAS01_Accounts Payable | Post open positions (dis-synergies) | Both | FALSE |  | 2016-02-28 | 20 | 2016-02-08 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 2 | AP teams |  |  |  | Training |  | 2 | [8 empty] | 2 | - | REVIEW | REVIEW
12 | EFAS01 | EFAS01_EFAS01_Accounts Payable_12 | Istvan Katus_Finance | EFAS01_Accounts Payable | Start the hiring process based on approved future org charts, including approved dis-synergie positions and new positions due to scope add | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Anikó Krizsány | Not Started | GSS management needs to approve | [7 empty] | 2016-02-15 | [24 empty] | Review | 8 | AP teams |  |  |  | Training |  | 8 | [8 empty] | 8 | - | - | REVIEW
17 | EFAS01 | EFAS01_EFAS01_Accounts Payable_17 | Istvan Katus_Finance | EFAS01_Accounts Payable | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | AP teams |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
19 | EFAS01 | EFAS01_EFAS01_Accounts Payable_19 | Istvan Katus_Finance | EFAS01_Accounts Payable | Identify how many IIPS licenses are needed - work with Procurement | Both | FALSE |  | 2016-04-30 | 20 | 2016-04-10 | 0% | TRUE | Procurement and Legal need to negotiate with system providers for licenses, support, etc. for the two separate companies/systems. | Anikó Krizsány | Not Started | [10 empty] | 2016-06-01 | [22 empty] | No Review | 8 | AP teams |  |  |  | Training |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
22 | EFAS01 | EFAS01_EFAS01_Accounts Payable_22 | Istvan Katus_Finance | EFAS01_Accounts Payable | Setup new printers (if it's required) | Up. Co. | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | AP teams |  |  |  | System config | [5 empty] | 1 |  |  |  |  | 1 | REVIEW | REVIEW | -
23 | EFAS01 | EFAS01_EFAS01_Accounts Payable_23 | Istvan Katus_Finance | EFAS01_Accounts Payable | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | AP teams |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
24 | EFAS01 | EFAS01_EFAS01_Accounts Payable_24 | Istvan Katus_Finance | EFAS01_Accounts Payable | Determine Authorized Persons for Shared Services Requests & Approvals OSF 17 | Up. Co. | FALSE |  | 2016-06-30 | 20 | 2016-06-10 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | AP teams |  |  |  | Training | [5 empty] | 2 |  |  |  |  | 2 | REVIEW | REVIEW | -
25 | EFAS01 | EFAS01_EFAS01_Accounts Payable_25 | Istvan Katus_Finance | EFAS01_Accounts Payable | Decide the owner of the OSF17 | Up. Co. | FALSE |  | 2016-06-30 | 20 | 2016-06-10 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | AP teams |  |  |  | Training | [5 empty] | 2 |  |  |  |  | 2 | REVIEW | REVIEW | -
27 | EFAS01 | EFAS01_EFAS01_Accounts Payable_27 | Istvan Katus_Finance | EFAS01_Accounts Payable | Localization setup where applicable (ie. Norwegian VAT Reconciliation Report; Spanish Input VAT Journal Report...) | Up. Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 4 | Functional Support Team |  |  |  | System config |  |  |  |  | 2 | 2 |  |  |  |  | 4 | REVIEW | REVIEW | -
29 | EFAS01 | EFAS01_EFAS01_Accounts Payable_29 | Istvan Katus_Finance | EFAS01_Accounts Payable | Configure IIPS application for new organizations | Up. Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 32 | Functional Support Team |  |  |  | System config |  |  |  |  | 16 | 16 |  |  |  |  | 32 | REVIEW | REVIEW | -
30 | EFAS01 | EFAS01_EFAS01_Accounts Payable_30 | Istvan Katus_Finance | EFAS01_Accounts Payable | Clone IIPS database for User Acceptance Test | Up. Co. | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 32 | Functional Support Team |  |  |  | System config | [5 empty] | 32 |  |  |  |  | 32 | REVIEW | REVIEW | -
32 | EFAS01 | EFAS01_EFAS01_Accounts Payable_32 | Istvan Katus_Finance | EFAS01_Accounts Payable | Archive information (archive pst, shared mailboxes) | Both | FALSE |  | 2016-07-31 | 20 | 2016-07-11 | 0% | FALSE | IT - what is the strategy? | Anikó Krizsány | Not Started | [6 empty] | 2016-05-31 | [26 empty] | No Review | 16 | Functional Support Team |  |  |  | System config | [6 empty] | 16 |  |  |  | 16 | REVIEW | REVIEW | -
33 | EFAS01 | EFAS01_EFAS01_Accounts Payable_33 | Istvan Katus_Finance | EFAS01_Accounts Payable | Data migration in IIPS (archive) | Up. Co. | FALSE |  | 2016-06-01 | 30 | 2016-05-02 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 16 | Functional Support Team |  |  |  | System config |  |  |  |  | 16 | [5 empty] | 16 | REVIEW | REVIEW | -
34 | EFAS01 | EFAS01_EFAS01_Accounts Payable_34 | Istvan Katus_Finance | EFAS01_Accounts Payable | Identify bank approvers in both companies | Both | FALSE |  | 2016-06-30 | 20 | 2016-06-10 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 3 | AP teams |  |  |  | Training | [5 empty] | 3 |  |  |  |  | 3 | REVIEW | REVIEW | -
35 | EFAS01 | EFAS01_EFAS01_Accounts Payable_35 | Istvan Katus_Finance | EFAS01_Accounts Payable | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-05-27 | [26 empty] | No Review | 260 | AP teams |  |  |  | Testing |  |  |  | 130 | 130 | [5 empty] | 260 | REVIEW | REVIEW | -
36 | EFAS01 | EFAS01_EFAS01_Accounts Payable_36 | Istvan Katus_Finance | EFAS01_Accounts Payable | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 400 | AP teams |  |  |  | Testing |  |  |  |  | 80 | 300 | 20 |  |  |  | 400 | REVIEW | REVIEW | -
38 | EFAS01 | EFAS01_EFAS01_Accounts Payable_38 | Istvan Katus_Finance | EFAS01_Accounts Payable | Create test plans | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 24 | AP teams |  |  |  | Testing |  | 24 | [8 empty] | 24 | - | - | REVIEW
39 | EFAS01 | EFAS01_EFAS01_Accounts Payable_39 | Istvan Katus_Finance | EFAS01_Accounts Payable | Request/arrange bank approver responsibilities (Citi, BBVA, Landsbankinn, Quantum) for Compliance staff | Both | FALSE |  | 2016-07-01 | 60 | 2016-05-02 | 0% | TRUE | Treasury Front Office | Anikó Krizsány | Not Started | [8 empty] | 2016-07-01 | [24 empty] | No Review | 1 | AP teams |  |  |  | Training | [5 empty] | 1 |  |  |  |  | 1 | REVIEW | REVIEW | -
40 | EFAS01 | EFAS01_EFAS01_Accounts Payable_40 | Istvan Katus_Finance | EFAS01_Accounts Payable | Clean up intercompany balances | Both | TRUE |  | 2016-09-29 | 2 | 2016-09-27 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 4 | AP teams |  |  |  | System config | [8 empty] | 4 |  | 4 | REVIEW | REVIEW | -
41 | EFAS01 | EFAS01_EFAS01_Accounts Payable_41 | Istvan Katus_Finance | EFAS01_Accounts Payable | Intercompany setup change | Both | FALSE |  | 2016-09-30 | 1 | 2016-09-29 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | AP teams |  |  |  | System config | [8 empty] | 2 |  | 2 | REVIEW | REVIEW | -
42 | EFAS01 | EFAS01_EFAS01_Accounts Payable_42 | Istvan Katus_Finance | EFAS01_Accounts Payable | Review of payment approval schedule | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | AP teams |  |  |  | Training | [6 empty] | 2 |  |  |  | 2 | REVIEW | REVIEW | -
43 | EFAS01 | EFAS01_EFAS01_Accounts Payable_43 | Istvan Katus_Finance | EFAS01_Accounts Payable | Identify ASP users, schedulers, define roles | Both | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 3 | AP teams |  |  |  | Training | [5 empty] | 3 |  |  |  |  | 3 | REVIEW | REVIEW | -
50 | EFAS04 | EFAS04_EFAS04_Compliance_50 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 8 | Compliance Team |  |  |  | Testing | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
52 | EFAS04 | EFAS04_EFAS04_Compliance_52 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | Compliance Team |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
54 | EFAS01 | EFAS01_EFAS01_Accounts Payable_54 | Istvan Katus_Finance | EFAS01_Accounts Payable | Modify process documentation (SOP, WI etc), update DocIndex | Both | FALSE |  | 2016-10-30 | 30 | 2016-09-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 40 | AP teams |  |  |  | Training | [9 empty] | 40 | 40 | REVIEW | REVIEW | -
55 | EFAS01 | EFAS01_EFAS01_Accounts Payable_55 | Istvan Katus_Finance | EFAS01_Accounts Payable | Create new shared mailbox for GPP | Up. Co. | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | AP teams |  |  |  | System config | [5 empty] | 2 |  |  |  |  | 2 | REVIEW | REVIEW | -
55 | EFAS01 | EFAS01_EFAS01_Accounts Payable_55 | Istvan Katus_Finance | EFAS01_Accounts Payable | Participate (testing) in pre-projects of separation of commingled legal entities and OUs (US/EUR) | Both | TRUE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-05-31 | [26 empty] | No Review | 200 | AP teams |  |  |  | Testing |  |  |  | 100 | 100 | [5 empty] | 200 | REVIEW | REVIEW | -
2 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_2 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Create training plans ((incl. training materials) for each areas - who, whom, what, when | Both | FALSE |  | 2016-02-10 | 30 | 2016-01-11 | 25% | FALSE |  | Anikó Krizsány | On Track | [33 empty] | No Review | 8 | TBO |  |  |  | Training | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
5 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_5 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Grant accesses to the new banks and folders, sharepoints, common mailboxes | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | TBO |  |  |  | System config |  |  | 2 | [7 empty] | 2 | REVIEW | REVIEW | -
7 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_7 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-05-27 | [26 empty] | No Review | 10 | TBO |  |  |  | Testing |  |  |  | 5 | 5 | [5 empty] | 10 | REVIEW | REVIEW | -
8 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_8 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 10 | TBO |  |  |  | Testing |  |  |  |  | 5 | 5 |  |  |  |  | 10 | REVIEW | REVIEW | -
10 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_10 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Create test plans- Quantum | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 8 | TBO |  |  |  | Testing |  | 8 | [8 empty] | 8 | - | - | REVIEW
11 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_11 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Start the hiring process based on approved future org charts, including approved dis-synergie positions and new positions due to scope add | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Anikó Krizsány | Not Started | GSS management needs to approve | [7 empty] | 2016-02-15 | [24 empty] | Review | 8 | TBO |  |  |  | Training |  | 8 | [8 empty] | 8 | - | - | REVIEW
13 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_13 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Finalize org charts internally (changes) | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 40% | FALSE |  | Anikó Krizsány | On Track | [33 empty] | No Review | 8 | TBO |  |  |  | Training | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
16 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_16 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | TBO |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
18 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_18 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Restructure capital structure. Collect info on new name, address, legal entity, tax number, bank account number, LBC, ownership change, Set of Books | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | TBO |  |  |  | Training |  |  |  | 1 | [6 empty] | 1 | REVIEW | REVIEW | -
20 | EFAS18 | EFAS18_EFAS18_T&E_20 | Istvan Katus_Finance | EFAS18_T&E | Start the hiring process based on approved future org charts, including approved dis-synergie positions and new positions due to scope add | Both | TRUE |  | 2016-02-15 | 5 | 2016-02-10 | 0% | TRUE | GSS management needs to approve | Anikó Krizsány | Not Started | GSS management needs to approve | [7 empty] | 2016-02-15 | [24 empty] | Review | 8 | T&E |  |  |  | Training |  | 8 | [8 empty] | 8 | - | - | REVIEW
22 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_22 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Identify ASP users, schedulers, define roles | Both | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | TBO |  |  |  | Training | [5 empty] | 2 |  |  |  |  | 2 | REVIEW | REVIEW | -
29 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_29 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Modify process documentation (SOP, WI etc), update DocIndex | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 32 | TBO |  |  |  | Training |  |  | 32 | [7 empty] | 32 | REVIEW | REVIEW | -
30 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_30 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Define new netting structure for both companies | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 3 | TBO |  |  |  | Training |  |  |  | 3 | [6 empty] | 3 | REVIEW | REVIEW | -
31 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_31 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Prepare cut over- transition plan- define SPA | Both | FALSE |  | 2016-02-27 | 20 | 2016-02-07 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 8 | TBO |  |  |  | Training |  | 8 | [8 empty] | 8 | - | REVIEW | REVIEW
2 | EFAS12 | EFAS12_EFAS12_IICS_2 | Istvan Katus_Finance | EFAS12_IICS | Create training plans ((incl. training materials) for each areas - who, whom, what, when | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 5% | FALSE |  | Anikó Krizsány | On Track | [33 empty] | No Review | 8 | IICS team |  |  |  | Training | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
7 | EFAS12 | EFAS12_EFAS12_IICS_7 | Istvan Katus_Finance | EFAS12_IICS | List activities to be transferred to Brazil | Up. Co. | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 5% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 5 | IICS team |  |  |  | Training |  |  |  | 5 | [6 empty] | 5 | REVIEW | REVIEW | -
8 | EFAS12 | EFAS12_EFAS12_IICS_8 | Istvan Katus_Finance | EFAS12_IICS | Request confirmation about the customer setup after the split (back to 3rd party in legacy, movex, order management…) | Both | FALSE |  | 2016-10-03 | 3 | 2016-09-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | IICS team |  |  |  | Training | [9 empty] | 1 | 1 | REVIEW | REVIEW | -
9 | EFAS12 | EFAS12_EFAS12_IICS_9 | Istvan Katus_Finance | EFAS12_IICS | Participate (testing) in pre-projects of separation of commingled legal entities and OUs (EUR) | Both | TRUE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-05-31 | [26 empty] | No Review | 16 | IICS team |  |  |  | Testing |  |  |  | 8 | 8 | [5 empty] | 16 | REVIEW | REVIEW | -
12 | EFAS12 | EFAS12_EFAS12_IICS_31 | Istvan Katus_Finance | EFAS12_IICS | Create new shared mailbox for GPP | Up. Co. | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | [5 empty] | System config | [10 empty] | 0 | REVIEW | REVIEW | -
13 | EFAS12 | EFAS12_EFAS12_IICS_13 | Istvan Katus_Finance | EFAS12_IICS | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | IICS team |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
16 | EFAS12 | EFAS12_EFAS12_IICS_16 | Istvan Katus_Finance | EFAS12_IICS | Setup FTP account | Both | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 4 | IICS team |  |  |  | System config | [6 empty] | 4 |  |  |  | 4 | REVIEW | REVIEW | -
17 | EFAS12 | EFAS12_EFAS12_IICS_17 | Istvan Katus_Finance | EFAS12_IICS | Update customer & vendor mapping | Both | FALSE |  | 2016-10-03 | 3 | 2016-09-30 | 0% | FALSE | Facility needs to be ready | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | IICS team |  |  |  | Training | [9 empty] | 8 | 8 | REVIEW | REVIEW | -
18 | EFAS12 | EFAS12_EFAS12_IICS_18 | Istvan Katus_Finance | EFAS12_IICS | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-05-27 | [26 empty] | No Review | 8 | IICS team |  |  |  | Testing |  |  |  | 4 | 4 | [5 empty] | 8 | REVIEW | REVIEW | -
19 | EFAS12 | EFAS12_EFAS12_IICS_19 | Istvan Katus_Finance | EFAS12_IICS | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 8 | IICS team |  |  |  | Testing |  |  |  |  | 4 | 4 |  |  |  |  | 8 | REVIEW | REVIEW | -
21 | EFAS12 | EFAS12_EFAS12_IICS_21 | Istvan Katus_Finance | EFAS12_IICS | Review and finalize test plans | Both | FALSE |  | 2016-02-27 | 10 | 2016-02-17 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 8 | IICS team |  |  |  | Testing |  | 8 | [8 empty] | 8 | - | REVIEW | -
22 | EFAS12 | EFAS12_EFAS12_IICS_22 | Istvan Katus_Finance | EFAS12_IICS | Identify ASP users, schedulers, define roles | Up. Co. | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | IICS team |  |  |  | Training | [5 empty] | 2 |  |  |  |  | 2 | REVIEW | REVIEW | -
28 | EFAS04 | EFAS04_EFAS04_Compliance_28 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Modify process documentation (SOP, WI etc) | Both | FALSE |  | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 40 | Compliance Team |  |  |  | Training | [7 empty] | 20 | 20 |  | 40 | REVIEW | REVIEW | -
30 | EFAS12 | EFAS12_EFAS12_IICS_30 | Istvan Katus_Finance | EFAS12_IICS | Modify process documentation (SOP, WI etc) | Up. Co. | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | IICS team |  |  |  | Training |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
2 | EFAS18 | EFAS18_EFAS18_T&E_2 | Istvan Katus_Finance | EFAS18_T&E | Create training plans ((incl. training materials) for each areas - who, whom, what, when | Both | FALSE |  | 2016-02-15 | 30 | 2016-01-16 | 5% | FALSE |  | Anikó Krizsány | On Track | [33 empty] | No Review | 8 | T&E |  |  |  | Training | 4 | 4 | [8 empty] | 8 | - | - | REVIEW
7 | EFAS18 | EFAS18_EFAS18_T&E_7 | Istvan Katus_Finance | EFAS18_T&E | Post open positions (dis-synergies) | Both | FALSE |  | 2016-02-28 | 10 | 2016-02-18 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 1 | T&E |  |  |  | Training |  | 1 | [8 empty] | 1 | REVIEW | REVIEW | -
11 | EFAS01 | EFAS01_EFAS01_Accounts Payable_11 | Istvan Katus_Finance | EFAS01_Accounts Payable | Treasury - bank account openings, setting up approvers, register them in banks and get tokens, check setup | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | N/A |  |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
13 | EFAS18 | EFAS18_EFAS18_T&E_13 | Istvan Katus_Finance | EFAS18_T&E | Communicate the new org structure to staff | Both | FALSE |  | 2016-04-30 | 1 | 2016-04-29 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | T&E |  |  |  | Training |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
15 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_15 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Treasury - bank account openings, setting up approvers, register them in banks and get tokens, check setup | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | TBO |  |  |  | System config |  |  |  | 1 | [6 empty] | 1 | REVIEW | REVIEW | -
16 | EFAS18 | EFAS18_EFAS18_T&E_16 | Istvan Katus_Finance | EFAS18_T&E | Contact Citibank about new implementation, fill in 'Implementation Grid' to provide all necessary information to the correct set up | Up. Co. | FALSE |  | 2016-07-30 | 60 | 2016-05-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | T&E |  |  |  | Training |  |  |  |  | 4 | 4 |  |  |  |  | 8 | REVIEW | REVIEW | -
17 | EFAS18 | EFAS18_EFAS18_T&E_17 | Istvan Katus_Finance | EFAS18_T&E | Contact Citibank about name changes , fill in 'Implementation Grid' to provide all necessary information to the correct set up | V-A Co. | FALSE |  | 2016-07-30 | 60 | 2016-05-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | T&E |  |  |  | Training |  |  |  |  | 4 | 4 |  |  |  |  | 8 | REVIEW | REVIEW | -
18 | EFAS18 | EFAS18_EFAS18_T&E_18 | Istvan Katus_Finance | EFAS18_T&E | Collect information about cardholders /T&E and LVP/ - template is sent out by T&E team (to set up users in Citibank, Concur and Egencia) | Both | FALSE |  | 2016-05-01 | 30 | 2016-04-01 | 0% |  |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 12 | T&E |  |  |  | Training |  |  |  | 12 | [6 empty] | 12 | REVIEW | REVIEW | -
19 | EFAS18 | EFAS18_EFAS18_T&E_19 | Istvan Katus_Finance | EFAS18_T&E | Company fuel cards modify in Köfém | Both | FALSE |  | 2016-07-20 | 30 | 2016-06-20 | 0% | TRUE | Procurement | Anikó Krizsány | Not Started | [10 empty] | 2016-07-20 | [22 empty] | No Review | 20 | T&E |  |  |  | System config | [5 empty] | 5 | 15 |  |  |  | 20 | REVIEW | REVIEW | -
20 | EFAS18 | EFAS18_EFAS18_T&E_20 | Istvan Katus_Finance | EFAS18_T&E | Request new T&E / LVP cards for users (incl FAS) | Both | FALSE |  | 2016-07-31 | 20 | 2016-07-11 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | T&E |  |  |  | Training | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
26 | EFAS18 | EFAS18_EFAS18_T&E_26 | Istvan Katus_Finance | EFAS18_T&E | Egencia is completed the technical set up of the new company | Up. Co. | FALSE |  | 2016-07-30 | 60 | 2016-05-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 3 | T&E |  |  |  | System config |  |  |  |  | 1 | 2 |  |  |  |  | 3 | REVIEW | REVIEW | -
27 | EFAS18 | EFAS18_EFAS18_T&E_27 | Istvan Katus_Finance | EFAS18_T&E | Egencia set up ready -> set up employees in Egencia system | Up. Co. | FALSE |  | 2016-07-30 | 45 | 2016-06-15 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 3 | T&E |  |  |  | System config | [6 empty] | 3 |  |  |  | 3 | REVIEW | REVIEW | -
28 | EFAS18 | EFAS18_EFAS18_T&E_28 | Istvan Katus_Finance | EFAS18_T&E | Inform Egencia users about log in information | Up. Co. | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | T&E |  |  |  | Training | [6 empty] | 2 |  |  |  | 2 | REVIEW | REVIEW | -
29 | EFAS18 | EFAS18_EFAS18_T&E_29 | Istvan Katus_Finance | EFAS18_T&E | Contact Concur support about new implementation | Up. Co. | FALSE |  | 2016-07-30 | 45 | 2016-06-15 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 4 | T&E |  |  |  | Training | [6 empty] | 4 |  |  |  | 4 | REVIEW | REVIEW | -
30 | EFAS18 | EFAS18_EFAS18_T&E_30 | Istvan Katus_Finance | EFAS18_T&E | Set up new company in Concur and create interface between Concur and Citibank in order to ensure data loading | Up. Co. | FALSE |  | 2016-07-30 | 45 | 2016-06-15 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 4 | T&E |  |  |  | System config | [6 empty] | 4 |  |  |  | 4 | REVIEW | REVIEW | -
31 | EFAS18 | EFAS18_EFAS18_T&E_31 | Istvan Katus_Finance | EFAS18_T&E | Create new user profiles in Concur if the setup is completed | Up. Co. | FALSE |  | 2016-07-30 | 45 | 2016-06-15 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | T&E |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
32 | EFAS18 | EFAS18_EFAS18_T&E_32 | Istvan Katus_Finance | EFAS18_T&E | After credit cards are activated, assign credit card and Concur profile | Up. Co. | FALSE |  | 2016-07-30 | 60 | 2016-05-31 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 8 | T&E |  |  |  | System config |  |  |  |  | 4 | 4 |  |  |  |  | 8 | REVIEW | REVIEW | -
33 | EFAS18 | EFAS18_EFAS18_T&E_33 | Istvan Katus_Finance | EFAS18_T&E | Inform Concur users about log in information | Up. Co. | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 6 | T&E |  |  |  | Training | [6 empty] | 6 |  |  |  | 6 | REVIEW | REVIEW | -
34 | EFAS18 | EFAS18_EFAS18_T&E_34 | Istvan Katus_Finance | EFAS18_T&E | Create new shared mailbox for GPP | Up. Co. | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | T&E |  |  |  | System config | [5 empty] | 1 |  |  |  |  | 1 | REVIEW | REVIEW | -
38 | EFAS18 | EFAS18_EFAS18_T&E_38 | Istvan Katus_Finance | EFAS18_T&E | Setup new printers (if it's required) | Up. Co. | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | T&E |  |  |  | system config | [6 empty] | 1 |  |  |  | 1 | REVIEW | REVIEW | -
39 | EFAS18 | EFAS18_EFAS18_T&E_39 | Istvan Katus_Finance | EFAS18_T&E | Move staff to new facility | Both | FALSE |  | 2016-08-06 | 3 | 2016-08-03 | 0% | TRUE | Facility needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-08-06 | [24 empty] | 2016-08-06 | Facility (engineering, contractors) | No Review | 24 | T&E |  |  |  | Other | [7 empty] | 24 |  |  | 24 | REVIEW | REVIEW | -
40 | EFAS18 | EFAS18_EFAS18_T&E_40 | Istvan Katus_Finance | EFAS18_T&E | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-05-27 | [26 empty] | No Review | 16 | T&E |  |  |  | Testing |  |  |  | 8 | 8 | [5 empty] | 16 | REVIEW | REVIEW | -
41 | EFAS18 | EFAS18_EFAS18_T&E_41 | Istvan Katus_Finance | EFAS18_T&E | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | 16 | T&E |  |  |  | Testing |  |  |  |  | 8 | 8 |  |  |  |  | 16 | REVIEW | REVIEW | -
42 | EFAS12 | EFAS12_EFAS12_IICS_42 | Istvan Katus_Finance | EFAS12_IICS | Treasury - bank account openings, setting up approvers, register them in banks and get tokens, check setup | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 1 | IICS team |  |  |  | System config |  |  |  | 1 | [6 empty] | 1 | REVIEW | REVIEW | -
43 | EFAS18 | EFAS18_EFAS18_T&E_43 | Istvan Katus_Finance | EFAS18_T&E | Create test plans | Both | FALSE |  | 2016-02-15 | 10 | 2016-02-05 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | Review | 8 | T&E |  |  |  | Testing |  | 8 | [8 empty] | 8 | - | - | REVIEW
44 | EFAS18 | EFAS18_EFAS18_T&E_44 | Istvan Katus_Finance | EFAS18_T&E | Identify ASP users, schedulers, define roles | Both | FALSE |  | 2016-07-10 | 20 | 2016-06-20 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | T&E |  |  |  | Training | [5 empty] | 2 |  |  |  |  | 2 | REVIEW | REVIEW | -
48 | EFAS18 | EFAS18_EFAS18_T&E_48 | Istvan Katus_Finance | EFAS18_T&E | Treasury - bank account openings, setting up approvers, register them in banks and get tokens, check setup | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 2 | T&E |  |  |  | System config |  |  |  | 2 | [6 empty] | 2 | REVIEW | REVIEW | -
50 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_50 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Test processing bank transfer from new bank acounts | Both | TRUE |  | 2016-08-01 | 45 | 2016-06-17 | 0% | TRUE | Treasury to make decision and select Customers/invoices | Judit Antli | Not Started | New payment method and bank accounts, lockbox process to be tested |  |  | 2016-08-01 | [29 empty] | No Review | 70 | NAM AR |  |  |  | Testing | [5 empty] | 30 | 40 |  |  |  | 70 | REVIEW | REVIEW | -
51 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_51 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Test processing bank transfer from new bank acounts | Both | TRUE |  | 2016-08-01 | 45 | 2016-06-17 | 0% | TRUE | Treasury to make decision and select Customers/invoices | Judit Antli | Not Started | New payment method and bank accounts to be tested |  |  | 2016-08-01 | [29 empty] | No Review | 140 | AC EUR (GL/AR) |  |  |  | Testing | [5 empty] | 80 | 60 |  |  |  | 140 | REVIEW | REVIEW | -
52 | EFAS18 | EFAS18_EFAS18_T&E_52 | Istvan Katus_Finance | EFAS18_T&E | Modify process documentation (SOP, WI etc), update DocIndex | Both | FALSE |  | 2016-07-30 | 45 | 2016-06-15 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 40 | T&E |  |  |  | Training | [5 empty] | 10 | 30 |  |  |  | 40 | REVIEW | REVIEW | -
7 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_7 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Review AR configuration - create separate OU for commingled legal entities and reconcile balances | Both | TRUE |  | 2016-05-01 | 35 | 2016-03-27 | 0% | TRUE | IT. Other GSS | Judit Antli | Not Started | Shared AR OU to be used by Up Stream Co ? | [5 empty] | 2016-02-22 |  | 2016-02-22 | [24 empty] | No Review | 100 | NAM AR |  |  |  | Training |  |  |  | 100 | [6 empty] | 100 | REVIEW | REVIEW | -
9 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_9 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Review existing documents and create new ones if needed | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | To make sure that processes are well documented at both companies | [32 empty] | No Review | 10 | NAM AR |  |  |  | Training | [6 empty] | 10 |  |  |  | 10 | REVIEW | REVIEW | -
10 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_10 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Create/update training Plan Cash Application, Maintenance and PC&E and Candian Process | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | FALSE |  | Judit Antli | Not Started | Update training materials ( lastly used by Infosys transition) with changes | [32 empty] | No Review | 8 | NAM AR |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
12 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_12 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Review knowledge base of the team members | Both | FALSE |  | 2016-02-28 | 15 | 2016-02-13 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | Review | 10 | NAM AR |  |  |  | Training |  | 10 | [8 empty] | 10 | - | REVIEW | REVIEW
13 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_13 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | NAM AR |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
14 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_14 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Complete any knowledge transfer/training required for target condition. | Both | FALSE |  | 2016-07-20 | 60 | 2016-05-21 | 0% | FALSE |  | Judit Antli | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. To make sure that required knowledge will be avaliable at both companies by D1 | [32 empty] | No Review | 80 | NAM AR |  |  |  | Training |  |  |  |  | 20 | 30 | 30 |  |  |  | 80 | REVIEW | REVIEW | -
15 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_15 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | NAM AR |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
16 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_16 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Create list of responsibilities, accesses needed to Lockbox | Both | FALSE |  | 2016-05-27 | 17 | 2016-05-10 | 0% | TRUE | Treasury is opening new lockboxes and grant accessess | Judit Antli | Not Started | New Lockboxes and bank accounts will be used |  |  | 2016-05-27 | [29 empty] | No Review | 16 | NAM AR |  |  |  | Training |  |  |  |  | 16 | [5 empty] | 16 | REVIEW | REVIEW | -
17 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_17 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Create access to new bank accounts, incl. Canada | Both | TRUE |  | 2016-07-20 | 30 | 2016-06-20 | 0% | TRUE | Treasury is opening new lockboxes and grant accessess | Judit Antli | Not Started | New bank accounts will be used |  |  | 2016-05-27 | [29 empty] | No Review | 32 | NAM AR |  |  |  | Training | [5 empty] | 12 | 20 |  |  |  | 32 | REVIEW | REVIEW | -
19 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_19 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Request shared mailboxes, rewrite worklflows, update AR templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-30 | [26 empty] | No Review | 80 | NAM AR |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
22 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_22 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Test the securization program | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Treasury and Coroprate to make decision | Judit Antli | Not Started | Continue current program but company name will be changed. Or new program to be launched ? |  |  | 2016-08-01 | [29 empty] | No Review | 40 | NAM AR |  |  |  | Testing | [6 empty] | 40 |  |  |  | 40 | REVIEW | REVIEW | -
26 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_26 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Request responsibilities, accesses for the users ( EBS), set up approval limits | Both | FALSE |  | 2016-04-25 | 20 | 2016-04-05 | 0% | TRUE | IT | Judit Antli | Not Started | Needed prior to testing and pre-reqvisits of testing phase | [5 empty] | 2016-04-25 | [26 empty] | No Review | 8 | NAM AR |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
27 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_27 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-16 |  | 2016-05-16 | [24 empty] | No Review | 160 | NAM AR |  |  |  | Testing |  |  |  | 80 | 80 | [5 empty] | 160 | REVIEW | REVIEW | -
28 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_28 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-07-04 | [24 empty] | No Review | 150 | NAM AR |  |  |  | Testing |  |  |  |  | 40 | 70 | 40 |  |  |  | 150 | REVIEW | REVIEW | -
29 | EFAS16 | EFAS16_EFAS16_PSC_29 | Istvan Katus_Procurement Services | EFAS16_PSC | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 120 | PSC Team |  |  |  | System config | [6 empty] | 120 |  |  |  | 120 | REVIEW | REVIEW | -
31 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_31 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Update daily cash controll/cash application controll process | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Other GSS and treasury | Judit Antli | Not Started | To make sure that all payments are booked at both Co. - communication and reporting with TBO | [7 empty] | 2016-08-01 | [24 empty] | No Review | 40 | NAM AR |  |  |  | Training | [6 empty] | 40 |  |  |  | 40 | REVIEW | REVIEW | -
33 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_33 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Change Customer set up from interco to third party for both relationship | Both | FALSE |  | 2016-09-30 | 2 | 2016-09-28 | 0% | TRUE | PSC | Judit Antli | Not Started | Customer master data to be reviewed and updated - external <> internal Customer | [7 empty] | 2016-09-30 | [24 empty] | No Review | 8 | NAM AR |  |  |  | System config | [8 empty] | 8 |  | 8 | REVIEW | REVIEW | -
35 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_35 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Create a process for misdirected payments | Both | FALSE |  | 2016-07-20 | 30 | 2016-06-20 | 0% | TRUE | Treasury | Judit Antli | Not Started | From Day 1 we need to develop a transparent process for both companies ( Customers will pay to wrong bank account) |  |  | 2016-08-01 | [29 empty] | No Review | 80 | NAM AR |  |  |  | Training | [5 empty] | 40 | 40 |  |  |  | 80 | REVIEW | REVIEW | -
36 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_36 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | NAM AR |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
1 | EFAS13 | EFAS13_EFAS13_Master Data Management_1 | Istvan Katus_Finance | EFAS13_Master Data Management | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Nóra Lukács | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 100 | MDM Team |  |  |  | System config | [6 empty] | 100 |  |  |  | 100 | REVIEW | REVIEW | -
2 | EFAS04 | EFAS04_EFAS04_Compliance_2 | Istvan Katus_Compliance and Reporting | EFAS04_Compliance | Separate Book Club - physically and the sharepoint | Both | FALSE |  | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE |  | Ágota Vízkeleti | Not Started | [33 empty] | No Review | 2 | Compliance Team |  |  |  | Other | [7 empty] | 1 | 1 |  | 2 | REVIEW | REVIEW | -
5 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_5 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | GSS to review R12 amortization cost | Both | FALSE |  | 2016-10-01 | 1 | 2016-09-30 | 0% | TRUE | CORP ? Legal ? | Judit Antli | Not Started | Currently the R12 amortization is charged to BU and sitting in RU - will be allococated and split ? |  |  |  | 2016-08-01 | [28 empty] | No Review | 8 | AC FA&PA |  |  |  | Training | [9 empty] | 8 | 8 | REVIEW | REVIEW | -
7 | EFAS09 | EFAS09_EFAS09_Finance System Support _7 | Istvan Katus_Finance | EFAS09_Finance System Support | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 300 | Functional Support Team | 216 | Project team |  | System config | [6 empty] | 516 |  |  |  | 516 | REVIEW | REVIEW | -
9 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_9 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Review existing documents and create new ones if needed | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | To make sure that processes are well documented at both companies | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
10 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_10 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Create/update training Plan for Assets and Projects | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | FALSE |  | Judit Antli | Not Started | Update training materials ( lastly used by Infosys transition) with changes | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
11 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_11 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Review knowledge base of the team members | Both | FALSE |  | 2016-02-28 | 15 | 2016-02-13 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | Review | 4 | AC FA&PA |  |  |  | Training |  | 4 | [8 empty] | 4 | - | REVIEW | REVIEW
13 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_13 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
14 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_14 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Complete any knowledge transfer/training required for target condition. | Both | FALSE |  | 2016-07-20 | 60 | 2016-05-21 | 0% | FALSE |  | Judit Antli | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. To make sure that required knowledge will be avaliable at both companies by D1 | [32 empty] | No Review | 170 | AC FA&PA |  |  |  | Training |  |  |  |  | 50 | 60 | 60 |  |  |  | 170 | REVIEW | REVIEW | -
15 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_15 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | AC FA&PA |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
17 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_17 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Request responsibilities, accesses for the users ( EBS) | Both | FALSE |  | 2016-04-25 | 20 | 2016-04-05 | 0% | TRUE | IT | Judit Antli | Not Started | Needed prior to testing and pre-reqvisits of testing phase | [5 empty] | 2016-04-25 | [26 empty] | No Review | 8 | AC FA&PA |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
18 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_18 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Request shared mailboxes, rewrite worklflows, update FA templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-18 | [26 empty] | No Review | 80 | AC FA&PA |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
19 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_19 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Set up of new eRFA system | Up. Co. | FALSE |  | 2016-04-18 | 10 | 2016-04-08 | 0% | TRUE | IT, BU | Judit Antli | Not Started | Will Upstrean use eRFA system :? | [5 empty] | 2016-04-18 | [26 empty] | No Review | N/A | AC FA&PA |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
20 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_20 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Global reporting set up - review and modification according to the separation | Both | FALSE |  | 2016-08-31 | 30 | 2016-08-01 | 0% | TRUE | BU | Judit Antli | Not Started | GPP use complex reporting accross regions, if needed set up and process need to be tested | [32 empty] | No Review | 80 | AC FA&PA |  |  |  | Training | [7 empty] | 80 |  |  | 80 | REVIEW | REVIEW | -
29 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_29 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Asset image copy and store | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | TRUE | IT | Judit Antli | Not Started | Due to server change | [5 empty] | 2016-10-01 | [26 empty] | No Review | N/A | AC FA&PA |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
30 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_30 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Write ( copy / paste ) macros | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | IT/KC | Judit Antli | Not Started | Write/update macros used on FA and PA | [5 empty] | 2016-08-01 | [26 empty] | No Review | 50 | AC FA&PA |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
25 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_25 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-20 |  | 2016-04-20 | [24 empty] | No Review | 150 | AC FA&PA |  |  |  | Testing |  |  |  | 80 | 70 | [5 empty] | 150 | REVIEW | REVIEW | -
26 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_26 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-05-23 | [24 empty] | No Review | 210 | AC FA&PA |  |  |  | Testing |  |  |  |  | 80 | 80 | 50 |  |  |  | 210 | REVIEW | REVIEW | -
27 | EFAS17 | EFAS17_EFAS17_Reporting_27 | Istvan Katus_Compliance and Reporting | EFAS17_Reporting | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 8 | DMR Team |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
30 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_30 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | AC FA&PA |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
1 | EFAS01 | EFAS01_EFAS01_Accounts Payable_1 | Istvan Katus_Finance | EFAS01_Accounts Payable | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 15 | AP teams |  |  |  | System config | [6 empty] | 15 |  |  |  | 15 | REVIEW | REVIEW | -
1 | EFAS01 |  | Istvan Katus_Finance | EFAS01_Accounts Payable | Complete trainings as per trainings plans | Both | FALSE |  | 2016-05-15 | 80 | 2016-02-25 | 0% | FALSE |  | Anikó Krizsány | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 190 | AP teams |  |  |  | Training |  | 20 | 100 | 40 | 30 | [5 empty] | 190 | REVIEW | REVIEW | -
2 | EFAS15 | EFAS15_EFAS15_Treasury BackOffice_2 | Istvan Katus_Treasury | EFAS15_Treasury BackOffice | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 16 | TBO |  |  |  | System config | [6 empty] | 16 |  |  |  | 16 | REVIEW | REVIEW | -
5 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_5 | Istvan Katus_Finance | EFAS06_FAPA_AUS | GSS to review R12 amortization cost | Both | FALSE |  | 2016-10-01 | 1 | 2016-09-30 | 0% | TRUE | CORP ? Legal ? | Judit Antli | Not Started | Currently the R12 amortization is charged to BU and sitting in RU - will be allococated and split ? |  |  |  | 2016-08-01 | [28 empty] | No Review | 8 | AC FA&PA |  |  |  | Training | [9 empty] | 8 | 8 | REVIEW | REVIEW | -
7 | EFAS12 | EFAS12_EFAS12_IICS_7 | Istvan Katus_Finance | EFAS12_IICS | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 8 | IICS team |  |  |  | System config | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
11 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_11 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | AC FA&PA |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
12 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_12 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
13 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_13 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Request shared mailboxes, rewrite worklflows, update FA templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-18 | [26 empty] | No Review | 80 | AC FA&PA |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
14 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_14 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Set up of new eRFA system | Up. Co. | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT, BU | Judit Antli | Not Started | Will Upstream use eRFA system :? | [5 empty] | 2016-04-18 | [26 empty] | No Review | N/A | AC FA&PA |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
15 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_15 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Global reporting set up - review and modification according to the separation | Both | FALSE |  | 2016-08-31 | 30 | 2016-08-01 | 0% | TRUE | BU | Judit Antli | Not Started | GPP use complex reporting accross regions, if needed set up and process need to be tested | [32 empty] | No Review | 80 | AC FA&PA |  |  |  | Training | [7 empty] | 80 |  |  | 80 | REVIEW | REVIEW | -
20 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_20 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Asset image copy and store | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | TRUE | IT | Judit Antli | Not Started | Due to server change | [5 empty] | 2016-10-01 | [26 empty] | No Review | N/A | AC FA&PA |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
21 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_21 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Write ( copy / paste ) macros | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | IT/KC | Judit Antli | Not Started | Write/update macros used on FA and PA | [5 empty] | 2016-08-01 | [26 empty] | No Review | 70 | AC FA&PA |  |  |  | System config | [6 empty] | 70 |  |  |  | 70 | REVIEW | REVIEW | -
16 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_16 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-16 |  | 2016-05-16 | [24 empty] | No Review | 90 | AC FA&PA |  |  |  | Testing |  |  |  | 30 | 60 | [5 empty] | 90 | REVIEW | REVIEW | -
17 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_17 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-07-04 | [24 empty] | No Review | 140 | AC FA&PA |  |  |  | Testing |  |  |  |  | 30 | 80 | 30 |  |  |  | 140 | REVIEW | REVIEW | -
18 | EFAS18 | EFAS18_EFAS18_T&E_18 | Istvan Katus_Finance | EFAS18_T&E | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 17 | 2016-07-15 | 0% | TRUE | IT needs to be ready | Anikó Krizsány | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | 16 | T&E |  |  |  | System config | [6 empty] | 16 |  |  |  | 16 | REVIEW | REVIEW | -
21 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_21 | Istvan Katus_Finance | EFAS06_FAPA_AUS | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | AC FA&PA |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
1 | EFAS02 | EFAS02_EFAS02_AR_CAN_USA_1 | Istvan Katus_Finance | EFAS02_AR_CAN_USA | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-08-01 |  | 2016-08-01 | [24 empty] | No Review | 50 | NAM AR |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
4 | EFAS08 | EFAS08_EFAS08_FAPA_EU_4 | Istvan Katus_Finance | EFAS08_FAPA_EU | GSS to review R12 amortization cost | Both | FALSE |  | 2016-10-01 | 1 | 2016-09-30 | 0% | TRUE | CORP ? Legal ? | Judit Antli | Not Started | Currently the R12 amortization is charged to BU and sitting in RU - will be allococated and split ? |  |  |  | 2016-08-01 | [28 empty] | No Review | 8 | AC FA&PA |  |  |  | Training | [9 empty] | 8 | 8 | REVIEW | REVIEW | -
6 | EFAS07 | EFAS07_EFAS07_FAPA_CAN_US_6 | Istvan Katus_Finance | EFAS07_FAPA_CAN_US | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-08-01 |  | 2016-07-12 | [24 empty] | No Review | 50 | AC FA&PA |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
12 | EFAS08 | EFAS08_EFAS08_FAPA_EU_12 | Istvan Katus_Finance | EFAS08_FAPA_EU | Review existing documents and create new ones if needed | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | To make sure that processes are well documented at both companies | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
13 | EFAS08 | EFAS08_EFAS08_FAPA_EU_13 | Istvan Katus_Finance | EFAS08_FAPA_EU | Create/update training Plan for Assets and Projects | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | FALSE |  | Judit Antli | Not Started | Update training materials ( lastly used by Infosys transition) with changes | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
14 | EFAS08 | EFAS08_EFAS08_FAPA_EU_14 | Istvan Katus_Finance | EFAS08_FAPA_EU | Review knowledge base of the team members | Both | FALSE |  | 2016-02-28 | 15 | 2016-02-13 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | Review | 16 | AC FA&PA |  |  |  | Training |  | 16 | [8 empty] | 16 | - | REVIEW | REVIEW
16 | EFAS08 | EFAS08_EFAS08_FAPA_EU_16 | Istvan Katus_Finance | EFAS08_FAPA_EU | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | AC FA&PA |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
17 | EFAS08 | EFAS08_EFAS08_FAPA_EU_17 | Istvan Katus_Finance | EFAS08_FAPA_EU | Complete any knowledge transfer/training required for target condition. | Both | FALSE |  | 2016-07-20 | 60 | 2016-05-21 | 0% | FALSE |  | Judit Antli | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. To make sure that required knowledge will be avaliable at both companies by D1 | [32 empty] | No Review | 160 | AC FA&PA |  |  |  | Training |  |  |  |  | 30 | 70 | 60 |  |  |  | 160 | REVIEW | REVIEW | -
18 | EFAS08 | EFAS08_EFAS08_FAPA_EU_18 | Istvan Katus_Finance | EFAS08_FAPA_EU | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | AC FA&PA |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
20 | EFAS08 | EFAS08_EFAS08_FAPA_EU_20 | Istvan Katus_Finance | EFAS08_FAPA_EU | Request responsibilities, accesses for the users ( EBS) | Both | FALSE |  | 2016-04-25 | 20 | 2016-04-05 | 0% | TRUE | IT | Judit Antli | Not Started | Needed prior to testing and pre-reqvisits of testing phase | [5 empty] | 2016-04-25 |  | #REF! | [24 empty] | No Review | 8 | AC FA&PA |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
21 | EFAS08 | EFAS08_EFAS08_FAPA_EU_21 | Istvan Katus_Finance | EFAS08_FAPA_EU | Request shared mailboxes, rewrite worklflows, update FA templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-18 | [26 empty] | No Review | 80 | AC FA&PA |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
| EFAS08 | EFAS08_EFAS08_FAPA_EU_ | Istvan Katus_Finance | EFAS08_FAPA_EU | Review FA&PA configuration - create separate OU for commingled legal entities and reconcile balances | Both | TRUE |  | 2016-05-01 | 35 | 2016-03-27 | 0% | TRUE | IT. Other GSS | Judit Antli | Not Started | Shared OU to be used by Up Stream Co ? | No Review | 320 | [30 empty] | No Review | 100 | AC FA&PA |  |  |  | System config |  |  |  | 100 | [6 empty] | 100 | REVIEW | REVIEW | -
22 | EFAS08 | EFAS08_EFAS08_FAPA_EU_22 | Istvan Katus_Finance | EFAS08_FAPA_EU | Set up of new eRFA system | Up. Co. | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT, BU | Judit Antli | Not Started | Will Upstrean use eRFA system :? | [5 empty] | 2016-04-18 | [26 empty] | No Review | N/A | AC FA&PA |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
23 | EFAS08 | EFAS08_EFAS08_FAPA_EU_23 | Istvan Katus_Finance | EFAS08_FAPA_EU | Global reporting set up - review and modification according to the separation | Both | FALSE |  | 2016-08-31 | 30 | 2016-08-01 | 0% | TRUE | BU | Judit Antli | Not Started | GPP use complex reporting accross regions, if needed set up and process need to be tested | [32 empty] | No Review | 80 | AC FA&PA |  |  |  | Training | [7 empty] | 80 |  |  | 80 | REVIEW | REVIEW | -
28 | EFAS08 | EFAS08_EFAS08_FAPA_EU_28 | Istvan Katus_Finance | EFAS08_FAPA_EU | Asset image copy and store | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | TRUE | IT | Judit Antli | Not Started | Due to server change | [5 empty] | 2016-10-01 | [26 empty] | No Review | N/A | AC FA&PA |  |  |  | System config | [10 empty] | 0 | REVIEW | REVIEW | -
29 | EFAS08 | EFAS08_EFAS08_FAPA_EU_29 | Istvan Katus_Finance | EFAS08_FAPA_EU | Write ( copy / paste ) macros | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | IT/KC | Judit Antli | Not Started | Write/update macros used on FA and PA | [5 empty] | 2016-08-01 | [26 empty] | No Review | 70 | AC FA&PA |  |  |  | System config | [6 empty] | 70 |  |  |  | 70 | REVIEW | REVIEW | -
31 | EFAS08 | EFAS08_EFAS08_FAPA_EU_31 | Istvan Katus_Finance | EFAS08_FAPA_EU | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-16 |  | 2016-05-16 | [24 empty] | No Review | 150 | AC FA&PA |  |  |  | Testing |  |  |  | 50 | 100 | [5 empty] | 150 | REVIEW | REVIEW | -
32 | EFAS08 | EFAS08_EFAS08_FAPA_EU_32 | Istvan Katus_Finance | EFAS08_FAPA_EU | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-07-04 | [24 empty] | No Review | 280 | AC FA&PA |  |  |  | Testing |  |  |  |  | 80 | 130 | 70 |  |  |  | 280 | REVIEW | REVIEW | -
33 | EFAS06 | EFAS06_EFAS06_FAPA_AUS_33 | Istvan Katus_Finance | EFAS06_FAPA_AUS | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-08-01 |  | 2016-08-01 | [24 empty] | No Review | 50 | AC FA&PA |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
30 | EFAS08 | EFAS08_EFAS08_FAPA_EU_30 | Istvan Katus_Finance | EFAS08_FAPA_EU | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | AC FA&PA |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
1 | EFAS08 | EFAS08_EFAS08_FAPA_EU_1 | Istvan Katus_Finance | EFAS08_FAPA_EU | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-08-01 |  | 2016-08-01 | [24 empty] | No Review | 50 | AC FA&PA |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
2 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_2 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-08-01 |  | 2016-08-01 | [24 empty] | No Review | 50 | NAM GL |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
6 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_6 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. |  |  | 2016-08-01 |  |  | 2016-08-01 |  | 2016-08-01 | [24 empty] | No Review | 50 | AC EUR (GL/AR) |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
8 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_8 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Define required action regarding annual reporting | Both | FALSE |  | 2016-08-01 | 10 | 2016-07-22 | 0% | TRUE | Legal decision | Judit Antli | Not Started | Statutory report . Taxpackage, MA-10000, Timliness Annual Survey of Manufactures (ASM) consists of Form MA-10000 (general statistics inquiry items and a value of product classes shipped inquiry |  |  |  | 2016-08-01 | [28 empty] | No Review | 32 | NAM GL |  |  |  | Training | [6 empty] | 32 |  |  |  | 32 | REVIEW | REVIEW | -
9 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_9 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Define required action regarding Aluminium association reporting | Both | FALSE |  | 2016-08-01 | 10 | 2016-07-22 | 0% | TRUE | Legal decision | Judit Antli | Not Started | Decision ot be made that report is required for both Co for statutory purposes - monthly reporting of aluminium production data to Aluminium Association - review reports and adjust to future company needs |  |  |  | 2016-08-01 | [28 empty] | No Review | 32 | NAM GL |  |  |  | Training | [6 empty] | 32 |  |  |  | 32 | REVIEW | REVIEW | -
12 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_12 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Review existing documents and create new ones if needed | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | To make sure that processes are well documented at both companies | [32 empty] | No Review | 40 | NAM GL |  |  |  | Training | [6 empty] | 40 |  |  |  | 40 | REVIEW | REVIEW | -
14 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_14 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Review knowledge base of the team members | Both | FALSE |  | 2016-02-28 | 15 | 2016-02-13 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | Review | 4 | NAM GL |  |  |  | Training |  | 4 | [8 empty] | 4 | - | REVIEW | REVIEW
15 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_15 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Create/update training Plan for USA and CAN processes | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | FALSE |  | Judit Antli | Not Started | Update training materials ( lastly used by Infosys transition) with changes | [32 empty] | No Review | 8 | NAM GL |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
16 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_16 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | NAM GL |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
17 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_17 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Complete any knowledge transfer/training required for target condition. | Both | FALSE |  | 2016-07-20 | 60 | 2016-05-21 | 0% | FALSE |  | Judit Antli | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. To make sure that required knowledge will be avaliable at both companies by D1 | [32 empty] | No Review | 240 | NAM GL |  |  |  | Training |  |  |  |  | 60 | 90 | 90 |  |  |  | 240 | REVIEW | REVIEW | -
18 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_18 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a for GL processes | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | NAM GL |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
19 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_19 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a for Cost Accounting processes | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | NAM GL |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
20 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_20 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a for System related tasks | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | NAM GL |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
21 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_21 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Maaden recharge review | Up. Co. | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | BU | Judit Antli | Not Started | BU involvment is needed how the the recharge will be processed at Up.Co. How to carry charges to Up.Co after separation | [32 empty] | No Review | 40 | NAM GL |  |  |  | Training | [6 empty] | 40 |  |  |  | 40 | REVIEW | REVIEW | -
22 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_22 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Dividend clearing - Interco trx - close and clear balances | Both | FALSE |  | 2016-10-01 | 5 | 2016-09-26 | 0% | TRUE | Legal | Judit Antli | Not Started | US process to close interco positions - prior to official separation |  |  |  | 2016-10-01 | [28 empty] | No Review | 80 | NAM GL |  |  |  | System config | [8 empty] | 80 |  | 80 | REVIEW | REVIEW | -
23 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_23 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Revise and rewrite Mass Allocations | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | FALSE |  | Judit Antli | Not Started | If LBC will be changed the Allocation and | [32 empty] | No Review | 140 | NAM GL |  |  |  | Training |  |  | 80 | 60 | [6 empty] | 140 | REVIEW | REVIEW | -
24 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_24 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Update / revise monthly checklist/ folders, etc | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | [33 empty] | No Review | 100 | NAM GL |  |  |  | Training | [6 empty] | 100 |  |  |  | 100 | REVIEW | REVIEW | -
26 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_26 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Update / revise IQY and Discoverer reports | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | IT, KC | Judit Antli | Not Started | Needed for Day 1 - serve BU with proper reports and support ME closing | [5 empty] | 2016-08-01 | [26 empty] | No Review | 150 | NAM GL |  |  |  | System config | [5 empty] | 80 | 70 |  |  |  | 150 | REVIEW | REVIEW | -
27 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_27 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Update / review of macro's | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | IT, KC | Judit Antli | Not Started | Macros to be collected , need to be rewritten according to separation | [5 empty] | 2016-08-01 | [26 empty] | No Review | 150 | NAM GL |  |  |  | System config | [5 empty] | 80 | 70 |  |  |  | 150 | REVIEW | REVIEW | -
28 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_28 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Request shared mailboxes, rewrite worklflows, update any GL templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-18 | [26 empty] | No Review | 80 | NAM GL |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
31 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_31 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Request responsibilities, accesses for the users ( EBS) | Both | FALSE |  | 2016-04-25 | 20 | 2016-04-05 | 0% | TRUE | IT | Judit Antli | Not Started | Needed prior to testing and pre-reqvisits of testing phase | [5 empty] | 2016-04-25 | [26 empty] | No Review | 8 | NAM GL |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
32 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_32 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-16 |  | 2016-05-16 | [24 empty] | No Review | 230 | NAM GL |  |  |  | Testing |  |  |  | 100 | 130 | [5 empty] | 230 | REVIEW | REVIEW | -
33 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_33 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-07-04 | [24 empty] | No Review | 470 | NAM GL |  |  |  | Testing |  |  |  |  | 80 | 320 | 70 |  |  |  | 470 | REVIEW | REVIEW | -
28 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_28 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E validation prior to go live | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. |  |  | 2016-08-01 |  |  | 2016-08-01 |  | 2016-08-01 | [24 empty] | No Review | 50 | AC EUR (GL/AR) |  |  |  | System config | [6 empty] | 50 |  |  |  | 50 | REVIEW | REVIEW | -
30 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_30 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Contact list update | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | FALSE |  | Judit Antli | Not Started | Contact lists to be updated both on GSS and BU side | [32 empty] | No Review | 32 | NAM GL |  |  |  | Training | [6 empty] | 32 |  |  |  | 32 | REVIEW | REVIEW | -
31 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_31 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | Booking entries on 2000%, 5% accounts | Both | FALSE |  | 2016-10-01 | 5 | 2016-09-26 | 0% | TRUE | Legal | Judit Antli | Not Started | Based on Ownership entries to be booked relate to separation |  |  |  | 2016-08-31 | [28 empty] | No Review | 96 | NAM GL |  |  |  | Training | [8 empty] | 96 |  | 96 | REVIEW | REVIEW | -
33 | EFAS10 | EFAS10_EFAS10_General Ledger_CAN_US_33 | Istvan Katus_Finance | EFAS10_General Ledger_CAN_US | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | NAM GL |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
6 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_6 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Review AR configuration - create separate OU for commingled legal entities and reconcile balances | Both | TRUE |  | 2016-05-01 | 35 | 2016-03-27 | 0% | TRUE | IT, Other GSS | Judit Antli | Not Started | AR OU to be used by Up Stream Co in Italy for ASV and ATR | [5 empty] | 2016-02-22 | 2016-02-22 | 2016-02-22 | [24 empty] | No Review | 100 | AC EUR (GL/AR) |  |  |  | Training |  |  |  | 100 | [6 empty] | 100 | REVIEW | REVIEW | -
8 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_8 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Review existing documents and create new ones if needed | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | To make sure that processes are well documented at both companies | [32 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | Training | [6 empty] | 8 |  |  |  | 8 | REVIEW | REVIEW | -
9 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_9 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Create/update training Plan Cash Application, Revenue upload, manual invoicing process | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | FALSE |  | Judit Antli | Not Started | Update training materials ( lastly used by Infosys transition) with changes | [32 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
10 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_10 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Review knowledge base of the team members | Both | FALSE |  | 2016-02-28 | 15 | 2016-02-13 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | Review | 4 | AC EUR (GL/AR) |  |  |  | Training |  | 4 | [8 empty] | 4 | - | REVIEW | REVIEW
11 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_11 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
12 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_12 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Complete any knowledge transfer/training required for target condition. | Both | FALSE |  | 2016-07-20 | 60 | 2016-05-21 | 0% | FALSE |  | Judit Antli | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. To make sure that required knowledge will be avaliable at both companies by D1 | [32 empty] | No Review | 160 | AC EUR (GL/AR) |  |  |  | Training |  |  |  |  | 30 | 70 | 60 |  |  |  | 160 | REVIEW | REVIEW | -
13 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_13 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | AC EUR (GL/AR) |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
14 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_14 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Create list of responsibilities, accesses needed to Lockbox | Both | FALSE |  | 2016-05-27 | 17 | 2016-05-10 | 0% | TRUE | Treasury is opening new lockboxes and grant accessess | Judit Antli | Not Started | New Lockboxes and bank accounts will be used |  |  | 2016-05-27 | [29 empty] | No Review | 32 | AC EUR (GL/AR) |  |  |  | Training |  |  |  |  | 32 | [5 empty] | 32 | REVIEW | REVIEW | -
15 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_15 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Create access to new bank accounts | Both | TRUE |  | 2016-07-20 | 30 | 2016-06-20 | 0% | TRUE | Treasury is opening new lockboxes and grant accessess | Judit Antli | Not Started | New bank accounts will be used |  |  | 2016-05-27 | [29 empty] | No Review | 32 | AC EUR (GL/AR) |  |  |  | Training | [5 empty] | 16 | 16 |  |  |  | 32 | REVIEW | REVIEW | -
16 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_16 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Request shared mailboxes, rewrite wroklflows, update AR templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-30 | [26 empty] | No Review | 80 | AC EUR (GL/AR) |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
20 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_20 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Test invoice file creation and invoice printing | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | IT | Judit Antli | Not Started | To make sure that company names and logos are properly printed | [5 empty] | 2016-05-27 | [26 empty] | No Review | 150 | AC EUR (GL/AR) |  |  |  | Testing | [5 empty] | 80 | 70 |  |  |  | 150 | REVIEW | REVIEW | -
22 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_22 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Request responsibilities, accesses for the users ( EBS) | Both | FALSE |  | 2016-04-25 | 20 | 2016-04-05 | 0% | TRUE | IT | Judit Antli | Not Started | Needed prior to testing and pre-reqvisits of testing phase | [5 empty] | 2016-04-25 | [26 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
23 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_23 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-16 |  | 2016-05-16 | [24 empty] | No Review | 170 | AC EUR (GL/AR) |  |  |  | Testing |  |  |  | 50 | 120 | [5 empty] | 170 | REVIEW | REVIEW | -
24 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_24 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-07-04 | [24 empty] | No Review | 270 | AC EUR (GL/AR) |  |  |  | Testing |  |  |  |  | 80 | 120 | 70 |  |  |  | 270 | REVIEW | REVIEW | -
27 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_27 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Update daily cash controll/cash application controll process | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Other GSS and BU involvment | Judit Antli | Not Started | To make sure that all payments are booked at both Co. - communication and reporting with TBO |  |  | 2016-08-01 |  |  |  |  | 2016-08-01 | [24 empty] | No Review | 40 | AC EUR (GL/AR) |  |  |  | Training | [6 empty] | 40 |  |  |  | 40 | REVIEW | REVIEW | -
29 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_29 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Change Customer set up from interco to third party for both relationship | Both | FALSE |  | 2016-09-30 | 2 | 2016-09-28 | 0% | TRUE | PSC | Judit Antli | Not Started | Customer master data to be reviewed and updated - external <> internal Customer | [7 empty] | 2016-09-30 | [24 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | System config | [8 empty] | 8 |  | 8 | REVIEW | REVIEW | -
31 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_31 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | Create a process for misdirected payments | Both | FALSE |  | 2016-07-20 | 30 | 2016-06-20 | 0% | TRUE | Treasury | Judit Antli | Not Started | From Day 1 we need to develop a transparent process for both companies ( Customers will pay to wrong bank account) |  |  | 2016-08-01 | [29 empty] | No Review | 80 | AC EUR (GL/AR) |  |  |  | Training | [5 empty] | 40 | 40 |  |  |  | 80 | REVIEW | REVIEW | -
32 | EFAS03 | EFAS03_EFAS03_Accounts Receivable_EU_32 | Istvan Katus_Finance | EFAS03_Accounts Receivable_EU | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | AC EUR (GL/AR) |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
10 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_10 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Participate (testing) in pre-projects of separation of commingled legal entities and OUs (US) | Both | TRUE |  | 2016-05-01 | 35 | 2016-03-27 | 0% | TRUE | IT. Other GSS | Judit Antli | Not Started | Italian Up.Co and V-A. Co. Are in shared SOB in GL | [32 empty] | No Review | 100 | AC EUR (GL/AR) |  |  |  | Testing |  |  |  | 100 | [6 empty] | 100 | REVIEW | REVIEW | -
12 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_12 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Review existing documents and create new ones if needed | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | To make sure that processes are well documented at both companies | [32 empty] | No Review | 16 | AC EUR (GL/AR) |  |  |  | Training | [6 empty] | 16 |  |  |  | 16 | REVIEW | REVIEW | -
13 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_13 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Review knowledge base of the team members | Both | FALSE |  | 2016-04-18 | 15 | 2016-04-03 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | Training |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
14 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_14 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Create/update training Plan for GL processes | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | FALSE |  | Judit Antli | Not Started | Update training materials ( lastly used by Infosys transition) with changes | [32 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
15 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_15 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Define task list and responsibility matrix (who will be responsible for each tasks at both companies) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal Process, as preparation for the training and test | [32 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | Training |  |  | 8 | [7 empty] | 8 | REVIEW | REVIEW | -
16 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_16 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Complete any knowledge transfer/training required for target condition. | Both | FALSE |  | 2016-07-20 | 60 | 2016-05-21 | 0% | FALSE |  | Judit Antli | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. To make sure that required knowledge will be avaliable at both companies by D1 | [32 empty] | No Review | 160 | AC EUR (GL/AR) |  |  |  | Training |  |  |  |  | 30 | 70 | 60 |  |  |  | 160 | REVIEW | REVIEW | -
17 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_17 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Develop test plans to make sure that all type of trx is captured and restricted to Up.Co and V.a for GL processes | Both | FALSE |  | 2016-04-17 | 30 | 2016-03-18 | 0% | FALSE |  | Judit Antli | Not Started | Plan to exclude non relevant trx | [32 empty] | No Review | 40 | AC EUR (GL/AR) |  |  |  | Testing |  |  | 20 | 20 | [6 empty] | 40 | REVIEW | REVIEW | -
18 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_18 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Revise and rewrite Mass Allocation, Revaluation Process | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | FALSE |  | Judit Antli | Not Started | If LBC will be changed the Allocation need to be revised | [32 empty] | No Review | 120 | AC EUR (GL/AR) |  |  |  | Training |  |  | 80 | 40 | [6 empty] | 120 | REVIEW | REVIEW | -
19 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_19 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Update / revise monthly checklist | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Judit Antli | Not Started | [33 empty] | No Review | 70 | AC EUR (GL/AR) |  |  |  | Training | [6 empty] | 70 |  |  |  | 70 | REVIEW | REVIEW | -
20 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_20 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Update / revise IQY and Discoverer reports | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | IT, KC | Judit Antli | Not Started | Needed for Day 1 - serve BU with proper reports and support ME closing | [5 empty] | 2016-08-01 | [26 empty] | No Review | 140 | AC EUR (GL/AR) |  |  |  | System config | [5 empty] | 70 | 70 |  |  |  | 140 | REVIEW | REVIEW | -
21 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_21 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Update / review of macro's | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | IT, KC | Judit Antli | Not Started | Macros to be collected , need to be rewritten according to separation | [5 empty] | 2016-08-01 | [26 empty] | No Review | 140 | AC EUR (GL/AR) |  |  |  | System config | [5 empty] | 70 | 70 |  |  |  | 140 | REVIEW | REVIEW | -
22 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_22 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Request shared mailboxes, rewrite worklflows, update any GL templates | Both | FALSE |  | 2016-04-18 | 30 | 2016-03-19 | 0% | TRUE | IT | Judit Antli | Not Started | As domain name will be changed is it needed for both Co ? | [5 empty] | 2016-04-30 | [26 empty] | No Review | 80 | AC EUR (GL/AR) |  |  |  | Training |  |  | 40 | 40 | [6 empty] | 80 | REVIEW | REVIEW | -
24 | EFAS09 | EFAS09_EFAS09_Finance System Support _24 | Istvan Katus_Finance | EFAS09_Finance System Support | Participate in internal testing activity 1 | Both | FALSE |  | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT needs to be ready | Ágota Vízkeleti | Not Started | Test the application | [5 empty] | 2016-04-15 | [26 empty] | No Review | 580 | Functional Support Team |  |  |  | System config/Testing |  |  | 380 | 200 | [6 empty] | 580 | REVIEW | REVIEW | -
25 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_25 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Request responsibilities, accesses for the users ( EBS) | Both | FALSE |  | 2016-04-25 | 20 | 2016-04-05 | 0% | TRUE | IT | Judit Antli | Not Started | Needed prior to testing and pre-reqvisits of testing phase | [5 empty] | 2016-04-25 | [26 empty] | No Review | 8 | AC EUR (GL/AR) |  |  |  | System config |  |  |  | 8 | [6 empty] | 8 | REVIEW | REVIEW | -
26 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_26 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE |  | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | Other GSS and BU involvment , IT -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-05-16 |  | 2016-05-16 | [24 empty] | No Review | 190 | AC EUR (GL/AR) |  |  |  | Testing |  |  |  | 80 | 110 | [5 empty] | 190 | REVIEW | REVIEW | -
27 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_27 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Other GSS, IT and BU involvment -make sure E2E testing and validation. | Judit Antli | Not Started | Integrated testing of systems and procedures to assure E2E processes are meeting target requirements. | [5 empty] | 2016-07-08 |  | 2016-07-04 | [24 empty] | No Review | 430 | AC EUR (GL/AR) |  |  |  | Testing |  |  |  |  | 80 | 300 | 50 |  |  |  | 430 | REVIEW | REVIEW | -
30 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_30 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Contact list update | Both | FALSE |  | 2016-08-01 | 20 | 2016-07-12 | 0% | FALSE |  | Judit Antli | Not Started | Contact lists to be updated both on GSS and BU side | [32 empty] | No Review | 32 | AC EUR (GL/AR) |  |  |  | Training | [6 empty] | 32 |  |  |  | 32 | REVIEW | REVIEW | -
31 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_31 | Istvan Katus_Finance | EFAS11_General Ledger_EU | Booking entries on 2000%, 5% accounts | Both | FALSE |  | 2016-10-01 | 5 | 2016-09-26 | 0% | TRUE | Legal | Judit Antli | Not Started | Based on Ownership entries to be booked relate to separation |  |  |  | 2016-08-31 | [28 empty] | No Review | 120 | AC EUR (GL/AR) |  |  |  | Training | [8 empty] | 120 |  | 120 | REVIEW | REVIEW | -
33 | EFAS11 | EFAS11_EFAS11_General Ledger_EU_33 | Istvan Katus_Finance | EFAS11_General Ledger_EU | SLA's, policies and procedures aligned with target condition. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE |  | Judit Antli | Not Started | Internal work to be completed. | [32 empty] | No Review | N/A | AC EUR (GL/AR) |  |  |  | Training | [10 empty] | 0 | REVIEW | REVIEW | -
|  |  |  | EFAS15_Treasury BackOffice | Complete work transition as per plan | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Anikó Krizsány | Not Started | [33 empty] | No Review | 640 | TBO |  |  |  | Training |  |  |  | 240 | 240 | 80 | 80 |  |  |  | 640 | REVIEW | REVIEW | -
[50 empty] | Review | [5 empty] | Total hours | 250 | 402 | 1541 | 4488 | 4539 | 4231 | 4060 | 469 | 403 | 73 |  | - | -
|  | __ | [47 empty] | Review | [5 empty] | Total FTEs | 1.4706 | 2.3647 | 9.0647 | 26.4 | 26.7 | 24.8882 | 23.8824 | 2.7588 | 2.3706 | 0.42941 |  | - | -
|  | __ | [47 empty] | Review | [5 empty] | Capacity |  |  |  | 2600 | 2600 | 2500 | 2500 |  |  |  |  | - | -
|  | __ | [47 empty] | Review | [5 empty] | Total hours - capacity | 250 | 402 | 1541 | 1888 | 1939 | 1731 | 1560 | 469 | 403 | 73 |  | - | -
|  | __ | [47 empty] | Review | [5 empty] | Training |  |  |  | 11.1059 | 11.4059 | 10.1824 | 9.1765 |  |  |  |  | - | -
|  | __ | [47 empty] | Review | [17 empty] | - | -
4 FTEs needed with special knowledge (e.g. External Oracle consultants)
The rest of the FTE needs can be handled if we start hiring for the dis-synergie or scope add positions
x
Formulas:
Start Date (Calculated) = +TasksTable[[#This Row],[Required Completion Date]]-TasksTable[[#This Row],[Days to Accomplish]]
Start Date (Calculated) = +[Required Completion Date]-[Days to Accomplish]
For GSS PMO Review? = IF(AND(TasksTable[[#This Row],[Status]]<>"On Track",TasksTable[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Start Date Review = IFERROR(IF(TasksTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF(TasksTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Global Shared Services (GSS) = [Required Completion Date]
Global Shared Services (GSS) = [Start Date (Calculated)]
IT = [Required Completion Date]

## Day 1 Project Costs_IK
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Project Costs
As Of | 2016-02-15 14:00
Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale

## Data Validation (hide) (hidden)
Master Function List | Sub-function list
Legal | Legal | HumanResources | FinanceandAccounting | OCIO | InvestorRelations | Communications | GPI | GlobalBilling | BusinessUnitFunctions | Yes/No | Day 1 Target State | TSA Feasibility | TSA Exit Activities
Human Resources | Benefits | HR Systems | Treasury | PMO | Investor Relations | Inc. PR | Business Office | Operational | Strategy | Yes | Replicate (Clone) | Possible - Low/Medium Complexity | Replicate (Clone)
Finance and Accounting | Stock Systems | GTA | FP&A | Facilities |  | Internal | Operations | Systems | Sales & Business Development | No | Give and Go | Possible - Very Complex | Give and Go
OCIO | Competition | MyHR | Tax | HR Systems |  | Brand / EVP | Tools |  | Marketing |  | New Build | Impossible | New Build
Investor Relations | Corporate | Comp/Ben/M&A | AP | Other Enabling Sys |  | Social Innovation | Services |  | Risk |  | Forward TSA | Not Required | Standalone
Communications | Employment | L&OD | Travel | Finance Systems |  |  | Platform |  | Trust & Safety |  | Reverse TSA |  | Discontinue
GPI | Compliance | Diversity | Purchasing | CS Systems |  |  | Data |  | CS |  | Standalone |  | Operating Agreement
Global Billing | Government Relations |  | Payroll | Traditional IT Systems |  |  | Infrastructure/Cloud |  | PD / Arch |  | Discontinue
Business Unit Functions | IP |  | Finance Separation |  |  |  | Data Center |  | Product |  | Operating Agreement
| Privacy |  | Accounting Policy | [5 empty] | Data
| Litigation |  | SEC Reporting | [5 empty] | Info Security
| Real Estate |  | SOX | [5 empty] | Regulatory
Finance Trans
Procurement

## Countries (hidden)
# | Location Country | Total Employees
1 | USA Total |  | USA | USA | FRA | GBR | CAN | DEU | IND | AUS | SWE | MEX | BEL | HKG | SGP | CHE | ARG | NLD | DNK | TWN | POL | NOR | THA | CZE | GRC | HUN | MCO | ESP | LUX | FIN | JPN | NZL | BRA | CHN | IRL | MYS | RUS
2 | FRA Total |  | FRA | USA: USA,FRA,GBR,CAN,DEU,IND,AUS,SWE,MEX,BEL,HKG,SGP,CHE,ARG,NLD,DNK,TWN,POL,NOR,THA,CZE,GRC,HUN,MCO,ESP,LUX,FIN,JPN,NZL,BRA,CHN,IRL,MYS,RUS
3 | GBR Total |  | GBR
4 | CAN Total |  | CAN
5 | DEU Total |  | DEU
6 | IND Total |  | IND
7 | AUS Total |  | AUS
8 | SWE Total |  | SWE
9 | MEX Total |  | MEX
10 | BEL Total |  | BEL
11 | HKG Total |  | HKG
12 | SGP Total |  | SGP
13 | CHE Total |  | CHE
14 | ARG Total |  | ARG
15 | NLD Total |  | NLD
16 | DNK Total |  | DNK
17 | TWN Total |  | TWN
18 | POL Total |  | POL
19 | NOR Total |  | NOR
20 | THA Total |  | THA
21 | CZE Total |  | CZE
22 | GRC Total |  | GRC
23 | HUN Total |  | HUN
24 | MCO Total |  | MCO
25 | ESP Total |  | ESP
26 | LUX Total |  | LUX
27 | FIN Total |  | FIN
28 | JPN Total |  | JPN
29 | NZL Total |  | NZL
30 | BRA Total |  | BRA
31 | CHN Total |  | CHN
32 | IRL Total |  | IRL
33 | MYS Total |  | MYS
34 | RUS Total |  | RUS
Grand Total

## Sheet1
EFAS01_Accounts Payable | EFAS01 | Istvan Katus_Finance
EFAS02_AR_CAN_USA | EFAS02 | Istvan Katus_Finance
EFAS03_Accounts Receivable_EU | EFAS03 | Istvan Katus_Finance
EFAS04_Compliance | EFAS04 | Istvan Katus_Compliance and Reporting
EFAS05_Cost Accounting | EFAS05 | Istvan Katus_Finance
EFAS06_FAPA_AUS | EFAS06 | Istvan Katus_Finance
EFAS07_FAPA_CAN_US | EFAS07 | Istvan Katus_Finance
EFAS08_FAPA_EU | EFAS08 | Istvan Katus_Finance
EFAS09_Finance System Support | EFAS09 | Istvan Katus_Finance
EFAS10_General Ledger_CAN_US | EFAS10 | Istvan Katus_Finance
EFAS11_General Ledger_EU | EFAS11 | Istvan Katus_Finance
EFAS12_IICS | EFAS12 | Istvan Katus_Finance
EFAS13_Master Data Management | EFAS13 | Istvan Katus_Finance
EFAS14_Process Support | EFAS14 | Istvan Katus_Finance
EFAS15_Treasury BackOffice | EFAS15 | Istvan Katus_Treasury
EFAS16_PSC | EFAS16 | Istvan Katus_Procurement Services
EFAS17_Reporting | EFAS17 | Istvan Katus_Compliance and Reporting
EFAS18_T&E | EFAS18 | Istvan Katus_Finance
EFAS19_Shared Facilities | EFAS19 | Transformation_Facilities

## hetvege kalkuláció
35 | 1.1667 | 9.3333
25.6667

## Instructions
Tab Day 1 Project List- Update weekly
1. Column “Required Completion Date” and Column “Days to Accomplish”- please make sure you have an accurate as possible estimate in these fields.
2. Column “% Complete”- Please either enter accurate % to show your progress on the project. If the project has started, you should show a % complete greater than 0.
3. Column “Status”- Please select the appropriate status for the project in the drop down list
4. Column “For GSS PMO Review?”- Cell will automatically populate to indicate if the project will be discussed in the upcoming GSS PMO review based on responses to the above fields. If “For Review” is displayed, you need to add a comment to the status Column “Comments / Notes”
Tab Project Plan(s) – Update weekly
1. Column “Required Completion Date” and Column “Days to Accomplish”- please make sure you have an accurate as possible estimate in these fields.
2. Column “% Complete”- Please either enter accurate % to show your progress on the project. If the project has started, you should show a % complete greater than 0.
3. Column “Status”- Please select the appropriate status for the project in the drop down list
4. Column “For GSS PMO Review?”- Cell will automatically populate to indicate if the project will be discussed in the upcoming GSS PMO review based on responses to the above fields. If “For Review” is displayed, you need to add a comment to the status Column Q “Comments / Notes”
· Current Criteria for “GSS PMO Review”
o Day 1 Project List: Column “Project for GSS PMO Review”
1. Project status is not equal to “On Track” AND
2. Project start date is within 7 days of today’s date OR
3. 25% of project tasks require review
o Project Plan(s): Column “For GSS PMO Review”
1. Task status is not equal to “On Track” AND
2. Task start date is within 7 days of today’s date
Status option | Definition | Impact on % complete | o “At Risk”- Project or task has POTENTIAL to fall behind schedule which could result in a status of off track (think YELLOW)
Not started | Project/task has NOT started | % complete=0 | o “Off Track”- Project or task is not on schedule and requires action (think RED)
On Track | Project/task has started and is going according to schedule | % complete > 0
At Risk | Option 1: Project/task has started but has potential to be off track | Option 1: % complete > 0
Option 2: Project/task has NOT started but has the potential to not start on time
Option 2: % complete=0
Off Track | Project/task has started but is off track and will impact project plan, action must be taken | % complete > 0
Complete | Project/task is complete, no further actions | % complete= 100