## SCOPE
Sub Function / Sub Workstream | Cochran |  | Nossa |  | Katus |  | Raaymakers |  | Tailefer |  | Smith |  | Polikova
| Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete
Compliance and reporting |  |  | TN22, TN27, TN28 | 12% | EFAS04, EFAS17 | 4% |  |  | AT18 | 0% | CAR06,CAR07, CAR09, CAR10 | 0% | CAR03 | 0%
Credit | HC06, HC18 | 0%
EHS | HC15 | 5% | TN25 | 9%
Finance | HC01-HC03, HC17 | 1% | TN01-TN04; TN06-TN09 | 7% | EFAS01-EFAS03; EFAS05-EFAS14; EFAS18 | 1% |  |  |  |  | CAR04, CAR08 | 0% | CAR01 | 0%
People Services_Benefits, Payroll, T&A | HC10-HC12; HC20-HC22 | 5% | TN12-TN15 | 0% |  |  | TR01-TR10 | 5% | AT01, AT02, AT14, AT39, AT13 | 2% | CAR05 | 0% | CAR02 | 0%
People Services_Other | HC07-HC09; HC13 | 4% | TN18-TN21 | 0% |  |  |  |  | AT15, AT16, | 0%
Procurement Services | HC04 | 1% | TN05 | 5% | EFAS16 | 2%
Records Management | HC14 | 5% | TN26 | 5% |  |  |  |  | AT29
Transportation | HC16 | 0%
Treasury |  |  | TN10, TN11 | 12% | EFAS15 | 8%
Other |  |  | TN23, TN24 | 10%
Not applicable
On Track
Not started
At Risk
Off Track
Completed

## Milestones_PSC
Updated as of 2 February 2016
# | Separation Strategy Milestones | EUR | US
MPSC_1 | Define/confirm target GSS organization structure to support scope of services - PSC | 2016-03-31 | 2016-03-31
MPSC_2 | Procurement completes contract with Quadrem as well as contracts between Quadrem and the suppliers. Integrated suppliers needed for CRP testing. | 2016-04-15 | 2016-04-15
MPSC_3 | Obtain strategy for intercompany transactions | 2016-05-15 | 2016-05-15
MPSC_4 | Obtain strategy for operating between OD1 And LD1 from Transaction Execution | 2016-06-30 | 2016-06-30
# | IT System Separation Milestones
MPSC_5 | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | 2016-04-04 | 2016-04-04
MPSC_6 | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | 2016-05-20 | 2016-05-20
MPSC_7 | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | 2016-07-08 | 2016-07-08
MPSC_8 | Update Blanket Purchase Agreements and Purchase Orders to align with contractual changes, including new terms and conditions, attachments, and standard notes. | 2016-06-30 | 2016-06-30
MPSC_9 | System readiness checkpoint for go live | 2016-07-08 | 2016-07-08
MPSC_10 | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system | 2016-08-01 | 2016-08-01
# | Organization Separation Milestones
MPSC_11 | Update GSS SLA's, policies and procedures for Value Add Co and Upstream Co. | 2016-06-30 | 2016-06-30
MPSC_12 | Complete any GSS knowledge transfer/training required for Value Add and Upstream Co | 2016-07-31 | 2016-07-31
Not applicable
On Track
Not started
At Risk
Off Track
Completed