## Workstream Dashboard (hidden)
Updated as of 1/22/16
Sub Function / Sub Workstream | Nossa | Katus | Raaymakers | Cochran | Taillefer | Smith | Poliakova
| % complete | % complete | % complete | % complete | % complete | % complete | % complete
Compliance and reporting | 12% | 4% |  |  |  | 0% | 0%
Credit |  |  |  | 0%
EHS | 9% |  |  | 5%
Facilities
Finance | 7% | 1% |  | 1% |  | 0% | 0%
People Services_Benefits, Payroll, T&A | 0% |  | 5% | 5% |  | 0% | 0%
People Services_Other | 0% |  |  | 4%
Procurement Services | 5% | 2% |  | 1%
Records Management | 5% |  |  | 5%
Transportation |  |  |  | 0%
Treasury | 12% | 8%
Other | 10%
Not applicable
On Track
Not started
At Risk
Off Track
Completed

## Workstream Dashboard (2) (hidden)
Sub Function / Sub Workstream | Cochran |  | Nossa |  | Katus |  | Raaymakers |  | Tailefer |  | Smith |  | Polikova
| Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete
Compliance and reporting |  |  | TN22, TN27, TN28 | 12% | EFAS04, EFAS17 | 4% |  |  | AT18 |  | CAR06,CAR07, CAR09, CAR10 | 0% | CAR03 | 0%
Credit | HC06, HC18 | 0%
EHS | HC15 | 5% | TN25 | 9%
Finance | HC01-HC03, HC17 | 1% | TN01-TN04; TN06-TN09 | 7% | EFAS01-EFAS03; EFAS05-EFAS14; EFAS18 | 1% |  |  |  |  | CAR04, CAR08 | 0% | CAR01 | 0%
People Services_Benefits, Payroll, T&A | HC10-HC12; HC20-HC22 | 5% | TN12-TN15 | 0% |  |  | TR01-TR10 | 5% | AT01, AT02, AT14, AT39, AT13 |  | CAR05 | 0% | CAR02 | 0%
People Services_Other | HC07-HC09; HC13 | 4% | TN18-TN21 | 0% |  |  |  |  | AT15, AT16,
Procurement Services | HC04 | 1% | TN05 | 5% | EFAS16 | 2%
Records Management | HC14 | 5% | TN26 | 5% |  |  |  |  | AT29
Transportation | HC16 | 0%
Treasury |  |  | TN10, TN11 | 12% | EFAS15 | 8%
Other |  |  | TN23, TN24 | 10%
Not applicable
On Track
Not started
At Risk
Off Track
Completed

## 1 (hidden)
Project Number | Project ID Blueprint # (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS)
HC01 | 54,57,60,63,65,68,70,79 | GSS | Hank Cochran_Finance
HC02 | 73,75,77 | GSS | Hank Cochran_Finance
HC03 | 74 | GSS | Hank Cochran_Finance
HC04 | 78 | GSS | Hank Cochran_Procurement Services
HC05 | 76, 228 | GSS | Hank Cochran_Finance
HC06 | 81, 91, 92, 210, 229 | GSS | Hank Cochran_Credit
HC07 | 80 | GSS | Hank Cochran_HR_Other
HC08 | 55, 58, 61, 64, 66, 69, 71, 86 | GSS | Hank Cochran_HR_Other
HC09 | 56, 59, 62, 67, 87 | GSS | Hank Cochran_HR_Other
HC10 | 82 | GSS | Hank Cochran_HR_Benefits, Payroll, T&A
HC11 | 83 | GSS | Hank Cochran_HR_Benefits, Payroll, T&A
HC13 | 85 | GSS | Hank Cochran_HR_Other
HC14 | 88 | GSS | Hank Cochran_Records Management
HC16 | 90 | GSS | Hank Cochran_Transportation
HC17 | N/A | GSS | Hank Cochran_Finance
HC18 | N/A | GSS | Hank Cochran_Credit
HC23 | N/A | GSS | Transformation_Facilities
HC15 | 89 | GSS | Hank Cochran_EHS
HC12 | 84 | GSS | Hank Cochran_HR_Benefits, Payroll, T&A
HC19 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A
HC21 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A
HC22 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A
HC20 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A

## Milestones_PS_Payroll
Updated as of 1 Feb 2016
|  | HUB Brazil | HUB Hungary | HUB Hungary | Spain | Switzerland | Italy | France | North UK | North N/L B/E | Germany | North Norway | North Iceland | US | CAN | MEX | AUS | RUS
| Payroll Model (Vendor or In-house) / System | ApData (Antares) | N/A | In-House/ Xber | Vendor/Conktia | Vendor/Applic8 | Vendor/Feinar | Vendor/Teams | Vendor/Nortgate | Vendor/ADP | Vendor/Datev | Vendor/Visma | Vendor/H3 | Hewitt/Peoplesoft | Desjardins | TRES | Vendor/inhouse | Boss Kadrovik (vendor)
| T&A Model (Vendor or In-house) | In-House (Ronda) | N/A | In-House/Winaccess | In-house/Spec | In-house | In-house/TPC&Join | In-house/Horoquartz | In-house/Mitrefinch | In-house/Pronet | In-house/various | In-house/Wintid | In-house/Vinnestund | Workbrain/Various | Kronos | TREs | na | In house
| UP Co # Employees | 2100 |  | 130 | 1950 | 14 | 17 | 0 | 0 | 20 | 0 | 1050 | 540 | 1500 Active/27500 est retirees | 2600 |  | 4000 | 0
| VA Co # Employees | 1900 |  | 2000 | 25 | 20 | 318 | 2900 | 2960 | 180 | 1530 | 0 | 0 | 20000 Active/50000 est retirees | 1000 | 2400 | 200 | 3058
# | People Services Separation Strategy Milestone
MPS_1 | Define/confirm target GSS organization structures to support scope of services for both companies. | 2016-02-29 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-04-30 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12
# | IT System Separation Milestone
MPS_2 | Determine IT system requirements and strategy by country | 2016-02-29 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-29 | 2016-02-28 |  | 2016-02-29
MPS_3 | Align IT systems strategy with IT organization | 2016-03-04 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 |  | 2016-03-30 |  | 2016-03-15
MPS_4 | Obtain system scope of work and timeline from vendor to stand- up second system | 2016-03-15 | 2016-03-01 | 1-Mar-2016 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-21
MPS_5 | Obtain IT sign off for vendor owned system scope of work |  | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-31
MPS_6 | Procurement to execute vendor owned system scope of work for standing up second system | 2016-02-29 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 |  | 2016-03-31 | 2016-03-31
MPS_7 | Vendor commences work to stand-up separate system | 2016-05-01 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 2016-03-01 | 2016-04-01
MPS_8 | Stakeholder Sign off on vendor completion of standing up second system | 2016-06-30 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 2016-07-31 | 2016-05-01
MPS_9 | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | 2016-06-30 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-01 |  | 2016-03-30
MPS_10 | Complete IT system configuration with target condition in preparation for testing | 2016-07-31 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | TBD | 2016-07-31 |  | 2016-04-15
MPS_11 | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | 2016-04-15 |  | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 |  | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15
MPS_12 | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | 2016-05-20 |  | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20
MPS_13 | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08
MPS_14 | Participate in GPS Testing- Test Test Event 1 | 2016-02-29: 2016-04-15 | TBD
MPS_15 | Participate in GPS Testing - CRP testing | 2016-02-29: 2016-05-20 | TBD
MPS_16 | Participate in GPS Testing - UAT testing | 2016-02-29: 2016-07-08 | TBD
MPS_17 | Vendor owned IT System/Application testing | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08
MPS_18 | Work with Legal on the Safe Harbor agreement - especially for the locations in Europe and US that have the services provided from the HUB | [12 empty] | 2016-04-30 | bar: 2016-02-29
MPS_19 | Complete employee physical and electronic data purging | 2016-06-30 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
MPS_20 | Complete the Testing of critical processes for Compensation (Hourly performance pay, compensation planning) and Talent Management (goal reporting, end cycle). | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
MPS_21 | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
MPS_22 | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | 2016-02-29: 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-15
MPS_23 | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
# | GSS People Services Organization Separation Milestones
MPS_24 | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | 2016-07-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 |  | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31
MPS_25 | Complete GSS employee knowledge transfer/training required for the new GSS Value Add and Upstream organizations. | 2016-07-31 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 |  | 2016-06-30 | 2016-06-30 | 2016-07-31 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
MPS_26 | Validate the Support Model is in place prior to the separation (Kiosks, HR Portal, HR Call Center and Escalation Level) | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 |  | 2016-06-30 | 2016-06-30 | 2016-08-01 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
Not applicable
On Track
Not started
At Risk
Off Track
Completed

## PS_Supplier Dashboard (hidden)
ORANGE fields are still being completed in the tracker
Application | Supplier Name | Process | Sub-process | In Scope country(s) | Day 1 Approach Value-Add | Day 1 Approach rationale Value add | Day 1 Approach Upstream | Day 1 Approach rationale Upstream | Application Wave | Separation Complexity | RU/BU Applications Team SPA | IT Track Lead | GSS SPA | Procurement SPA | Status of application separation Supplier engagement | Target Contract Separation Date | Date Contract Separation Complete | GSS owns scope creation process? | Date contact made with application SPA prior to contacting vendor (DD-Mon-YY) | GSS supplier contact date to discuss scope and timeline | Scope and timeline obtained from vendor? | IT approved scope? | Cost Estimate | Date Procurement executed scope | Separation Work Start Date | Separation Work End Date | Scope execution acceptance date | System Go live date | Comments
ADP - Gennevilliers Casting-HGC Payroll Dives Casting-HNC Payroll | ADP | Human Resources | Payroll |  | No change |  |  |  | SH Wave 7 | <SELECT> | Hulce, Brad | Linda Berardelli | Raaymakers, Toine |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
Catalogs - Vinimaya | Vinimaya | Procurement | Other | US | No Change | Value-Add will keep current system | Stand-Up | New environment will need to be created. Data can be imported from existing environment. | SH Wave 7 | <SELECT> | Gorrepati, Samatha |  | Ridilla, Kathy |  | <SELECT> | 2016-02-29 |  | Yes | 2016-01-22 |  | <Select> | <Select>
Invoice Process Automation - ACS | Xerox | Procurement | Other | US | No Change | Value-Add will keep current system | Stand-Up | New environment will need to be created. Data can be imported from existing environment. | SH Wave 7 | <SELECT> | Gorrepati, Samatha |  | Ridilla, Kathy |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
Supplier B2B Network - Quadrem B2B Network | Quadrem | Procurement | Other | Global | No Change | Value-Add will keep current system | Stand-Up | New contracts for this process will need to be put in place | Wave 5 | <SELECT> | Gorrepati, Samatha |  | Ridilla, Kathy |  | <SELECT> | 2016-01-31 |  | Yes | 2016-01-22 |  | <Select> | <Select>
Jordan Lawrence |  | Legal & Compliance | Other |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. |  | Snyder, Steve Grego, Timoty Freire, Marcelo |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
BRM Online |  | Asset Management | Other |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. |  | Snyder, Steve Grego, Timoty Freire, Marcelo |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
IM Connect (Iron Mountain) | Iron Mountain | Asset Management | Other |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. |  | Snyder, Steve Grego, Timoty Freire, Marcelo |  | <SELECT> | 2016-03-31 |  | <Select> |  |  | <Select> | <Select>
Feinar | Feinar | Human Resources | Payroll |  | No Change | Continue to use outsource service externally | Stand-Up | Continue existing practice | UP Wave 5 | <SELECT> | Fischer, Róbert | Linda Berardelli | Raaymakers, Toine |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
GPCN |  | Human Resources | Payroll |  | Eliminate | Will be used only by Upstream | No Change | Continue existing practice | SH Wave 7 | <SELECT> | Fischer, Róbert | Linda Berardelli | Raaymakers, Toine |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Applic8 | Applic8 | Human Resources | Payroll |  | No Change | Continue to use outsource service externally | Stand-Up | Continue existing practice | VA Wave 6 | <SELECT> | Fischer, Róbert | Linda Berardelli | Raaymakers, Toine |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
GIP (PRESENZE) |  | Human Resources | Other |  | No Change | Continue to use outsource service externally | Stand-Up | Continue existing practice | VA Wave 6 | <SELECT> | Fischer, Róbert | Linda Berardelli | Raaymakers, Toine |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Horoquartz |  | Human Resources | Other |  | No Change | Continue to use outsource service externally | No Change | Continue existing practice |  | <SELECT> | Fischer, Róbert | Linda Berardelli | Raaymakers, Toine |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Equifax Workforce Solutions (I-9) | TALX | Human Resources | Other |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment |  | <SELECT> |  | Linda Berardelli | Freire, Marcelo Stallard, Faye Laymon, Jenea |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Equifax Workforce Solutions (Case Builder) | TALX | Human Resources | Other | [6 empty] | <SELECT> |  | Linda Berardelli | Freire, Marcelo F. |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Web Based Reports |  | Human Resources | Other |  | No change | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment |  | <SELECT> |  | Linda Berardelli | Freire, Marcelo Stallard, Faye Peleck, Jessica Vieger, Nickolet |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Weichert My Win | Weichert | Human Resources | Other |  | No change | Both companies need- will need to purge appropriate data out of each companies application-discuss with Concur | Stand-Up | Set up separate accounts and move as needed |  | <SELECT> |  | Linda Berardelli | McCleary, Michael |  | <SELECT> | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Mercer Data Table | Mercer | Human Resources | Other |  | No change | Both companies need- These are data tables that will be accessed by Global Mobilty and Weichert | Stand-Up | Both companies need- These are data tables that will be accessed by Global Mobilty and Weichert |  | <SELECT> |  | Linda Berardelli | McCleary, Michael |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Celergo website | CELERGO LLC | Human Resources | Payroll |  | No change | Both companieswill need these | Stand-Up | Both companieswill need these |  | <SELECT> |  | Linda Berardelli | McCleary, Michael |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Standard Register | Standard Register | Finance | Accounts Receivable | [6 empty] | <SELECT> | Gorrepati, Samatha | Paul Stamatakis | Ridilla, Kathy |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
Hewitt ePay | Hewitt ePay | Human Resources | Payroll |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. | Linda Berardelli | Marie, Lisa updated on behalf of Lowry, Angela |  | <SELECT> | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Hewitt Peoplesoft | Hewitt Peoplesoft | Human Resources | Payroll |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. | Linda Berardelli | Raaymakers, Toine; Marie, Lisa |  | <SELECT> | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Hewitt YBR (now called Aon Hewitt UPoint) | Hewitt YBR (now called Aon Hewitt UPoint) | Human Resources | Benefits |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. | Linda Berardelli | Hatlas, Lynne; Heuber, Karen |  | <SELECT> | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Hewitt Financial Engines | Hewitt Financial Engines | Human Resources | Other |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | SH Wave 7 | <SELECT> | Morse, Travis E. | Linda Berardelli | Carozza, David |  | <SELECT> | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Web Based Reports | Human Resources | Other | [7 empty] | <SELECT> |  |  | Freire, Marcelo F. |  | <SELECT> |  |  | <Select> |  |  | <Select> | <Select>
DOQSYS | DOQSYS KFT | Finance | Other |  | No Change | Value-Add continues to use the system | Stand-Up | Clone application purge if needed Value-Add data | SH Wave 7 | <SELECT> | Kékesi, József László | Paul Stamatakis | Ago Vizkeleti |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| WALLMEDIEN AG | Procurement | [7 empty] | <SELECT> |  |  |  |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| DLM SOLUTIONS | [8 empty] | <SELECT> |  |  |  |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| Intersoft (Xbér) | Human Resources | Payroll | [6 empty] | <SELECT> |  |  |  |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| API - APLIC Y PROYECTOS INFORMATICOS SA | Human Resources | Payroll | [6 empty] | <SELECT> |  |  |  |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| Desjardins | Human Resources | Payroll | [6 empty] | <SELECT> |  |  |  |  | <SELECT> | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| APDATA DO BRASIL SOFTWARE LTDA | Human Resources | Payroll | [6 empty] | <SELECT> |  |  |  |  | <SELECT> | 2016-03-31 |  | <Select> |  |  | <Select> | <Select>

## Owned Applications (hidden)
INSTRUCTIONS: Complete Orange fields if you plan to contact the vendor
Application | Supplier Name | In Scope country | Day 1 Approach Value-Add | Day 1 Approach rationale Value add | Day 1 Approach Upstream | Day 1 Approach rationale Upstream | Separation Complexity | Process | Sub-process | RU/BU Applications Team SPA | IT Track Lead | Application Wave | GSS Category | GSS SPA | Procurement SPA | Target Contract Separation Date | Date Separation Complete | GSS owns scope creation process? | Date contact made with application SPA prior to contacting vendor (DD-Mon-YY) | GSS supplier contact date to discuss scope and timeline | Scope and timeline obtained from vendor? | IT approved scope? | Cost Estimate | Date Procurement executed scope | Separation Work Start Date | Separation Work End Date | Scope execution acceptance date | System Go live date | Comments
ADP - Gennevilliers Casting-HGC Payroll Dives Casting-HNC Payroll | ADP |  | No change |  |  |  | <SELECT> | Human Resources | Payroll | Hulce, Brad | Linda Berardelli | SH Wave 7 | Owner | Raaymakers, Toine |  | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
Catalogs - Vinimaya | Vinimaya | US | No Change | Value-Add will keep current system | Stand-Up | New environment will need to be created. Data can be imported from existing environment. | <SELECT> | Procurement | Other | Gorrepati, Samatha |  | SH Wave 7 | Owner | Ridilla, Kathy |  | 2016-02-29 |  | Yes | 2016-01-22 |  | <Select> | <Select>
Invoice Process Automation - ACS | Xerox | US | No Change | Value-Add will keep current system | Stand-Up | New environment will need to be created. Data can be imported from existing environment. | <SELECT> | Procurement | Other | Gorrepati, Samatha |  | SH Wave 7 | Owner | Ridilla, Kathy |  | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
Supplier B2B Network - Quadrem B2B Network | Quadrem | Global | No Change | Value-Add will keep current system | Stand-Up | New contracts for this process will need to be put in place | <SELECT> | Procurement | Other | Gorrepati, Samatha |  | Wave 5 | Owner | Ridilla, Kathy |  | 2016-01-31 |  | Yes | 2016-01-22 |  | <Select> | <Select>
Jordan Lawrence |  |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Legal & Compliance | Other | Morse, Travis E. |  | SH Wave 7 | Owner | Snyder, Steve Grego, Timoty Freire, Marcelo |  |  |  | <Select> |  |  | <Select> | <Select>
BRM Online |  |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Asset Management | Other | Morse, Travis E. |  | SH Wave 7 | Owner | Snyder, Steve Grego, Timoty Freire, Marcelo |  |  |  | <Select> |  |  | <Select> | <Select>
IM Connect (Iron Mountain) | Iron Mountain |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Asset Management | Other | Morse, Travis E. |  | SH Wave 7 | Owner | Snyder, Steve Grego, Timoty Freire, Marcelo |  | 2016-03-31 |  | <Select> |  |  | <Select> | <Select>
Feinar | Feinar |  | No Change | Continue to use outsource service externally | Stand-Up | Continue existing practice | <SELECT> | Human Resources | Payroll | Fischer, Róbert | Linda Berardelli | UP Wave 5 | Owner | Raaymakers, Toine |  | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
GPCN |  |  | Eliminate | Will be used only by Upstream | No Change | Continue existing practice | <SELECT> | Human Resources | Payroll | Fischer, Róbert | Linda Berardelli | SH Wave 7 | Owner | Raaymakers, Toine |  |  |  | <Select> |  |  | <Select> | <Select>
Applic8 | Applic8 |  | No Change | Continue to use outsource service externally | Stand-Up | Continue existing practice | <SELECT> | Human Resources | Payroll | Fischer, Róbert | Linda Berardelli | VA Wave 6 | Owner | Raaymakers, Toine |  | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
GIP (PRESENZE) |  |  | No Change | Continue to use outsource service externally | Stand-Up | Continue existing practice | <SELECT> | Human Resources | Other | Fischer, Róbert | Linda Berardelli | VA Wave 6 | Owner | Raaymakers, Toine |  |  |  | <Select> |  |  | <Select> | <Select>
Horoquartz |  |  | No Change | Continue to use outsource service externally | No Change | Continue existing practice | <SELECT> | Human Resources | Other | Fischer, Róbert | Linda Berardelli |  | Owner | Raaymakers, Toine |  |  |  | <Select> |  |  | <Select> | <Select>
Equifax Workforce Solutions (I-9) | TALX |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Human Resources | Other |  | Linda Berardelli |  | Owner | Freire, Marcelo Stallard, Faye Laymon, Jenea |  |  |  | <Select> |  |  | <Select> | <Select>
Equifax Workforce Solutions (Case Builder) | TALX | [5 empty] | <SELECT> | Human Resources | Other |  | Linda Berardelli |  | Owner | Freire, Marcelo F. |  |  |  | <Select> |  |  | <Select> | <Select>
Web Based Reports |  |  | No change | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Human Resources | Other |  | Linda Berardelli |  | Owner | Freire, Marcelo Stallard, Faye Peleck, Jessica Vieger, Nickolet |  |  |  | <Select> |  |  | <Select> | <Select>
Weichert My Win | Weichert |  | No change | Both companies need- will need to purge appropriate data out of each companies application-discuss with Concur | Stand-Up | Set up separate accounts and move as needed | <SELECT> | Human Resources | Other |  | Linda Berardelli |  | Owner | McCleary, Michael |  | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Mercer Data Table | Mercer |  | No change | Both companies need- These are data tables that will be accessed by Global Mobilty and Weichert | Stand-Up | Both companies need- These are data tables that will be accessed by Global Mobilty and Weichert | <SELECT> | Human Resources | Other |  | Linda Berardelli |  | Owner | McCleary, Michael |  |  |  | <Select> |  |  | <Select> | <Select>
Celergo website | Celergo |  | No change | Both companieswill need these | Stand-Up | Both companieswill need these | <SELECT> | Human Resources | Payroll |  | Linda Berardelli |  | Owner | McCleary, Michael |  |  |  | <Select> |  |  | <Select> | <Select>
Standard Register | Standard Register | [5 empty] | <SELECT> | Finance | Accounts Receivable | Gorrepati, Samatha | Paul Stamatakis |  | Owner | Ridilla, Kathy |  |  |  | <Select> |  |  | <Select> | <Select>
Hewitt ePay | Hewitt ePay |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Human Resources | Payroll | Morse, Travis E. | Linda Berardelli | SH Wave 7 | Business Process Owner | Marie, Lisa updated on behalf of Lowry, Angela |  | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Hewitt Peoplesoft | Hewitt Peoplesoft |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Human Resources | Payroll | Morse, Travis E. | Linda Berardelli | SH Wave 7 | Business Process Owner | Raaymakers, Toine; Marie, Lisa |  | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Hewitt YBR (now called Aon Hewitt UPoint) | Hewitt YBR (now called Aon Hewitt UPoint) |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Human Resources | Benefits | Morse, Travis E. | Linda Berardelli | SH Wave 7 | Business Process Owner | Hatlas, Lynne; Heuber, Karen |  | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Hewitt Financial Engines | Hewitt Financial Engines |  | No Change | Assume existing environment will stay with Value-Add | Stand-Up | Existing environment will stay with Value-Add so will need to Clone & Purge into new environment | <SELECT> | Human Resources | Other | Morse, Travis E. | Linda Berardelli | SH Wave 7 | Business Process Owner | Carozza, David |  | 2016-01-31 |  | <Select> |  |  | <Select> | <Select>
Web Based Reports | Human Resources | [5 empty] | <SELECT> | Other |  |  |  |  | Owner | Freire, Marcelo F. |  |  |  | <Select> |  |  | <Select> | <Select>
DOQSYS | DOQSYS KFT |  | No Change | Value-Add continues to use the system | Stand-Up | Clone application purge if needed Value-Add data | <SELECT> | Finance | Other | Kékesi, József László | Paul Stamatakis | SH Wave 7 | Owner | Ago Vizkeleti |  | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| WALLMEDIEN AG | [5 empty] | <SELECT> | Procurement | [7 empty] | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| DLM SOLUTIONS | [5 empty] | <SELECT> | [8 empty] | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| Intersoft (Xbér) | [5 empty] | <SELECT> | Payroll | [7 empty] | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| API - APLIC Y PROYECTOS INFORMATICOS SA | [5 empty] | <SELECT> | Payroll | [7 empty] | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| Desjardins | [5 empty] | <SELECT> | Payroll | [7 empty] | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| CELERGO LLC | [5 empty] | <SELECT> | Payroll | [7 empty] | 2016-02-29 |  | <Select> |  |  | <Select> | <Select>
| APDATA DO BRASIL SOFTWARE LTDA | [5 empty] | <SELECT> | Payroll | [7 empty] | 2016-03-31 |  | <Select> |  |  | <Select> | <Select>