## SCOPE
Sub Function / Sub Workstream | Cochran |  | Nossa |  | Katus |  | Raaymakers |  | Tailefer |  | Smith |  | Polikova
| Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete | Project(s) | % complete
Compliance and reporting |  |  | TN22, TN27, TN28 | 12% | EFAS04, EFAS17 | 4% |  |  | AT18 | 0% | CAR06,CAR07, CAR09, CAR10 | 0% | CAR03 | 0%
Credit | HC06, HC18 | 0%
EHS | HC15 | 5% | TN25 | 9%
Finance | HC01-HC03, HC17 | 1% | TN01-TN04; TN06-TN09 | 7% | EFAS01-EFAS03; EFAS05-EFAS14; EFAS18 | 1% |  |  |  |  | CAR04, CAR08 | 0% | CAR01 | 0%
People Services_Benefits, Payroll, T&A | HC10-HC12; HC20-HC22 | 5% | TN12-TN15 | 0% |  |  | TR01-TR10 | 5% | AT01, AT02, AT14, AT39, AT13 | 2% | CAR05 | 0% | CAR02 | 0%
People Services_Other | HC07-HC09; HC13 | 4% | TN18-TN21 | 0% |  |  |  |  | AT15, AT16, | 0%
Procurement Services | HC04 | 1% | TN05 | 5% | EFAS16 | 2%
Records Management | HC14 | 5% | TN26 | 5% |  |  |  |  | AT29
Transportation | HC16 | 0%
Treasury |  |  | TN10, TN11 | 12% | EFAS15 | 8%
Other |  |  | TN23, TN24 | 10%
Not applicable
On Track
Not started
At Risk
Off Track
Completed

## Milestones_Treasury
Updated as of
# | Separation Strategy Milestones | EUR | LAC
MT_1 | Back-Office Scope Definition | 2016-01-31 | 2016-02-28
MT_2 | Define organization structure and commence hiring process to cover dis-synergies | 2016-02-15 | 2016-02-28
MT_3 | Obtain strategy for operating between OD1 And LD1 from Transaction Execution | 2016-05-31 | 2016-02-28
# | Treasury and IT Milestones | EUR | LAC
MT_4 | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | 2016-04-04 | 2016-04-04
MT_5 | Obtain captial structure definition from Treasury | 2016-04-30 | 2016-04-30
MT_6 | Confirm set up of third party IT systems (Treasury) | 2016-04-30 | 2016-03-18
MT_7 | Obtain bank account information and approver set up from Treasury | 2016-06-15 | 2016-05-04
MT_8 | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | 2016-05-20 | 2016-05-20
MT_9 | Test Third party Treasury systems | 2016-05-20 | 2016-06-09
MT_10 | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | 2016-07-08 | 2016-07-08
MT_11 | Test processing bank transfer from new bank accounts | 2016-07-01 | 2016-06-15
MT_12 | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | 2016-07-31 | 2016-08-01
# | Organization Separation Milestones | EUR | LAC
MT_13 | Update GSS SLA's, policies and procedures for Value Add Co and Upstream Co. | 2016-07-31 | 2016-09-30
MT_14 | Review and update GSS ASAT process, and content for Value Add and Upstream Co | 2016-07-31 | 2016-09-30
MT_15 | Complete any GSS knowledge transfer/training required for Value Add and Upstream Co | 2016-07-31 | 2016-07-31
MT_16 | Implement target GSS organization for Value Add Co. and Upstream Co. | 2016-07-31 | 2016-07-31
MT_17 | Operational readiness checkpoint | 2016-07-31 | 2016-07-31
Not applicable
On Track
Not started
At Risk
Off Track
Completed