## Instructions and Descriptions
Project Elevation
High-Level Separation Workplan - Instructions, Descriptions, and Examples
Below are instructions for the high-level separation workplan template
This template comprises of three tabs: one focused a list of Day 1 projects, the second focused on capturing the tasks and milestones required to complete those projects, and final focused on capturing project-associated costs
1) Follow the directions in the light grey rows of example tables below. There is an example table for each of the three tabs; example line items are provided in italics.
2) This template is designed to be modular - if you need to create multiple Project Plan tabs to break up workplanning, please do so. Indicate your tab divisions by renaming the tab where it says "{Project}"
3) Please refer any questions to your separation counterpart or contact. Leverage your contact for help with submission and plan consolidation
| Day 1 Project List Tab | Orange fields due for completion by 4 December 2015
| Activity-Level Description | [14 empty] | Dependency Resolution Checklist
| Project ID (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | Day 1 Project Description | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with a workstream-defined three letter code for WS & SWS and a unique 3 digit code for the activity within | List the name of the Resource Unit, Function, or division acting as a workstream with the separation | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Provide a detailed description (what, why and where) of the Day 1 Project | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Provide the date by which this project must be completed | Provide an estimate of the number of calendar days it will take to complete the entire project | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the project is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
x | HRD-LRL-001 | Human Resources | Labor Relations | French Works Council Approval | Adjusting organizations in France requires gaining approval from the Works Council via a formal proposal | Both | 2016-06-01 | 132 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Will require input from X, Y, and Z | [27 empty] | 2016-01-15
| HRD-LRL-002 | Human Resources | Labor Relations | German Works Council Approval | Adjusting organizations in Germany requires gaining approval from the Works Council via a series of formal meetings | Both | 2016-06-01 | 102 | 2016-02-20 | 0% | FALSE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Will require input from X, Y, and Z | [27 empty] | 2015-10-31
| Project Plan Tab | Fields due for completion by 17 December 2015
| Task-Level Description | [14 empty] | Dependency Resolution Checklist
| Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with workstream-defined three letter code for SWS, the unique 3 digit code for the activity, and a two digit code for the task | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Identify the name of the task that must be done to complete the project. Only list one task per row | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Mark whether or not this task is a milestone for a project. Milestones are the most critical tasks within a project, which are often time-sensitive. | Provide the date by which this task must be completed | Provide an estimate of the number of calendar days it will take to complete the entire task | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the task is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, important subtasks that must be captured, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
| LRL-001-01 | Labor Relations | French Works Council Approval | -Draft Proposal | Both | FALSE | 2016-02-20 | 30 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-001-02 | Labor Relations | French Works Council Approval | -Submit Proposal | Both | TRUE | 2016-03-01 | 10 | 2016-02-20 | 0% | FALSE |  | Dominique Bordeaux | Not Started
| LRL-001-03 | Labor Relations | French Works Council Approval | -Follow up after 3 months | Both | FALSE | 2016-06-01 | 90 | 2016-03-03 | 0% | FALSE |  | Dominique Bordeaux | Not Started
x | LRL-002-01 | Labor Relations | German Works Council Approval | -Draft Proposal | Both | FALSE | 2016-03-20 | 30 | 2016-02-19 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-002-02 | Labor Relations | German Works Council Approval | -Submit Proposal | Both | TRUE | 2016-04-01 | 10 | 2016-03-22 | 0% | FALSE |  | Petra Schmidt | Not Started
| LRL-002-03 | Labor Relations | German Works Council Approval | -Follow up after 2 months | Both | FALSE | 2016-06-01 | 60 | 2016-04-02 | 0% | FALSE |  | Petra Schmidt | Not Started
Project Costs Tab
| Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale
| Provide the unique ID for the project defined on the Day 1 Projects tab | Provided the name of the Day 1 project defined on the Day 1 Projects tab | Provide a description of what the cost is and why it exists | Indicate if this cost is a dis-synergy (incl stranded cost) (True/False) | Indicate if this cost is a one-time cost (True/False) | Indicate who will own the plan to minimize and address this cost | Provide an estimated cost for all or part of this Day 1 Project | Briefly describe rationale (business case) for cost estimate
| HRD-LRL-002 | German Works Council Approval | Lobbying - Gaining approval often requires spending money to lobby key officials | No | Yes | Peter Schmidt | 10000 | Spending this money will reduce risk and speed transition for German Org
x
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Instructions and Descriptions'!$[Required Completion Date]),"",'Instructions and Descriptions'!$[Required Completion Date]-'Instructions and Descriptions'!$[Days to Accomplish])

## Day 1 Project List_HC
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Projects
| As Of | 2016-02-02 11:34
| Project-Level Description | [16 empty] | Dependency Resolution Checklist
Project Number | Project ID Blueprint # (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | In scope sub processes | Day 1 Project Description | Country of Service Delivery | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | Total # Tasks in Project | # of Tasks for Review | % Project Tasks For review | Project For GSS PMO Review?
HC01 | 54,57,60,63,65,68,70,79 | GSS | Hank Cochran_Finance | Finance System Support | Support, Enhancements | Ensuring we are able to perform all financial business functions, including but not limiit to GL, FAPA, Credit, AR, Procurement Support, AP, and reporting. Also to ensure that interfaces between ERP and legacy systems are functioning properly as well as those to/from external systems. | Australia, Brazil, Canada, China, Europe, Mexico, Russia, US | Both | 2016-07-31 | 210 | 2016-01-03 | 2% | TRUE | 1. GIS must deliver a test-ready system in enough time to perform "solutions" level testing and remediation before funtional user testing occurs. We are expect 2-3 rounds of such testing. If dependency not fulfilled, there is a risk of not have proper separation of systems or error/omission in the financials, or being unable to transact business across all applications. 2. Treasury: Establishing and configuring new bank accounts and arrangements/configurations in time for testing so as not to risk rework and retesting. 3. Tax: Taxware engine needs to be functional and accurate. Based on R12 upgrade this is a BIG RISK. Failure would mean tax compliance and liability issues. 4. GSS: Need close connection with GSS support and functional counterparts around the world, else project plans could run off track, and jeopardize the go-live. 5. Vendor: Procurement needs to negotiate with system providers for licenses, support, etc. for the two separate companies. this is so we can operate. 6. Vendor Support: Working in conjunction with GIS, we will need prompt resolution of showstopper issues. Vendors include: Oracle, TCS, etc. Without critical support from vendors, the overall solution will be jeopardized. 7. ATC: Special location which is a superuser, has special processes, and some they orchestrate and maintain themselves. Strong connection will be key, else the solution could be damaged. 8. Other dependencies listed in column AX. | Ridilla | On Track | 25-JAN-2016: Continuing with activities listed below. Also reached agreement on direction for AR Shared Services OUs and RTP NON OU. 12-JAN-2016: Preparing detailed project plans, aligning efforts with associated groups, creating/updating SOPs and reviewing configurations for impact. |  | X | X |  |  | X |  | X |  | X |  |  |  |  | X |  | X | X | X | X | X | [9 empty] | X | Oracle Dev and Support TCS Functional Org--Testing. BU locations using legacy systems (important for testing) Intercompany and IICS | 33 | 4 | 12.12% | No Review
HC02 | 73,75,77 | GSS | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Acquisition/Divestiture Services ASAT Management General Ledger Accounting Government Compliance Reporting Intercompany Accounting Tax Planning Tax Returns and Reporting eRFA Fixed Asset Accounting Acquisition/Divestiture Services ASAT Management Tax Planning Tax Returns and Reporting Government Compliance Reporting Standard costing updates (cost builds) and revaluation New item costing Inventory OPM Accounting Pre-Processor/Create Accounting procedures Inventory organization maintenance Daily Showcase queries and JDE updates Daily Scrap/Dross Shipments analysis Weekly On Hold Job review analysis | All general ledger, FAPA, and Cost Accounting will be completed on separate systems for both companies by Day 1 in order for no disruption of services. All transactions, legal enitities, L-Parents, projects, and assets will be separated to be company specific by Day 1 with processes being documented and staff being trained accordingly to ensure proper recording of entries and closing of books. | US | Both | 2016-07-31 | 180 | 2016-02-02 | 0.1026% | TRUE | IT systems need to be establised for both companies. Determination of how the systems will be split needs completed by 1/1/16. Data needs to be copied as necessary onto the new systems by 2/28/16, and systems need to be available for testing by 3/31/16. Legal entities and L-Parents need to be established for both companies by 1/31/16. Testing to ensure legal entities are set up correctly needs completed by 2/28/15 so that new systems can be loaded correctly. Accounting transactions/projects need to be separated by 4/30/16 so that testing can be completed by 5/31/16 incase any issues are identified that need fixed. Procedures need to be created for all processes by 4/30/16 so that proper training can occur by 7/31/16. Organization structure needs to be established by 3/31/16 in order for staff division and proper cross training to occur by 7/31/16. | Donaldson | Not Started | [6 empty] | X |  | X | [6 empty] | X | [17 empty] | 52 | 0 | 0% | Review
HC03 | 74 | GSS | Hank Cochran_Finance | Accounts Payable | Invoice processing Payment processing Holds resolution Customer service GRNI Back end controls for compliance Reporting Subledger closing | The accounts payable sub processes and interfaces need to be functional on Day 1 of both companies in order to avoid disruption to on-time payment to suppliers. Day 1 as the target is required because invoice processing, issue / holds resolution, and payments to critical suppliers must be available to avoid suppliers stopping shipments and / or services which could cause plant or line shutdowns. | US | Both | 2016-07-31 | 202 | 2016-01-11 | 1% | TRUE | IT: Oracle (JD Edwards for Norcross) must be operational for invoice and payment functionality. Manual transactions are not an option. System decision required by 1/1/2016, testing schedule to be provided by 1/31/2016. Interfaces to Ariba/Quadrem (B2B), IQN, and Xerox (invoice scanning) must be available for the same testing schedule. Treasury: Must confirm funds available for payment. Must be available 7/31/2016. Tax: Tax must be calculated on invoices; tax personnel provide support, and decisions about company can have tax consequences. Must be available for testing and if having a separate test plan, it must be available by 1/31/2016. Procurement: Invoices are paid as the final process to purchases that are made. Current Procurement organization is needed starting 1/1/2016 for decision making, and throughout testing period if needed for confirmation of test results, full functionality for each company by 7/31/2016 | Donna Koenig, Bryan Verardi | On Track |  |  | X |  |  |  | X |  |  |  | X | [22 empty] | 79 | 0 | 0% | No Review
HC04 | 78 | GSS | Hank Cochran_Procurement Services | PSC | Purchase Order processing and maintenance Change Order processing Purchase Agreement and Contract Agreement Maintenance Delivery management / late shipment follow up Inventory management Approvals maintenance Customer service Reporting | The procurement services sub processes and interfaces need to be functional on Day 1 of both companies in order to avoid disruption to on-time delivery of goods and services from suppliers. Day 1 as the target is required because purchase order processing, issue resolution, tracking down late shipments, and receiving are critical to avoid plant or line shutdowns. | US | Both | 2016-07-31 | 202 | 2016-01-11 | 1% | TRUE | IT: Oracle must be operational for requisition and purchase order processing. Manual transactions are not an option. System decision required by 1/1/2016, testing schedule to be provided by 1/31/2016. . Interfaces to Ariba/Quadrem (B2B), IQN, and Vinimaya (Alcoa Mall) must be available for the same testing schedule. Tax: Tax must be calculated on invoices; tax personnel provide support, and decisions about company can have tax consequences. Must be available for testing and if having a separate test plan, it must be available by 1/31/2016. | Donna Koenig, Linda Miller | On Track |  |  | X |  |  |  | X | [26 empty] | 147 | 0 | 0% | No Review
HC05 | 76, 228 | GSS | Hank Cochran_Finance | Accounts Receivable | Revenue posting; cash application; customer account maintenance, Customer invoice generation and distribution | Establishing separate, fully functional operating teams to perform accounts receivable processing required by each entity. | US | Both | 2016-07-31 | 210 | 2016-01-03 | 2% | TRUE | • Strategic decision on the ERP & AR applications solution. • Strategic decision on banking relationships and account structures. • Determine if third party invoicing solution will be leveraged for both companies. | Caldwell, Antli | On Track |  |  | X | X |  |  | X |  | X |  | X | [13 empty] | X | [8 empty] | 29 | 1 | 3.448% | No Review
HC06 | 81, 91, 92, 210, 229 | GSS | Hank Cochran_Credit | Credit (NOA, Europe, China) | Credit risk management; collections; forecasting; portfolio management | Establishing separate, fully functional operating teams to perform credit and collection services required by each entity. | US, Europe, China | Both | 2016-07-31 | 210 | 2016-01-03 | 1% | TRUE | • Strategic decision on the ERP (incl Collection Module)& AR, Hyperion applications solution. • Strategic decision on hedging/commodity trading approach for both companies. • Understand direction of ETC (DMR) linked to reporting , statement sender solution • Decision on credit reporting provider | Caldwell, Lintner | On Track |  |  |  | X |  |  | X |  | X |  | X | [13 empty] | X | [8 empty] | 37 | 0 | 0% | No Review
HC07 | 80 | GSS | Hank Cochran_HR_Other | T&E | Concur Expense/Travel | Separate companies will have a functioning US Travel and Expense tool supporting travel as well as Low Value Procurement (LVP). It is assumed that the current functionality will be maintained for both Value Add and Upstream. This would include reservation booking, expense processing, credit card payments, ledger & payroll feeds and policy | US | Both | 2016-07-31 | 179 | 2016-02-03 |  | TRUE | Critical dependency: 1) The strategic decision on the HR applications solution. 2) Determine if the Concur Tool will be Cloned or not. 3) Decisions on US payroll processes 4) Determination if new credit Cards will need to be issued (awaiting determination by vendor) 5) Procurement decisions related to existing Air, Car and hotel negotiated rate and optimal leverage for both entities as well as credit card rebates | Lowry, Angela Mccleary, Mike Borsos, Tamás | Not Started | [6 empty] | x |  | x |  | x | [7 empty] | x | x | x | x | [11 empty] | 24 | 0 | 0% | Review
HC08 | 55, 58, 61, 64, 66, 69, 71, 86 | GSS | Hank Cochran_HR_Other | People Services System Support | GPS Support, GPS Global Support - provide support for compensation, talent mgmt and employee/manager questions and issues | Separate companies will have a functioning HR system to support employee talent, compensation and self service processes. Value Add will continue using GPS as they are currently using it today. Upstream project scope is to be determined based on the strategic decision that needs to be made (move GPP to GPS cloud solution, remain in GPS with TSA, move to third party solution, etc). | Australia, Brazil, Canada, China, Europe, Mexico, Russia, US | Both | 2016-10-01 | 275 | 2015-12-31 | 5% | TRUE | The most critical interdependencies are with related to 1) Decision being made on the IT strategic decision 2) Data privacy restrictrions/laws we need to abide by. 3) Organizational decisions on the global and regional GPS support teams - will the help desk be split by companies, or can they serve both companies 4) will a TSA be in place? 5) Do the changes in Safe Harbor laws impact the GPS GLobal support model? 6) Are we required to purge data out of system for non-company employees? 7) Will contracts will external vendors change, thereby impacting interfaces? | Lowry, Sterlitz | On Track | 1/6 - Cloud analysis is underway for Value Add and upstream. EBS Clone option was approved for Upstream pending cloud analysis | X |  |  | X | X | X |  | X |  | x | [22 empty] | 40 | 0 | 0% | No Review
HC09 | 56, 59, 62, 67, 87 | GSS | Hank Cochran_HR_Other | Global Mobility | Weichert My Win System | Separate companies will have a functioning US Domestic Relocation and Expatriate programs. Primary link for these programs is the Weichert System. Upstream and Value Add will be setup as separate accounts within this system. Existing policies will be kept. | Australia, Brazil, Canada, Europe, US, China | Both | 2016-09-01 | 250 | 2015-12-26 | 1% | TRUE | Critical dependency: 1) The strategic decision on the HR applications solution. 2) Visa decisions for certain individuals working within the US and potentially other countries (team has been formed Legal, GM & Fragomen: actiion plian in development stage) 3) Decision on the Global Employment Company (GEC) ie clone or eliminate (team formed: Storm, Laun, Kenna, GM (currently reviewing alterntives) 4) Decisions on global payroll processes for related Expat payrolls: (refers to split of all local payrolls, assoiciated feeds, tax reporting changes) | Lowry, Angela Mccleary, Mike | On Track |  |  |  |  | x |  | x |  | x |  | x |  | x | [5 empty] | x | x | x | x | [9 empty] | x | Decision on GEC | 23 | 0 | 0% | No Review
HC10 | 82 | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | Domestic Payroll Production, Payroll Tax Administration, Garnishment Administration, SUB Payroll Production, Payroll Accounting & Account Reconciliation, Expatriate Payroll Production | Provide payroll & payroll rax services for all US employees. Decisions need to be made as to the provider and systems to be used for each company. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | Critical dependencies: 1.) The strategic decision regarding the provider and systems to be used. Each option has a very different project plan & timeline 2.) The strategic decision regarding taxes to be used /new legal companies | Lowry, Kerekes | On Track |  | X | X | X | X | X | X |  | X |  | X | [20 empty] | x | Industrial Relations | 28 | 1 | 3.571% | No Review
HC11 | 83 | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Workbrain Time & Attendance Support | Separate companies will have a functionaing T&A system to support time tracking, clock maintenances and file transmission to payroll system.Value Add will continue using Workbrain as they are currently using it today. Upstream project scope is to be determined based on the strategic decision that needs to be made (move T&A operation to Kronos (GPP Canadian solution), remain in current Workbrain solution, create replicated WOrkbrain solution for GPP only) | US | Both | 2016-10-01 | 212 | 2016-03-03 | 5% | TRUE | Critical dependency are the strategic decisions on the T&A applications solution as well as legal entity structure. Each different option has a very different project plan and timeline. | Lowry, Sterlitz, Clive | On Track |  |  |  |  | X | X | X |  | X |  | x | [12 empty] | x | x | [6 empty] | x | Industrial Relations | 19 | 0 | 0% | No Review
HC13 | 85 | GSS | Hank Cochran_HR_Other | People Services Transaction Support | - Transactional support to most of the US employees (22,000k) for Payroll & T&A, Data Management, Compliance, Business Process and Hourly Recruiting - Reporting & Analytics for US and Global Units | The separation process will require the definition of the new scope for both companies, organization, roles and responsibilities, tools that are used to support the customers, new SLAs, etc. The team supports most of the US locations and the new organization will impact on Payroll, Time & Attendance, Compliance, Reporting, Recruiting, Data Management and Business Processes. The definitions regarding system (in special GPS, Workbrain, Web based Reports and Brassring) will be very important for the project. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | Critical dependencies: (1) IT: HR systems (GPS, Workbrain, Web based Reports and Brassring). If the systems will continue for both companies. (2) HR for each one of the GBUs and RU: defining the scope and SLA for future support. Both dependencies will impact the organization, transition, scope and the way the services is provided nowadays. | Lowry, Angela Freire, Marcelo | On Track |  | x |  |  | x | x | x |  | x |  | x | [13 empty] | x | [8 empty] | 25 | 0 | 0% | No Review
HC14 | 88 | GSS | Hank Cochran_Records Management | Records Management | - Governance of US records and retention schedules globally - Development of SOPs and continuous monitoring of the environment (including compliance) - Training and knowledge transfer to BUs/Rus | The separation process will require the definition organization, roles and responsibilities, tools that are used to support the customers, new SLAs, etc. One of the critical decisions would be the documents separation among both companies. | US (supporting globally the retention schedule documents) | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | Critical dependencies: (1) Legal: Tracking system (Jordan Lawrence). If the system will continue for both companies. (2) Legal: strategy to separate documents for both companies. Both dependencies will impact the organization, transition, scope and the way the services is provided nowadays. | Lowry, Angela Freire, Marcelo Snyder, Steve | On Track |  |  | X |  | X | [5 empty] | X | [13 empty] | x | [6 empty] | x | Closed or curtailed facilities; Ethics & Compliance | 23 | 0 | 0% | No Review
HC16 | 90 | GSS | Hank Cochran_Transportation | Transportation Support | Outsourced Transportation systems management: TDW (includes data warehouse, contract data base & carrier rate approval portal) BestTransport truck shipment execution IPS Worldwide FA & P, including automated ledger feed Blue Rock FA & P Integrate new companies to Alcoa contracts & implement onto Alcoa Transportation systems Ensure compliance with Alcoa transportation policies & requirements of global Transportation ASAT FP69 and FP77. Review & approve ASAT tests done by GSS | The transportation support sub processes and interfaces need to be functional on Day 1 of both companies in order to avoid disruption to the services of carriers. Day 1 as the target is required because inbound and outbound freight shipments, the support of the systems required to do so, and payment to the carriers to avoid stoppages are critical to avoid plant or line shutdowns. | US, North America, Europe, Global | Both | 2016-07-31 | 212 | 2016-01-01 | 1% | TRUE | IT: Oracle must be operational to pay carriers. System decision required by 1/1/2016, testing schedule to be provided by 1/31/2016. Interfaces to Devware, BestTransport, IPS Worldwide, Blue Rock, and Interlogmust be available for the same testing schedule. Transportation: Function is to support Transportation Organization. Current Transportation organization is needed starting 1/1/2016 for decision making, and throughout testing period if needed for confirmation of test results, full functionality for each company by 7/31/2016 Procurement: Provides contracts for external providers. Current Procurement organization is needed starting 1/1/2016 for decision making, and throughout testing period if needed for confirmation of test results, full functionality for each company by 7/31/2016 | Donna Koenig, Janine McWilliams | On Track | [6 empty] | X |  |  |  | X | [14 empty] | X | [7 empty] | 46 | 0 | 0% | No Review
HC17 | N/A | GSS | Hank Cochran_Finance | Accounts Receivable(JDE) | KNA NOA Cash application performed in Kofem on JDE | Establishing separate, fully functional operating teams to perform accounts receivable processing required by each entity. | US | V-A Co. | 2016-07-31 | 150 | 2016-03-03 |  | TRUE | • Strategic decision on the ERP & AR applications solution. | Caldwell/Randall, Antli | Not Started |  |  | X | X |  |  | X |  | X |  | X | [13 empty] | X | [8 empty] | 7 | 0 | 0% | No Review
HC18 | N/A | GSS | Hank Cochran_Credit | Credit (US) | Credit risk management; collections; forecasting; portfolio management | Establishing separate, fully functional operating teams to perform credit and collection services required by each entity. | US | V-A Co. | 2016-07-31 | 150 | 2016-03-03 |  | TRUE | • Strategic decision on the ERP & AR, Hyperion applications solution. • | Caldwell/Randall, | Not Started |  |  |  | X |  |  | X |  | X |  | X | [13 empty] | X | [8 empty] | 7 | 0 | 0% | No Review
HC23 | N/A | GSS | Transformation_Facilities | Shared Facilities | Physical location of office and all supporting infrastructure | Project to address all infrastructure to support both orgs | US | Both | 2016-07-31 |  | 2016-07-31 |  | TRUE | Facilities IT | Lisa Marie | <Select> | [6 empty] | X | [8 empty] | X | [17 empty] | 0 | 0 | #DIV/0! | No Review
HC15 | 89 | GSS | Hank Cochran_EHS | EHS | Manage the reglar and HD work. Run the system, upgrade/path, run reports | Provide IHS Systems Support and the running of reports as needed for all businesses in all regoins. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | Will need guidance on how to proceed, system separation and which companies internal resources will support. Systems may also need to be cloned and decisions will need to be made by IT, EHS and GSS on how to separate systems and resources. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [6 empty] | X |  | X |  |  | X | [21 empty] | 12 | 0 | 0% | No Review
HC12 | 84 | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | Defined Benefits Pension | Provide benefits administration for U.S. based programs for all 26K active employees, 100K+ retirees and active/retiree dependents. DB includes 8 pension plans with 80 structures. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | The most critical interdependencies are with Plan Design (HR), Legal, Tax, Procurement, IT and Industrial Relations (IR). These are the groups where I would expect to receive direction on how to separate. The biggest questions I have for separation for these groups are: a) For all active employees and retirees due a current or future benefit, what companies (Upstream or Value Add) will they go to in TBA (Aon Hewitt’s benefits system)? We have given data to Plan Design (Rachel and Scott) to make decisions. b) A benefits administration team needs to be in place for both companies as soon as possible. When will this occur? c) What will be done with the benefit plans for each company (How will benefit plans be separated?) d) What will be done with our vendor contracts, specifically Aon Hewitt, BNY Mellon, Buck, etc. e) Will there be any impact due to union contracts. Warrick and Kingston will be negotiating with changes effective 4/1/2016. Interdependencies and decisions with Industrial Relations will need to be made. f) What will be done with the GPS Portal and any links to UPoint and H&W vendors (Highmark, Caremark, UCCI, etc.)? How will systems be split? Interdependencies with IT will need to be reviewed. g) Develop procedures. h) Develop training documents. i) Complete knowledge transfer. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track |  |  | X |  | X | X | X |  | X |  | X | [12 empty] | X | [7 empty] | X | Industrial Relations | 22 | 0 | 0% | No Review
HC19 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | Health and Welfare | Provide benefits administration for U.S. based programs for all 26K active employees, 40K+ retirees and active/retiree dependents. H&W for 3 active, 10 pre-65 retiree and 10 post-65 retiree H&W Plans that cover 57K+ active and retired employees, plus another 18K+ at One Exchange. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | The most critical interdependencies are with Plan Design (HR), Legal, Tax, Procurement, IT and Industrial Relations (IR). These are the groups where I would expect to receive direction on how to separate. The biggest questions I have for separation for these groups are: a) For all active employees and retirees due a current or future benefit, what companies (Upstream or Value Add) will they go to in TBA (Aon Hewitt’s benefits system)? We have given data to Plan Design (Rachel and Scott) to make decisions. b) A benefits administration team needs to be in place for both companies as soon as possible. When will this occur? c) What will be done with the benefit plans for each company (How will benefit plans be separated?) d) What will be done with our vendor contracts, specifically Aon Hewitt, BNY Mellon, Buck, etc. e) Will there be any impact due to union contracts. Warrick and Kingston will be negotiating with changes effective 4/1/2016. Interdependencies and decisions with Industrial Relations will need to be made. f) What will be done with the GPS Portal and any links to UPoint and H&W vendors (Highmark, Caremark, UCCI, etc.)? How will systems be split? Interdependencies with IT will need to be reviewed. g) Develop procedures. h) Develop training documents. i) Complete knowledge transfer. j) What will we do for 2017 Annual Enrollment? The work for 2017 AE should occur between May, 2016 and December, 2016. The actual enrollment period typically would occur in October, 2016. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track |  |  | X |  | X | X | X |  | X |  | X | [12 empty] | X | [7 empty] | X | Industrial Relations | 21 | 0 | 0% | No Review
HC21 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | Defined Contribution Pension | Provide benefits administration for U.S. based programs for all 26K active employees plus 10K inactives with an account balance. DC includes 5 plans when RTI is added on for the value add company, and will need to split out 2 additional plans for the upstream business. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | The most critical interdependencies are with Plan Design (HR), Legal, Tax, Procurement, IT and Industrial Relations (IR). These are the groups where I would expect to receive direction on how to separate. The biggest questions I have for separation for these groups are: a) For all active employees and retirees due a current or future benefit, what companies (Upstream or Value Add) will they go to in TBA (Aon Hewitt’s benefits system)? We have given data to Plan Design (Rachel and Scott) to make decisions. b) A benefits administration team needs to be in place for both companies as soon as possible. When will this occur? c) What will be done with the benefit plans for each company (How will benefit plans be separated?) d) What will be done with our vendor contracts, specifically Aon Hewitt, BNY Mellon, Buck, etc. e) Will there be any impact due to union contracts. Warrick and Kingston will be negotiating with changes effective 4/1/2016. Interdependencies and decisions with Industrial Relations will need to be made. f) What will be done with the GPS Portal and any links to UPoint and H&W vendors (Highmark, Caremark, UCCI, etc.)? How will systems be split? Interdependencies with IT will need to be reviewed. g) Develop procedures. h) Develop training documents. i) Complete knowledge transfer. | Angela Lowry, Joseph Adamietz, David Carozza | On Track |  |  | X |  | X | X | X |  | X |  | X | [12 empty] | X | [7 empty] | X | Industrial Relations | 19 | 0 | 0% | No Review
HC22 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | Benefits Admin Customer Service | Provide benefits administration for U.S. based programs for all 26K active employees, 100K+ retirees and active/retiree dependents. DB includes 8 pension plans with 80 structures. DC includes 5 plans. H&W for 3 active, 10 pre-65 retiree and 10 post-65 retiree H&W Plans that cover 57K+ active and retired employees, plus another 18K+ at One Exchange. We also have a call center run by our vendor that supports over 170K+ monthly hits to the website, plus an additional 12K+ monthly calls to the service center, including escalations and appeals. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | The most critical interdependencies are with Plan Design (HR), Legal, Tax, Procurement, IT and Industrial Relations (IR). These are the groups where I would expect to receive direction on how to separate. The biggest questions I have for separation for these groups are: a) For all active employees and retirees due a current or future benefit, what companies (Upstream or Value Add) will they go to in TBA (Aon Hewitt’s benefits system)? We have given data to Plan Design (Rachel and Scott) to make decisions. b) A benefits administration team needs to be in place for both companies as soon as possible. When will this occur? c) What will be done with the benefit plans for each company (How will benefit plans be separated?) d) What will be done with our vendor contracts, specifically Aon Hewitt, BNY Mellon, Buck, etc. e) Will there be any impact due to union contracts. Warrick and Kingston will be negotiating with changes effective 4/1/2016. Interdependencies and decisions with Industrial Relations will need to be made. f) What will be done with the GPS Portal and any links to UPoint and H&W vendors (Highmark, Caremark, UCCI, etc.)? How will systems be split? Interdependencies with IT will need to be reviewed. g) Develop procedures. h) Develop training documents. i) Complete knowledge transfer. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track |  |  | X |  | X | X | X |  | X |  | X | [12 empty] | X | [7 empty] | X | Industrial Relations | 22 | 0 | 0% | No Review
HC20 | N/A | GSS | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | Tuition Reimbursement | Provide tuition reimbursement assistance and processes for approxiamtely employees. We use GP as our tuition assistance vendor. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | US | Both | 2016-07-31 | 212 | 2016-01-01 | 5% | TRUE | The most critical interdependencies are with Plan Design (HR), Legal, Tax, Procurement, IT and Industrial Relations (IR). These are the groups where I would expect to receive direction on how to separate. The biggest questions I have for separation for these groups are: a) For all active employees and retirees due a current or future benefit, what companies (Upstream or Value Add) will they go to in TBA (Aon Hewitt’s benefits system)? We have given data to Plan Design (Rachel and Scott) to make decisions. b) A benefits administration team needs to be in place for both companies as soon as possible. When will this occur? c) What will be done with the benefit plans for each company (How will benefit plans be separated?) d) What will be done with our vendor contracts, specifically Aon Hewitt, BNY Mellon, Buck, etc. e) Will there be any impact due to union contracts. Warrick and Kingston will be negotiating with changes effective 4/1/2016. Interdependencies and decisions with Industrial Relations will need to be made. f) What will be done with the GPS Portal and any links to UPoint and H&W vendors (Highmark, Caremark, UCCI, etc.)? How will systems be split? Interdependencies with IT will need to be reviewed. g) Develop procedures. h) Develop training documents. i) Complete knowledge transfer. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track |  |  | X |  | X | X | X |  | X |  | X | [12 empty] | X | [7 empty] | X | Industrial Relations | 15 | 0 | 0% | No Review
x
Formulas:
Start Date (Calculated) = IF(ISBLANK(ProjectsTable[[#This Row],[Required Completion Date]]),"",ProjectsTable[[#This Row],[Required Completion Date]]-ProjectsTable[[#This Row],[Days to Accomplish]])
Project For GSS PMO Review? = IF(AND(ProjectsTable[[#This Row],[Status]]<>"On Track",ProjectsTable[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review",IF(OR(BA10>0.25),"Review","No Review"))

## Risk Register_HC
Lisa to complete in PMO
Date risk recorded | Project Number | Day 1 Project Name | Sub-Workstream (SWS) | Related project Task ID(s) | Risk Title | Mitigating Action(s) | Probability of occurance (0-100%) 0% being less probable | Degree of Impact (1-10) 1 being low impact | Risk rating (Probability x Impact) | For discussion in GSS PMO? (Y/N) | Status | Weekly Status Comments (enter date DD-MON-YYYY (06-JAN-2016) then comment) | Person recording risk (Last name, First name) | Date Reviewed in PMO DD-MON-YYYY (06-JAN-2016) | Track in Deloitte tool? | SPO escalation?
2016-01-11 | All | All | All | All | Procurement: GSS and Procurement need to negotiate separated vendor contracts. Several vendors will need to undertake actions to support our separation (e.g. system clones, interface work, internal staffing split, etc.). Lead times can be long, and their project complex. Separation fees and ongoing operating costs can be difficult to negotiate. | Tight linkage and participation with Procurement and the vendors involved during negotiations. GSS is going to negotiate some contracts themselves, per training provided by procurement. | 75% | 10 | 7.5 | Y | OnTrack | 13-Jan-2016: Initial highlight | Cochran, Hank |  | <Select> | <Select>
2016-01-12 | All | All | All | All | Vendor managed projects: Several vendors (e.g AonHewitt, etc.) will have to manage large projects very well in order to ensure clean separation. | Define requirements in January. Weekly track of vendor projects including progress, corrective actions, existing and new risks. Also ensure key integration points (functional decision, testing, and system/interface) are being maintained. | 50% | 10 | 5 | Y | OnTrack | 13-Jan-2016: Initial highlight | Cochran, Hank |  | Y | N
2016-01-12 | All | All | All | All | Alcoa GIS: Risk of system clones not completing on time and delaying integrated functional testing (data, applications, interfaces) and remediation. Risk of not having GPS decided by end of January. | Participate with GIS, and deliver needed inputs and knowledge…prepare for timely and thorough testing. | 75% | 10 | 7.5 | Y | OnTrack | 13-Jan-2016: Initial highlight | Cochran, Hank |  | <Select> | <Select>
2016-01-12 | All | All | All | All | Resourcing: Need to ensure sufficient testing resources are in place to support functional testing. Incremental resources need to be brought with proper lead time so as to be productive during testing and remdiation. | Identify and pre-arrange the resourcing needed. Operate with 75-90 day lead time so we are ready. | 50% | 9 | 4.5 | Y | OnTrack | 13-Jan-2016: Initial highlight | Cochran, Hank |  | <Select> | <Select>
2016-01-12 | All | All | All | All | Key Decisions (General and Specific): Need Decision on WFM path and GEC by 2/1 so project can be framed. BU and LE Hierarchy needs decided in order to enable system setup and testing, along with identifying any changes in instruction to locations and outsourcers. Many other decisions (TBO, commodity desk structure and systems, financing and bank accounts, branding, interim closing process, interim reporting needs, cutover processes, etc.) need finalized. | Staying connected with the relevant groups, some where we have direct influence, but some where we just need to understand the implications of the decision. | 50% | 10 | 5 | Y | OnTrack | 25-Jan-2016: Recommendation for WFM GPP solution being developed. Reaching out to GPP leadership week of 1/25 to present proposal. 13-Jan-2016: Initial highlight | Cochran, Hank |  | <Select> | <Select>
2016-01-25 | HC11 | T&A | Hank Cochran_HR_Benefits, Payroll, T&A | N/A (HC11-02) | Infrastucture sizing is required for the IT folks to properly establish application infrastucture on schedule for March 1. | IT organization is heading up this effort. Vondor has been somewhat responsive. We've received first draft from vendor but needs corrections | 25% | 5 | 1.25 | <Select> | OnTrack | 1/25 - Added to risk register |  |  | <Select> | <Select>
2016-01-26 | HC-03 | Accounts Payable | Hank Cochran_Finance | AP-CRP-04, AP-UAT-04, AP-PRD-04 | On time payment to critical global energy invoices relies on a connection from Siemens Customer Care to AGILARC LLC (formerly through Cyber) to Alcoa. Siemens is on Procurement's list as Tier4 which has been moved out to June 1. We should have this connection available to test in both CRP (starts Apr 18) and UAT (starts (May 23). Secondly, AGILARC LLC does not have a contract and is not on Procurement's list. We need to get it onto a list for GSS contact. | 1) Need to request Procurement move contact with Siemens earlier than June 1, and 2) Need AGILARC on a contact list. | 50% | 8 | 4 | N | At Risk | 1/26 (dk) Added to risk register | Koenig, Donna |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>

## Project Plan(s) - {HC revised}
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
|  | As Of | 2016-02-02 11:34
|  | Task-Level Description | [15 empty] | Dependency Resolution Checklist | [41 empty] | Total Work Hours by Bucket |  |  |  | 2016-01-01 |  |  |  | 2016-02-01 |  |  |  | 2016-03-01 |  |  |  | 2016-04-01 |  |  |  | 2016-05-01 |  |  |  | 2016-06-01 |  |  |  | 2016-07-01 |  |  |  | 2016-08-01 |  |  |  | 2016-09-01 |  |  |  | 2016-10-01
| Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) PLEASE ADD DATE BEFORE ANY COMMENT | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Riveiw? | Internal (Hanks Depts) Resource Work Hours Required (Team 1) | Internal (Hanks Depts) Team 1 Description | Internal (Hanks Depts) Resource Work Hours Required (Team 2) | Internal (Hanks Depts) Team 2 Description | External (to Alcoa) Resource Work Hours | Process (All, GL, FA, PA, CA) | Common Dependencies | Task Independent of all other GBS areas or RUs | Dependent Task SPA | Total Training and Knowledge transfer hours | Total System configuration hours | Total GSS IT system Testing Hours | Total Other hours | JAN Total Training and Knowledge transfer hours | JAN Total System configuration hours | JAN Total GSS IT system Testing Hours | JAN Total Other hours | FEB Total Training and Knowledge transfer hours | FEB Total System configuration hours | FEB Total GSS IT system Testing Hours | FEB Total Other hours | MAR Total Training and Knowledge transfer hours | MAR System configuration hours | MAR GSS IT system Testing Hours | MAR Total Other hours | APR Total Training and Knowledge transfer hours | APR Total System configuration hours | APR Total GSS IT system Testing Hours | APR Total Other Hours | MAY Total Training and Knowledge transfer hours | MAY Total System configuration hours | MAY Total GSS IT system Testing Hours | MAY Total Other hours | JUN Total Training and Knowledge transfer hours | JUN Total System configuration hours | JUN Total GSS IT system Testing Hours | JUN Total Other Hours | JUL Total Training and Knowledge transfer hours | JUL Total System configuration hours | JUL Total GSS IT system Testing Hours | JUL Total Other hours | AUG Total Training and Knowledge transfer hours | AUG Total System configuration hours | AUG Total GSS IT system Testing Hours | AUG Total Other Hours | SEPT Training and Knowledge transfer hours | SEPT Total System configuration hours | SEPT Total GSS IT system Testing Hours | SEPT Total Other hours | OCT Total Training and Knowledge transfer hours | OCT Total System configuration hours | OCT Total GSS IT system Testing Hours | OCT Total Other Hours | Check
HC08 | HC08 | N/A (HC08-01) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Organization Structure planning | Both | TRUE | MPS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Need a decision made on the IT strategy and if a TSA will be in place | [7 empty] | 2016-03-31 | [24 empty] | #REF! | 40 | GSS Leadership | [5 empty] | Yes
| HC08 | 80 - (HC07-01) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Hewitt payroll splits between companies and all associated functionalities will need to be known. | Both | TRUE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Dependent upon local payroll determinations which will impact how we proceed | Lowry, McCleary | Not Started | Critical to ensure cash reimbursments are set up properly | [7 empty] | X | [22 empty] | 2016-03-31 |  | No Review | 20 | T&E | 40 | GPS Solutions/Financial Accounting
| HC08 | 80 - (HC07-02) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Identify the T&E team members for each company | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Level 2 Management needs to determine split between Value-Add and Upstream | Lowry, McCleary | Not Started | Waiting for split determination - must include Hungary support group | [7 empty] | X | [24 empty] | No Review | 8 | GSS lead team
| HC08 | 80 - (HC07-03) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Obtain the new accounting structure for both entities and ensure that these structures are set up properly in the all vendors systems for which information is transferred (i.e. Concur, Citibank, American Express) | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Tax and Accounting | Lowry, McCleary | Not Started |  | X | X | [5 empty] | X | [24 empty] | No Review | 150 | T&E | 50 | GPS Solutions/Financial Accounting | 20
| HC08 | 80 - (HC07-04) | Hank Cochran_HR_Other | T&E | People Services - LOW - Duplicate the T&E Share Drive, Outlook Mailbox, Archives, SharePoint and other common files | Both | TRUE |  | 2016-10-01 | 90 | 2016-07-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [6 empty] | X |  | X | [24 empty] | No Review | 60 | T&E
| HC08 | 80 - (HC07-05) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM: Clone the existing T&E and LVP policies. | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 60 | T&E
| HC08 | 80 - (HC07-06) | Hank Cochran_HR_Other | T&E | People Services - LOW - Reveiow scope and SLA for each entity and make necessary changes | Both | FALSE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review
| HC08 | 80 - (HC07-07) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Transfer specified T&E knowledge, transfer or create training documents, transfer and/or revise SOPs | Both | TRUE |  | 2016-10-01 | 150 | 2016-05-04 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | [7 empty] | Yes
| HC08 | 80 - (HC07-08) | Hank Cochran_HR_Other | T&E | People Services - LOW - Clone all ASAT testing documents and determine to which entity historical information will be transferred to. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | [7 empty] | Yes
| HC08 | 80 - (HC07-09) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Identify which company, Upstream or Value-Add, each employee record will be transferred to, including historical records | Both | TRUE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X |  | No Review | 120 | T&E | 100 | GPS Solutions/Financial Accounting | 10
| HC08 | 80 - (HC07-10) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Clone Concur travel and expense systems and determiine approprate data purge process | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X |  | No Review | 200 | T&E | 200 | GPS Solutions/Financial Accounting | 20
| HC08 | 80 - (HC07-11) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Update / Change / or Revise login details specific to the Concur system | Both | TRUE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X |  | No Review | 50 | T&E | 100 | GPS Solutions/Financial Accounting
| HC08 | 80 - (HC07-12) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Reconcile all open accounts and distribute appropriate communications for next steps to the employees for account clean-up | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X |  | No Review | 100 | T&E
| HC08 | 80 - (HC07-13) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Review automated and standardized reporting to determine necessity and any potential revisions dependent upon the separation; including any changes in email addresses | Both | TRUE |  | 2016-08-01 | 120 | 2016-04-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | CONCUR | No Review | 120 | T&E | 200 | GPS Solutions/Financial Accounting
| HC08 | 80 - (HC07-14) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - For Concur, Citibank, and American Express, determine under which company the record will be assigned. Communicate to all appropriate parties as requred | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | Concur is the expense system so the accounts and any changes in Supervisory approval will need to be captured. Citiback issues the credit cards so the proper entity and acocunting codes will need to be determined. AMEX relates to the travel profile and appropriate credit card set ups. Waiting for split determination | [7 empty] | X | [22 empty] | X |  | No Review | 120 | T&E | 80 | GPS Solutions/Financial Accounting
| HC08 | 80 - (HC07-15) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Evaluate opportunities for transfer of work to KOFEM | Both | TRUE |  | 2016-10-01 | 200 | 2016-03-15 | 15% | FALSE | N/A | Lowry, McCleary | On Track | [8 empty] | X | [24 empty] | No Review
| HC08 | 80 - (HC07-16) | Hank Cochran_HR_Other | T&E | People Services - HIGH - IT system strategy for Global People Systems (GPS), server space, computers, general eldger, telephones, VPN, etc. | Both | TRUE |  | 2016-03-31 | 45 | 2016-02-15 | 0% | TRUE | This will be determined by GSS/IS and the BU. | Lowry, McCleary | Not Started | [6 empty] | X | [26 empty] | No Review | 80 | T&E
| HC08 | 80 - (HC07-17) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Implement Procurement contract strategy for all vendors and obtain necessary contracts. Ensure strategy includes impact on PO's. | Both | TRUE |  | 2016-03-31 | 50 | 2016-02-10 | 10% | TRUE | Assumption - no changes in 3rd party vendors. Dependencies relate to vendor feeds from GPS, Payroll, and funding sources. | Lowry, McCleary | On Track | Waiting for procurement to provide assistance |  |  | X |  |  | X |  |  |  | X | [22 empty] | No Review | 40 | T&E
| HC08 | 80 - (HC07-18) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Key Partner Summit to identify and review deliverables and develop detailed implementation plans | Both | TRUE |  | 2016-02-15 | 20 | 2016-01-26 | 5% | FALSE | N/A | Lowry, McCleary | On Track | IT and Procurement decisions need to be made in order to structure the summit discussion and determine next steps |  |  | X |  |  | X |  |  |  | X | [22 empty] | No Review | 16 | T&E |  |  | 50
| HC08 | 80 - (HC07-19) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Establish cutoff for separation related to credit card and payroll expense processing and revise schedule prospectively | Both | TRUE |  | 2016-10-01 | 90 | 2016-07-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 50 | T&E | 10 | GPS Solutions/Financial Accounting
| HC08 | 80 - (HC07-20) | Hank Cochran_HR_Other | T&E | People Services - HIGH - Issue new corporate credit cards to those assigned to Upstream and cancel old cards | Up. Co. | TRUE |  | 2016-10-01 | 90 | 2016-07-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | Issue new card, reconcile/clean up old account, cancel previous card | [7 empty] | X | [24 empty] | No Review | 100 | T&E
| HC08 | 80 - (HC07-21) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Establish necessary proceedures and accouting allocation for Citibank rebates | Both | TRUE |  | 2016-10-01 | 90 | 2016-07-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 20 | T&E | 10 | Financial Accounting | 10
| HC08 | 80 - (HC07-22) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Establish new process related to the auditing and rebates related to VAT receipts | Both | TRUE |  | 2016-10-01 | 90 | 2016-07-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 20 | T&E |  |  | 10
| HC08 | 80 - (HC07-23) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Establish process and ownership for Business Records Management | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 20 | T&E | 20 | Global Records Management
| HC08 | 80 - (HC07-24) | Hank Cochran_HR_Other | T&E | People Services - MEDIUM - Establish process for customer support and inquiries related to the Remedy system and the emergency phone support | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 40 | T&E
| HC08 | 84 (HC12-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | Waiting for direction from Plan Design |  |  |  |  | 2016-02-29 | [27 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | MPS_1 | 2016-04-30 | 30 | 2016-03-31 | 20% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | Waiting for direction from GBS/GSS | [7 empty] | 2016-04-30 | [24 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Determine how the benefit plans will be split. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | Waiting for direction from Plan Design, Legal and Tax. |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
|  | 84 (HC12-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, BNY Mellon, Buck Consulting, Buck Suriname, Millenium Trust, Aetna, etc. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | Waiting for direction from Procurement and Legal. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
|  | 84 (HC12-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - MED - determine how union contracts will be handled. Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2016-03-31 | 2016-03-31 | [25 empty] | 2016-03-31 | Industrial Relations | No Review | 10 | Benefits Administration Team | [5 empty] | No
|  | 84 (HC12-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | Waiting for direction from IT. | [5 empty] | 2016-03-31 | [26 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - MED - DEVELOP PROCEDURES | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC08 | 84 (HC12-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC08 | 84 (HC12-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - MED - DB Claims/Appeals - Process needs to be split and training is needed. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Defined Benefits | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started |  |  |  |  | 2016-04-30 | [28 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Month End Funding (pension payroll), Off Cycles, and MetLife funding - Process will need to be done at Upstream and Value Add companies. Training needed. Access needs to be granted to additional analyst to BNY Mellon Work Bench site, reports, contacts. | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Defined Benefits, BNY Mellon, Alcoa Legal to sign/review contracts for additional business, Upper Management Signatures needed for any additional signature cards and contracts, and Treasury Department | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started |  | 2016-04-30 |  | 2016-04-30 | 2016-04-30 | [28 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - PwC Audit - Independent annual audit requirement that outside auditors review plan procedures, payments, documents, calculations, etcetera. Works closely with DB and Benefits Accounting. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Defined Benefits and Benefits Accounting (DB works very closely with Benefits Accounting during audit and the relationship is very dependent) | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [24 empty] | 2016-05-31 | [8 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - Monthly and Annual Overpayment Processes. IRS requires some process to reimburse the Trust accounts for uncollectible pension amounts paid to participants in error. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Defined Benefits, Aon Hewitt, Alcoa Legal, Benefit Appeals Committee (Aon Hewitt sends files to DB, DB reviews and sends data to Alcoa Legal, annual uncollectibles go to BAC for decisions). | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started |  |  |  |  | 2016-05-31 | [28 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - Suriname is a major part of month end funding. If the company goes with the Upstream or Value Add, the entire month end funding process will have to be changed. Also, process to reissue pension payment returns/rejects. |  | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 5% | TRUE | Defined Benefits, Benefits Accounting, BNY Mellon, Buck Suriname. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track |  |  |  |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - Data Dump - Aon Hewitt sends updated participant data feed to DB Admin monthly. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE | Aon Hewitt and Defined Benefits. Aon Hewitt will need to send data to both companies. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Disability Pension Process - Before participants can go on disability retirement need to go through the process for approval with Aetna and Aon Hewitt. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Defined Benefits, Aon Hewitt, and Aetna. Aon Hewitt is the gatekeeper and Aetna determines the medical approvals or denials. DB handles additional level of appeal for denials. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started |  |  |  |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Trust Accounts will need to be split between companies and not just based on the cash value, but also will need new accounts (Holding accounts, General asset account, disbursement accounts, non-qualified account), at BNY Mellon and new signature cards and signers at the new company Treasury department and Human Resource signer. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | Defined Benefits, BNY Mellon, Alcoa Legal to sign/review contracts for additional business, Upper Management Signatures needed for any additional signature cards and contracts, and Treasury Department | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - MED - Valid Values/Plan Mapping - When there are new locations, Ben Admin receives notification to determine impacts on beenfits. | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 5% | TRUE | Benefits Administration (all 3 services), Defined Benefits, HRMS | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track |  |  |  |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC08 | 84 (HC12-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | FALSE | Defined Benefits, Aetna, Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
HC11 | HC11 | 84 (HC12-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Vendor Data Feeds - Data is passed from USBS and Alcoa locations to update participant records on a daily basis. Aon Hewitt also provides Actuarial Valuation files to Buck/Xerox Consultants for active, DV, and retiree data. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | USBS, Company Locations, Aon Hewitt, Buck/Xerox Consultants-participant changes and updates are submitted to Aon Hewitt nightly through a system feed from USBS and from Co Locations | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track | [6 empty] | 2016-03-31 | [26 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC11 | 84 (HC12-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - LOW - BRM/Richmond Pension Files - Will these files need to be split by Value Add vs. Upstream? Users at either company will need to have authorization to request files. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 5% | TRUE | Defined Benefits, Global Records Mgt, BRM | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track |  |  |  |  | 2016-04-30 | [28 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC11 | 84 (HC12-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Plan Documents, SPD's, Requirements need to be updated/rewritten for both companies, etc. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Angela Lowry, Joseph Adamietz, Natalie Thomas | On Track |  |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC11 | 84 (HC12-23) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | People Services - HIGH - Work with vendors to execute split of pension plans. | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | We will need to work with Vendors, Plan Design and Legal to ensure the split of both company's benefit plans have been executed legally and in accordance with the plan documents. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started |  |  | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 450 | Benefits Administration Team | [5 empty] | No
|  | 84 (HC12-24) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | Test Vendor-owned Systems | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | Test Vendor-owned Systems | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
|  | 84 (HC12-25) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | Test Single Sign-on of vendor sites | Both | TRUE | MPS_21 | 2016-07-31 | 15 | 2016-07-16 | 0% | TRUE | Test Single Sign-on of vendor sites | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not Started | [33 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC11 | 85 (HC 13-01) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Understand the size of GPP organization to be supported (potential employees to be served) | Up. Co | TRUE |  | 2016-01-31 | 30 | 2016-01-01 | 100% | TRUE | GPP leadership needs to define the size of the organization that will be supported in the future | Freier, Marcelo | On Track | 22-JAN-2016: GPP under definition | [30 empty] | X | GPP | No Review | [7 empty] | No
| HC11 | 85 (HC 13-02) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Understand the size of Value Add company - 2016 and anticipated growth for the next 3 - 5 years. | V-A Co. | FALSE |  | 2016-01-31 | 30 | 2016-01-01 | 100% | TRUE | Value Add leadership needs to define the size of the organization that will be supported in the future | Freier, Marcelo | On Track | [31 empty] | X | Value Add | No Review | [7 empty] | No
| HC11 | 85 (HC 13-03) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Define the systems that will be used by each of the companies (GPS, Workbrain, Web Based Reports, Equifax, Case Builder, ASP and Brassring) | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 20% | TRUE | IT needs to define the systems that will be used to support both groups | Freier, Marcelo | On Track | [6 empty] | X | [26 empty] | No Review | [7 empty] | No
| HC11 | 85 (HC 13-04) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Define the organization in Hungary that will support both companies, including GSS for Compliances activities. | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 10% | FALSE | N/A | Freier, Marcelo | On Track | [33 empty] | No Review | 15 | USBS | [5 empty] | No
| HC11 | 85 (HC 13-05) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Define the organization in US that will support both companies | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 5% | FALSE | N/A | Freier, Marcelo | On Track | [33 empty] | No Review | 15 | USBS | [5 empty] | No
| HC11 | 85 (HC 13-06) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Confirm if the same ASAT protocols will be applied for both companies | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 50% | TRUE | Audit needs to define the program that will be used in the future to support both companies | Freier, Marcelo | On Track | [24 empty] | X | [8 empty] | No Review | [7 empty] | No
| HC11 | 85 (HC 13-07) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Confirm the plans for Safe Harbor for both companies since this could impact our off shore operation | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 5% | TRUE | Legal and IT (security) need to define the document that will allow support from Hungary | Freier, Marcelo | On Track |  |  |  |  | X |  | X | [26 empty] | No Review | 10 | USBS | [5 empty] | No
| HC11 | 85 (HC 13-08) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Review scope and SLA for each one of the customers. | Both | TRUE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Customers will be involved in the process to validate future SLA and scope | Freier, Marcelo | Not Started | [31 empty] | X | Customers | No Review | [7 empty] | No
| HC11 | 85 (HC 13-09) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Review procedures to reflect the new reality | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | [7 empty] | No
| HC11 | 85 (HC 13-10) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Define and implement controls regarding access to data on fileshare, SharePoint, emails, and with vendors | Both | TRUE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT and Procurement needs to support the process | Freier, Marcelo | Not Started | [6 empty] | X |  |  |  | X | [22 empty] | No Review | 20 | USBS | [5 empty] | No
| HC11 | 85 (HC 13-11) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Create location and HR listings for each one of the companies | Both | FALSE |  | 2016-06-30 | 150 | 2016-02-01 | 10% | FALSE | N/A | Freier, Marcelo | On Track | [33 empty] | No Review | [7 empty] | Yes
| HC11 | 85 (HC 13-12) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Separate the documents (physical or electronic) for both companies | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT and Records Management need to support the process | Freier, Marcelo | Not Started | [6 empty] | X |  | X | [24 empty] | No Review | 100 | USBS | 20 | Global Records Management |  |  |  | No
| HC11 | 85 (HC 13-13) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Create a knowledge transfer plan to guarantee the organization skill and capabilities. | Both | TRUE |  | 2016-06-30 | 150 | 2016-02-01 | 10% | FALSE | N/A | Freier, Marcelo | On Track | [33 empty] | No Review | 30 | USBS | [5 empty] | Yes
| HC11 | 85 (HC 13-14) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Involve Procurement to negotiate the contracts - separation | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | Work with procurement on the commerical side of the program | Freier, Marcelo | Not Started | [10 empty] | X | [22 empty] | No Review | 20 | USBS | [5 empty] | No
| HC11 | 85 (HC 13-15) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Communicate the main changes to the customers (if there is a change in the scope) | Both | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | 5 | USBS | [5 empty] | No
| HC11 | 85 (HC 13-16) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Define and start the transition process among the team members | Both | FALSE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | [7 empty] | No
HC10 | HC10 | 85 (HC 13-17) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Work with People Systems Solutions to guarantee the testing process | Both | TRUE |  | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Freier, Marcelo | Not Started | [8 empty] | X | [24 empty] | No Review | 500 | USBS | [5 empty] | No
| HC10 | 85 (HC 13-18) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Work with HRDTA to guarantee the testing process | Both | TRUE |  | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Freier, Marcelo | Not Started | [8 empty] | X | [24 empty] | No Review | 500 | USBS | [5 empty] | No
| HC10 | 85 (HC 13-19) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Implement new controls to manage the process (if there are changes in the processes) | Both | TRUE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | [7 empty] | No
| HC10 | 85 (HC 13-20) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Implement actions to evaluate and measure the productivity for USBS based on the new reality | Both | FALSE |  | 2016-07-30 | 60 | 2016-05-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | [7 empty] | No
| HC10 | 85 (HC 13-21) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Perform an assessment to evaluate risks and opportunities to improve compliance process for USBS | Both | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | [7 empty] | No
| HC10 | 85 (HC 13-22) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Move employees between offices (to office location based on their new Company) - especially TN, Pittsburgh and Kofem | Both | TRUE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | 20 | USBS | [5 empty] | No
| HC10 | 85 (HC 13-23) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Evaluate opportunities after the transition to move further activities to Hub (Kofem) | Both | FALSE |  | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | [7 empty] | No
| HC10 | 85 (HC 13-24) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - HIGH - Implement the new help chain model - Remedy | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | 25 | USBS | [5 empty] | No
| HC10 | 85 (HC 13-25) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Create new mailbox for one of the companies | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | 20 | USBS | [5 empty] | No
| HC10 | 85 (HC 13-26) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - LOW - Create a new name/branding (USBS) that fits with the business models for GSS & separation to support both companies | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started | [33 empty] | No Review | 15 | USBS | [5 empty] | No
| HC10 | 85 (HC 13-27) | Hank Cochran_HR_Other | People Services Transaction Support | People Services - MEDIUM - Create authorized approver listings - transition of employees between V-A & Up. Co. | Both | TRUE |  | 2016-08-01 | 182 | 2016-02-01 | 10% | FALSE | N/A | Freier, Marcelo | On Track | [33 empty] | No Review | [7 empty] | Yes
| HC10 | 88 (HC 14-01) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Define the organization in US that will support both companies | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 5% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo | On Track | 2/1 - GBS/GSS to determine plan |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | 20 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-02) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Take a decision about the tracking system (Jordan Lawrence). If the system will continue for both companies. | Both | TRUE |  | 2016-06-30 | 150 | 2016-02-01 | 5% | TRUE | Legal & Ethics and Compliance to determine if continue with Jordan Lawrence | Freire, Marcelo Steve Snyder | On Track | heeter, garfinkel quinn to mention with ralph what does this offer upstream cost options |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | 15 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-03) | Hank Cochran_Records Management | Records Management | People Services - HIGH - Define the strategy to separate documents for both companies - according to Legal, recommendation is that records that are truly “corporate” and can’t be split stay with Value-Add | Both | TRUE |  | 2016-03-31 | 90 | 2016-01-01 | 5% | TRUE | Legal to provide direction | Freire, Marcelo Steve Snyder | On Track | 2/1 - Tim to set up meeting with Quinn/Marilyn; process should be similar to electroniuc data |  |  |  | X | [28 empty] | No Review | 50 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-04) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Confirm if the same ASAT protocols will be applied for both companies | Both | TRUE |  | 2016-04-30 | 120 | 2016-01-01 | 50% | TRUE | Audit needs to define the program that will be used in the future to support both companies | Freire, Marcelo Steve Snyder | On Track | 2/1 - On-going meetings with audit to determine ASAT's | [23 empty] | X | [8 empty] | No Review | [7 empty] | No
| HC10 | 88 (HC 14-05) | Hank Cochran_Records Management | Records Management | People Services - LOW - Review scope and SLA for each one of the customers. | Both | TRUE |  | 2016-06-30 | 150 | 2016-02-01 | 20% | TRUE | Legal and Ethis and Compliance will be involved in the process to validate future SLA and scope | Freire, Marcelo Steve Snyder | On Track | 2/1 - RIM Team to create SLA and rview with Marcelo, then discuss with Max/Sue for discussion with location controllers |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | [7 empty] | No
| HC10 | 88 (HC 14-06) | Hank Cochran_Records Management | Records Management | People Services - LOW - Review procedures to reflect the new reality | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started | 2/1 - Kathy to review during the annual SOP review and ensure processes are generci in nature, i.e. do not reference specific contacts (s/b titles) | [32 empty] | No Review | [7 empty] | No
| HC10 | 88 (HC 14-07) | Hank Cochran_Records Management | Records Management | People Services - HIGH - Involve Procurement to negotiate the contracts - separation | Both | TRUE |  | 2016-05-30 | 120 | 2016-01-31 | 5% | TRUE | Work with procurement on the commerical side of the program | Freire, Marcelo Steve Snyder | On Track | 2/1 - Discussing with Procurement | [9 empty] | X | [22 empty] | No Review | 50 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-08) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Define the funding for the program - Corporate for both Companies? This is very specific for Records Mgt since Corporate pays for the area | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Not Started | 2/1 - GBS/GSS to determine plan, then discuss with Max/Sue |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | 30 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-09) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Confirm if the retention schedule should be applied for both companies - according to Legal, recommendation is to clone existing Policy, Procedures and (new) Retention Schedules | Both | TRUE |  | 2016-02-28 | 60 | 2015-12-30 | 100% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Complete | 2/1 - Schedules will be used for both companies (will be included in other separation tasks related to communication) |  |  |  | X | [26 empty] | X | Ethics and Compliance | Review | 30 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-10) | Hank Cochran_Records Management | Records Management | People Services - HIGH - Work with RUs to ensure they understand that Records Segregation is one of their work streams, and what can and should be done pre-separation | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Customers will need to be involved in this review | Freire, Marcelo Steve Snyder | Not Started | 2/1 - Communication plan will need created - on-going with Sue/Max/Quinn | X | X | X | X | X | X | X |  |  | X | X | X | X |  | X | X | [6 empty] | X |  |  | X | [6 empty] | No Review | 50 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-11) | Hank Cochran_Records Management | Records Management | People Services - HIGH - Set Access Ground Rules for after the Separation | Both | TRUE |  | 2016-06-30 | 150 | 2016-02-01 | 5% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | On Track | 2/1 - Quinn and Marilyn to determine ground rules; then RIM can implement and ensure access is restricted as defined |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | 30 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-12) | Hank Cochran_Records Management | Records Management | People Services - LOW - Define Steering Team(s) and escalation plans (tax, legal, ethics and compliance) for each company | Both | FALSE |  | 2016-04-30 | 90 | 2016-01-31 | 5% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | On Track | 2/1 - Reviewing team makeup, and going to come up with proposal / recommendation |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | 30 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-13) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Partner with IT regarding guidance and protocols for electronic storage | Both | TRUE |  | 2016-05-30 | 120 | 2016-01-31 | 5% | TRUE | IT needs to support the process | Freire, Marcelo Steve Snyder | On Track | 2/1 - Meeting set up with Legal and IT teams | [5 empty] | X | [26 empty] | No Review | 200 | Global Records Management | [5 empty] | No
| HC10 | 88 (HC 14-14) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Define and implement controls regarding access to data on fileshare, SharePoint, emails, and with vendors | Both | TRUE |  | 2016-05-30 | 120 | 2016-01-31 | 5% | TRUE | IT needs to support the process | Freire, Marcelo Steve Snyder | On Track | 2/1 - Meeting set up with Jim Kavlinka - working with stakeholders; maybe one of the team can sit in on the meetings | [5 empty] | X | [26 empty] | No Review | [7 empty] | No
| HC10 | 88 (HC 14-15) | Hank Cochran_Records Management | Records Management | People Services - LOW - Create location and custodian listings, as well as standard metrics, for each company | Both | FALSE |  | 2016-05-31 | 150 | 2016-01-02 | 5% | FALSE | N/A | Freire, Marcelo Steve Snyder | On Track | 2/1 - On-going meetings with audit to determine beneficial metrics; internally, working on separating lists, DL's, etc | [32 empty] | No Review | [7 empty] | Yes
| HC10 | 88 (HC 14-16) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Complete to identify the Orphaned Boxes (boxes with no identification). Critical to identify prior to the separation. | Both | TRUE |  | 2016-04-30 | 120 | 2016-01-01 | 70% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | On Track | 2/1 - Tim to check with Reed Smith to see if can include in statistical sampling. If so, need plan for any boxes kept after review |  |  |  | X | [26 empty] | X | Ethics and Compliance | No Review | 20 | Global Records Management | [5 empty] | No
HC13 | HC13 | 88 (HC 14-17) | Hank Cochran_Records Management | Records Management | People Services - LOW - Communicate the main changes to the customers (if there is a change in the scope) | Both | FALSE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started | 2/1 - RIM team to develop trainings, faq's - in conjunction with Quinn and Marilyn | [32 empty] | No Review | 25 | Global Records Management | [5 empty] | No
| HC13 | 88 (HC 14-18) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Define and start the transition process among the team members | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 15% | FALSE | N/A | Freire, Marcelo Steve Snyder | On Track | 2/1 - GBS/GSS to determine plan | [32 empty] | No Review | [7 empty] | No
| HC13 | 88 (HC 14-19) | Hank Cochran_Records Management | Records Management | People Services - LOW - Implement actions to evaluate and measure the productivity for Records Management based on the new reality | Both | FALSE |  | 2016-06-30 | 61 | 2016-04-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started | 2/1 - Working on developing current metrics first | [32 empty] | No Review | [7 empty] | No
| HC13 | 88 (HC 14-20) | Hank Cochran_Records Management | Records Management | People Services - MEDIUM - Perform an assessment to evaluate risks and opportunities to improve compliance process for Records Management | Both | FALSE |  | 2016-05-30 | 120 | 2016-01-31 | 5% | FALSE | N/A | Freire, Marcelo Steve Snyder | On Track | 2/1 - On-going | [32 empty] | No Review | [7 empty] | No
| HC13 | 88 (HC 14-21) | Hank Cochran_Records Management | Records Management | People Services - LOW - Involve Steering Group Meeting to evaluate results after the separation (group supports strategical decisions within the area) | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started | [33 empty] | No Review | [7 empty] | No
| HC13 | 88 (HC 14-22) | Hank Cochran_Records Management | Records Management | People Services - LOW - Define the Records Coordinators network after separation | Both | TRUE |  | 2016-07-30 | 150 | 2016-03-02 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started | [33 empty] | No Review | [7 empty] | Yes
| HC13 | 88 (HC 14-23) | Hank Cochran_Records Management | Records Management | People Services - LOW - Move employees between offices (to office location based on their new Company) | Both | TRUE |  | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started | [33 empty] | No Review | 20 | Global Records Management | [5 empty] | No
| HC13 | 89 (HC15-01) | Hank Cochran_EHS | EHS | People Services - HIGH - ORG STRUCTURE - Determine how EHS Support resources will be split between companies | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 20% | TRUE | GBS/GSS/EHS will need to determine how the EHS Support teams will look in the new companies | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | Waiting for direction from GBS/GSS/EHS | [7 empty] | 2016-04-30 |  |  | 2016-04-30 | [21 empty] | No Review | 5 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-02) | Hank Cochran_EHS | EHS | People Services - HIGH - IT SYSTEMS STRATEGY - Determine how systems will be split between companies. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | IT will need to determine how the EHS Support systems will look in the new companies | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | Waiting for direction from IT | [5 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-03) | Hank Cochran_EHS | EHS | People Services - MED - DEVELOP PROCEDURES | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not Started | [33 empty] | No Review | 0 | US GSS EHS | [5 empty] | Yes
| HC13 | 89 (HC15-04) | Hank Cochran_EHS | EHS | People Services - LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not Started | [33 empty] | No Review | 0 | US GSS EHS | [5 empty] | Yes
| HC13 | 89 (HC15-05) | Hank Cochran_EHS | EHS | People Services - LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not Started | [33 empty] | No Review | 0 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-06) | Hank Cochran_EHS | EHS | People Services - HIGH - EHS SYSTEMS - Identify which EHS systems (IHS, SEM, OHM, etc.) each company (Upstream or Value Add) will use after the split. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | GBS/GSS/EHS will need to identify which systems will be used in the new companies. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [6 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-07) | Hank Cochran_EHS | EHS | People Services - HIGH - EHS SYSTEMS - how will upgrades to OHM and Comply Plus be handled? | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | EHS will need to provide plan of moving forward and role GSS plays in supporting these systems. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [11 empty] | 2016-03-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-08) | Hank Cochran_EHS | EHS | People Services - LOW - EHS SYSTEM SUPPORT - how will shared inboxes (IHS Help, EHS Help, etc.) be split - what happens to the archived, historical data? | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 5% | TRUE | GBS/GSS/EHS will need to determine how support will be done in the new company - split existing inboxes? Create new support structure? Etc. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [6 empty] | 2016-05-31 |  | 2016-05-31 |  |  | 2016-05-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-09) | Hank Cochran_EHS | EHS | People Services - MED - IHS REPORTS - Determine how existing custom excel reports will be split. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 5% | TRUE | EHS will need to provide plan on how reports will be handled for both companies. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [11 empty] | 2016-05-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-10) | Hank Cochran_EHS | EHS | People Services - MED - QBR PROCESS - Determine how the QBR process will be completed for both companies. Does the process remain the same? | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 5% | TRUE | EHS will need to provide plan on how the QBR will be generated and provided for both companies. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [11 empty] | 2016-05-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-11) | Hank Cochran_EHS | EHS | People Services - LOW - WELLNESS PROGRAM - Identify which company (Upstream or Value Add) will use the current Wellness program(s). | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 5% | TRUE | GBS/GSS/EHS/Wellness will need to identify which programs both new companies will continue to complete and the role GSS plays for analyses. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [6 empty] | 2016-05-31 |  | 2016-05-31 |  |  | 2016-05-31 | [21 empty] | No Review | 5 | US GSS EHS | [5 empty] | No
| HC13 | 89 (HC15-12) | Hank Cochran_EHS | EHS | People Services - MED - WELLNESS PROGRAM - Determine how Wellness programs (GCC, PROCAM, Lighten Up, etc.) historical analyses are split. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 5% | TRUE | GBS/GSS/EHS/Wellness will need to decide how historical data will be split for future analsyes. Will both companies be required to view all historical data for trending purposes? | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | On Track | [6 empty] | 2016-05-31 |  | 2016-05-31 |  |  | 2016-05-31 | [21 empty] | No Review | 10 | US GSS EHS | [5 empty] | No
| HC13 | AP-CRP-00 | Hank Cochran_Finance | Accounts Payable | Conduct end to end test of Accounts Payable in CRP | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Oracle instance availability; Taxware for tax calculations | Koenig,Verardi | Not Started |  |  | 42478 |  |  |  | 2016-04-18 |  | 2016-04-18 | [24 empty] | No Review | 112 | USBPC |  | Solutions
| HC13 | AP-CRP-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing (CRP Testing) | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Oracle CRP instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-04-18 |  | 2016-04-18 | [24 empty] | No Review | 16 | USBPC |  | Solutions
| HC13 | AP-CRP-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay (CRP Testing) | Both | FALSE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-04-18 |  | 2016-04-18 |  | 2016-04-25 | [22 empty] | No Review | 8 | USBPC |  | Solutions
| HC13 | AP-CRP-13 | Hank Cochran_Finance | Accounts Payable | Duplicate and test invoicing connections including Pullpay, B2B, ECM (CRP Testing) | Both | FALSE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Oracle CRP instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor availability of testing instances. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-04-18 |  | 2016-04-18 |  | 2016-04-25 | [22 empty] | No Review | 16 | USBPC |  | Solutions
| HC13 | AP-CRP-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports (CRP Testing) | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Oracle CRP instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-04-18 |  | 2016-04-18 | [24 empty] | No Review | 24 | USBPC |  | Solutions
| HC13 | AP-CRP-26 | Hank Cochran_Finance | Accounts Payable | Split Xerox contract and duplicate/test interface and connections to Oracle (CRP Testing) | Both | FALSE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-04-18 |  | 2016-04-18 |  | 2016-04-25 | [22 empty] | No Review | 16 | USBPC |  | Solutions
| HC13 | AP-CRP-31 | Hank Cochran_Finance | Accounts Payable | Test AP Subledger Closing for each company (CRP Testing) | Both | FALSE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Oracle CRP instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-04-18 |  | 2016-04-18 | [24 empty] | No Review | 8 | USBPC |  | Solutions
| HC13 | AP-PRD-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split for Production | Both | TRUE |  | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-07-04 |  | 2016-07-04 | [24 empty] | No Review | 16 | USBPC |  | Solutions
HC14 | HC14 | AP-PRD-03 | Hank Cochran_Finance | Accounts Payable | Create Oracle payment setups + technical connection to banks. Includes: EBS, FMW, FundTech, SWIFT, Bank (Production Setups) | Both | TRUE |  | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD testing schedule and instance availability; Supplier Maintenance Team and Solutions complete most setups. Treasury must create the bank accounts and ensure availability of bank testing resources and bank testing environment. | Koenig,Verardi | Not Started |  |  |  | 2016-06-30 |  |  | 2016-06-30 |  | 2016-06-30 | [24 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-PRD-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay (Production Setups) | Both | FALSE |  | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-07-04 |  | 2016-07-04 |  | 2016-07-04 | [22 empty] | No Review | 8 | USBPC |  | Solutions
| HC14 | AP-PRD-13 | Hank Cochran_Finance | Accounts Payable | Create production setups for invoicing connections including Pullpay, B2B, ECM (Production Setups) | Both | FALSE |  | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor coordination. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-07-04 |  | 2016-07-04 |  | 2016-07-04 | [22 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-PRD-17 | Hank Cochran_Finance | Accounts Payable | Production Setup of all Discoverer + Pi2P reports (Production Setups) | Both | TRUE |  | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD instance ready for setups and testing. Pi2P system set up and ready for testing. Solutions support for setups | Koenig,Verardi | Not Started | [6 empty] | 2016-07-04 |  | 2016-07-04 | [22 empty] | 2016-07-04 | GBS COE | No Review | 24 | USBPC |  | Solutions
| HC14 | AP-PRD-21 | Hank Cochran_Finance | Accounts Payable | Create people assignments and complete training | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | GSS decision regarding ORG structure for each company | Koenig,Verardi | Not Started | [8 empty] | 2016-05-01 | [24 empty] | No Review | 16 | USBPC
| HC14 | AP-PRD-26 | Hank Cochran_Finance | Accounts Payable | Create production interface and connections between Xerox and Oracle (Production Setups) | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for setup. | Koenig,Verardi | Not Started | [6 empty] | 2016-07-04 |  | 2016-07-04 |  | 2016-07-04 | [22 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-PRD-30 | Hank Cochran_Finance | Accounts Payable | Splitting of all contracts including FSG and AP recoveries | Both | FALSE |  | 2016-07-01 | 60 | 2016-05-02 | 0 | TRUE | Procurement action to split contracts | Koenig,Verardi | Not Started | [10 empty] | 2016-05-02 | [22 empty] | No Review | 4 | USBPC
| HC14 | AP-PRD-31 | Hank Cochran_Finance | Accounts Payable | Administrative Production Setups and Data Management | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0 | FALSE |  | Koenig,Verardi | Not Started | [33 empty] | #REF! | 150 | USBPC
| HC14 | AP-PRD-32 | Hank Cochran_Finance | Accounts Payable | Team Training and Change Communication | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0 | FALSE |  | Koenig,Verardi | Not Started | [33 empty] | #REF! | 100 | USBPC
| HC14 | AP-PRD-33 | Hank Cochran_Finance | Accounts Payable | Create Payment Access/Setups | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0 | FALSE |  | Koenig,Verardi | Not Started | [33 empty] | #REF! | 8 | USBPC
| HC14 | AP-UAT-00 | Hank Cochran_Finance | Accounts Payable | Conduct end to end test of Accounts Payable in UAT | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0 | TRUE | Oracle instance availability; Taxware for tax calculations | Koenig,Verardi | Not Started |  |  | 42513 |  |  |  | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 72 | USBPC |  | Solutions
| HC14 | AP-UAT-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing (UAT Testing) | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0 | TRUE | Oracle UAT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-UAT-03 | Hank Cochran_Finance | Accounts Payable | Create Oracle payment setups + technical connection to banks. Includes: EBS, FMW, FundTech, SWIFT, Bank (UAT Testing) | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0 | TRUE | Oracle UAT testing schedule and instance availability; Supplier Maintenance Team and Solutions complete most setups. Treasury must create the bank accounts and ensure availability of bank testing resources and bank testing environment. | Koenig,Verardi | Not Started |  |  |  | 2016-05-23 |  |  | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-UAT-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay (UAT Testing) | Both | FALSE |  | 2016-07-08 | 40 | 2016-05-29 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-05-23 |  | 2016-05-23 |  | 2016-05-30 | [22 empty] | No Review | 8 | USBPC |  | Solutions
| HC14 | AP-UAT-13 | Hank Cochran_Finance | Accounts Payable | Duplicate and test invoicing connections including Pullpay, B2B, ECM (UAT Testing) | Both | FALSE |  | 2016-07-08 | 40 | 2016-05-29 | 0 | TRUE | Oracle UAT instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor availability of testing instances. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-05-23 |  | 2016-05-23 |  | 2016-05-30 | [22 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-UAT-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports (UAT Testing) | Both | TRUE |  | 2016-07-08 | 40 | 2016-05-29 | 0 | TRUE | Oracle UAT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 24 | USBPC |  | Solutions
| HC14 | AP-UAT-18 | Hank Cochran_Finance | Accounts Payable | End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. (UAT Testing) | Both | FALSE |  | 2016-07-08 | 40 | 2016-05-29 | 0 | TRUE | Oracle UAT testing schedule and instance availability. Any changes, if needed, made in Taxware. | Koenig,Verardi | Not Started |  |  | 2016-05-23 |  |  |  | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 24 | USBPC |  | Solutions
| HC14 | AP-UAT-26 | Hank Cochran_Finance | Accounts Payable | Split Xerox contract and duplicate/test interface and connections to Oracle (UAT Testing) | Both | FALSE |  | 2016-07-08 | 40 | 2016-05-29 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-05-23 |  | 2016-05-23 |  | 2016-05-30 | [22 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-UAT-31 | Hank Cochran_Finance | Accounts Payable | Test AP Subledger Closing for each company (UAT Testing) | Both | FALSE |  | 2016-07-08 | 40 | 2016-05-29 | 0 | TRUE | Oracle UAT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 8 | USBPC |  | Solutions
| HC14 | AP-UNI-00 | Hank Cochran_Finance | Accounts Payable | Conduct end to end test of Accounts Payable in Unit Testing; does nto contain any testing of connections external to Alcoa | Both | TRUE |  | 2016-04-15 | 90 | 2016-01-16 | 0.01 | TRUE | Oracle Unit testing schedule and instance availability; Taxware for tax calculations | Koenig, Verardi | On Track | This is part of the Oracle system Unit testing. |  | 42444 |  |  |  | 2016-03-15 |  | 2016-03-15 | [24 empty] | No Review | 152 | USBPC |  | Solutions
| HC14 | AP-UNI-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing (Unit Testing) | Both | TRUE |  | 2016-04-15 | 31 | 2016-03-15 | 0 | TRUE | Oracle UNIT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | We will need to determine if both companies with to use Alcoa direct as a vendor portal. There are also several purchasing/payment processes which flow through AD. | [5 empty] | 2016-03-15 |  | 2016-03-15 | [24 empty] | No Review | 16 | USBPC |  | Solutions
| HC14 | AP-UNI-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports (Unit Testing) | Both | TRUE |  | 2016-04-15 | 31 | 2016-03-15 | 0 | TRUE | Oracle UNIT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | A huge amount of AP compliance, analysis and support tasks are done with the support of Discoverer and Pi2P reporting. These tools must be in working order for both companies in order to administer the AP function. | [5 empty] | 2016-03-15 |  | 2016-03-15 | [24 empty] | No Review | 24 | USBPC |  | Solutions
| HC14 | AP-UNI-31 | Hank Cochran_Finance | Accounts Payable | Test AP Subledger Closing for each company (Unit Testing) | Both | FALSE |  | 2016-04-15 | 31 | 2016-03-15 | 0 | TRUE | Oracle UNIT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not Started | [6 empty] | 2016-03-15 |  | 2016-03-15 | [24 empty] | No Review | 8 | USBPC |  | Solutions
| HC14 | FSS-HC01-01 | Hank Cochran_Finance | Finance System Support | Create / Update SOPs and Training Documents | Both | FALSE |  | 2016-05-15 | 135 | 2016-01-01 | 5% | FALSE |  | Ridilla | On Track | In preparation for an organization separation, create/update training documents and SOPs to be use for cross-training and future reference. Also, ensure SharePoint site and Fileshare data will be available for both companies. | [32 empty] | No Review | 120 | Fin/RTP Solutions
HC01 | HC01 | FSS-HC01-02 | Hank Cochran_Finance | Finance System Support | Identify SharePoint/FileShare/Portal strategy- for all documentation | Both | FALSE |  | 2016-06-30 |  | 2016-06-30 | 0% | TRUE | Identify strategy for replication of SharePoint sites/fileshares in order to store documentation and information | IT | Not Started | [6 empty] | 2016-03-31 | [26 empty] | No Review | 40 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-03 | Hank Cochran_Finance | Finance System Support | Resolve Software Licensing/Contracts | Both | TRUE |  | 2016-01-31 |  | 2016-01-31 | 2% | TRUE | Procurement and Legal need to negotiate with system providers for licenses, support, etc. for the two separate companies/systems. | Procurement | On Track |  |  |  |  | 2016-01-31 | [5 empty] | 2016-01-31 | [22 empty] | No Review | 40 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-04 | Hank Cochran_Finance | Finance System Support | Separation of Cloud Solution Environments | Both | TRUE |  | 2016-04-15 | 75 | 2016-01-31 | 1% | TRUE | Identify SPAs for Cloud Solutions and, once Procurement/Legal arranges licensing, work with our vendors to create a second environment for the Upstream company. This includes but is not limited to Ariba/Quadrem, Vinimaya, Walmedian, ACS, Standard Register, IQN, IPS, PiLog | GSS, Procurement & COE | On Track | [6 empty] | 2016-04-15 |  | 2016-04-15 |  | 2016-04-15 | [22 empty] | No Review | 400 | Fin/RTP Solutions
| HC01 | FSS-HC01-05 | Hank Cochran_Finance | Finance System Support | Separation of Data within Systems | Both | TRUE |  | 2016-04-15 | 102 | 2016-01-04 | 2% | TRUE | Data within our systems which is shared across companies (e.g. POs, Contracts, Assets, Projects, GL Balances, Asset Blue Sheets, etc.) needs to be separated by the process owners to position us for the clone of software. Also, a strategy needs to be established for what to do with existing data (i.e. bleed out or convert). | GSS & Procurement | On Track |  | 2016-04-30 | 2016-04-30 | 2016-04-30 |  | 2016-04-30 | 2016-04-30 |  | 2016-04-30 |  | 2016-04-30 | [6 empty] | 2016-04-30 | [7 empty] | 2016-04-30 | [7 empty] | No Review | 200 | Fin/RTP Solutions
| HC01 | FSS-HC01-06 | Hank Cochran_Finance | Finance System Support | Automated process for Separation of Data in Shared OU/Inventory Orgs | Both | TRUE |  | 2016-04-15 | 60 | 2016-02-15 | 0% | TRUE | Define process to move data from one OU/Inventory Org to another for those that share both future companies' data. | Business Units | Not Started | 09-JAN-2016: Awaiting direction on approach for data separation to determine if there is a system solution needed. | [5 empty] | 2016-03-31 |  | 2016-03-31 |  | 2016-03-31 | [20 empty] | 2016-04-30 | BUs, RUs, Canada | No Review | 150 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-07 | Hank Cochran_Finance | Finance System Support | Resolving NON Operating Unit activity | Both | TRUE |  | 2016-04-15 | 102 | 2016-01-04 | 5% | TRUE | Define direction for separation/movement of comingled data within the NON operating unit. | GSS, Procurement & COE | On Track | 09-JAN-2016: Meeting scheduled for next week to discuss approach for NON OU. | [7 empty] | 2016-03-31 |  | 2016-03-31 | [20 empty] | 2016-04-30 | BUs, RUs, Canada | No Review | 400 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-08 | Hank Cochran_Finance | Finance System Support | AR Shared Services Orgs | Both | TRUE |  | 2016-04-15 | 102 | 2016-01-04 | 5% | FALSE |  | GSS | On Track | 09-JAN-2016: Meeting scheduled for next week to discuss approach. Determine a strategy for how to handle the data in the 3 AR Shared Services Operating Units in EBS (likely don't need to do anything with MEX) | [30 empty] | 2016-04-30 | BUs, RUs, Canada | No Review | 200 | Fin/RTP Solutions
| HC01 | FSS-HC01-09 | Hank Cochran_Finance | Finance System Support | Establish new Legal entities and/or L-Parents | Both | TRUE |  | 2016-05-15 | 135 | 2016-01-01 | 0% | TRUE | Legal entities and L-Parents need to be established for both companies. Corporate Consolidations will lead via Tax. | Legal | Not Started |  | 2016-03-31 | [31 empty] | Review | 100 | [5 empty] | X
| HC01 | FSS-HC01-10 | Hank Cochran_Finance | Finance System Support | Establish new Bank Accounts | Both | TRUE |  | 2016-04-15 | 130 | 2015-12-07 | 2% | TRUE | Establish and configure new AP, AR and SWIFT bank accounts and arrangements/configurations in time for testing so as not to risk rework and retesting. | Treasury | On Track | 09-JAN-2016: Awaiting Treasury efforts (need to be in the loop). |  |  | 2016-03-31 |  |  |  |  | 2016-03-31 | [24 empty] | No Review | 200 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-11 | Hank Cochran_Finance | Finance System Support | Resolving Intercompany and IICS | Both | TRUE |  | 2016-05-15 | 100 | 2016-02-05 | 1% | FALSE | Plans need to be made for how Intercompany and IICS will be handled with the new companies and when the intercompany vs. third party designation will be changed in the system. | Finance | On Track | 09-JAN-2016: Need to ensure all Intercompany transactions are being addressed(and need to be in the loop). | 2016-03-31 | 2016-03-31 |  | 2016-03-31 | [28 empty] | No Review | 500 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-12 | Hank Cochran_Finance | Finance System Support | Prepare Testing Strategy | Both | FALSE |  | 2016-04-15 | 80 | 2016-01-26 | 0% | FALSE |  | Ridilla | Not Started | Prepare a Test Plan for each application that ensures adequate testing within GSC, TCS and Alcoans and consider whether or not this can be an opportunity to cross-train resources in the process. Also ensure resource availability for production support to be maintained during the Separation process. | [27 empty] | 2016-03-31 |  |  |  |  | Review | 500 | Fin/RTP Solutions
| HC01 | FSS-HC01-13 | Hank Cochran_Finance | Finance System Support | Identify System Configuration Changes | Both | FALSE |  | 2016-04-15 | 100 | 2016-01-06 | 1% | FALSE |  | Ridilla | On Track | Identify configuration changes that will be need to be made in the system once the clone is complete. Examples include links and trusted internet access to external sites (e.g. ACS, PiLog), ship-to address, GL Cross Validations rules, MOAC Setups, Projects OU Structure, etc. | [32 empty] | No Review | 200 | Fin/RTP Solutions
| HC01 | FSS-HC01-14 | Hank Cochran_Finance | Finance System Support | Understanding Rules of Engagement between OD1 and LD1 | Both | FALSE |  | 2016-05-20 | 130 | 2016-01-11 | 0% | TRUE | Need to better understand how we will operation on Operational Day 1 so that we can configure the systems properly (e.g. Will Oplinger need approval capability in both companies until LD1?) | Separtion Office | Not Started |  | 2016-04-30 |  |  | 2016-04-30 | [28 empty] | Review | 200 | [5 empty] | X
| HC01 | FSS-HC01-15 | Hank Cochran_Finance | Finance System Support | IT Code Remediation | Both | TRUE |  | 2016-03-31 |  | 2016-03-31 | 0% | TRUE | GIS needs to identify any company/org-specific coding that should be remediated for the separation. This includes but is not limited to Customer Facing documents/logos, Terms and Conditions, references to instance ids, alcoa.com and AP Check signatures. Also need to understand plan for updating e-mail addresses across the systems when alcoa.com changes to a new domain. | IT | Not Started | [6 empty] | 2016-03-31 | [26 empty] | No Review | 0 | [5 empty] | X
| HC01 | FSS-HC01-16 | Hank Cochran_Finance | Finance System Support | Tax Software Configuration (Taxware/EBTax) | Both | FALSE |  | 2016-03-15 |  | 2016-03-15 | 0% | TRUE | Taxware engine needs to be functional and accurate. This includes but is not limited to Direct Pay Permits, Goods and Services Codes and Entity Codes. Also, a sales tax exemption certificate is needed in order to make tax-free purchases of items and services that are taxable. Each company will need its own. This is currently handled by Taxware (Sovos). | Tax & IT | Not Started |  |  | 2016-03-31 |  |  |  | 2016-03-31 | [26 empty] | No Review | 0 | [5 empty] | X
| HC01 | FSS-HC01-17 | Hank Cochran_Finance | Finance System Support | Identifying and Tesitng System Interfaces | Both | FALSE |  | 2016-04-15 | 90 | 2016-01-16 | 0% | TRUE | All system interfaces for Upstream will need to be identified and repointed to the appropriate new environment and interfaces to both companies' systems will need to be tested | IT & GSS | On Track | [6 empty] | 2016-03-31 |  | 2016-03-31 | [22 empty] | 2016-03-31 | BUs and RUs | No Review | 300 | Fin/RTP Solutions |  |  |  |  | X
| HC01 | FSS-HC01-18 | Hank Cochran_Finance | Finance System Support | Update Existing RTP Hierarchies | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | The new organization structures will need to be finalized in order to populate the new hierarchies | Ridilla | Not Started | Due to all of the Organization Changes, new RTP Hierarchies will need to be created in EBS | [32 empty] | No Review | 175 | Fin/RTP Solutions
| HC01 | FSS-HC01-19 | Hank Cochran_Finance | Finance System Support | Alcoa-Hosted Systems Ready for Testing | Both | TRUE |  | 2016-03-15 |  | 2016-03-15 | 0% | TRUE | GIS must deliver a test-ready system in enough time to perform "solutions" level testing and remediation before funtional user testing occurs. We are expect 2-3 rounds of such testing. If dependency not fulfilled, there is a risk of not have proper separation of systems or error/omission in the financials, or being unable to transact business across all applications. | GSS, Procurement & COE | Not Started | [6 empty] | 2016-03-01 |  | 2016-03-31 |  | 2016-03-31 | [22 empty] | No Review | 0
| HC01 | FSS-HC01-20 | Hank Cochran_Finance | Finance System Support | Testing Event 1 | Both | TRUE |  | 2016-04-15 | 31 | 2016-03-15 | 0% | FALSE |  | GSS & Procurement | Not Started | Test all systems (EBS, non-EBS and hosted) in light with GBS-IS Dev, CRP and UAT timelines | [5 empty] | 2016-03-01 | [26 empty] | No Review | 1750 | Fin/RTP Solutions
| HC01 | FSS-HC01-21 | Hank Cochran_Finance | Finance System Support | Testing Event 2 - CRP | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0% | FALSE |  | GSS & Procurement | Not Started | Test all systems (EBS, non-EBS and hosted) in light with GBS-IS Dev, CRP and UAT timelines | [5 empty] | 2016-04-25 | [26 empty] | No Review | 1750 | Fin/RTP Solutions
| HC01 | FSS-HC01-22 | Hank Cochran_Finance | Finance System Support | Testing Event 3 - UAT | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0% | FALSE |  | GSS & Procurement | Not Started | Test all systems (EBS, non-EBS and hosted) in light with GBS-IS Dev, CRP and UAT timelines | [5 empty] | 2016-05-30 | [26 empty] | No Review | 2000 | Fin/RTP Solutions
| HC01 | FSS-HC01-23 | Hank Cochran_Finance | Finance System Support | Software Vendor Assistance | Both | FALSE |  | 2016-03-31 |  | 2016-03-31 | 0% | FALSE |  | IT | Not Started | Working in conjunction with GIS, we will need prompt resolution of showstopper issues. Vendors include: Oracle, TCS, Sovos, etc. Without critical support from vendors, the overall solution will be jeopardized. | [5 empty] | 2016-03-31 | [26 empty] | No Review | 0
| HC01 | FSS-HC01-24 | Hank Cochran_Finance | Finance System Support | Train Future IT Support & Developers | Both | FALSE |  | 2016-04-30 |  | 2016-04-30 | 0% | TRUE | GIS needs to identify our support model for the two companies going forward and ensure personnel are trained to function effectively on OD1. | IT | Not Started | [6 empty] | 2016-04-30 | [26 empty] | No Review | 0
| HC01 | FSS-HC01-25 | Hank Cochran_Finance | Finance System Support | Global Solution Coordination | Both | FALSE |  | 2016-07-31 | 170 | 2016-02-12 | 0% | FALSE |  | Ridilla | Not Started | Need close connection with GSS support and functional counterparts around the world for global solutions. | [32 empty] | No Review | 100 | Fin/RTP Solutions
| HC01 | FSS-HC01-26 | Hank Cochran_Finance | Finance System Support | Revisiting ATC Projects Superuser | Both | FALSE |  | 2016-04-15 | 70 | 2016-02-05 | 0% | FALSE |  | Ridilla | Not Started | ATC is a special location which is a Projects superuser, has special processes, and some they orchestrate and maintain themselves. Strong connection will be key, else the solution could be damaged. | [32 empty] | Review | 100 | Fin/RTP Solutions
| HC01 | FSS-HC01-27 | Hank Cochran_Finance | Finance System Support | Identify new Solutions orgs and cross-train personnel | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | FALSE |  | Ridilla | Not Started | The new Solutions organizations need to be determined and personnel need to be trained so that all applicable solutions can be supported in both new companies. | [7 empty] | 2016-05-13 | [19 empty] | 2016-05-13 |  |  |  |  | No Review | 400 | Fin/RTP Solutions
| HC01 | FSS-HC01-28 | Hank Cochran_Finance | Finance System Support | Develop Cutover Plan | Both | TRUE |  | 2016-05-13 | 80 | 2016-02-23 | 0% | FALSE |  | GSS, Procurement, COE & IT | Not Started | Define Cutover plan for any changes that need to be orchestrated within and across applications (e.g. GL structures/period, concurrent program schedules, configuration changes, Reconciliation process, etc.) | [5 empty] | 2016-05-13 |  | 2016-05-13 | [24 empty] | No Review | 300 | Fin/RTP Solutions
| HC01 | FSS-HC01-29 | Hank Cochran_Finance | Finance System Support | Understanding EBS Archive Instance Strategy | Both | FALSE |  | 2016-06-30 |  | 2016-06-30 | 0% | TRUE | GBS-IS will need to identify and implement a plan for the data currently stored in the EBS Archive Instance | IT | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | 120 | Fin/RTP Solutions
| HC01 | FSS-HC01-30 | Hank Cochran_Finance | Finance System Support | Identifying Application Security revisions | Both | FALSE |  | 2016-05-13 | 85 | 2016-02-18 | 0% | FALSE |  | GSS & IT | Not Started | EBS and Non-EBS Application Security will need to be reviewed to ensure (1) individuals can do what they need to and (2) can't do what they should be able to any longer. Also, new owners will need to be identified for shared accounts (e.g. Scheduling Accounts) and we need to ensure that we are SOD-compliant. In addition, LBC Security rules will need to be manipulated (which directly links to Responsbilities). This impacts all applications. | [5 empty] | 2016-05-13 |  | 2016-05-13 | [24 empty] | No Review | 300 | Fin/RTP Solutions
| HC01 | FSS-HC01-31 | Hank Cochran_Finance | Finance System Support | MOAC Setup revisions | Both | FALSE |  | 2016-04-15 | 30 | 2016-03-16 | 0% | FALSE |  | GSS & IT | Not Started | Review/revise Multi-Org Access setups for new company structures | [7 empty] | 2016-05-13 | [24 empty] | No Review | 200 | Fin/RTP Solutions
| HC01 | FSS-HC01-32 | Hank Cochran_Finance | Finance System Support | Go Live with New Systems | Both | TRUE |  | 2016-08-01 |  | 2016-08-01 | 0% | TRUE |  | All | Not Started | Execute Cutover Plan and go live with New Systems | [32 empty] | No Review | 300 | Fin/RTP Solutions
| HC01 | FSS-HC01-33 | Hank Cochran_Finance | Finance System Support | Deactivation Plan / Purge System Data | Both | FALSE |  | 2016-06-30 | 75 | 2016-04-16 | 0% | TRUE | Determine if there is a legal need to purge data from either/both systems once cloned | GSS, Procurement & IT | Not Started | Prepare a plan for deactivating obsolete data within each instance of each application once the clone is complete (to avoid errant data being entered). Potentially consider security controls as an alternative. | [5 empty] | 2016-05-13 |  | 2016-05-13 | [24 empty] | No Review | 250 | Fin/RTP Solutions
| HC01 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | EBS Testing of systems post cloning - 3 test cycles (QA, CRP, UAT) - 3 months of testing - May, Jun, Jul for August 1, 2016 Go Live | Both | TRUE |  | 2016-07-08 | 90 | 2016-04-09 | 0% | TRUE | Dependant on IT having the systems separated and data loaded to the test environment | Chris Hoerger | Not Started | 2 to 3 weeks testing per test cycle - standard testing cycles historically performed for Alcoa system implementations, upgrades leading up to GoLive. | [5 empty] | X | [26 empty] | No Review | 360 | US FAS Team |  |  |  | All |  |  | Schoeffler, Richard
HC05 | HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Non EBS Testing of systems | Both | TRUE |  | 2016-07-15 | 90 | 2016-04-16 | 0% | TRUE | Dependant on IT having the systems separated and data loaded to the test environment | Chris Hoerger | Not Started | 2 to 3 weeks testing per test cycle - standard testing cycles historically performed for Alcoa system implementations, upgrades leading up to GoLive. | [5 empty] | X | [26 empty] | No Review | 360 | US FAS Team |  |  |  | All |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Testing or Create Accounting in Final Mode - actually imports and posts from the Inventory Module activity to the General Ledger. | Both | FALSE |  | 2016-07-15 | 90 | 2016-04-16 | 0% | TRUE | Dependant on IT having the systems separated and data loaded to the test environment | Angela Deliman | Not Started | All Create Accounting activities will need to be tested to ensure that the data is populated correctly, there are no menu changes that are not expected, reports can be run without issues, queries can be run without issues, all appropriate inventory orgs appear when they should in the responsibility that they should, etc. | [5 empty] | X | [26 empty] | No Review | 360 | US FAS Team |  |  |  | CA |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Shared Location separation - Identify list of Alcoa shared Lparents that contain both VA and Upstream Tranactiosn and re-direct transactions to the appropirtae LBCs | Both | TRUE |  | 2016-02-28 | 30 | 2016-01-29 | 2% | TRUE | Finance team needs to create and modify Lparent hierarchy. | Chris Hoerger | Not Started | For operating plants, many costs - H&W from Pittsburgh Corp, Projects, etc go to a general LBC(GN LBC) then get allocated in Oracle GL to the individual operating LBCs based on mass allocations set up in Oracle. All those costs will need re-directed to the individual LBCs or new LBCs - Reach out to financial transactions group to determine what is required in order for transactions to be separated between companies. - Confirm with the financial transactions group as to when the transactions will be separated between companies - Review current LBC Mapping file and identify Lparents that cross both companies - Reach out to consolidations group and financial transactions team to understand all implications of Lparent separation - Confirm with finance team as to when LBC separation will be completed - Once the Shared Locations have a list of the new L-parents, we need to ensure proper Cost Accounting team members are in place for obtaining system access, participating in the testing cycles, verifying that the data/menu options are correct, etc. | X | [31 empty] | Review | 240 | US FAS Team |  |  |  | All |  | Y | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine reconciliation system and process for each company | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE |  | Chris Hoerger | Not Started | Will both companies use Shared Servies to reconcile and continue with the new Global RST Tool and Virtual Reconciliation process? The Global RST Tool is loaded through concurrent manager processes that run on WD2 to load GL balances to the RST Tool, as well as Subsystem balances to the RST Tool. | [32 empty] | No Review | 240 | US FAS Team |  |  |  | GL/CA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Suport IT with the system clone process | Both | TRUE |  | 2016-04-30 | 90 | 2016-03-01 | 0% | TRUE | Replicate the appropriate data on both companies. Work with IT on how excluding or deleting data from each system will be accomplished. | Mike Donaldson | Not Started | How will the companies be separated in the system - clone? Feeds into separate systems? How will Shared Locations be separated - ie. L0059 Corporate HQ, L0016 ATC, L0033 Warrick, L0030 Tennessee, Massena, etc. FAS will need involved in how being separated and if upfront work or breakout of data is needed to flow properly to each separate company. MRO and eAM activity properly separated into individual inventory orgs The eRFA system should be cloned and made available for both. Existing Open and On-Hold RFA's that are owned by currently shared locaitons will need to be revised and re-assigned to the appropriate business. Need to review the .pdf download of archived RFA's and ensure that an efficient process is available for retrieving archive RFA's. | X |  |  |  |  | X |  | X | [24 empty] | No Review | 180 | US FAS Team |  |  |  | All |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Work with Financial Transactions and Corp RUs to determine the carve outs needed for the Pittsburgh HQ LBCs (L0059) | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Angela Huey | Not Started | Over 20 RUs supported through Corp HQ (L0059), and each has varying levels of services provided, with Global Mobility being one of the most complex. Determine for each RU the journal entries, tasks, and misc tasks required for each company. | [32 empty] | No Review | 180 | US FAS Team |  |  |  | GL
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine the EBS system access requirements for employees of each company | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE | Who needs GL access and what type of access. Help IT coordinate the set-up and chages and removal from existing systems. | Jeff Koslow | Not Started | Two systems, two system access. (1) what is the process to request access or remove access if changing from one company to the other and different systems. (2) what accesses are required - ie. P599 (multiple access - GL USER, AP inquiry for various OUs, PO inquiry for various OUs, P594, Discoverer, Hyperion, JDE, T&E, etc. | [32 empty] | No Review | 120 | US FAS Team |  |  |  | GL |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Evaluate current 2978 positions to ensure in balance | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Angela Deliman | Not Started | BPO centralized team can determine the 2978xxxx relationships between the two companies and clear to the 12201000/30101000 for settlement and discontinue those transactions and use of the Category to create 2978 balancing. | [7 empty] | X | [24 empty] | No Review | 120 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Duplicate ASAT testing documents for each company | Both | FALSE |  | 2016-06-01 | 30 | 2016-05-02 | 0% | FALSE |  | Steve Shepard | Not Started | ASAT Objectives will need to be clearly defined as GL, FA, PA, or All FAS. Duplicate ASATs should be created for each business. - Review all ASATs to confirm which ones need setup for both companies - Duplicate ASATs so that both companies have all necessarry scripts - Create ASAT schedule for both companies - Ensure controls are in place for both companies - Assign SPAs for each ASAT for both companies | [32 empty] | No Review | 120 | US FAS Team |  |  |  | GL | X | Y
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine configuration for fixed asset books, appraisal issues, tax requirements | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Randy Couch | Not Started | Many of the fixed asset books will be needed for both businesses. A thorough review of these books and a determination of the structure will be determined for both. All tax books will be copied and used for both. | [32 empty] | No Review | 120 | US FAS Team |  |  |  | FA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine Shared Project separation for Project Accounting | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Randy Couch | Not Started | All projects that have an LBC that is not clearly assigned to an LBC that will go upstream or value add will need to reviewed and reassigned to the appropriate business. Shared projects may need to be duplicated and split between businesses referencing the original approved RFA. | [32 empty] | No Review | 120 | US FAS Team |  |  |  | PA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine the system access requirements for Cost Accounting employees | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | Who needs system access and what type i.e. Oracle; Discoverer; AS400; JD Edwards; ShowCase Query and coordinate set-up. | Angela Deliman | Not Started | Once the Shared Services staffing assignments are available in April-2016, we need to ensure proper Cost Accounting team members are in place for obtaining system access, participating in the testing cycles, verifying that the data/menu options are correct, etc. | [32 empty] | No Review | 120 | US FAS Team |  |  |  | CA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Develop test scripts for EBS system testing | Both | FALSE |  | 2016-04-30 | 15 | 2016-04-15 | 0% | FALSE |  | Ashley/Chris | Not Started | GL: Develop test scripts to test GL which will include all feeds from 3rd parties, intercompany (approximately 75 test scripts for customized process), AR (Susbsytem feeds into ledger), AP (subsystem feeds into ledger), discover . These test scripts are very similar to scripts used in R12 testing. FA/PA: We can use test scripts here that were used in the Oracle R12 upgrade. Testing of project set up, feeds from Oracle feeders, manual FET uploads, and other sources that impact project costing. Testing of all fixed asset transactions (additions, retirements, transfers, adjustments, asset splits, depreciable life changes, etc.) need to be performed in the asset system and test their accounting results that are fed to the general ledger. When the new Oracle system for the spin off business is available, we need to rely heavily on the Hungary team members for performing transaction tests. CA: We can use test scripts here that were used in the Oracle R12 upgrade. When the new Oracle system for the spin off business is available, we need to rely heavily on the Hungary team members for performing transaction tests. All daily, weekly, and monthly cost accounting activities will need to be tested to ensure that the data is populated correctly, there are no menu changes that are not expected, reports can be run without issues, queries can be run without issues, all appropriate inventory orgs appear when they should in the responsibility that they should, etc. | [32 empty] | No Review | 90 | US FAS Team |  |  |  | All |  | ?
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Work with the Global IICS team to design plan for intercompany handling | Both | FALSE |  | 2016-04-30 | 90 | 2016-02-15 | 0% | TRUE | Global IICS Team needs to establish intercompany relationships for the two companies and settle any intercompanies which will turn into 3rd party relationships once separated. | Ashley Nayden | Not Started | Process in place for any missed AR/AP customer/supplier set ups which flow through intercompany. How to handle and record properly in the current period. | [7 empty] | X | [24 empty] | No Review | 90 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Map all intercompany settlement scenarios and evaluate issues related to shared cash accounts | Both | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE |  | Ashley Nayden | Not Started | Determine who will be responsible for the intercompany settlements - Global IICS team, Treasury or FAS. What is the cutoff and timing. Are the netting setup properly. | [7 empty] | X | [24 empty] | No Review | 90 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Ensure proper recording of Interco Clearing Settlements (inside / outside Global IICS System) | Both | FALSE |  | 2016-08-01 | 90 | 2016-05-03 | 0% | FALSE |  | Ashley Nayden | Not Started | Actual settlement and reconciling process once recorded to ensure recorded properly. US to US invoiced cleared on a montly basis to manual interco accounts. | [7 empty] | X | [24 empty] | No Review | 90 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Create or modify policies and procedures relating to management of General Ledger, Fixed Assets and Projects, Cost Accounting. | Both | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | FALSE |  | Ashley/Chris | Not Started | GL: This would be a duplication of policies and procedures for both companies. Documentation would be for any new p&p implemented for either company. FA/PA: Copy all SOP's. Review the two groups of SOP's and separate specific upstream and value add business procedures. Delete those that will not pertain to the applicable business. There are many exceptions related to the upstream GPP locaitons that will not apply to the Value Add locations. CA: All daily, weekly, and monthly cost accounting activities will need to be tested to ensure that the data is populated correctly, there are no menu changes that are not expected, reports can be run without issues, queries can be run without issues, all appropriate inventory orgs appear when they should in the responsibility that they should, etc. Any modifications to the SOPs, checklists, key documents, etc. need to be updated. | [32 empty] | No Review | 90 | US FAS Team |  |  |  | All
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Shared folder setup and access for US FAS Team | Both | FALSE |  | 2016-04-30 | 15 | 2016-04-15 | 2% | TRUE | Shared folders are used to store journals, account reconciliations, processes and procedures. The two companies will need to be on different servers, thus all information will need split between the two servers | Steve Shepard | Not Started | Set up of new Shared folder/server for one of the companies, assuming one will keep existing. Separation of the exiting company to the new Shared folder/server. Access for the identified employees to the new server. | [5 empty] | X | [26 empty] | No Review | 60 | US FAS Team |  |  |  | All |  | Y
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Aid in the Portal Design for each company and relink the neccesary documents for each Compnay | Both | FALSE |  | 2016-04-30 | 15 | 2016-04-15 | 0% | TRUE | It will have to be decieded whether the current Alcoa portal will be replicated or not for both companies and what will be required for re-link based on required docuemnts for each company | Angela Huey | Not Started | [6 empty] | X | [26 empty] | No Review | 60 | US FAS Team |  |  |  | All
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | SharePoint setup and access for US FAS Team | Both | FALSE |  | 2016-04-30 | 15 | 2016-04-15 | 0% | TRUE | Sharepoint sites are used within Shared Services as well as between locations and Shared Services. | Mike Donaldson | Not Started | Set up of new Sharepoint sites if shared. Access for the identified employees to the new server. Removal of employees from security on existing Sharepoint sites. | [5 empty] | X | [26 empty] | No Review | 60 | US FAS Team |  |  |  | All |  | Y
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Confirm the proper accounting and separation of 3rd party billings to Corp HQ (L0059) | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE | 3rd party, would need to break out all billing into two companies accurately based on inviduals. Confirm the cutoff / transfer of consolidated billings: - Cell phones - AT&T calling cards - ePlus - Genesys - VPN - Others? | Angela Huey | Not Started | Charges should split by company based on individual set up. Primary contact will be Ed Belajac for phones and Eplus, and potentially Dan Copeland. | [32 empty] | No Review | 60 | US FAS Team |  |  |  | GL
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Change AR customer setups - from Intercompany to 3rd Party | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | AR and AP need to change setups in order for the proper relationships to flow into the GL | Heather Bloss | Not Started | AR and AP need to change customer and supplier setups for intercompany to 3rd party. | [7 empty] | X | [24 empty] | No Review | 60 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Change AP customer setups - from Intercompany to 3rd Party | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | AR and AP need to change setups in order for the proper relationships to flow into the GL | Angela Huey | Not Started | AR and AP need to change customer and supplier setups for intercompany to 3rd party. | [7 empty] | X | [24 empty] | No Review | 60 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Evaluate current 1220/3010 positions to ensure in balance | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Angela Deliman | Not Started | Determine intercompany relationships that will need settled. Evaluate any out of balance and resolve 2-3 months in advance of settlement date. | [7 empty] | X | [24 empty] | No Review | 60 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Record Separation Accounting Entries - Cash, Stock, Goodwill, Debt, etc | Both | FALSE |  | 2016-09-30 | 30 | 2016-08-31 | 0% | FALSE |  | Chris Hoerger/Ashley Nayden | Not Started | FAS working with FP&A, Financial Transactions, etc on how the deal will be recorded, when, how, etc. | [32 empty] | No Review | 60 | US FAS Team |  |  |  | GL
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine Shared Fixed Asset separation | Both | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | TRUE |  | Randy Couch | Not Started | Operating locaitons such as Warrick, Tennessee, Pittsburgh, Alcoa Technical Center, Massena, and possbily others have fixed assets that will need to be separated by Upstream and Val Add businesses. We will work directly with these locations to determine the designated owner of the assets to they can be reassigned accordingly. | X | [13 empty] | X | [17 empty] | No Review | 60 | US FAS Team |  |  |  | FA |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine Oracle Project Operating Units and the assignment of locations to the OU's | Both | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | FALSE |  | Randy Couch | Not Started | Many of the Oracle OU's are already aligned by business, but there are OU's such as the NON OU that has shared Corporate projects. Tennessee and Warrick are in the RPD OU which will need to be split into RPD and the existing Primary Products OU. This can be determine mostly by the LBC assignment of projects in Oracle. Project assigned to GN (LBC's ending in 0) will need to be reassigned to one of the operating LBC's that get moved to upstream or value added OU's. | [32 empty] | No Review | 60 | US FAS Team |  |  |  | PA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Separate Capitalized Interest Significant Spreasheet | Both | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | FALSE |  | Bob Mankos | Not Started | The capitalized interest spreadsheet is considered a significant spreadsheet and is reviewed by PwC on a monthly basis and during audit for access controls and accuracy of formulas. This spreadsheet will need to be separated by business and project for future use by each of the businesses. | [32 empty] | No Review | 60 | US FAS Team |  |  |  | PA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Separate Capitalized Interest Assets on Corporate Ledger | Both | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | FALSE |  | Bob Mankos | Not Started | All capitalized interest fixed assets will need to be split into assets according to their owning business. Any unclear ownership assets will need to be reviewed and future ownership will be approved before reassigining the the separate business entities. | [32 empty] | No Review | 60 | US FAS Team |  |  |  | FA
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Separate the Tennessee and Warrick Asset Sale for Tax Benefit (Recorded under shared LPs of VA and Upstream) | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE |  | Randy / Bob | Not Started | There are separate legal entities set up for the ownership of fixed assets that were sold for tax benefits for both Tennessee (Alcoa Cooling) and Warrick (Warrick Partnership). Step up logic and accounting enries feeds will need to be copied and asset will need to be split accordingly between Primary and RPD. Will also review the option of 'undoing' this structure and place the assets back on the operating LBC's to simplify the process. The tax department will need to approve this option or be involved in the set up of duplicate entities structures if we mainatin the process going forward for both companies. | X | X | [30 empty] | No Review | 60 | US FAS Team |  |  |  | FA |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Create or modify SLA's relating to US FAS support. | Both | FALSE |  | 2016-06-30 | 15 | 2016-06-15 | 0% | FALSE |  | Mike Donaldson | Not Started | [33 empty] | No Review | 60 | US FAS Team |  |  |  | All |  | Y
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Shared Mailboxes will need to be reviewed and reassinged for customer locaitons and/or renamed to fit the new structure | Both | FALSE |  | 2016-05-31 | 10 | 2016-05-21 | 0% | FALSE |  | Randy Couch | Not Started | We currently have 8 Outlook mailboxes for customer use for fixed asset transactions (1 mailbox names Property Accounting Fixed Asset Transactions) and 7 different BU Group mailboxes that are specific for locaiton use depending on their owning BU. These will need to be reviewed and reconfigured for the two new businesses and communicated for customer use. | [32 empty] | No Review | 40 | US FAS Team |  |  |  | All | X
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine IICS entries that are no longer needed due to separation and identify entries that should now be booked as 3rd party. | Both | FALSE |  | 2016-03-31 | 15 | 2016-03-16 | 0% | TRUE | Work with Global IICS Team to identify the entire population of transactions that will need changed. | Ashley Nayden | Not Started | Determine / query intercompany relationships between the two companies and discontinue; work with the location to process as 3rd party. Will need to work with SZE Global team to ensure these items are not setup in GDW as well. | [7 empty] | X | [24 empty] | No Review | 30 | US FAS Team |  |  |  | GL |  |  | Pap, Edina
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine impact of sale on EBS asset value | Both | FALSE |  | 2016-04-30 | 10 | 2016-04-20 | 0% | TRUE |  | Randy Couch | Not Started | Not sure that this will need to be treated as a sale vs. splitting the EBS assets beforehand and assigning the split portions to the appropriate business. | X |  |  |  |  | X | [26 empty] | No Review | 10 | US FAS Team |  |  |  | FA |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Aid IT in Identify Systems and Interfaces needed for each Company | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | The entire accounting process relies on the System structure being established for both companies (Oracle P599, GDW P594, Intercompany System, Discoverer, Hyperion, Inventory, T&E, Freight, Projects, Fixed Assets, JD Edwards, AS400, ShowCase, etc.) | Mike Donaldson | Not Started | Feeds into Oracle GL are set up and flow to the proper Company and Locations. Purchasing, Inventory, Payables, Receivables, Payroll, T&E, Freight, Assets, Projects, Temp Labor, Treasury (Quantum). Individuals will be assigned to each segment to work with the RU and SS to ensure information is separated appropriately. It aslo needs to be determined if IT will be testing non-core programs e.g. JD Edwards, AS400, and ShowCase, etc) | X |  |  |  |  | X |  | X | [24 empty] | No Review | 0 | N/A - Non US FAS |  |  |  | All | X |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Identify and test the Legacy and 3rd Party feeds into EBS Systems | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | 3rd Party, Subsystems, Legacy systems need to flow into the respecitive systems accurately and timely (Payroll, Freight, Temp Labor, T&E, Inventory, etc) | Chris Hoerger | Not Started | How will legacy and 3rd party interfaces feed into the two separate systems. What is the change over timing, will this be determined and implemented for the testing period starting in May? | [5 empty] | X | [26 empty] | No Review | 0 | N/A - Non US FAS |  |  |  | GL/CA |  |  | Schoeffler, Richard
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | In conjunction with Tax, Corporate Consolidation, FP&A, Financial Transactions and BU Controllers review and implement LEC/LBC/BU structure for each company. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | The entire accounting process relies on the LBC structure being complete and hierarchy established. Review and understand the use for any new entities. Review structure of deal in terms of LBC's included and LBC's excluded where complete LEC's or OU's could be accomplished. LBC request list, fiscal requirements (LEC / SOB / OU set up) | Chris Hoerger | Not Started | There are many LBCs that roll up into the same Lparent, SubBU, BU then Legal Entity. What will the new structure be for both companies. | X |  |  |  |  | X | [26 empty] | No Review | 0 | N/A - Non US FAS |  |  |  | All |  |  | Fontecchio, John M
| HC05 | HC02-73,75,77 | Hank Cochran_Finance | General Ledger, FAPA, Cost Accounting | Determine Closing Process for each company | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Chris Hoerger | Not Started | Timing of close? Will it remain the same for both companies. If differs, how does that affect the systems cutoff timing (AR, AP, Purchasing, Projects, Fixed Assets, Inventory, etc) | X | [31 empty] | No Review | 0 | N/A - Non US FAS |  |  |  | All |  |  | Schoeffler, Richard
HC06 | HC06 | N/A (HC05-01) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on ERP & AR applications solution | Both | TRUE |  | 2016-01-31 | 0 | 2016-01-31 | 50% | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | On Track | Clone and remediate data? | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-02) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on approach for separating/segregating data in the cloned environments | Both | TRUE |  | 2016-03-01 | 0 | 2016-03-01 |  | TRUE | SPMO/Finance decision on transactional data strategy needed by 1/31/16. | Caldwell/Antli | Not Started | Will current/open transactions be removed from each respective instance? Will there be a bleed-out period between OD1 & LD1. What about history data? | 2016-01-31 | [31 empty] | No Review | 0
| HC06 | N/A (HC05-03) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on approach for handling archived instance and related transactions at time of separation | Both | TRUE |  | 2016-03-01 | 0 | 2016-03-01 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell | Not Started | What is the plan for supporting archived data for both entities at time of separation? | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-04) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on OTC invoicing solution | Both | TRUE |  | 2016-01-31 | 0 | 2016-01-31 | 50% | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | On Track | Will both entities leverage current model? If so, need new contracts with Standard Register along with new interface testing and implementation. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-05) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on legal entity/LBC structure and names | Both | TRUE |  | 2016-03-01 | 0 | 2016-03-01 |  | TRUE | Decision by EC/Legal on new entity name and alignment of existing entities by 3/1/16. | Caldwell/Antli | Not Started | Prerequisite to testing invoice changes and establishing new bank accounts. |  |  |  | 2016-03-01 | [28 empty] | No Review | 0
| HC06 | N/A (HC05-06) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on banking relationships and account structures | Both | TRUE |  | 2016-03-01 | 0 | 2016-03-01 |  | TRUE | Decision by Treasury on banking relationships and account structures by 3/1/16. | Caldwell | Not Started | Will same or different institutions be involved? If different, significantly more testing of payment interfaces will be required. |  |  | 2016-03-01 | [29 empty] | No Review | 0
| HC06 | N/A (HC05-07) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on potential changes to current AR securitization programs due to separation | Both | TRUE |  | 2016-04-01 | 0 | 2016-04-01 |  | TRUE | Decision by Treasury on banking relationships and account structures by 3/1/16. | Caldwell/Antli | Not Started | Determine impact of separation on existing securitization programs as well as evaluate efforts needed to support any new program that may be proposed by Treasury. |  |  | 2016-03-01 | [29 empty] | No Review | 0
| HC06 | N/A (HC05-08) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on approach for handling intercompany transactions at time of separation | Both | TRUE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | SPMO/Finance decision on transactional data strategy needed by 1/31/16. | Caldwell/Antli | Not Started | What is the plan for eliminating intercompany transactions and relationships at time of separation? (POs/Sos/Invoices/etc.) | 2016-01-31 | [31 empty] | No Review | 0
| HC06 | N/A (HC05-09) | Hank Cochran_Finance | Accounts Receivable | Establish/create target systems environment to enable configuration udpates and testing activities | Both | TRUE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Replicate EBS environment for all BU and RU groups to perform any configuration changes needed along with full cycle testing activities | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-10) | Hank Cochran_Finance | Accounts Receivable | Create duplicate EDI environment to support new trading partner arrangements | Both | TRUE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Replicate e-commerce environment for all transaction sets and update/modify data setups to reflect new entities/trading partner relationships. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-11) | Hank Cochran_Finance | Accounts Receivable | Configurations - custom processes | Both | FALSE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Final pricing, summary billing, IICS, adjustments, bolt-on parameters, etc. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-12) | Hank Cochran_Finance | Accounts Receivable | Configurations - tax regimes | Both | FALSE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Ensure Taxware in place for US.; EBTax for CA/MX | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-13) | Hank Cochran_Finance | Accounts Receivable | Configurations - Trade Management | Both | FALSE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell | Not Started | Replicate and/or modify claim types, routing and approval rules, write-off codes, etc. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-14) | Hank Cochran_Finance | Accounts Receivable | Configurations - Interfaces | Both | FALSE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Update related setups to support data flows between systems. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC06 | N/A (HC05-15) | Hank Cochran_Finance | Accounts Receivable | Validate current AR configurations and OU operating model will support future solution | Both | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 10% | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | On Track | Will both entities employ SSAR OU structure? Does upstream have a need for the shared AR OU structure going forward? | [5 empty] | 2016-01-15 | [26 empty] | No Review | 24 | NA AR
| HC06 | N/A (HC05-16) | Hank Cochran_Finance | Accounts Receivable | Identify and assess impact of permanent configuration settings (e.g OU settings, etc.) | Both | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 10% | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | On Track | Will desired or required changes in configurations be feasible based on Oracle AR design and current settings | [5 empty] | 2016-01-31 | [26 empty] | No Review | 16 | NA AR
| HC06 | N/A (HC05-17) | Hank Cochran_Finance | Accounts Receivable | Identify and assess impact of changes to the alcoa.com domain | Both | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 1% | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | On Track | AR operations will be significantly impacted due to link to receipt of remittance data from customers, AR invoicing, etc. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 32 | NA AR
| HC06 | N/A (HC05-18) | Hank Cochran_Finance | Accounts Receivable | Establish new contracts with Standard Register to support invoice processing for both entities | Both | FALSE |  | 2016-03-31 | 75 | 2016-01-16 | 1% | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | On Track | [6 empty] | 2016-01-31 | [26 empty] | No Review | 40 | NA AR
| HC06 | N/A (HC05-19) | Hank Cochran_Finance | Accounts Receivable | Decision on future organization structure & staffing approach | Both | TRUE |  | 2016-03-31 | 0 | 2016-03-31 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Understand organizational direction and develop plan to align AR staffing accordingly. | [7 empty] | 2016-03-31 | [24 empty] | No Review | 0
| HC06 | N/A (HC05-20) | Hank Cochran_Finance | Accounts Receivable | Identify and develop testing plan including approach for ensuring post-clone processing is restricted to only the respective entity's transactions | Both | FALSE |  | 2016-04-15 | 30 | 2016-03-16 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | What is the plan for excluding the other's transactions during post-separation processing? | [5 empty] | 2016-01-15 | [26 empty] | No Review | 32 | NA AR
| HC06 | N/A (HC05-21) | Hank Cochran_Finance | Accounts Receivable | Update and test configurations to enable printing new entity name on invoices | Both | FALSE |  | 2016-04-15 | 31 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Update related setups to enable invoice printing. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 8 | NA AR
| HC06 | N/A (HC05-22) | Hank Cochran_Finance | Accounts Receivable | Update and test configurations to enable processing payment data from new bank accounts | Both | FALSE |  | 2016-04-15 | 31 | 2016-03-15 |  | TRUE | Decision by Treasury on banking relationships and account structures by 3/1/16. | Caldwell/Antli | Not Started | Create new banks, accounts, payment methods, etc. |  |  | 2016-03-31 |  |  | 2016-01-31 | [26 empty] | No Review | 8 | NA AR
| HC06 | N/A (HC05-23) | Hank Cochran_Finance | Accounts Receivable | Testing activity 1: Design and unit testing | Both | FALSE |  | 2016-04-15 | 31 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Perform testing of applications and environment per plan. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 68 | NA AR
| HC06 | N/A (HC05-24) | Hank Cochran_Finance | Accounts Receivable | Identify customers of both businesses that will need to be contacted to alert them to processing changes. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Identify those customers which buy from both future entities and develop communication process to ensure alignment with future process and transactional flows. | [7 empty] | 2016-03-31 | [24 empty] | No Review | 24 | NA AR
| HC06 | N/A (HC05-25) | Hank Cochran_Finance | Accounts Receivable | Develop training and cross-training plan to ensure both organizations have sufficient expertise to sustain operations | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Identify skillset needs of future organizations and develop training plan to ensure both teams have knowledgable resources for all aspects of processing. | [7 empty] | 2016-03-31 | [24 empty] | No Review | 16 | NA AR
| HC06 | N/A (HC05-26) | Hank Cochran_Finance | Accounts Receivable | Establish AR operational approval limits for both entities (adjustments, refunds, etc.) | Both | FALSE |  | 2016-05-20 | 50 | 2016-03-31 |  |  | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Update AR configurations for operations teams in line with new management guidelines. | [7 empty] | 2016-03-31 | [24 empty] | No Review | 8 | NA AR
| HC06 | N/A (HC05-27) | Hank Cochran_Finance | Accounts Receivable | Testing activity 2: CRP | Both | FALSE |  | 2016-05-20 | 32 | 2016-04-18 |  |  | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Perform testing of applications and environment per plan. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 68 | NA AR
| HC06 | N/A (HC05-28) | Hank Cochran_Finance | Accounts Receivable | Identify destination for replication of key process documentation (file share, file admin, etc.) | Both | TRUE |  | 2016-05-31 | 90 | 2016-03-02 |  |  | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Determine new file server structure for storage of replicated and new process documentation. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 32 | NA AR
| HC06 | N/A (HC05-29) | Hank Cochran_Finance | Accounts Receivable | Define approach & process for handling post-split activity (cash from customers, etc.). | Both | FALSE |  | 2016-05-31 | 60 | 2016-04-01 |  |  | SPMO/Finance decision on transactional data strategy needed by 1/31/16. | Caldwell/Antli | Not Started | Determine plan and process to ensure cash received from customers by one entity belonging to the other entity is handled appropriately. | 2016-01-31 | [31 empty] | No Review | 32 | NA AR
| HC06 | N/A (HC05-30) | Hank Cochran_Finance | Accounts Receivable | Understand approach and develop processes to accommodate 2-month window between OD1 and LD1 | Both | FALSE |  | 2016-05-31 | 60 | 2016-04-01 |  |  | SPMO/Finance decision on transactional data strategy needed by 1/31/16. | Caldwell/Antli | Not Started | Will both entities run entirely separately or can a bleed-out approach be employed? Key considerations are directing cash from customers to proper entity, creation & use of second operations structure (e.g. AR mailbox, staff, etc.) |  |  | 2016-03-01 | [29 empty] | No Review | 48 | NA AR
| HC06 | N/A (HC05-31) | Hank Cochran_Finance | Accounts Receivable | Notify customers of new remittance instructions | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 |  |  | Decision by Treasury on banking relationships and account structures by 3/1/16. | Caldwell/Antli | Not Started | Need to send notices to customers of new remittance guidance 30-60 days in advance of effective date of change. | [7 empty] | 2016-03-31 | [24 empty] | No Review | 24 | NA AR
| HC06 | N/A (HC05-32) | Hank Cochran_Finance | Accounts Receivable | Notify shared customers of impact of impending split as it relates to invoicing, payment, and customer service processing. | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 |  |  | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Ned to send alerts to customers of potential, pending changes in invoicing, payment, and customer service/inquiry processes 30-60 days in advance of change. | [7 empty] | 2016-03-31 | [24 empty] | No Review | 32 | NA AR
| HC06 | N/A (HC05-33) | Hank Cochran_Finance | Accounts Receivable | Establish shared mailboxes, AR templates, and related workflows for both entities | Both | FALSE |  | 2016-07-01 | 60 | 2016-05-02 |  |  | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Duplicate current model for both entities | [7 empty] | 2016-03-31 | [24 empty] | No Review | 40 | NA AR
| HC06 | N/A (HC05-34) | Hank Cochran_Finance | Accounts Receivable | Dedine and implement cash control procedures with the Treasury Back Office teams of both entities | Both | FALSE |  | 2016-07-01 | 60 | 2016-05-02 |  |  | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli | Not Started | Duplicate current model for both entities | [7 empty] | 2016-04-30 | [24 empty] | No Review | 16 | NA AR
| HC06 | N/A (HC05-35) | Hank Cochran_Finance | Accounts Receivable | Configurations - update customer records to reflect external vs. internal status | Both | FALSE |  | 2016-07-01 | 30 | 2016-06-01 |  | TRUE | Identification of impacted intercompany customers by 4/30/16 | Caldwell/Antli | Not Started | Customer master changes needed on both sides. | [7 empty] | 2016-04-30 | [24 empty] | No Review | 16 | NA AR
| HC06 | N/A (HC05-36) | Hank Cochran_Finance | Accounts Receivable | Prepare cutover plan | Both | FALSE |  | 2016-07-01 | 30 | 2016-06-01 |  | TRUE |  | Caldwell/Antli | Not Started | Finalize approach for interim period and publish related procedures | [5 empty] | 2016-01-31 | [26 empty] | No Review | 16 | NA AR
| HC06 | N/A (HC05-37) | Hank Cochran_Finance | Accounts Receivable | Testing activity 3: UAT | Both | FALSE |  | 2016-07-08 | 46 | 2016-05-23 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Perform testing of applications and environment per plan. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 112 | NA AR
HC15 | HC15 | N/A (HC05-38) | Hank Cochran_Finance | Accounts Receivable | Establish new configurations in production both pre-and post-clone to expedite cutover | Both | FALSE |  | 2016-08-01 | 60 | 2016-06-02 |  | TRUE |  | Caldwell/Antli | Not Started | [33 empty] | No Review | 32 | NA AR
| HC15 | N/A (HC06-01) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish or renew 3rd party contracts for Credit Information Reporting ( D&B, CRM, Elipru, Cortera) | Both | TRUE |  | 2016-07-01 | 120 | 2016-03-03 | 2 | TRUE | Procurement need to work through this to determine how the D&B, CRM contract will be impacted and split at the time of separation. Need to ensure no price increase to occur with the split of contracts | Lintner -EUR and Caldwell/Heroux -US | On Track | We need to move current contract from Alcoa Kofem to the new Value add co, prepare document to follow the entity changes ensuring no distruption in report usuage and history. We need analyze the amount of report needs. For Upstream we need a new contract and review if exitsing monitoring services of the year could be pulled in the new contract | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Credit EUR | 20 | Credit NAM |  |  | x
| HC15 | N/A (HC06-02) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish or renew 3rd party agreements with collections agencies (Coface-EUR and AGA-NAM) | Both | TRUE |  | 2016-07-01 | 60 | 2016-05-02 |  | TRUE | Procurement need to work through this to determine how the contract will need to be split between the Co, listing the new Legal entity names to cover | Lintner -EUR | Not Started | Provide list of open cases to proc that will be open at the time of separation. We need both Co to have the contract in place | [9 empty] | 2016-07-01 | [22 empty] | No Review | 0 | Credit EUR | 0 | Credit NAM |  |  | x
| HC15 | N/A (HC06-03) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish new Credit authorization guidelines (Delegation of Authorities, Bad Debt approval authorities, refund limits, etc.) for teams servicing both entities | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 |  |  |  | Cochran/Caldwell/Lintner | Not Started | define responsibilities according to new roles and organization | [32 empty] | No Review |  | Credit EUR |  | Credit NAM
| HC15 | N/A (HC06-04) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Revise, re-run, and review new charge outs for both entities (re-run model) | Both |  |  | 2016-04-30 | 30 | 2016-03-31 |  |  |  | Cochran | Not Started | Request Finance Director to rerun the chargeback model for the new structure and rediscuss with BU | [32 empty] | No Review |  | Credit EUR |  | Credit NAM
| HC15 | N/A (HC06-05) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Arrange L/C Banking support for both entities (EUR: Credit Suiss L/C - Treasury) | Both | TRUE |  | 2016-07-01 | 60 | 2016-05-02 |  | TRUE | Work with Treasury in order to make sure that contract for L/C accounts are transfered /negociated and we have new account for the differnt 2 entities in place | Castiello -EUR, Chen for China | Not Started |  |  |  | 2016-03-31 | [29 empty] | No Review | 20 | Credit EUR
| HC15 | N/A (HC06-06) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Arrange LC banking support for both entities (NOA: US Bank L/C - Treasury) | Both | TRUE |  | 2016-07-01 | 40 | 2016-05-22 |  | TRUE | Work with Treasury to identify the new LC advising bank and negotiate agreements | Eisler | Not Started | Currently with US Bank but will depend on core banks for new entity. |  |  | 2016-03-31 | [29 empty] | No Review |  |  | 24 | Credit NAM
| HC15 | N/A (HC06-07) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Coordinate customer communications concerning new remittance instructions: EUR_Treasury Bank accounts: 1) Citibank access, 2) New bank accounts who/when to inform customers | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 |  | TRUE | work to be done in agreement with Treasury, BU / PLANT, Controllers, IT | Castiello - EUR/Chen for China | Not Started | be linked with treasury to make sure that our citicard access will remain and that we will be informed on new bank accounts/name changes in a appropriate way. Coordinate with BU's and controller in order to make sure that customer recieves right info on time on where to pay, and that the invoices will report correct bank name and account number for payments |  |  | 2016-03-31 |  |  | 2016-03-31 |  | 2016-03-31 | [24 empty] | No Review | 80 | Credit EUR |  | Credit Nam
| HC15 | N/A (HC06-08) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish and/or renew Credit user access to customer/vendor portals | Both | FALSE |  | 2016-08-01 | 40 | 2016-06-22 | 5 | TRUE | After new emil addresses are available and new legal forms are registered | Erdei | On Track | After the new co legal entities are registered we must ensure our Team updates customer vendor portal access to be in lign with the company they represent. Need to create a list of All vendor portals split by Value Add/Upstream or both | [5 empty] | 2016-03-31 | [26 empty] | No Review | 100 | Credit EUR | 40 | Credit NAM |  |  | x
| HC15 | N/A (HC06-09) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Confirm New Customer set up and entry process will be same for both entities - MDM TEAM | Both | TRUE |  | 2016-05-30 | 10 | 2016-05-20 | 2 |  | Connect with MDM Team and confirm on the current process if it is a copy past | Lintner | On Track | [33 empty] | No Review | 8 | Credit EUR (3); MDM (6) | 8 | Credit NAM |  |  | x
| HC15 | N/A (HC06-10) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Review BU-Credit Reporting requirements and align custom reports with corresponding entities | Both |  |  | 2016-06-30 | 60 | 2016-05-01 | 5 |  |  |  | On Track | Review the report list and determine what will need to be changed to two seraration. Also connect with ETC who maintains the list and runs tha reports to confirm action is done by them for building 2 report list for the 2 entities. Közös folderbe megy most minden, meg kell adni az új útvonalat. Mit kell duplikálni. | [32 empty] | No Review | 60 | Credit EUR (120); DMR (100) | 60 | Credit NAM
| HC15 | N/A (HC06-11) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish Bad debt Tool for both entities; split data accordingly | Both | TRUE |  | 2016-07-30 | 30 | 2016-06-30 |  | TRUE | IT create the webtool by migrating for Upstream - Work with ETC Team to split tool for the 2 companies | Stuiver - EUR | Not Started | Need to split the 2 companies by LBC, will there new LBC's established or will we use existing ones ? Will names of BU's change ? Check authorisation levels and develop new set of names for approvals (write off etc.). For Kofem, we need to make the split in documentation for the 2 companies (evidence). Advisable is to develop test database with Data center when framework is known for the 2 companies. Test the file with 2Q but surely 3Q before go live. Ensure training for both Teams. | [5 empty] | 2016-03-31 |  | 2016-03-31 | [24 empty] | No Review | 30 | Credit EUR (20); DMR (40) | 30 | Credit NAM |  |  | x
HC12 | HC12 | N/A (HC06-12) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Ensure Statement Service tools are established and supported for both entities | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 |  | TRUE | Statement Service while ran by Credit, the macro writing is done by ETC, we need to ensure for both entities there is resouce available to continue to run the service on both ETC and Credit level. | Lintner | Not Started | ETC to create 2 control file for both entities in their own Oracle settings Statement team to work with Credit staff and split the communication template, rework the wording of the template including signitures, requesting in both outlook environment a general mailbox set up, ensure there is knowledge in both entities to run the program, have the required legacy access in place for invoice copy - GDW álljon fel, Tamás copy past | [5 empty] | 2016-03-31 |  | 2016-03-31 | [24 empty] | No Review | 80 | Credit EUR (120); DMR (200) | 80 | Credit NAM |  |  | x
| HC12 | N/A (HC06-13) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Define approach for segregating contents of Global Credit shared folders: 1) review what needs to be split other than containder folder 2) container folder - split, | Both | TRUE |  | 2016-08-01 | 90 | 2016-05-03 | 2 | FALSE | Per current knowledge, IT will replicate the shared folder, which means we will need to clean up the container folders - | Castiello EUR/ Caldwell NOA | On Track | deep dive in the Global credit Europe file move the info that need to be splitted, check and make sure that we are aligned with ETC for having separated report in case of common report saved (work with DSG) | [7 empty] | 2016-03-31 | [24 empty] | No Review | 120 | Credit EUR (1000); DMR (16) | 120 | Credit NAM
| HC12 | N/A (HC06-14) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Identify any legal constraints governing replication or sharing of data stored in customer container files -check with Legal | Both | TRUE |  | 2016-05-30 | 27 | 2016-05-03 |  |  | check with legal wich kind of info can be copied / reported historical data for both new entities | Castiello EUR/ Caldwell NOA | Not Started | understand clearly legal position on the transfert of historical data (what will be done behind the scene as comunication to the customers) this work can be done in // of te other 2 tasks |  |  |  | 2016-03-31 | [28 empty] | No Review | 10 | Credit EUR | 2 | Credit NAM |  |  | x
| HC12 | N/A (HC06-15) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish Separate Shared mailboxes | Both | TRUE |  | 2016-08-01 | 90 | 2016-05-03 |  | TRUE | Will need IT direction on how the shared mailbox operate after the cloning if shared mailboxes are cloned or need to request as new | Lintner EUR/ Caldwell NOA | Not Started | List the existing mailbox, user accesses and determine new name and ownership | [7 empty] | 2016-03-31 | [24 empty] | No Review | 12 | Credit EUR | 12 | Credit NAM
| HC12 | N/A (HC06-16) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Identify customers shared by both entities and define approach for populating customer container files - common customers | Both | TRUE |  | 2016-08-01 | 90 | 2016-05-03 |  |  | work with DSG to idetify : common customer (same oracle number invoiced by both new cos) and to indetify the CL given on group level that includes both new CO. | Castiello EUR/ Caldwell NOA | Not Started | work with DSG on lists, review | [5 empty] | 2016-03-31 |  | 2016-03-31 | [24 empty] | No Review | 20 | Credit EUR | 20 | Credit NAM
| HC12 | N/A (HC06-17) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Confirm approach for handling ASAT testing for both entities: keeping report on Brazil sharedpoint?, shared mailbox, compliance calendar | Both | TRUE |  | 2016-06-01 | 30 | 2016-05-02 |  | TRUE | waiting Brazil COE advise on direction | Cochran | Not Started | waiting decision to build plan based on direction | [20 empty] | 2016-01-31 | [11 empty] | No Review |  |  | 0
| HC12 | N/A (HC06-18) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Define approach for replicating the Global Credit portal and related content: Revise Forms and Documents for update. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 |  | TRUE | Waiting for direction from IT. | Erdei for EUR | Not Started | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. We need to revise all Documents & Forms. Update all FORM to reflect the new co UP and VA, ensure links, macro's are properly working. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 20 | Credit EUR | 20 | Credit NAM
| HC12 | N/A (HC06-19) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Ensure new Legal documents (bank guarantee, corp guarantee, NDAs, etc.) are established and available for both entities. | Both |  |  | 2016-08-01 | 60 | 2016-06-02 |  | TRUE | Need new co legal name to establish the revision of documents. Need legal advise if documents currentéy covering Upstream BU could stay in their current format? |  | Not Started | Identify the customers of Legal document, bank and corp guarantee. Review all legal document and make necessary step to update with new co names. | [32 empty] | No Review | 100 | Credit EUR | 100 | Credit NAM | [7 empty] | 100 | [15 empty] | 10 |  |  |  | 30 |  |  |  | 50 |  |  |  | 10 | [13 empty] | 0
| HC12 | N/A (HC06-20) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Conduct thorough testing of EBS environment: US Oracle Linda Schuster to perform order management test and account details, discoverer. Create list of responsibilities and collector codes. Clean up of accounts | Both | TRUE |  | 2016-08-01 |  | 2016-08-01 |  | TRUE | Waiting for direction from IT and EBS Support | McGuinness | Not Started | Task: UAT/Dev resouces need (vacations)Question to clarify: how many resources are required and to check availability. New set of OU's to establish. Deep authorisation check to be performed by IT / Credit | [5 empty] | 2016-01-31 | [26 empty] | No Review |  | Credit EUR |  | Credit NAM | [7 empty] | 0 | [15 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 0
| HC12 | N/A (HC06-21) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Conduct thorough testing of EUR Oracle (ETC to perform order management test and account details, discoverer - MDM to perform customer standard test) support Teams in testing. Create list of responsibilities and collector codes. Clean up of accounts | Both | TRUE |  | 2016-08-01 | 75 | 2016-05-18 |  | TRUE | Waiting for direction from IT and EBS Support | Stuiver EUR/ Chen China | Not Started | Are we going to continue with the current collector codes or will we create new process for this as this is used for our Hold order panels as well ? Can we continue to use current customer number(ing) and/or need to setup additional ones for shared customers. Check need for reports running from Discoverer, do we need to create specific reports for the split ? IT / Credit need to look to the authorisation split System/ banking Interfaces testing | [5 empty] | 2016-01-31 | [26 empty] | No Review | 40 | Credit EUR | 40 | Credit NAM | [7 empty] | 40 | [15 empty] | 4 |  |  |  | 12 |  |  |  | 20 |  |  |  | 4 | [13 empty] | 0
| HC12 | N/A (HC06-22) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Conduct thorough testing of the Advanced Collections Module ( EBS Oracle - CRP testing 4/18 - 5/20; UAT testing 5/23 - 7/8; Cutover 7/15 - 7/31 - established live production system ) | Both | TRUE |  | 2016-08-01 | 75 | 2016-05-18 |  | TRUE | Waiting for direction from IT and EBS Support | Stuiver/ McGuinness | Not Started | Need to create 2 testing teams for the Oracle collection module.Question to clarify: how many resources are required and to check availability. New set of OU's being established by IT. Deep authorisation check to be performed by IT / Credit. Is ETC able to continue support for both companies | [5 empty] | 2016-01-31 | [26 empty] | No Review | 240 | Credit EUR | 180 | Credit NAM | [5 empty] | 240 | [7 empty] | 240 | 0 | 0 | 0 | [32 empty] | 0
| HC12 | N/A (HC06-23) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Determine whether both entities will leverage Hyperion Credit Reporting tool | Both | TRUE |  | 2016-08-01 |  | 2016-08-01 |  | TRUE | Waiting for direction from IT and EBS Support | Stuiver EUR | Not Started | Will both companies make use of Hyperion and would there be a need for specific ones. IT/Credit need to check authorisation as BU's are having access as well. New set of OU's to be established | [5 empty] | 2016-01-31 | [26 empty] | No Review | 3 | Credit EUR | 1 | Credit NAM | [6 empty] | 3 | [23 empty] | 120 |  |  |  | 120 | [14 empty] | 237
| HC12 | N/A (HC06-24) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Identify internal customer records that will need converted to external: Review current intercompanies for 3rd party sale | Both |  |  | 2016-08-01 | 40 | 2016-06-22 |  | TRUE | waiting for ICCS direction |  | Not Started | [33 empty] | No Review | 20 | Credit EUR (40); IICS (8) | 20 | Credit NAM | [6 empty] | 20 | [6 empty] | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 10 | 0 | 0 | [24 empty] | 0
| HC12 | N/A (HC06-25) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Alcoa Direct | Both |  |  | 2016-08-01 | 30 | 2016-07-02 |  | TRUE | Waiting for direction from IT and BU |  | Not Started | use alcoa direct for invoice copies - also customers use this application | [32 empty] | No Review |  | Credit EUR |  | Credit NAM | [5 empty] | 0 | [11 empty] | 180 | [31 empty] | 180
| HC12 | N/A (HC06-26) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Review and revise key process documents; SLA's, policies and procedures aligned with target condition and agree with BU | Both |  |  | 2016-08-01 | 60 | 2016-06-02 |  | TRUE | Waiting for direction from IT on storage | Lintner EUR/ Caldwell NOA | Not Started | Review policies and SLA and confirm alignment with new co | [32 empty] | No Review | 20 | Credit EUR | 20 | Credit NAM | [6 empty] | 20 | [11 empty] | 120 | [30 empty] | 100
| HC12 | N/A (HC06-27) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Identify SRMC reporting needs of both entities and align internal resports accordingly |  |  |  | 2016-08-01 | 20 | 2016-07-12 |  |  |  | Heroux | Not Started | Work out the split of reports and train team members on both co | [32 empty] | No Review |  |  | 8 | Credit NAM | [5 empty] | 0 | [19 empty] | 60 |  |  |  | 60 | [19 empty] | 120
| HC12 | N/A (HC06-28) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Realign credit locations to corresponding entity's ASAT: Define the clear split of Credit Location in our ASAT | both | TRUE |  | 2016-08-01 | 20 | 2016-07-12 |  |  | To determine which Credit Locations remain in scope of Global credit ASAT Value add and Upstrean | Lintner/Caldwell | Not Started | [8 empty] | 2016-03-31 | [24 empty] | No Review |  | Credit EUR | [10 empty] | 0 | [19 empty] | 120 | [20 empty] | 120
| HC12 | N/A (HC06-29) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Identify and traing the ASAT Coordinators for both Companies | both | TRUE |  | 2016-08-01 | 80 | 2016-05-13 |  |  | Suggestion is to have training sessions during the testing cycles each month to ensure knowledge transfer | Lintner/Caldwell | Not Started | thourough training lesson | [7 empty] | 2016-03-31 | [24 empty] | No Review | 0 | Credit EUR | 0 | [7 empty] | 0 | [23 empty] | 120 | [18 empty] | 120
| HC12 | N/A (HC06-30) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Establish compliance calendars for both entities | both | TRUE |  | 2016-08-01 | 20 | 2016-07-12 |  |  | To prepare as normally and split before go live | Lintner/Caldwell | Not Started | [8 empty] | 2016-03-31 | [24 empty] | No Review |  | Credit EUR | [7 empty] | 0 | [11 empty] | 120 | [31 empty] | 120
| HC12 | N/A (HC06-31) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Confirm SOA COE will continue to coordinate ASAT activities for both entities | both | TRUE |  | 2016-08-01 | 90 | 2016-05-03 |  | TRUE | Sample selection/Evalaution on testing/Access to Brazilian Share Point where test templates are stored. /Global Credit ASAT Mailbox - owner is the SOA COE ASAT Group | Lintner/Caldwell | Not Started | Sample selection and testing evaluation is done by SOA COE ASAT for Global Credit testing it should be determined who will perform this task for both companies. To determine where to store data by the time of splitting company. New owner of the Mailbox is to be determined | [7 empty] | 2016-03-31 | [24 empty] | No Review |  | Credit EUR |  | SOA COE ASAT | [6 empty] | 0 | [23 empty] | 60 |  |  |  | 60 | [14 empty] | 120
| HC12 | N/A (HC06-32) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Assess potential impact of separation on audit schedules and scopes | both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 |  |  |  | Lintner/Caldwell | Not Started | [24 empty] | 2016-05-01 | [8 empty] | No Review | 5 | Credit EUR | 5 | Credit NAM | [6 empty] | 5 | [15 empty] | 90 | [26 empty] | 85
| HC12 | N/A (HC06-33) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Support negotiation of new ISDA contracts/agreements | Up. Co | TRUE |  | 2016-08-01 | 150 | 2016-03-04 |  | TRUE | Treasurer sets negotiation parameters | Eisler | Not Started | Up Co treasurer needs to set parameters for the new agreements and the trading desks need to ID the brokers they wish to use. |  |  | 2016-03-31 | [29 empty] | No Review |  |  | 128 | Credit NAM | [5 empty] | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [24 empty] | 0
| HC12 | N/A (HC06-34) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Training - Transfer Derivative trading knowledge | Up. Co | FALSE |  | 2016-08-01 | 14 | 2016-07-18 |  | FALSE |  | Eisler | Not Started | The credit risk will need to be coverd by the other company and currently only Eisler, Cochran and Caldwell have background in this area | [32 empty] | No Review |  |  | 64 | Credit NAM | [5 empty] | 0 | [11 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [23 empty] | 0
HC19 | HC19 | N/A (HC06-35) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Training - Transfer Collateral Security Agreement knowledge | Up. Co | FALSE |  | 2016-08-01 | 14 | 2016-07-18 |  | FALSE |  | Eisler | Not Started | Understanding of the CSA agreements and the market will need to be transferred. | [32 empty] | No Review |  |  | 48 | Credit NAM | [5 empty] | 0 | [19 empty] | 30 |  |  |  | 30 |  |  |  | 30 | [15 empty] | 90
| HC19 | N/A (HC06-36) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Training - Transfer Energy Trading Knowledge | Up. Co | FALSE |  | 2016-08-01 | 14 | 2016-07-18 |  | FALSE |  | Eisler | Not Started | Currently Eisler sets credit limits and approves trading activity for Electricity trading activity and NG retail purchases with no backup. | [32 empty] | No Review |  |  | 48 | Credit NAM | [8 empty] | 0 | [23 empty] | 90 | [16 empty] | 90
| HC19 | N/A (HC06-37) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Coordinate customer communications concerning new remittance instructions: NAM: Treasury Bank accounts: 1) PNC and Mellon access, 2) new bank accounts when to inform customers | Both | TRUE |  | 2016-07-31 | 30 | 2016-07-01 |  |  | work to be done in agreement with Treasury and IT | Caldwell | Not Started | Open new accounts for new legal entity and build feeds into the cash application module |  |  | 2016-03-31 | [29 empty] | No Review |  |  | 32 | Credit NAM | [8 empty] | 0 | [15 empty] | 60 | [24 empty] | 60
| HC19 | N/A (HC08-02) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High IT system strategy - work with the IT organization to determine the best approach for post-separation IT solution. Present recommendation to SPO and BU's to gain approval. | Both | TRUE | MPS_2 | 2016-02-29 | 55 | 2016-01-05 | 50% | TRUE | This will be determined by GSS/IS and the BU. This is of upmost priority as our project plan changes dramatically depending on what the IT strategy is. | Lowry, Sterlitz | On Track | Waiting for decision on the HR application solution | [5 empty] | 2016-02-15 | [26 empty] | #REF! | 55 | GPS Systems Support | [5 empty] | Yes |  |  | 55 | [15 empty] | 60 | [26 empty] | 5
| HC19 | N/A (HC08-03) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Procurement contract strategy | Both | TRUE |  | 2016-03-31 | 55 | 2016-02-05 | 5% | TRUE | Assumption - no changes in 3rd party vendors. Changes to vendor contacts may impact GPS interfaces. Note that this a concern for all countries/regions. Will vendors require 2 interfaces, 1 for each company? We have to start to work on interfaces Q1. | Lowry, Sterlitz | On Track | Waiting for decision on the HR application solution. | [9 empty] | 2016-03-31 | [22 empty] | #REF! | 20 | GPS Systems Support | [5 empty] | Yes |  |  |  |  | 20 | [15 empty] | 60 | [24 empty] | 40
| HC19 | N/A (HC08-04) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Develop proceedures | Both | TRUE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | With the assumption that GPS remains in place for both companies, I would expect the common, standard GPS processes would support the two companies (such as compensation, talent, etc) | Lowry, Sterlitz | Not Started | Need decision on HR solution so procedures can be defined | [5 empty] | 2016-02-15 | [26 empty] | #REF! | 40 | GPS Systems Support | [5 empty] | No |  | 40 | [11 empty] | 60 | [31 empty] | 20
| HC19 | N/A (HC08-05) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Develop training documents | Both | TRUE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | Assumption - Upstream will remain on GPS with TSA in place. No training would be needed as existing processes would be used. | Lowry, Sterlitz | Not Started | Need decision on HR solution so procedures can be defined | [5 empty] | 2016-04-30 | [26 empty] | #REF! | 80 | GPS Systems Support | [5 empty] | No |  | 80 | [23 empty] | 30 |  |  |  | 30 | [15 empty] | -20
| HC19 | N/A (HC08-06) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Complete knowledge transfer | Both | TRUE |  | 2016-08-31 | 120 | 2016-05-03 | 0% | TRUE | Assumption - Upstream will remain on GPS with TSA in place. Longer Term - the expert level knowledge resides with 1 person today and this knowledge will need to be shared with another person so both companies can be adequately supported going forward | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 400 | GPS Systems Support | [5 empty] | No |  | 400 | [23 empty] | 30 |  |  |  | 30 | [15 empty] | -340
| HC19 | N/A (HC08-07) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Data purge - work with legal team and separation team to determind the data purge requirements | Both | TRUE |  | 2016-02-29 | 20 | 2016-02-09 | 30% | TRUE | Decision from legal - will any historical data need to be protected/purged? Will GPS support teams be able to retain access to all employees throughout TSA? | Lowry, Sterlitz | On Track | Waiting for decision on the HR application solution and legal decision on data privacy requirements |  |  |  | 2016-02-15 | [28 empty] | #REF! | 10 | GPS Systems Support | [5 empty] | Yes |  | 10 | [19 empty] | 30 |  |  |  | 30 | [19 empty] | 50
| HC19 | N/A (HC08-09) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Remove user accounts in R12 and Fusion. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution and legal decision on data privacy requirements |  |  |  | 2016-02-15 | [28 empty] | #REF! | 120 | GPS Systems Support | [5 empty] | No |  | 120 | [31 empty] | 60 | [11 empty] | -60
| HC19 | N/A (HC08-10) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Update Security Profiles to remove other companies organizations. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | FALSE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution and legal decision on data privacy requirements | [32 empty] | #REF! | 120 | GPS Systems Support | [5 empty] | No |  | 120 | [23 empty] | 60 | [19 empty] | -60
| HC19 | N/A (HC08-11) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Run Security Process to sync up responsiblities with the profile changes | Both | FALSE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | FALSE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution and legal decision on data privacy requirements | [32 empty] | #REF! | 4 | GPS Systems Support | [5 empty] | No |  |  | 4 | [23 empty] | 60 | [18 empty] | 56
| HC19 | N/A (HC08-12) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Low Notify support and HR the changes are complete | Both | FALSE |  | 2016-10-01 | 2 | 2016-09-29 | 0% | FALSE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution and legal decision on data privacy requirements | [32 empty] | #REF! | 4 | GPS Systems Support | [5 empty] | No |  | 4 | [23 empty] | 60 | [19 empty] | 56
| HC19 | N/A (HC08-13) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity Level = High Hiearchy Changes - Remove other Company Business Group, Business Unit, LBC Structure from the Hiearchy | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE | GPS Hiearchy will need to be redefined to aligh with Finance Hierarchy | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | 2016-02-29 | [31 empty] | #REF! | 64 | GPS Systems Support | [5 empty] | No |  | 64 | [23 empty] | 60 | [19 empty] | -4
| HC19 | N/A (HC08-14) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity Level = Medium Hiearchy Changes -End Date structures | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE | GPS Hiearchy will need to be redefined to aligh with Finance Hierarchy | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 96 | GPS Systems Support | [5 empty] | No |  | 96 | [23 empty] | 60 | [19 empty] | -36
| HC19 | N/A (HC08-15) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity Level = Low Hiearchy Changes - Run Security List Maintenance to Sync up structure | Both | FALSE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 20 | GPS Systems Support | [5 empty] | No |  |  |  |  | 20 | [23 empty] | 60 | [16 empty] | 40
| HC19 | N/A (HC08-16) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity Level = High Hiearchy Changes - confirm changes are made in Fusion | V-A Co. | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 20 | GPS Systems Support | [5 empty] | No |  |  |  |  | 20 | [23 empty] | 40 | [16 empty] | 20
| HC19 | N/A (HC08-17) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity Level = High Change name of Global Hierarchy | Both | FALSE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 5 | GPS Systems Support | [5 empty] | No |  | 5 | [11 empty] | 30 | [31 empty] | 25
| HC19 | N/A (HC08-18) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - Low Single Sign on - Determine Web page or pages (regional) that will have link to access system. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-02-28 | [26 empty] | #REF! | 128 | GPS Systems Support | [5 empty] | Yes |  | 128 | [15 empty] | 10 | [27 empty] | -118
| HC19 | N/A (HC08-19) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Single Sign on - Remediate Single Sign on and define solution for external SSO working for 2 companies within GPS | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [6 empty] | 2016-02-28 | [26 empty] | #REF! | 192 | GPS Systems Support | [5 empty] | No |  |  | 192 | [6 empty] | 0 | 192 | 0 | 0 | [32 empty] | 0
| HC19 | N/A (HC08-20) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Single Sign on - Test solution with all 3rd party vendors and internal applications | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [6 empty] | 2016-05-31 | [26 empty] | #REF! | 128 | GPS Systems Support | [5 empty] | No |  |  |  | 128 | [41 empty] | -128
| HC19 | N/A (HC08-21) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Remove 'Alcoa' References for Value Add hiearchy code. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. |  |  |  | 2016-02-28 |  | 2016-04-30 | [26 empty] | #REF! | 50 | GPS Systems Support | [5 empty] | No |  | 50 | [7 empty] | 50 | 0 | 0 | 0 | [32 empty] | 0
HC21 | HC21 | N/A (HC08-22) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Remove 'Alcoa' References for Value Add program code. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. |  |  |  | 2016-02-28 |  | 2016-04-30 | [26 empty] | #REF! | 50 | GPS Systems Support | [5 empty] | No |  | 50 | [43 empty] | -50
| HC21 | N/A (HC08-23) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Remove 'Alcoa' References for Value Add reporting. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. |  |  |  | 2016-02-28 |  | 2016-04-30 | [26 empty] | #REF! | 50 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-24) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Remove 'Alcoa' References for Value Add program names. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. |  |  |  | 2016-02-28 |  | 2016-04-30 | [26 empty] | #REF! | 50 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-25) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Terminate Upstream employees and re-hire under new company code | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 15 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-26) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Purging the system - employee data is removed | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 480 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-27) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Security - Remove or confirm Fusion accounts were removed as part of HR2HR | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 160 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-28) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = HIgh Purging the system - Any configurations being used within exisiting populations will be updated to remove Alcoa. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 352 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-29) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Security - Remove User accounts in R12 | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 160 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-30) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Purging the system - Delete configurations items that legally need purged. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [32 empty] | #REF! | 352 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-31) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Low Compile a list of Interfaces (total ~125) (Global and Regional) (Internal Corporate Apps, Outside Vendors) (Inbound, Outbound) | Both | TRUE |  | 2016-01-31 | 4 | 2016-01-27 | 100% | TRUE |  | Lowry, Sterlitz | On Track | Waiting for decision on the HR application solution. | [5 empty] | 2016-01-31 | [26 empty] | #REF! | 60 | GPS Systems Support | [5 empty] | Yes
| HC21 | N/A (HC08-32) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium At a high level, assess the potential impact of Separation on interfaces. | Both | TRUE |  | 2016-02-28 | 10 | 2016-02-18 | 70% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-01-31 |  | 2016-01-31 | [24 empty] | #REF! | 340 | GPS Systems Support | [5 empty] | Yes
| HC21 | N/A (HC08-33) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Review GPS, Interface stategy, its impact on interfaces with the Alcoa internal teams (That manage internal Corporate Applications) | Both | TRUE |  | 2016-03-31 | 20 | 2016-03-11 | 0% | TRUE | Key Assumuption: Internal Applications(WorkBrain, T&E, EHS…) will remain same | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-02-25 | [26 empty] | #REF! | 228 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-34) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = Medium Review GPS, Interface stategy, its impact on interfaces with the Alcoa internal teams (that manage external Vendors), with the corresponding Outside Vendors | Both | TRUE |  | 2016-03-31 | 20 | 2016-03-11 | 0% | TRUE | Key Assumuption: Third Party Vendors (Payroll, Benefirs, Alcoa Learn…) will remain same | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-02-25 | [26 empty] | #REF! | 200 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-35) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Remediate (document, Code changes, setup changes, Unit test) Outbound/Inbound Interfaces to send/receive data. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-06-30 | [26 empty] | #REF! | 504 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-36) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Remediate(document, Code changes, setup changes, Unit test) - Pull views - Outbound - used by internal Alcoa applications | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-06-30 | [26 empty] | #REF! | 700 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-37) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Integration testing - Inbound/Outbound interfaces with thrid party vendors to receive/send files with the change. | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-06-30 | [26 empty] | #REF! | 1000 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-38) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity = High Integration testing - Outbound Pull interface Views - Test it with internal Alcoa applications to ensure they are able to access data | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | Waiting for decision on the HR application solution. | [5 empty] | 2016-06-30 | [26 empty] | #REF! | 1780 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-39) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Determine if Remedy People Serivces will be utilized by both companies and remediate if necessary | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 10% | TRUE |  | Lowry, Sterlitz | On Track | [6 empty] | 2016-04-30 | [26 empty] | #REF! | 160 | GPS Systems Support | [5 empty] | Yes
| HC21 | N/A (HC08-40) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - Medium Review scope of SLA and revise | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 30 | GPS Systems Support | [5 empty] | No
| HC21 | N/A (HC08-41) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Testing of critical processes for comp - Hourly performance pay, compensation planning, etc | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 240 | GPS Systems Support | [5 empty] | No
HC22 | HC22 | N/A (HC08-42) | Hank Cochran_HR_Other | People Services System Support | People Services - Complexity - High Testing of critical processes for talent - goal planning, reporting, end cycle, etc | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE |  | Lowry, Sterlitz | Not Started | [33 empty] | #REF! | 240 | GPS Systems Support | [5 empty] | No
| HC22 | N/A (HC09-01) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Identify the Global Mobility team members for each company | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Level 2 Management needs to determine split between Value-Add and Upstream | Lowry, McCleary | Not Started | Waiting for split determination | [7 empty] | X | [24 empty] | No Review | 10 | GSS lead team
| HC22 | N/A (HC09-02) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Obtain the new accounting structure for both entities and ensure that these structures are set up properly in the all vendors systems for which information is transferred (i.e. Weichert, Fragomen, Suddath, Deloitte, Celergo, Nuss, Santa Fe) | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Tax and Accounting | Lowry, McCleary | Not Started |  | X | X | [5 empty] | X | [24 empty] | No Review | 120 | Global Mobilty |  |  | 60
| HC22 | N/A (HC09-03) | Hank Cochran_HR_Other | Global Mobility | People Services - LOW - Duplicate the Global Mobility Share Drive, Outlook Mailbox, Archives, SharePoint for both FAS access and outside vendor access, | Both | FALSE |  | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [6 empty] | X |  | X | [24 empty] | No Review | 60 | Global Mobilty
| HC22 | N/A (HC09-04) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM: Amend both the domestic and International repayment agreements to specify the separate organizations. Amend the international Letters of Understanding (LOUs) to specify the separate organizations. Amend any Tax Secondment agreements. Redistrute all douments | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started |  |  | X |  | X |  |  |  | X | [24 empty] | No Review | 120 | Global Mobilty
| HC22 | N/A (HC09-05) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM: Clone the existing 4 domestic and 6 international policies. As part of the cloning/revisions the additional 3 Primary Ma'aden specific policies will need to be amended to reflect Upsteam only. | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 60 | Global Mobilty |  |  | 160
| HC22 | N/A (HC09-06) | Hank Cochran_HR_Other | Global Mobility | People Services - LOW - Reveiow scope and SLA for each entity and make necessary changes | Both | FALSE |  | 2016-10-01 | 120 | 2016-06-03 | 10% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL BUs | No Review
| HC22 | N/A (HC09-07) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Transfer to appropriate individuals relocation specific knowledge , transfer or create training documents, transfer and/or revise SOPs. | Both | TRUE |  | 2016-10-01 | 150 | 2016-05-04 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | [7 empty] | Yes
| HC22 | N/A (HC09-08) | Hank Cochran_HR_Other | Global Mobility | People Services - LOW - Configure International SOS feeds for expats | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | 8 | Global Mobilty
| HC22 | N/A (HC09-09) | Hank Cochran_HR_Other | Global Mobility | People Services - LOW - Clone all ASAT testing documents and determine to which entity historical information will be transferred to. | Both | FALSE |  | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review | [7 empty] | Yes
| HC22 | N/A (HC09-10) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Identify which company, Upstream or Value-Add, each relocating employee record will be transferred to, including historical records. Ensure all relevant parties are notified and incorporate into the appropriate separation plans | Both | TRUE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL GROUPS | No Review | 120 | Global Mobilty |  |  | 120
| HC22 | N/A (HC09-11) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Clone all Weichert systems for both international and domestic relocating employees including the My Win relocation tracking system , the comp and benefits system, host expense reporting, expense management system and others. | Both | TRUE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | WEICHERT | No Review | 300 | Global Mobilty |  |  | 400
| HC22 | N/A (HC09-12) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Identify remaining accruals for active relocations to determine which entity, Upstream or Value-Add, will need to recognize the liability (Deloitte, Fragomen, Weichert, Celergo, etc.). Provide business with necessary details for record required entries | Both | FALSE |  | 2016-09-01 | 50 | 2016-07-13 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL OUTSIDE VENDORS | No Review | 150 | Global Mobilty | 40 | Financial Accounting | 30
| HC22 | N/A (HC09-13) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Determine the proper allocation of ledger accounts to either Upstream or Value-Add. Domestically, this would be focused around mortage and equity for home sales and any properties in inventory. On the international side, this would primarily focus on tax equalization payments or receipts. Provide business with necessary details for record required entries | Both | TRUE |  | 2016-09-01 | 30 | 2016-08-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started |  | X | [6 empty] | X | [22 empty] | X | DELOITTE AND WEICHERT | No Review | 60 | Global Mobilty | 10 | Financial Accounting | 40
| HC22 | N/A (HC09-14) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Determine appropriate process for payment of Weichert invoices ($50-$60M), along with appropriate process for funding multiple payroll via Celergo. Docuemt and deploy as appropriate | Both | TRUE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE | N/A | Lowry, McCleary | Not Started |  | X |  | X |  |  |  |  | X | [22 empty] | X | ALL OUTSIDE VENDORS | No Review | 20 | Global Mobilty |  |  | 10
| HC22 | N/A (HC09-15) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - For Celergo, Fragomen and Deloitte, determine under which company the record will be assigned to and communicate to appropriate parties | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL OUTSIDE VENDORS | No Review | 20 | Global Mobilty |  |  | 20
| HC22 | N/A (HC09-16) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Clone all Celergo home / host / cash payroll feeds. Prepare a test program and implement | Both | FALSE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | CELERGO | No Review | 40 | Global Mobilty | 20 | Financial Accounting | 60
| HC22 | N/A (HC09-17) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Document procedure(s) for Deloitte filing of all Global tax returns that will take place after the separation. | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | DELOITTE | No Review | 30 | Global Mobilty |  |  | 20
| HC22 | N/A (HC09-18) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Update / Change / or Revise login details specific to the Celergo payroll system to sure all employees maintain access to their payroll information under only ONE company. | Both | TRUE |  | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | CELERGO | No Review | 40 | Global Mobilty |  |  | 100
| HC22 | N/A (HC09-19) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Evaluate opportunities for transfer of work to KOFEM. Deploy where appropriate | Both | FALSE |  | 2016-10-01 | 200 | 2016-03-15 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [24 empty] | No Review
| HC22 | N/A (HC09-20) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Identify IT system strategy for Global People Systems (GPS), server space, computers, general ledger, telephones, VPN, etc. Once Identified take appropriate action. | Both | TRUE |  | 2016-03-31 | 45 | 2016-02-15 | 0% | TRUE | This will be determined by GSS/IS and the BU. | Lowry, McCleary | Not Started | Waiting for decision on the HR application solution - includes portal pages, GPS, GL, Outlook, Share Drives etc. | [5 empty] | X | [26 empty] | No Review | 20 | Global Mobilty
| HC22 | N/A (HC09-21) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Implement Procurement contract strategy for all vendors and obtain necessary contracts. Ensure strategy includes impact on PO's. | Both | TRUE |  | 2016-03-31 | 50 | 2016-02-10 | 10% | TRUE | Assumption - no changes in 3rd party vendors. Dependencies relate to vendor feeds from GPS, Payroll, and funding sources. | Lowry, McCleary | On Track | Waiting for procurement to provide assistance |  |  | X |  |  | X |  |  |  | X | [22 empty] | No Review | 40 | Global Mobilty | 20 | Procurement
| HC22 | N/A (HC09-22) | Hank Cochran_HR_Other | Global Mobility | People Services - MEDIUM - Complete a Key Partner Summit to identify and review deliverables and develop detailed implementation plans | Both | FALSE |  | 2016-02-15 | 20 | 2016-01-26 | 5% | TRUE | Dependent upon determinations made for IT Systems and Procurement | Lowry, McCleary | On Track | IT and Procurement decisions need to be made in order to structure the summit discussion and determine next steps |  |  | X |  |  | X |  |  |  | X | [22 empty] | No Review | 12 | Global Mobilty |  |  | 20
| HC22 | N/A (HC09-23) | Hank Cochran_HR_Other | Global Mobility | People Services - HIGH - Complete Global Visa Determinations for Upstream vs. Value-Add with recommendations and action plans for finalization of compliance with each country's immigration requirements. Provide recommendations to all related parties | Both | TRUE |  | 2016-01-31 | 52 | 2015-12-10 | 90% | TRUE | Level 2 Management, Legal, HR. BU Level decision making | Lowry, McCleary | On Track | Critical decision to ensure onging employment - post-separation |  |  |  | X | X | [25 empty] | X | Fragomen and all Business Units | No Review | 50 | Global Mobilty |  |  | 150
HC20 | HC20 | N/A (HC09-24) | Hank Cochran_HR_Other | Global Mobility | People Services - Med - Determine and move GEC accounting process to the Upstream accounting support group. Implement necessary test program and procedures | Both | TRUE |  | 2016-01-31 | 52 | 2015-12-10 | 90% | TRUE | Level 2 Management, Legal, HR. BU Level decision making | Lowry, McCleary | On Track | Critical decision to ensure onging employment - post-separation | X |  |  | X | X | [25 empty] | X | Fragomen and all Business Units | No Review |  |  | 50 | Financial Accounting | 10
| HC20 | N/A (HC10-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Organization Structure - determine structure and submit requests to third parties to update systems | Both | TRUE |  | 2016-04-30 | 90 | 2016-01-31 | 0% | TRUE | Assumption - Value-Add will retain existing payroll support organization and Upstream will contract with external expert services for payroll support. Several vendors are available. Decision must be made on this quickly, but is dependant on the Procurement contract process | Lowry, Kerekes | Not Started | Waiting for decision on procurement contract strategy - clone existing system v new system/new provider | [5 empty] | 42400 |  |  |  | 42400 | [22 empty] | #REF! | 6 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - IT System - Confirm strategy to clone systems, work with third party providers on planned approach and associated tasks | Both | TRUE |  | 2016-03-30 | 27 | 2016-03-03 | 0% | TRUE | Assumption - Value-Add will remain on existing PeopleSoft, Upstream will be cloned and PeopleSoft will be available via TSA at separation. Decision must be made quickly whether to clone at Aon Hewitt or move to another payroll provider. Decision is dependant on the Procurement contract strategy Assumption - Value-Add will remain on existing Workbrain, Upstream will be cloned and GPS will be available via TSA at separation. Decision must be made quickly whether to clone in-house or move to SAAS with the software vendor. Decision is dependant on the Procurement contract strategy | Lowry, Kerekes | Not Started | Waiting for decision on Procurement contract and IT system strategies - clone existing system v new system/new provider | [5 empty] | 42400 |  |  |  | 42400 | [22 empty] | #REF! | 30 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Naming/Tax Strategy - Upate regulatory agencies with new legal names, file for new tax IDs, update systems to reflect name changes | Both | TRUE |  | 2016-03-30 | 27 | 2016-03-03 | 0% | TRUE | Dependent on corporate tax/organization strategy to determine agency filing requirements and system impact | Lowry, Kerekes | Not Started | Waiting for decisions from Legal and Tax as well as decision on IT system strategy |  | 42400 |  | 42400 |  | 42400 | [26 empty] | #REF! | 45 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Procurement Contract Strategy - Once confirmed, work to support contract discussions and implement any changes needed to support new contracts | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | We will need Procurement and Legal to work on contract changes and vendor selectionl. Proposal evaluation and contracts are the starting point for all other changes. | Lowry, Kerekes | Not Started | Waiting for direction from Procurement and Legal |  |  |  | 42400 | [5 empty] | 42400 | [22 empty] | #REF! | 20 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Union Contract Changes - Understand any changes, then modify systems, procedures custom programs to support changes as needed | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Impact of pay rule and other changes from Union Contract negotiations is unknown | Lowry, Kerekes | Not Started | Waiting for direction from Industrial Relations | [30 empty] | 42400 | Industrial Relations | #REF! | 25 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Business Hiearchy/Organization Changes - Once confirmed, implement changes in all associated systems | Both | TRUE |  | 2016-02-29 | 53 | 2016-01-07 | 0% | TRUE | PeopleSoft and Workbrain hiearchy and determination of which company each LBC will be in is dependant on Legal & Tax | Lowry, Kerekes | Not Started | Waiting for direction from IT and Finance | 42429 |  |  |  |  | 42429 | [26 empty] | #REF! | 30 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Develop Procedures - Create procedures for any new procedures required | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Assumption: Value-Add procedures remain the same. Upstream procedures will change depending on IT/vendor strategy, TSA and any application interface changes. Must have decision on TSA for payroll services | Lowry, Kerekes | Not Started | Waiting for decisions documented here |  |  |  |  | 42490 |  |  | 42490 | [24 empty] | #REF! | 0 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Develop Training Documents - Duplicate & update and create new documentation where needed | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Assumption: Value-Add procedures remain the same. Upstream procedures will change depending on IT/vendor strategy, TSA and any application/provder interface changes. Must have decision on TSA for payroll services | Lowry, Kerekes | Not Started | Waiting for decisions documented here |  |  |  |  | 42490 |  |  | 42490 | [24 empty] | #REF! | 0 | US Payroll | [5 empty] | Yes
| HC20 | N/A (HC10-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Complete Knowledge Transfer - Train team members to enable them to support future work assignments; train new team members on all procedures and policies | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Assumption: Value-Add will not require knowledge transfer. Upstream requirements are dependant on IT/vendor strategy and Organization structure | Lowry, Kerekes | Not Started | Waiting for decisions documented here | [7 empty] | 42582 | [24 empty] | #REF! | 0 | US Payroll | [5 empty] | Yes
| HC20 | N/A (HC10-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Data History Strategy - Determine process to purge data where needed. Review & reorganize electronic & paper records | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Assumption: Both companies will retain history and purging is not required | Lowry, Kerekes | Not Started | Waiting for decision from Legal and decision on IT system strategy | [7 empty] | 42582 | [24 empty] | #REF! | 25 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Remove 'Alcoa' References from hiearchy codes and any other references to Alcoa in Value-Add application | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Many references will be fed from the HR solution. Assumption is that TSA will be in place and GPS will feed changes for both companies. Remaining references will be manually removed | Lowry, Kerekes | Not Started | Dependant on Legal Decisions and split of locations/LBCs between companies |  |  |  | 42490 | 42490 | 42490 |  | 42490 | [24 empty] | #REF! | 30 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Develop replacement strategy for login/SSO for Upstream business on PeopleSoft hosted solution | Up. Co. | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Kerekes | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 42400 |  | 42400 | [22 empty] | 42400 | Vendor Aon Hewitt | #REF! | 30 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Develop security strategy for Vista Reports hosted solution | Up. Co. | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Security strategy must be defined for the Upstream company if PeopleSoft strategy is to maintain single instance split only by security | Lowry, Kerekes | Not Started | Dependent on decision regarding PeopleSoft | [5 empty] | 42400 |  | 42400 | [22 empty] | 42400 | Vendor Aon Hewitt | #REF! | 20 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Ownership/purging of data history strategy | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Assumption is that both companies will retain history and purging is not required | Lowry, Kerekes | Not Started | Need decision from Legal |  |  |  | 42369 | [28 empty] | #REF! | 20 | US Payroll | [5 empty] | No
| HC20 | N/A (HC10-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Payroll Provider / Split Contract | Up. Co. | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Assumption is that both companies will continue to use Aon Hewitt hosted PeopleSoft, requiring contract split | Lowry, Kerekes | Not Started | Need decision from Legal and Procurement |  |  |  | 42369 | [5 empty] | 42369 | [22 empty] | #REF! | 20 | US Payroll | [5 empty] | No
HC09 | HC09 | N/A (HC10-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - LOW - Review scope and SLA for each company | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Customers will be involved in the process to validate future SLA and scope | Lowry, Kerekes | Not Started | [31 empty] | X | Customers | #REF! | 20 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Define and implement controls regarding access to data on fileshare, SharePoint, emails, and with vendors | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT and Procurement needs to support the process | Lowry, Kerekes | Not Started | [6 empty] | X |  |  |  | X | [22 empty] | #REF! | 40 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - LOW - Create location and HR listings, as well as standard metrics, for each company | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | FALSE | N/A | Lowry, Kerekes | Not Started | [33 empty] | #REF! | 40 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Work with People Systems Solutions to guarantee the testing process | Both | TRUE |  | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Lowry, Kerekes | Not Started | [8 empty] | X | [24 empty] | #REF! | 110 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Work with HRDTA to guarantee the testing process | Both | TRUE |  | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Lowry, Kerekes | Not Started | [8 empty] | X | [24 empty] | #REF! | 50 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Implement the new help chain model - Remedy | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | N/A | Lowry, Kerekes | Not Started | [33 empty] | #REF! | 70 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - LOW - Create new mailbox for one of the companies & deploy to users | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | N/A | Lowry, Kerekes | Not Started | [33 empty] | #REF! | 8 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-23) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - LOW - Create location and HR listings, as well as standard metrics, for each company | Both | FALSE |  | 2016-06-30 | 101 | 2016-03-21 | 0% | FALSE | N/A | Lowry, Kerekes | Not Started | [33 empty] | #REF! | 100 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-24) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Create new fileshare, SharePoint site, email shared mailboxes & move records | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not Started | [6 empty] | X |  |  |  | X | [22 empty] | #REF! | 120 | US Payroll | [5 empty] | Yes
| HC09 | N/A (HC10-25) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - MEDIUM - Determine approach to split & secure Seibel ticketing system. Complete testing and deploy | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE |  | Lowry, Kerekes | Not Started | [31 empty] | X | Vendor Aon Hewitt | #REF! | 15 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-26) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Replicate secured Payroll Reuest Form technology and proess for Upstream Co, purge Upstream location informataion from security tables, update Authorized team information with third party providers | Up. Co. | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not Started | [6 empty] | X | [26 empty] | #REF! | 45 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-27) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Determine if trailing payments will occur (equity, performance pay, incentive comp) and if so how those will be handled (charged back, split) | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not Started | [6 empty] | X | [26 empty] | #REF! | 10 | US Payroll | [5 empty] | No
| HC09 | N/A (HC10-28) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | People Services - HIGH - Test replication of systems, including interfaces and custom programs | Both | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not Started | [6 empty] | X | [26 empty] | #REF! | 500 | US Payroll | [5 empty] | No
| HC09 | N/A (HC11-01) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity High - IT system strategy - Work with IT to determine if in house or SAAS implementation for Upstream | Up. Co. | TRUE | MPS_2 | 2016-02-01 | 60 | 2015-12-03 | 45% | TRUE | Assumption - Value-Add will remain on existing Workbrain, Upstream will be cloned and GPS will be available via TSA at separation. Decision must be made quickly whether to clone in-house or move to SAAS with the software vendor. Decision is dependant on the cost and any impact of reduced functionality | Lowry, Sterlitz, Clive | On Track | 20160115 - Value-Add will remain in current data center with no IT changes. Still waiting for costing on upstream in-house and hosted solution | [5 empty] | 2016-01-31 |  | 2016-01-31 |  | 2016-01-31 | [20 empty] | 2016-01-31 | GPP | #REF! | 40 | GSS WFM Support Team | [5 empty] | Yes
| HC09 | N/A (HC11-02) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Determine Infrastructure sizing | Both | FALSE |  | 2016-03-01 | 30 | 2016-01-31 | 100% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Complete | 20160125 - Document received from Infor. Need to work through details with Infor. 20160115 - Split between upstream and Val-Add is 20/80. No benefit in downsizing Val-Add. Need to downsize Upstream. | [5 empty] | 2016-01-31 |  |  |  | 2016-01-31 | [22 empty] | #REF! | 10 | GSS WFM Support Team | [5 empty] | Yes
| HC09 | N/A (HC11-03) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Determine Payroll Vendor and HR application for each company | Both | TRUE |  | 2016-04-01 | 60 | 2016-02-01 | 100% | TRUE | Assumption is that both companies may will continue to use Hewitt Payroll and GPS | Lowry, Sterlitz, Clive | Complete | 20160115 - Waiting for Payroll decision. Affects amount of development needed if new interfaces need to be created. GPS will be available for Upstream, but without Fusion, which breaks our SSO solution for them. Must determine new SSO or develop Password process | [32 empty] | #REF! | 40 | GSS WFM Support Team | [5 empty] | Yes
| HC09 | N/A (HC11-04) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Work with vendor to split of Licenses/contracts/maintenance agreements between companies | Both | TRUE |  | 2016-04-01 | 60 | 2016-02-01 | 20% | TRUE | This decision has an impact on the cost/benefit of the SAAS vs in-house solution and must be determined early | Lowry, Sterlitz, Clive | At Risk | 20160115 - Procurement has contacted the vendor Infor and started negotiations on current licenses/contracts. | [5 empty] | 2016-04-30 | [26 empty] | #REF! | 40 | GSS resources are upper mgmt and procurement | [5 empty] | Yes
| HC09 | N/A (HC11-05) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Procurement contract strategy | Up. Co. | TRUE |  | 2016-03-31 | 55 | 2016-02-05 | 20% | TRUE | We will need Procurement to work on best cost for SAAS hosted solution proposal. Proposal evaluation and contracts are the starting point for all other changes. How will licenses affect this decision. What is needed from Legal on this? | Lowry, Sterlitz, Clive | At Risk | 20160115 - Procurement is in the loop as we start discussions with the vendor on SAAS solution for Upstream. Waiting on vendor Infor for initial costs | [32 empty] | #REF! | 20 | GSS WFM Support Team | [5 empty] | Yes
| HC09 | N/A (HC11-06) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Develop replacement strategy for Discoverer reporting if hosted | Up. Co. | TRUE |  | 2016-03-30 | 45 | 2016-02-14 | 0% | TRUE | Replacement strategy must be defined for the Upstream company if SAAS solution selected. Assumption is that Discoverer will not be available on SAAS. | Lowry, Sterlitz, Clive | Not Started | Need a decision on in-house vs SAAS and whether SAAS will support Discoverer reporting | [5 empty] | 2016-06-30 | [24 empty] | 2016-06-30 | IT and Functional Support Vendor | #REF! | 40 | GSS WFM Support Team | [5 empty] | No
| HC09 | N/A (HC11-07) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Data Ownership strategy - will data history need to be purged in each application | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Assumption is changed to both companies will purge history | Lowry, Sterlitz, Clive | Not Started | Need decision from Legal |  |  |  | 2016-03-31 | 2016-03-31 | 2016-03-31 | [26 empty] | #REF! | 40 | GSS WFM Support Team | [5 empty] | No
| HC09 | N/A (HC11-08) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Develop replacement strategy for login/SSO for Upstream business | Up. Co. | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-03-01 | [24 empty] | 2016-01-31 | Vendor Infor | #REF! | 40 | GSS WFM Support Team | [5 empty] | No
| HC09 | N/A (HC11-09) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity High - Upstream Existing System Modifications (Downsizing, Interface Remediation, Config Changes, Data Changes, data purging, Clock purging, Discoverer conversion, SSO solution). Remediation of these objects and testing in multiple instances. | Up. Co. | TRUE |  | 2016-10-01 | 200 | 2016-03-15 | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-01-31 | [24 empty] | 2016-01-31 | GPP | #REF! | 1053 | GSS WFM Support Team | [5 empty] | No
| HC09 | N/A (HC11-10) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity High - Value-Add Existing System Modifications (Interface Remediation, Config Changes, Data Changes, data purging, Clock purging, Discoverer clean-up etc). Remediation of these objects and testing in multiple instances. | V-A Co. | TRUE |  | 2016-10-01 | 200 | 2016-03-15 | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [32 empty] | #REF! | 800 | GSS WFM Support Team | [5 empty] | No
| HC09 | N/A (HC11-11) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - GSS Support Organization Structure planned for both companies | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE |  | Lowry, Sterlitz, Clive | On Track | Dependant on decision on in-house vs SAAS, and selection of vendor for IT and Functional support. Working on determining options with vendor and procurement | [32 empty] | #REF! | 40 | GSS Leadership | [5 empty] | Yes
HC07 | HC07 | N/A (HC11-12) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Remove 'Alcoa' References from hiearchy codes and any other references to Alcoa in Value-Add application | V-A Co. | FALSE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE | Many references will be fed from the HR solution. Assumption is that TSA will be in place and GPS will feed changes for both companies. Remaining references will be manually removed | Lowry, Sterlitz, Clive | Not Started | Dependant on Legal Decisions and split of locations/LBCs between companies |  |  |  | 2016-03-30 |  |  |  |  | 2016-03-30 | [23 empty] | #REF! | 40 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-13) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Remediate for Hiearchy/Organization Changes | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE | Workbrain Hiearchy and determination of which company each LBC will be in is dependant on Legal | Lowry, Sterlitz, Clive | Not Started | Dependant on Legal Split |  |  |  | 2016-03-30 | [28 empty] | #REF! | 40 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-14) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Application Support - Define processes for support (USBS, IT, GSS) | Both | FALSE |  | 2016-10-01 | 180 | 2016-04-04 | 0% | TRUE | Dependant on USBS and Payroll support structures | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [7 empty] | 2016-05-31 | [24 empty] | #REF! | 60 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-15) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Define GSS support model - RPS changes, mailbox, etc) | Both | TRUE |  | 2016-10-01 | 180 | 2016-04-04 | 5% | TRUE |  | Lowry, Sterlitz, Clive | On Track | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [32 empty] | #REF! | 60 | GSS WFM Support Team | [5 empty] | Yes
| HC07 | N/A (HC11-16) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Med - Develop/modify SOP proceedures | Both | TRUE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | Value-Add procedures remain the same. Upstream procedures will change depending on IT system strategy, HR application/TSA and any application interface changes. | Lowry, Sterlitz, Clive | Not Started | No change for Value-Add. Dependant on decision on in-house vs SAAS, Payroll Vendor and TSA for GPS for Upstream. Need EAM interface decision made. | [32 empty] | #REF! | 0 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-17) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity Low - Develop training documents | Both | TRUE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | Value-Add procedures remain the same. Upstream procedures will change depending on IT system strategy, HR application/TSA and any application interface changes. | Lowry, Sterlitz, Clive | Not Started | No change for Value-Add company. Need a decision on in-house vs SAAS for Upstream | [32 empty] | #REF! | 80 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-18) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity High - Complete knowledge transfer | Both | TRUE |  | 2016-08-31 | 120 | 2016-05-03 | 0% | TRUE | Value-Add will not require knowledge transfer. Upstream requirements are dependant on IT system strategy and Organization structure | Lowry, Sterlitz, Clive | Not Started | No change for Value-Add. Dependant on decision on in-house vs SAAS for Upstream to determine extent of KT | [5 empty] | 2016-07-22 |  | 2016-07-22 | [24 empty] | #REF! | 400 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-19) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | People Services - Complexity High - Determine if there are Union Contract Changes because of separation activity | Both | FALSE |  | 2016-10-01 | 130 | 2016-05-24 | 0% | TRUE | Impact to payrules and other processes from Union Contract negotiations during split is unknown. | Lowry, Sterlitz, Clive | Not Started | Need information/decision from Industrial Relations | [5 empty] | 2016-07-22 |  | 2016-07-22 | [22 empty] | 2016-04-30 | Industrial Relations | #REF! | 80 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC11-20) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Updates to documentation (technical and support) | Both | TRUE |  | 2016-10-01 | 120 | 2016-06-03 | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [32 empty] | #REF! | 120 | GSS WFM Support Team | [5 empty] | No
| HC07 | N/A (HC17-01) | Hank Cochran_Finance | Accounts Receivable(JDE) | Configurations - Interfaces | V-A Co. | TRUE |  | 2016-03-15 |  | 2016-03-15 | 0% | FALSE |  | Steve Shepard | Not Started | [33 empty] | No Review | 0 | US FAS Team
| HC07 | N/A (HC17-02) | Hank Cochran_Finance | Accounts Receivable(JDE) | Obtain guidance on approach for handling intercompany transactions at time of separation | V-A Co. | TRUE |  | 2016-03-15 | 0 | 2016-03-15 |  | TRUE | SPMO/Finance decision on transactional data strategy needed by 1/31/16. | Caldwell/Antli | Not Started | What is the plan for eliminating intercompany transactions and relationships at time of separation? (POs/Sos/Invoices/etc.) | [5 empty] | 2016-01-31 | [26 empty] | No Review | 0
| HC07 | N/A (HC17-03) | Hank Cochran_Finance | Accounts Receivable(JDE) | Identify and assess impact of changes to the alcoa.com domain | V-A Co. | TRUE |  | 2016-04-15 | 30 | 2016-03-16 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | AR operations will be significantly impacted due to link to receipt of remittance data from customers, AR invoicing, etc. | 2016-01-31 | [31 empty] | No Review | 0
| HC07 | N/A (HC17-04) | Hank Cochran_Finance | Accounts Receivable(JDE) | Testing activity 1: Design and unit testing | V-A Co. | TRUE |  | 2016-04-15 | 31 | 2016-03-15 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Perform testing of applications and environment per plan. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 16 | NA AR
| HC07 | N/A (HC17-05) | Hank Cochran_Finance | Accounts Receivable(JDE) | Testing activity 2: CRP | V-A Co. | TRUE |  | 2016-05-20 | 32 | 2016-04-18 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Perform testing of applications and environment per plan. | [5 empty] | 2016-01-31 | [26 empty] | No Review | 16 | NA AR
| HC07 | N/A (HC17-06) | Hank Cochran_Finance | Accounts Receivable(JDE) | Understand approach and develop processes to accommodate 2-month window between OD1 and LD1 | V-A Co. | TRUE |  | 2016-05-31 | 60 | 2016-04-01 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Antli | Not Started | Will both entities run entirely separately or can a bleed-out approach be employed? Key considerations are directing cash from customers to proper entity, creation & use of second operations structure (e.g. AR mailbox, staff, etc.) | [5 empty] | 2016-01-31 | [26 empty] | No Review | 8 | NA AR
| HC07 | N/A (HC17-07) | Hank Cochran_Finance | Accounts Receivable(JDE) | Testing activity 3: UAT | V-A Co. | TRUE |  | 2016-07-08 | 46 | 2016-05-23 |  | TRUE | SPMO/Finance decision on transactional data strategy needed by 1/31/16. | Caldwell/Antli | Not Started | Perform testing of applications and environment per plan. | 2016-01-31 | [31 empty] | No Review | 24 | NA AR
| HC07 | N/A (HC18-01) | Hank Cochran_Credit | Credit (US) | Establish or renew 3rd party contracts for Credit Information Reporting ( D&B, CRM, Elipru, Cortera) | Both | TRUE |  | 2016-07-01 | 120 | 2016-03-03 |  | TRUE | Procurement need to work through this to determine how the D&B, CRM contract will be impacted and split at the time of separation. Need to ensure no price increase to occur with the split of contracts | Caldwell/Antli | Not Started | We need to move current contract from Alcoa Kofem to the new Value add co, prepare document to follow the entity changes ensuring no distruption in report usuage and history. We need analyze the amount of report needs. For Upstream we need a new contract and review if exitsing monitoring services of the year could be pulled in the new contract | [5 empty] | 2016-01-31 | [26 empty] | No Review |  | Credit Nam
| HC07 | N/A (HC18-02) | Hank Cochran_Credit | Credit (US) | Establish new Delegation of Authorities, Bad Debt approval authorities, refund limits, etc. for teams servicing both entities | Both | FALSE |  | 2016-08-01 | 30 | 2016-07-02 |  | TRUE | define responsibilities according to new roles and organization | Caldwell/Randall | Not Started | define responsibilities according to new roles and organization | [9 empty] | 2016-03-31 | [22 empty] | No Review | 8 | Credit NAM
| HC07 | N/A (HC18-03) | Hank Cochran_Credit | Credit (US) | Establish and/or renew Credit user access to customer/vendor portals | Both | FALSE |  | 2016-08-01 | 40 | 2016-06-22 |  | TRUE | After new email addresses are available and new legal forms are registered | Caldwell/Randall | Not Started | After the new co legal entities are registered we must ensure our Team updates customer vendor portal access to be in lign with the company they represent. Need to create a list of All vendor portals split by Value Add/Upstream or both | [9 empty] | 2016-03-31 | [22 empty] | No Review | 8 | Credit NAM
| HC07 | N/A (HC18-04) | Hank Cochran_Credit | Credit (US) | New Customer set up and entry- MDM TEAM | Both | TRUE |  | 2016-05-30 | 10 | 2016-05-20 |  | TRUE | Connect with MDM Team and confirm on the current process if it is a copy past | Caldwell/Randall | Not Started | Connect with MDM Team and confirm on the current process if it is a copy past | [9 empty] | 2016-03-31 | [22 empty] | No Review | 2 | Credit NAM
| HC07 | N/A (HC18-05) | Hank Cochran_Credit | Credit (US) | EBS Testing Events ( EBS Oracle - CRP testing 4/18 - 5/20; UAT testing 5/23 - 7/8; Cutover 7/15 - 7/31 - established live production system ) | Both | TRUE |  | 2016-08-01 | 75 | 2016-05-18 |  | TRUE | IT ERP Decision and testing schedule to be provided by 1/31/16 | Caldwell/Randall | Not Started | Perform testing of applications and environment per plan. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 80 | Credit NAM
| HC07 | N/A (HC18-06) | Hank Cochran_Credit | Credit (US) | Identify and assess impact of changes to the alcoa.com domain | Both | FALSE |  | 2016-04-15 | 30 | 2016-03-16 |  | TRUE | Waiting for direction from IT and EBS Support | Caldwell/Randall | Not Started | AR & Credit operations will be significantly impacted due to link to receipt of remittance data from customers, AR invoicing, etc. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Credit NAM
| HC07 | N/A (HC18-07) | Hank Cochran_Credit | Credit (US) | Alcoa Direct/Kawneer Direct | Both | FALSE |  | 2016-04-15 | 30 | 2016-03-16 |  | TRUE | Waiting for direction from IT and EBS Support | Caldwell/Randall | Not Started | AR & Credit operations will be significantly impacted due to link to receipt of remittance data from customers, AR invoicing, etc. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 40 | Credit NAM
| HC07 | N/A (HC19-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from Plan Design |  |  |  |  | 2016-02-29 | [27 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
HC04 | HC04 | N/A (HC19-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | MPS_1 | 2016-04-30 | 30 | 2016-03-31 | 20% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from GBS/GSS | [7 empty] | 2016-04-30 | [24 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - Determine how the benefit plans will be split. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from Plan Design, Legal and Tax. |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, Truven Analytics, Solenture, Benefit Wallet, Highmark, Caremark, UCCI, Davis Vision, MetLife, Aetna, etc. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from Procurement and Legal. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - MED - determine how union contracts will be handled. There is one union for the 4/1/16 enrollment - Kingston NY. They went thru negotiations in November. There is one union negotiating in 2016 and it is for Chandler, AZ. Hampton may be ready in 2016, but unsure. | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2016-03-31 | 2016-03-31 | [25 empty] | 2016-03-31 | Industrial Relations | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | MPS_2 | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from IT. | [5 empty] | 2016-03-31 | [26 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - MED - What will be done with the 2017 Annual Enrollment? | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 20% | TRUE | Plan Design (HR), GBS/GSS and Legal need to work through this to determine how how 2017 Annual Enrollment needs to be executed by the different companies. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from Plan Design, Legal and Tax. |  | 2016-04-30 |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - MED - DEVELOP PROCEDURES | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC04 | N/A (HC19-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC04 | N/A (HC19-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - VENDOR FEEDS - Will need to be set up for medical (Highmark), Rx (Caremark), dental (UCCI), vision (Davis), life (MetLife), disability (Aetna), AD&D (MetLife), tuition (GP), HMOs, HSA (Benefit Wallet), analytics (Truven), etc. Decisions to be made by Plan Design (HR). | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Will need to be set up for medical (Highmark), Rx (Caremark), dental (UCCI), vision (Davis), life (MetLife), disability (Aetna), AD&D (MetLife), tuition (GP), HMOs, HSA (Benefit Wallet), analytics (Truven), etc. Decisions to be made by Plan Design (HR). | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | Waiting for direction from Plan Design |  |  |  | 2016-03-31 | 2016-03-31 | 2016-03-31 | [26 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - PAYROLL DEDUCTION FEEDS - Will need to be established for payroll deduction codes. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | Will need to be established for payroll deduction codes. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track | Waiting for direction from Plan Design |  |  |  |  | 2016-03-31 | 2016-03-31 | [26 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - INTERNAL WEB SITES - MyAlcoabenefits.com website and HR SharePoint websites will need to be updated/split for the two companies. Decisions to be made by HR and IT. | Both | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 10% | TRUE | MyAlcoabenefits.com website and HR SharePoint websites will need to be updated/split for the two companies. Decisions to be made by HR and IT. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track |  |  |  |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | [26 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - MED - ONEEXCHANGE - Retirees and future retirees will need to be splt between the two companies. This also effects feeds from Hewitt to OneExchange (Towers Watson) which are sent monthly. Also, Account Administration will need to be set up for both companies. Decisions needed by HR as to which company the retirees will go. | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 5% | TRUE | Retirees and future retirees will need to be splt between the two companies. This also effects feeds from Hewitt to OneExchange (Towers Watson) which are sent monthly. Also, Account Administration will need to be set up for both companies. Decisions needed by HR as to which company the retirees will go. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track |  |  |  |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | [26 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - LOW - SURVIVING SPOUSE PAYMENTS - Typically done in last month of the year. Will need to be set up for both companies with Hewitt. | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Typically done in last month of the year. Will need to be set up for both companies with Hewitt. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started |  |  |  |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - MED - DOMESTIC PARTNER SOLICITATION - Typically done in 3rd/4th quarter. Will need to be set up for both companies with Hewitt. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Typically done in 3rd/4th quarter. Will need to be set up for both companies with Hewitt. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started |  |  | 2016-05-31 |  | 2016-05-31 | 2016-05-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - MED - MEDICARE PART B PROJECT - This kicks off in February. But, retirees could be in separate company at the end of the year when project ends. | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | This kicks off in February. But, retirees could be in separate company at the end of the year when project ends. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started |  |  | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - LOW - ELIGIBILITY RECORDS - This kicks off in February. But, retirees could be in separate company at the end of the year when project ends. | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | This kicks off in February. But, retirees could be in separate company at the end of the year when project ends. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started |  |  |  |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - Plan Documents, SPD's, Requirements, etc. - We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | On Track |  |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - LOW - Data Dump - Aon Hewitt sends updated participant data feed to HW Admin monthly. - Aon Hewitt and Health & Welfare. Aon Hewitt will need to send data to both companies. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE | Aon Hewitt and Health & Welfare. Aon Hewitt will need to send data to both companies. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | FALSE | H&W, Truven and Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC19-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | People Services - HIGH - Work with vendors to execute split of health and welfare plans. | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | We will need to work with Vendors, Plan Design and Legal to ensure the split of both company's benefit plans have been executed legally and in accordance with the plan documents. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started |  |  | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 450 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC19-23) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | Test Vendor-owned Systems | Both | TRUE | MPS_17 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Test Vendor-owned Systems | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC19-24) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | Test Single Sign-on of vendor sites | Both | TRUE | MPS_21 | 2016-07-31 | 15 | 2016-07-16 | 0% | TRUE | Test Single Sign-on of vendor sites | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC19-25) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | Test for Operation Readiness (any gaps) | Both | TRUE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Test for Operation Readiness (any gaps) | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC19-26) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | Test Split of Plans in TBA. | Both | TRUE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Test Split of Plans in TBA. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not Started | [33 empty] | No Review | 40 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 20% | TRUE | This is necessary to split benefits when the companies split. This will determined based on decisions made by Plan Design (HR) as to which company employees will go. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track | Waiting for direction from Plan Design |  |  |  |  | 2016-02-29 |  |  | 2016-02-29 | [24 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | MPS_1 | 2016-04-30 | 30 | 2016-03-31 | 20% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track | Waiting for direction from GBS/GSS | [7 empty] | 2016-04-30 | [24 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Determine how the benefit plans will be split. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track | Waiting for direction from Plan Design, Legal and Tax. |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: GP Strategies, etc. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track | Waiting for direction from Procurement and Legal. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - MED - determine how union contracts will be handled. Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2016-03-31 | 2016-03-31 | [25 empty] | 2016-03-31 | Industrial Relations | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | MPS_2 | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | IT and GP Strategies need to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Paula Bustinger | On Track | Waiting for direction from IT. | [5 empty] | 2016-03-31 | [26 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - MED - DEVELOP PROCEDURES | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC04 | N/A (HC20-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC04 | N/A (HC20-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Funding for courses. Determine how the separation impacts funding, and then implement the new process for both companies. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | Funding for courses. GP sends a bi-weekly file requesting funds to pay tuition to the schools. Will need to know how to separate and charge back appropriately. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started |  |  |  |  | 2016-03-31 | 2016-03-31 |  |  | 2016-03-31 | [24 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Payroll deductions. - Funding for courses. GP sends a bi-weekly file requesting funds to pay tuition to the schools. Will need to know how to separate and charge back appropriately. | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Payroll deductions. When an ee has courses that are taxable or they did not get the required grade for reimbursement, a file is sent by GP to payroll. These files would need to be split depending on which company the employee works for. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started |  |  |  |  | 2016-04-30 | 2016-04-30 |  |  | 2016-04-30 | [24 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Approval matrix. - There is an approval matrix that is used to route applications, and most businesses have 4 levels of approval for tuition applications. Will the approval structure remain the same, and if so, it would need to be determined who would be in the approval chain based on the new management structures. | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | There is an approval matrix that is used to route applications, and most businesses have 4 levels of approval for tuition applications. Will the approval structure remain the same, and if so, it would need to be determined who would be in the approval chain based on the new management structures. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started |  |  |  |  | 2016-04-30 | 2016-04-30 |  |  | 2016-04-30 | [24 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Repayment terms - There are repayment terms if an employee leaves the company. Will this be the same for both companies. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | There are repayment terms if an employee leaves the company. Will this be the same for both companies. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started |  |  |  |  | 2016-04-30 | 2016-04-30 |  |  | 2016-04-30 | [24 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Hewitt sends a weekly demographic feed to GP. - Hewitt sends a weekly demographic feed to GP which identifies employees who are eligible to particpate in the tuition plan. This file will need to be separated. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Hewitt sends a weekly demographic feed to GP which identifies employees who are eligible to particpate in the tuition plan. This file will need to be separated. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started |  |  |  |  | 2016-05-31 | 2016-05-31 |  |  | 2016-05-31 | [24 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. - GP Strategies and H&W. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | FALSE | GP Strategies and H&W. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC20-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | People Services - HIGH - Work with vendor to execute split of tuition assistance program. | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | We will need to work with Vendors, Plan Design and Legal to ensure the split of both company's benefit plans have been executed legally and in accordance with the plan documents. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started |  |  | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 60 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC20-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | Test Vendor-owned Systems | Both | TRUE | MPS_17 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Test Vendor-owned Systems | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not Started | [33 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC21-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting for direction from Plan Design |  |  |  |  | 2016-02-29 | [27 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC21-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | MPS_1 | 2016-04-30 | 30 | 2016-03-31 | 20% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting for direction from GBS/GSS | [7 empty] | 2016-04-30 | [24 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC04 | N/A (HC21-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - Determine how the benefit plans will be split. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting for direction from Plan Design, Legal and Tax. |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, BNY Mellon, Millenium Trust, Aon Financial Advisors, Solenture, etc. | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting for direction from Procurement and Legal. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
HC03 | HC03 | N/A (HC21-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - MED - determine how union contracts will be handled. Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2016-03-31 | 2016-03-31 | [25 empty] | 2016-03-31 | Industrial Relations | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | MPS_2 | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting for direction from IT. | [5 empty] | 2016-03-31 | [26 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - MED - DEVELOP PROCEDURES | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC03 | N/A (HC21-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC03 | N/A (HC21-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - AON FEED TO BNY MELLON | BOTH | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 5% | TRUE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | On Track | need to know what the plans will look like prior to creating a feed between Aon and BNY Mellon |  |  | 2016-04-30 | 2016-04-30 |  | 2016-04-30 | [26 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - AON FEED TO MILLENNIUM TRUST | BOTH | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 5% | TRUE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | On Track | need to know what the plans will look like prior to creating a feed between Aon and Millennium Trust |  |  | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | [26 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - BNY MELLON FEED TO MILLENNIUM TRUST | BOTH | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 5% | TRUE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | On Track | need to know what the plans will look like prior to creating a feed between BNY Mellon and Millennium Trust |  |  | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | [26 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - FUND LINEUP FOR BOTH PLANS | BOTH | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | Fund lineup will be identical for both plans, however, the new plan will need all the funds establsihed. Waiting for BMC approval | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting on Confirmation on Fund Lineups from BMC |  |  | 2016-03-31 | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - WRAP CONTRACTS SET UP FOR BOTH PLANS | BOTH | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting on Confirmation on Fund Lineups from BMC |  |  | 2016-03-31 | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - BASIS POINT FEE ANALYSIS | BOTH | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 5% | TRUE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting on projected Plan Cost Analysis Associated with Fund Lineup |  |  | 2016-04-30 | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - CREATE DEFERRED COMPENSATION PLAN AND DISTRIBUTION OPTION ELECTIONS FOR BOTH PLANs | BOTH | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 5% | TRUE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | On Track | Waiting on Determination from Plan Design |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - Plan Documents, SPD's, Requirements need to be updated/re-written for both companies, etc. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Angela Lowry, Joseph Adamietz, David Carozza | On Track |  |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - LOW - Data Dump - Aon Hewitt sends updated participant data feed to DC Admin monthly. | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE | Aon Hewitt and Defined Contributions. Aon Hewitt will need to send data to both companies. | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | FALSE | Defined Contributions and Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC21-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | People Services - HIGH - Work with vendors to execute split of 401(k) Plans. | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | We will need to work with Vendors, Plan Design and Legal to ensure the split of both company's benefit plans have been executed legally and in accordance with the plan documents. | Angela Lowry, Joseph Adamietz, David Carozza | Not Started |  |  | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 450 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC21-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | Test Vendor-owned Systems | Both | TRUE | MPS_17 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Test Vendor-owned Systems | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC21-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | Test Single Sign-on of vendor sites | Both | TRUE | MPS_21 | 2016-07-31 | 15 | 2016-07-16 | 0% | TRUE | Test Single Sign-on of vendor sites | Angela Lowry, Joseph Adamietz, David Carozza | Not Started | [33 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | Waiting for direction from Plan Design |  |  |  |  | 2016-02-29 | [27 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | MPS_1 | 2016-04-30 | 30 | 2016-03-31 | 20% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | Waiting for direction from GBS/GSS | [7 empty] | 2016-04-30 | [24 empty] | No Review | 5 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - Determine how the benefit plans will be split. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | Waiting for direction from Plan Design, Legal and Tax. |  | 2016-03-31 |  | 2016-03-31 | 2016-03-31 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, Solenture, etc. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | Waiting for direction from Procurement and Legal. | [9 empty] | 2016-03-31 | [22 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - determine how union contracts will be handled. Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 20% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2016-03-31 | 2016-03-31 | [25 empty] | 2016-03-31 | Industrial Relations | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | MPS_2 | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | Waiting for direction from IT. | [5 empty] | 2016-03-31 | [26 empty] | No Review | 15 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - DEVELOP PROCEDURES | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC03 | N/A (HC22-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | Yes
| HC03 | N/A (HC22-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - ISSUE TRACKING SYSTEMS (SIEBEL AND REMEDY)- how will access to information be shared between the companies? Seems as though the sytems will need to be duplicated. | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | IT and Hewitt will need to work thorugh how access will be granted and issues will be stored in the future | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track |  |  |  |  | 2016-03-31 |  | 2016-03-31 | [26 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC03 | N/A (HC22-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - CUSTOMER SERVICE CENTERS - how will dedicated cernters be handled. Will both companies have access to same customer service centers? | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | Once centers have been created, IT may need to be involved with arrangeing access | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track |  |  |  |  | 2016-03-31 | 2016-03-31 |  |  | 2016-03-31 | [24 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
HC16 | HC16 | N/A (HC22-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - REVIEW AND ACCESS TO BENEFITS COMMUNICATIONS - will need to be able to access historic documentation including enrollment guides, SPDs, etc. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Dependent on Plan Design, Legal and Benefits Communiation | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  |  |  | 2016-05-31 | 2016-05-31 | [27 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
| HC16 | N/A (HC22-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - LOW - CALL CALIBRATIONS - will need to coordinate with vendors to ensure that company-specific calls are provided to persons responsible for review | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE | Dependent on Plan Design and vendors. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC16 | N/A (HC22-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - ACCESS TO POAs, QDROs and QMCSOs - how will this information be shared? Will one company own theinformation and the other have to reach out to get what is needed? | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Dependent on Hewitt | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  |  |  | 2016-05-31 | [28 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC16 | N/A (HC22-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - LOW - ADOPTION ASSISTANCE, EXECUTIVE LIFE INSURANCE PROCESSES | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE | Dependent on Payroll | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  | 2016-05-31 |  | 2016-05-31 | 2016-05-31 |  |  | 2016-05-31 | [24 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC16 | N/A (HC22-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - EXPAT BENEFIT ADMINISTRATION | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 10% | TRUE | Dependent on Global Mobility and Plan Design | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track |  |  |  |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC16 | N/A (HC22-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - HIPAA PROCESS | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Dependent upon Plan Design | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  |  |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
HC02 | HC02 | N/A (HC22-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - SOLENTURE SERVICES - Will Solenture handle benefits for both Company's Execs? | Both | TRUE |  | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Dependent on Plan Design | Angela Lowry, Joseph Adamietz, Karen Heuber | On Track | [5 empty] | 2016-02-29 | [27 empty] | No Review | 25 | Benefits Administration Team | [5 empty] | No
| HC02 | N/A (HC22-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - MED - LAW SUITS/GRIEVENCES/ARBITRATION CASES - how and where will this information be stored? | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Dependent on Legal | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  |  |  | 2016-04-30 | [26 empty] | 2016-04-30 | Industrial Relations | No Review | 20 | Benefits Administration Team | [5 empty] | No
| HC02 | N/A (HC22-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - LOW - JOINT HEALTH CARE MTGS - who will handle facilitation of these required meetings? | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | Dependent on Legal and IR | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC02 | N/A (HC22-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - APPEALS COMMITTEE need to be established for both companies. | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Dependent on Legal | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  |  |  | 2016-04-30 | 2016-04-30 | [27 empty] | No Review | 40 | Benefits Administration Team | [5 empty] | No
| HC02 | N/A (HC22-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0% | FALSE | Customer Service and Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 0 | Benefits Administration Team | [5 empty] | No
| HC02 | N/A (HC22-23) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - Work with vendors to execute split of service center processes. | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | We will need to work with Vendors, Plan Design and Legal to ensure the split of both company's benefit plans have been executed legally and in accordance with the plan documents. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 300 | Benefits Administration Team | [5 empty] | No
| HC02 | N/A (HC22-24) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | People Services - HIGH - Benefits communications necessary for separation will need to be created, reviewed, fulfilled and mailed. | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | We will need to work with Vendors, Plan Design and Legal to ensure that employees and retirees understand what is happening and how their benefits are impacted. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started |  |  |  |  | 2016-07-31 | 2016-07-31 | [27 empty] | No Review | 450 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC22-25) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | Test Vendor-owned Systems | Both | TRUE | MPS_17 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Test Vendor-owned Systems | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 50 | Benefits Administration Team | [5 empty] | No
|  | N/A (HC22-26) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | Test Single Sign-on of vendor sites | Both | TRUE | MPS_21 | 2016-07-31 | 15 | 2016-07-16 | 0% | TRUE | Test Single Sign-on of vendor sites | Angela Lowry, Joseph Adamietz, Karen Heuber | Not Started | [33 empty] | No Review | 10 | Benefits Administration Team | [5 empty] | No
| HC02 | PSC-CRP-00 | Hank Cochran_Finance | PSC | CRP end to end testing - Individual tasks are on a detailed project plan originally on this spreadsheet as PSC-CRP-01 through PSC-CRP-36 | Both | TRUE |  | 2016-05-20 | 32 | 2016-04-18 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not Started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. |  | 2016-04-18 |  |  |  | 2016-04-18 |  | 2016-04-18 | [24 empty] | No Review | 200 | USBPC |  | Solutions
| HC02 | PSC-PRD-01 | Hank Cochran_Finance | PSC | Updates to PO's to align with contractual changes, including new terms and conditions, attachments, and standard notes | Both | TRUE |  | 2016-07-22 | 40 | 2016-06-12 | 0 | TRUE | New T&C's and Contractual changes to PO's by Procurement | Koenig, Miller | Not Started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-06-12 |  | 2016-06-12 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-02 | Hank Cochran_Finance | PSC | Updates to BPA's to align with contractual changes, including new terms and conditions, attachments, and standard notes. | Both | TRUE |  | 2016-07-22 | 40 | 2016-06-12 | 0 | TRUE | New T&C's and Contractual changes to PO's by Procurement | Koenig, Miller | Not Started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-06-12 |  | 2016-06-12 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-03 | Hank Cochran_Finance | PSC | Manufacturing Part Number tool needs to be split (Access Database) | Both | FALSE |  | 2016-05-31 | 40 | 2016-04-21 | 0 | TRUE | Need to find a resource, likely on Data & Reporting team, with knowledge to work on this tool. | Koenig, Miller | Not Started | Estimated due date and days needed to accomplish - will be discussed with Data & Reporting Team | [7 empty] | 2016-04-21 | [22 empty] | 2016-04-21 | GBS COE D&R Team | No Review | 16 | USBPC
| HC02 | PSC-PRD-04 | Hank Cochran_Finance | PSC | Master Req Pool Tool needs to be split (Access Database) | Both | FALSE |  | 2016-05-31 | 40 | 2016-04-21 | 0 | TRUE | Need to find a resource, likely on Data & Reporting team, with knowledge to work on this tool. | Koenig, Miller | Not Started | Estimated due date and days needed to accomplish - will be discussed with Data & Reporting Team | [7 empty] | 2016-04-21 | [22 empty] | 2016-04-21 | GBS COE D&R Team | No Review | 16 | USBPC
| HC02 | PSC-PRD-05 | Hank Cochran_Finance | PSC | Review org structure, roles and responsibilities with Hungary Team | Both | FALSE |  | 2016-06-01 | 30 | 2016-05-02 | 0 | TRUE |  | Koenig, Miller | Not Started | [8 empty] | 2016-04-21 | [24 empty] | No Review | 8 | USBPC | 8 | Hungary PSC
| HC02 | PSC-PRD-06 | Hank Cochran_Finance | PSC | Capital Testing - Capital PMO SharePoint site separated for use by both companies | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Decision by Mike Petro concerning use of the Sharepoint site by both companies | Koenig, Miller | Not Started | This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-05-02 |  | 2016-05-02 | [22 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-07 | Hank Cochran_Finance | PSC | Capital Testing - Communication method for new projects | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Decision is needed by Mike Petro (Cap Proc) to determine what communication methods will be used to relay capital projects to the procurement team. | Koenig, Miller | Not Started | This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-05-02 |  | 2016-05-02 | [22 empty] | No Review | 4 | USBPC
| HC02 | PSC-PRD-08 | Hank Cochran_Finance | PSC | Duplicate shared drives for collection of reports needed for buy and pay processes | Both | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0 | TRUE | Networks / Windows available for both companies, IT decision | Koenig, Miller | Not Started | Folders are used not only for manually storing materials, but are also designated in Discoverer report output as the default storage. | [5 empty] | 2016-03-02 |  | 2016-03-02 | [24 empty] | No Review | 16 | USBPC
| HC02 | PSC-PRD-09 | Hank Cochran_Finance | PSC | Distribute Histroical data from shared drives to appropriate company | Both | FALSE |  | 2016-05-31 | 30 | 2016-05-01 | 0 | TRUE | IT decision for data storage and legal for ownership | Koenig, Miller | Not Started |  |  |  |  | 2016-05-01 |  | 2016-05-01 |  | 2016-05-01 | [24 empty] | No Review | 16 | USBPC
| HC02 | PSC-PRD-10 | Hank Cochran_Finance | PSC | Updates to our new operating units | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Need data on naming convention | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-12 | Hank Cochran_Finance | PSC | Separate Sharepoint sites for pull Pay and PSC | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Creation of sites and accesses | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-13 | Hank Cochran_Finance | PSC | Separate buyers | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Setup of responsibilities | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 4 | USBPC
| HC02 | PSC-PRD-15 | Hank Cochran_Finance | PSC | Split Keep it Common | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Work with PIT EBS | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 16 | USBPC | 8 | MDM
| HC02 | PSC-PRD-16 | Hank Cochran_Finance | PSC | Safety prequalification process | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Access to all for Capital and who will work the GPP PSQ | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-17 | Hank Cochran_Finance | PSC | Supplier education on how to work with new companies | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Training documentation created as well as communication | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 4 | USBPC
| HC02 | PSC-PRD-18 | Hank Cochran_Finance | PSC | UPS Codes are provided by locations - will need to be separated | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE | Follow-up with location procurement | Koenig, Miller | Not Started | [8 empty] | 2016-05-31 | [24 empty] | No Review | 2 | USBPC
| HC02 | PSC-PRD-19 | Hank Cochran_Finance | PSC | Duplicate item numbers | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | FALSE |  | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 8 | USBPC | 8 | MDM
| HC02 | PSC-PRD-20 | Hank Cochran_Finance | PSC | Bleed out period for open PO's and Invoices across companies | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | FALSE |  | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 24 | USBPC
| HC02 | PSC-PRD-21 | Hank Cochran_Finance | PSC | Cross training of employees for new company assignments | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Training documentation created as well as communication | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-22 | Hank Cochran_Finance | PSC | Separate Daily Management Boards | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Determination of needs and updated macros | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 16 | USBPC
| HC02 | PSC-PRD-23 | Hank Cochran_Finance | PSC | Split / duplicate SLA | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE |  | Koenig, Miller | Not Started | Organizational decisions | [7 empty] | 2016-05-31 | [24 empty] | No Review | 2 | USBPC
| HC02 | PSC-PRD-24 | Hank Cochran_Finance | PSC | People assignments | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Training documentation created as well as communication | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 2 | USBPC
| HC02 | PSC-PRD-25 | Hank Cochran_Finance | PSC | Setup new printers | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Icon/IT assistance and purchase of new printers | Koenig, Miller | Not Started | [6 empty] | 2016-04-01 |  | 2016-04-01 | [24 empty] | No Review | 2 | USBPC
| HC02 | PSC-PRD-26 | Hank Cochran_Finance | PSC | Create/split USBPC Portal page for each company | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | IT intranet | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 4 | USBPC
| HC02 | PSC-PRD-27 | Hank Cochran_Finance | PSC | Recurring Data Requests | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Work with COE | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-28 | Hank Cochran_Finance | PSC | Delta Process flat file testing | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE |  | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 16 | USBPC
| HC02 | PSC-PRD-29 | Hank Cochran_Finance | PSC | Update Outlook DL lists | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Who wil lbe in each group. Ticket creation | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 2 | USBPC
| HC02 | PSC-PRD-31 | Hank Cochran_Finance | PSC | Duplicate Progress Payment Tracker for new company | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE |  | Koenig, Miller | Not Started | [8 empty] | 2016-05-02 | [24 empty] | No Review | 8 | USBPC
| HC02 | PSC-PRD-32 | Hank Cochran_Finance | PSC | New SPQ access for new company | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE |  | Koenig, Miller | Not Started | Who will determine | [7 empty] | 2016-05-02 | [24 empty] | No Review | 4 | USBPC
| HC02 | PSC-PRD-33 | Hank Cochran_Finance | PSC | B2B testing: Contracts between Quadrem and the suppliers need to be updated | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Need updated contracts from COE | Koenig, Miller | Not Started | [8 empty] | 2016-04-01 | [24 empty] | No Review | 16 | USBPC
| HC02 | PSC-PRD-34 | Hank Cochran_Finance | PSC | eCM testing - Separate Sharepoint site for eCM Onboarding and Update requests | Both | FALSE |  | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Sharepoint needs to be available for both companies | Koenig, Miller | Not Started | This task is copied onto the Procurement Separation Project Plan. SharePoint team to create new site for new company. Site Owner to create new forms on the new site. | [5 empty] | 2016-05-02 |  | 2016-05-02 | [24 empty] | No Review | 8 | USBPC
HC17 | HC17 | PSC-PRD-35 | Hank Cochran_Finance | PSC | Reassignment of PO's to new buyers | Both | FALSE |  | 2016-07-22 | 16 | 2016-07-06 | 0 | TRUE | Contractual changes to PO's by Procurement | Koenig, Miller | Not Started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-07-06 |  | 2016-07-06 | [24 empty] | No Review | 4 | USBPC
| HC17 | PSC-PRD-36 | Hank Cochran_Finance | PSC | Split Infopath form for Remedy is production ready | Both | TRUE |  | 2016-07-03 | 21 | 2016-06-12 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not Started | [8 empty] | 2016-06-12 | [24 empty] | No Review | 24 | USBPC
| HC17 | PSC-PRD-37 | Hank Cochran_Finance | PSC | Discoverer and Pi2P reports is production ready | Both | TRUE |  | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not Started | Dependent on CRP testing results | [7 empty] | 2016-05-30 | [24 empty] | No Review | 24 | USBPC
| HC17 | PSC-PRD-38 | Hank Cochran_Finance | PSC | Duplicate Work Instructions | Both | FALSE |  | 2016-05-31 | 60 | 2016-04-01 |  | FALSE |  | Koenig, Miller | Not Started | [33 empty] | No Review | 4 | USBPC
| HC17 | PSC-PRD-39 | Hank Cochran_Finance | PSC | Duplicate and test all macros and other non-Oracle automation tools used by USBPC | Both | FALSE |  | 2016-07-31 | 27 | 2016-07-04 | 0 | FALSE |  | Koenig, Miller | Not Started | [8 empty] | 2016-07-04 | [24 empty] | No Review | 24 | USBPC
| HC17 | PSC-PRD-40 | Hank Cochran_Finance | PSC | Master Req Pool Consolidator Tool needs to be split (Access Database) | Both | FALSE |  | 2016-05-31 | 40 | 2016-04-21 | 0 | TRUE | Need to find a resource, likely on Data & Reporting team, with knowledge to work on this tool. | Koenig, Miller | Not Started | Estimated due date and days needed to accomplish - will be discussed with Data & Reporting Team | [7 empty] | 2016-04-21 | [22 empty] | 2016-04-21 | GBS COE D&R Team | No Review | 24 | USBPC
| HC17 | PSC-UAT-00 | Hank Cochran_Finance | PSC | UAT Testing end to end testing - Individual tasks are on a detailed project plan originally on this spreadsheet as PSC-UAT-01 through PSC-UAT-36 | Both | TRUE |  | 2016-07-08 | 46 | 2016-05-23 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not Started | Dependent on CRP testing results |  | 2016-05-23 |  |  |  | 2016-05-23 |  | 2016-05-23 | [24 empty] | No Review | 200 | USBPC |  | Solutions
HC18 | HC18 | PSC-UNI-00 | Hank Cochran_Finance | PSC | Unit Testing end to end testing - Individual tasks are on a detailed project plan originally on this spreadsheet as PSC-UNI-01 through PSC-UNI-36 | Both | TRUE |  | 2016-04-15 | 95 | 2016-01-11 | 1% | TRUE | Oracle Unit testing schedule and instance availability | Koenig, Miller | On Track | This is part of the Oracle system Unit testing. |  | 2016-03-15 |  |  |  | 2016-03-15 |  | 2016-03-15 | [24 empty] | No Review | 200 | USBPC |  | Solutions
| HC18 | TRN-BST-02 | Hank Cochran_Other | Transportation Support | Best Transport - Segregate and split (create new) BestTransport accounts and processes | Both | FALSE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE |  | Williams/McWilliams/D. Benner | Not Started | See detailed project plan for specific tasks, dates & SPAs | [5 empty] | 2016-04-26 | [18 empty] | 2016-04-26 | [7 empty] | No Review | 40 | ALSO
| HC18 | TRN-IPS-03 | Hank Cochran_Other | Transportation Support | IPS - Segregate and split (create new) IPS data and processes | Both | FALSE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | Oracle instance required; GSS Ledger & RtP; OM & PO systems | McWilliams/Brock/E. Strawn | Not Started | See detailed project plan for specific tasks, dates & SPAs | [5 empty] | 2016-03-03 |  | 2016-03-03 | [24 empty] | No Review | 225 | ALSO | 10 | GSS Ledger
| HC18 | TRN-PRD-04 | Hank Cochran_Other | Transportation Support | Procurement contracts for IPS, Best Transport, QTS, BlueRock Logistics, Interlog and DevWare | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | Procurement for both businesses to be identified and able to begin contract negotiations | M. Dausch/McWilliams | Not Started | start working the new contracts ASAP. | [9 empty] | 2016-04-02 | [22 empty] | No Review | 20 | ALSO
| HC18 | TRN-PRD-05 | Hank Cochran_Other | Transportation Support | MISC: setup new webpages, mailboxes, etc. | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Brock/Williams/McWilliams | Not Started | ALSO needs to be identified by 4/30/16 | [32 empty] | No Review | 10 | ALSO
| HC18 | TRN-PRD-07 | Hank Cochran_Other | Transportation Support | GBS Transportation SharePoint split - create new for new business; identify owner | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | McWilliams | Not Started | Sharepoint infrastructure ready | [5 empty] | 2016-05-01 | [26 empty] | No Review | 10 | ALSO
| HC18 | TRN-TDW-01 | Hank Cochran_Other | Transportation Support | TDW - Segregate and splt (create new) TDW data and processes | Both | FALSE |  | 2016-07-31 | 200 | 2016-01-13 | 7% | TRUE |  | Devware/McWilliams | On Track | See detailed project plan for specific tasks, dates & SPAs | [5 empty] | 2016-01-13 | [24 empty] | 2016-06-30 | GBS CoE Data & Reporting | No Review | 80 | ALSO
[11 empty] | #REF! |  | TRUE | Waiting for direction from IT and EBS Support | Caldwell/Randall | Not Started | Evaluate and remediate potential impact of entity name & domain name changes | [9 empty] | 2016-03-31 | [22 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
[11 empty] | #REF! | [38 empty] | #REF!
0
[60 empty] | 1407 | 299 | 268 | 60 | 0 | 0 | 0 | 0 | 290 | 194 | 0 | 0 | 390 | 128 | 0 | 0 | 10 | 160 | 14 | 120 | 120 | 0 | 42 | 120 | 420 | 360 | 70 | 190 | 90 | 180 | 14 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 938
[60 empty] | 1.3529 | 0.2875 | 0.25769 | 0.057692 | 0 | 0 | 0 | 0 | 1.6731 | 1.1192 | 0 | 0 | 2.25 | 0.73846 | 0 | 0 | 0.057692 | 0.92308 | 0.080769 | 0.69231 | 0.69231 | 0 | 0.24231 | 0.69231 | 2.4231 | 2.0769 | 0.40385 | 1.0962 | 0.51923 | 1.0385 | 0.080769 | 0 | 0.34615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1904
[60 empty] | 69.17% | 14.7% | 13.18% | 2.95%
x
Formulas:
Start Date (Calculated) = TasksTable4[[#This Row],[Required Completion Date]]-TasksTable4[[#This Row],[Days to Accomplish]]
Start Date (Calculated) = [Required Completion Date]-[Days to Accomplish]
For GSS PMO Riveiw? = IF(AND([7]!TasksTable4[[#This Row],[Status]]<>"On Track",[7]!TasksTable4[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
For GSS PMO Riveiw? = IF(AND(TasksTable4[[#This Row],[Status]]<>"On Track",TasksTable4[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
IT = [Start Date (Calculated)]
Global Shared Services (GSS) = [Start Date (Calculated)]

## Project Plan(s) - {HC} (hidden)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-02 11:34
| Task-Level Description | [14 empty] | Dependency Resolution Checklist
| Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
HC08 | N/A (HC08-01) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Organization Structure planning | Both | TRUE | 2015-12-31 | 23 |  | 20% | TRUE |  | Lowry, Sterlitz | Not started | Need a decision made on the IT strategy and if a TSA will be in place
HC08 | N/A (HC08-02) | Hank Cochran_HR_Other | People Services System Support | Complexity = High IT system strategy | Both | TRUE | 2015-12-31 | 23 |  | 50% | TRUE | This will be determined by GSS/IS and the BU. This is of upmost priority as our project plan changes dramatically depending on what the IT strategy is. | Lowry, Sterlitz | In progress | Waiting for decision on the HR application solution
HC08 | N/A (HC08-03) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Procurement contract strategy | Both | TRUE | 2016-01-31 | 51 |  | 0% | TRUE | Assumption - no changes in 3rd party vendors. Changes to vendor contacts may impact GPS interfaces. Note that this a concern for all countries/regions. Will vendors require 2 interfaces, 1 for each company? We have to start to work on interfaces Q1. | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-04) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Develop proceedures | Both | TRUE | 2016-03-31 | 114 |  | 0% | TRUE | With the assumption that GPS remains in place for both companies, I would expect the common, standard GPS processes would support the two companies (such as compensation, talent, etc) | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-05) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Develop training documents | Both | TRUE | 2016-03-31 | 114 |  | 0% | TRUE | Assumption - Upstream will remain on GPS with TSA in place. No training would be needed as existing processes would be used. | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-06) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Complete knowledge transfer | Both | TRUE | 2015-12-31 | 23 |  | 0% | TRUE | Assumption - Upstream will remain on GPS with TSA in place. Longer Term - the expert level knowledge resides with 1 person today and this knowledge will need to be shared with another person so both companies can be adequately supported going forward | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | 7 | Hank Cochran_HR_Other | People Services System Support | Complexity = High Decision point - is data required to be purged (masked) post separation? | Both | TRUE | 2016-01-31 | 23 |  | 30% | TRUE | Decision from legal - will any historical data need to be protected/purged? Will GPS support teams be able to retain access to all employees throughout TSA? | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution and legal decision on data privacy requirements
HC08 | N/A (HC08-08) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Confirm data has been purge out of the system. | Both | TRUE | 2016-01-31 |  |  | 0% |  | Legal decision | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution and legal decision on data privacy requirements
HC08 | N/A (HC08-09) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Remove user accounts in R12 and Fusion. | Both | TRUE | 2016-10-01 |  |  | 0% |  |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution and legal decision on data privacy requirements
HC08 | N/A (HC08-10) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Update Security Profiles to remove other companies organizations. | Both | TRUE | 2016-10-01 |  |  | 0% |  |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution and legal decision on data privacy requirements
HC08 | N/A (HC08-11) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Run Security Process to sync up responsiblities with the profile changes | Both | TRUE | 2016-10-01 |  |  | 0% |  |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution and legal decision on data privacy requirements
HC08 | N/A (HC08-12) | Hank Cochran_HR_Other | People Services System Support | Complexity = Low Notify support and HR the changes are complete | Both | TRUE | 2016-10-01 |  |  | 0% |  |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution and legal decision on data privacy requirements
HC08 | N/A (HC08-13) | Hank Cochran_HR_Other | People Services System Support | Complexity Level = High Hiearchy Changes - Remove other Company Business Group, Business Unit, LBC Structure from the Hiearchy | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE | GPS Hiearchy will need to be redefined to aligh with Finance Hierarchy | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution. | 2015-12-31
HC08 | N/A (HC08-14) | Hank Cochran_HR_Other | People Services System Support | Complexity Level = Medium Hiearchy Changes -End Date structures | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE | GPS Hiearchy will need to be redefined to aligh with Finance Hierarchy | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-15) | Hank Cochran_HR_Other | People Services System Support | Complexity Level = Low Hiearchy Changes - Run Security List Maintenance to Sync up structure | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-16) | Hank Cochran_HR_Other | People Services System Support | Complexity Level = High Hiearchy Changes - confirm changes are made in Fusion | V-A Co. | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-17) | Hank Cochran_HR_Other | People Services System Support | Complexity Level = High Change name of Global Hierarchy | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-18) | Hank Cochran_HR_Other | People Services System Support | Complexity - Low Single Sign on - Determine Web page or pages (regional) that will have link to access system. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-19) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Single Sign on - Remediate Single Sign on and define solution for external SSO working for 2 companies within GPS | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-20) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Single Sign on - Test solution with all 3rd party vendors and internal applications | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-21) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Remove 'Alcoa' References for Value Add hiearchy code. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-22) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Remove 'Alcoa' References for Value Add program code. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-23) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Remove 'Alcoa' References for Value Add reporting. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-24) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Remove 'Alcoa' References for Value Add program names. First need to identfiy where Alcoa is referenced, then work with Oracle on gaining script to rename. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-25) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Terminate Upstream employees and re-hire under new company code | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-26) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Purging the system - employee data is removed | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-27) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Purging the system - Remove or confirm Fusion accounts were removed as part of HR2HR | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-28) | Hank Cochran_HR_Other | People Services System Support | Complexity = HIgh Purging the system - Any configurations being used within exisiting populations will be updated to remove Alcoa. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-29) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Purging the system - Remove User accounts in R12 | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-30) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Purging the system - Delete configurations items that legally need purged. | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-31) | Hank Cochran_HR_Other | People Services System Support | Complexity = Low Compile a list of Interfaces (total ~125) (Global and Regional) (Internal Corporate Apps, Outside Vendors) (Inbound, Outbound) | Both | TRUE | 2016-01-31 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-32) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium At a high level, assess the potential impact of Separation on interfaces. | Both | TRUE | 2016-02-28 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-33) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Review GPS, Interface stategy, its impact on interfaces with the Alcoa internal teams (That manage internal Corporate Applications) | Both | TRUE | 2016-03-31 |  |  | 0% | TRUE | Key Assumuption: Internal Applications(WorkBrain, T&E, EHS…) will remain same | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-34) | Hank Cochran_HR_Other | People Services System Support | Complexity = Medium Review GPS, Interface stategy, its impact on interfaces with the Alcoa internal teams (that manage external Vendors), with the corresponding Outside Vendors | Both | TRUE | 2016-03-31 |  |  | 0% | TRUE | Key Assumuption: Third Party Vendors (Payroll, Benefirs, Alcoa Learn…) will remain same | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-35) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Remediate (document, Code changes, setup changes, Unit test) Outbound/Inbound Interfaces to send/receive data. | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-36) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Remediate(document, Code changes, setup changes, Unit test) - Pull views - Outbound - used by internal Alcoa applications | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-37) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Integration testing - Inbound/Outbound interfaces with thrid party vendors to receive/send files with the change. | Both | TRUE | 2016-09-30 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-38) | Hank Cochran_HR_Other | People Services System Support | Complexity = High Integration testing - Outbound Pull interface Views - Test it with internal Alcoa applications to ensure they are able to access data | Both | TRUE | 2016-09-30 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started | Waiting for decision on the HR application solution.
HC08 | N/A (HC08-39) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Determine if Remedy People Serivces will be utilized by both companies and remediate if necessary | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-40) | Hank Cochran_HR_Other | People Services System Support | Complexity - Medium Review scope of SLA and revise | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC08 | N/A (HC08-41) | Hank Cochran_HR_Other | People Services System Support | Complexity - High Testing of critical processes for comp - Hourly performance pay, compensation planning, etc | Both | TRUE | 2016-10-01 |  |  | 0% | TRUE |  | Lowry, Sterlitz | Not started
HC11 | N/A (HC11-01) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Organization Structure planning | Both | TRUE | 2016-01-31 | 53 |  | 10% | TRUE | Assumption - Value-Add will retain existing application support organization and Upstream will contract with external expert services for IT and Functional system support. Several vendors are available. Decision must be made on this quickly, but is dependant on the Procurement contract process | Lowry, Sterlitz, Clive | In Progress | Dependant on decision on in-house vs SAAS, and selection of vendor for IT and Functional support. Working on determining options with vendor and procurement | [5 empty] | 2016-01-31 |  | 42400 |  | 2016-01-31 | [20 empty] | 42400 | GPP
HC11 | N/A (HC11-02) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity High - IT system strategy | Both | TRUE | 2016-01-15 | 37 |  | 10% | TRUE | Assumption - Value-Add will remain on existing Workbrain, Upstream will be cloned and GPS will be available via TSA at separation. Decision must be made quickly whether to clone in-house or move to SAAS with the software vendor. Decision is dependant on the Procurement contract strategy | Lowry, Sterlitz, Clive | In Progress | Need a decision on in-house vs SAAS. Working with Procurement and vendor to determine cost/benefits for both solutions | [5 empty] | 2016-01-15 |  | 42384 |  | 2016-01-15
HC11 | N/A (HC11-03) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Procurement contract strategy | Both | TRUE | 2016-01-15 | 37 |  | 10% | TRUE | We will need Procurement to work on best cost for SAAS hosted solution proposal. Proposal evaluation and contracts are the starting point for all other changes. How will licenses affect this decision. What is needed from Legal on this? | Lowry, Sterlitz, Clive | In Progress | Need a decision on in-house vs SAAS. Working with vendor to obtain pricing information on SAAS and sizing for staging an in-house solution |  |  |  | 2016-01-15 |  | 2016-01-15 |  | 42384 |  | 2016-01-15
HC11 | N/A (HC11-04) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Develop proceedures | Both | TRUE | 2016-04-30 | 142 |  | 0% | TRUE | Value-Add procedures remain the same. Upstream procedures will change depending on IT system strategy, HR application/TSA and any application interface changes. Must have decision on TSA for GPS. | Lowry, Sterlitz, Clive | Not Started | No change for Value-Add. Dependant on decision on in-house vs SAAS, Payroll Vendor and TSA for GPS for Upstream. Need EAM interface decision made. | [5 empty] | 2016-04-30 |  | 42490
HC11 | N/A (HC11-05) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Low - Develop training documents | Both | TRUE | 2016-05-30 | 172 |  | 0% | TRUE | Value-Add procedures remain the same. Upstream procedures will change depending on IT system strategy, HR application/TSA and any application interface changes. | Lowry, Sterlitz, Clive | Not Started | No change for Value-Add company. Need a decision on in-house vs SAAS for Upstream | [7 empty] | 42520
HC11 | N/A (HC11-06) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity High - Complete knowledge transfer | Both | TRUE | 2016-06-30 | 202 |  | 0% | TRUE | Value-Add will not require knowledge transfer. Upstream requirements are dependant on IT system strategy and Organization structure | Lowry, Sterlitz, Clive | Not Started | No change for Value-Add. Dependant on decision on in-house vs SAAS for Upstream to determine extent of KT | [5 empty] | 2016-06-30 |  | 42551 | [22 empty] | 42551 | IT and Functional Support Vendor
HC11 | N/A (HC11-07) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Remove 'Alcoa' References from hiearchy codes and any other references to Alcoa in Value-Add application | V-A Co. | FALSE | 2016-04-30 | 142 |  | 0% | TRUE | Many references will be fed from the HR solution. Assumption is that TSA will be in place and GPS will feed changes for both companies. Remaining references will be manually removed | Lowry, Sterlitz, Clive | Not Started | Dependant on Legal Decisions and split of locations/LBCs between companies |  |  |  | 2016-04-30 | 42490 | 2016-04-30
HC11 | N/A (HC11-08) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Develop replacement strategy for login/SSO for Upstream business on Hosted solution | Up. Co. | TRUE | 2016-01-31 | 53 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-01-31 |  | 42400 | [22 empty] | 42400 | Vendor Infor
HC11 | N/A (HC11-09) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Develop replacement strategy for Discoverer reporting | Up. Co. | TRUE | 2016-01-31 | 53 |  | 0% | TRUE | Replacement strategy must be defined for the Upstream company if SAAS solution selected. Assumption is that Discoverer will not be available on SAAS. | Lowry, Sterlitz, Clive | Not Started | Need a decision on in-house vs SAAS and whether SAAS will support Discoverer reporting | [5 empty] | 2016-01-31 |  | 42400 | [22 empty] | 42400 | Vendor Infor
HC11 | N/A (HC11-10) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Hiearchy/Organization Changes | Both | TRUE | 2016-02-28 | 23 |  | 0% | TRUE | Workbrain Hiearchy and determination of which company each LBC will be in is dependant on Legal | Lowry, Sterlitz, Clive | Not Started | Dependant on Legal Split |  |  |  | 2016-01-31
HC11 | N/A (HC11-11) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Ownership/purging of data history strategy | Both | TRUE | 2015-12-31 | 23 |  | 0% | TRUE | Assumption is that both companies may will retain history and purging is not required | Lowry, Sterlitz, Clive | Not Started | Need decision from Legal |  |  |  | 2015-12-31
HC11 | N/A (HC11-12) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Payroll Vendor | Up. Co. | TRUE | 2016-01-31 | 53 |  | 0% | TRUE | Assumption is that both companies may will continue to use Hewitt Payroll | Lowry, Sterlitz, Clive | Not Started | Need decision from Legal and Procurement |  |  |  | 2016-01-31 |  |  |  |  | 42400
HC11 | N/A (HC11-13) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Split of Licenses/contracts/maintenance agreements | Both | TRUE | 2016-01-15 | 37 |  | 10% | TRUE | This decision has an impact on the cost/benefit of the SAAS vs in-house solution and must be determined early | Lowry, Sterlitz, Clive | Not Started | Need decision from Legal |  |  |  | 2016-01-15
HC11 | N/A (HC11-14) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity High - Union Contract Changes | Both | TRUE | 2016-04-30 | 142 |  | 0% | TRUE | Impact of payrules and other changes from Union Contract negotiations is unknown. | Lowry, Sterlitz, Clive | Not Started | Need information/decision from Industrial Relations | [30 empty] | 42490 | Industrial Relations
HC11 | N/A (HC11-15) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Updates to documentation (technical and support) | Both | TRUE | 2016-07-22 | 224 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-07-22
HC11 | N/A (HC11-16) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Determine Infrastructure sizing | Both | TRUE | 2016-01-15 | 37 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-01-15 | [24 empty] | 42384 | Vendor Infor
HC11 | N/A (HC11-17) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity High - Existing System Modifications (Interface Remediation, Config Changes, Data Changes, Clock Sizing, Discoverer Remains - Sizing?, etc). Remediation of these objects and testing in multiple instances. | Both | TRUE | 2016-09-23 | 285 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-09-23
HC11 | N/A (HC11-18) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Application Support - Define processes for support (USBS, IT, GSS) | Both | TRUE | 2016-07-22 | 224 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. |  |  |  |  | 42573 | 2016-07-22 |  | 42573
HC11 | N/A (HC11-19) | Hank Cochran_HR_Benefits, Payroll, T&A | T&A | Complexity Med - Define GSS support model - RPS changes, mailbox, etc) | Both | TRUE | 2016-07-22 | 224 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Sterlitz, Clive | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-07-22 |  | 42573
HC10 | N/A (HC10-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Organization Structure Planning | Both | TRUE | 2016-01-31 | 27 |  | 0% | TRUE | Assumption - Value-Add will retain existing payroll support organization and Upstream will contract with external expert services for payroll support. Several vendors are available. Decision must be made on this quickly, but is dependant on the Procurement contract process | Lowry, Kerekes | Not started | Waiting for decision on procurement contract strategy - clone existing system v new system/new provider | [5 empty] | 2016-01-31 |  |  |  | 2016-01-31
HC10 | N/A (HC10-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - IT System Strategy | Both | TRUE | 2016-01-31 | 27 |  | 0% | TRUE | Assumption - Value-Add will remain on existing PeopleSoft, Upstream will be cloned and PeopleSoft will be available via TSA at separation. Decision must be made quickly whether to clone at Aon Hewitt or move to another payroll provider. Decision is dependant on the Procurement contract strategy Assumption - Value-Add will remain on existing Workbrain, Upstream will be cloned and GPS will be available via TSA at separation. Decision must be made quickly whether to clone in-house or move to SAAS with the software vendor. Decision is dependant on the Procurement contract strategy | Lowry, Kerekes | Not started | Waiting for decision on Procurement contract and IT system strategies - clone existing system v new system/new provider | [5 empty] | 2016-01-31 |  |  |  | 2016-01-31
HC10 | N/A (HC10-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Naming/Tax Strategy - Upate regulatory agencies with new legal names, file for new tax IDs, update systems to reflect name changes | Both | TRUE | 2016-01-31 | 27 |  | 0% | TRUE | Dependent on corporate tax/organization strategy to determine agency filing requirements and system impact | Lowry, Kerekes | Not started | Waiting for decisions from Legal and Tax as well as decision on IT system strategy |  | 2016-01-31 |  | 2016-01-31 |  | 2016-01-31
HC10 | N/A (HC10-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Procurement Contract Strategy | Both | TRUE | 2016-01-31 | 27 |  | 0% | TRUE | We will need Procurement and Legal to work on contract changes and vendor selectionl. Proposal evaluation and contracts are the starting point for all other changes. | Lowry, Kerekes | Not started | Waiting for direction from Procurement and Legal |  |  |  | 2016-01-31 | [5 empty] | 2016-01-31
HC10 | N/A (HC10-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Union Contract Changes | Both | TRUE | 2016-01-31 | 27 |  | 0% | TRUE | Impact of pay rule and other changes from Union Contract negotiations is unknown | Lowry, Kerekes | Not started | Waiting for direction from Industrial Relations | [30 empty] | 2016-01-31 | Industrial Relations
HC10 | N/A (HC10-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Business Hiearchy/Organization Changes | Both | TRUE | 2016-02-29 | 53 |  | 0% | TRUE | PeopleSoft and Workbrain hiearchy and determination of which company each LBC will be in is dependant on Legal & Tax | Lowry, Kerekes | Not started | Waiting for direction from IT and Finance | 2016-02-29 |  |  |  |  | 2016-02-29
HC10 | N/A (HC10-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Develop Procedures | Both | TRUE | 2016-04-30 | 147 |  | 0% | TRUE | Assumption: Value-Add procedures remain the same. Upstream procedures will change depending on IT/vendor strategy, TSA and any application interface changes. Must have decision on TSA for payroll services | Lowry, Kerekes | Not started | Waiting for decisions documented here |  |  |  |  | 2016-04-30 |  |  | 2016-04-30
HC10 | N/A (HC10-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Develop Training Documents | Both | TRUE | 2016-04-30 | 147 |  | 0% | TRUE | Assumption: Value-Add procedures remain the same. Upstream procedures will change depending on IT/vendor strategy, TSA and any application/provder interface changes. Must have decision on TSA for payroll services | Lowry, Kerekes | Not started | Waiting for decisions documented here |  |  |  |  | 2016-04-30 |  |  | 2016-04-30
HC10 | N/A (HC10-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Complete Knowledge Transfer | Both | TRUE | 2016-07-31 | 237 |  | 0% | TRUE | Assumption: Value-Add will not require knowledge transfer. Upstream requirements are dependant on IT/vendor strategy and Organization structure | Lowry, Kerekes | Not started | Waiting for decisions documented here | [7 empty] | 2016-07-31
HC10 | N/A (HC10-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Data History Strategy | Both | TRUE | 2016-07-31 | 237 |  | 0% | TRUE | Assumption: Both companies will retain history and purging is not required | Lowry, Kerekes | Not started | Waiting for decision from Legal and decision on IT system strategy | [7 empty] | 2016-07-31
HC10 | N/A (HC10-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Remove 'Alcoa' References from hiearchy codes and any other references to Alcoa in Value-Add application | V-A Co. | FALSE | 2016-04-30 | 142 |  | 0% | TRUE | Many references will be fed from the HR solution. Assumption is that TSA will be in place and GPS will feed changes for both companies. Remaining references will be manually removed | Lowry, Kerekes | Not started | Dependant on Legal Decisions and split of locations/LBCs between companies |  |  |  | 2016-04-30 | 2016-04-30 | 2016-04-30 |  | 2016-04-30
HC10 | N/A (HC10-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Develop replacement strategy for login/SSO for Upstream business on PeopleSoft hosted solution | Up. Co. | TRUE | 2016-01-31 | 53 |  | 0% | TRUE | Dependancy on TSA for GPS and selection of IT Strategy being Hosted. Assumption is that TSA will be available. | Lowry, Kerekes | Not Started | Dependant on decision on in-house vs SAAS, and ability for vendor to provide appropriate SSO protocol. May need input from GPP organization/Shared Services. | [5 empty] | 2016-01-31 |  | 2016-01-31 | [22 empty] | 2016-01-31 | Vendor Aon Hewitt
HC10 | N/A (HC10-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Develop security strategy for Vista Reports hosted solution | Up. Co. | TRUE | 2016-01-31 | 53 |  | 0% | TRUE | Security strategy must be defined for the Upstream company if PeopleSoft strategy is to maintain single instance split only by security | Lowry, Kerekes | Not Started | Dependent on decision regarding PeopleSoft | [5 empty] | 2016-01-31 |  | 2016-01-31 | [22 empty] | 2016-01-31 | Vendor Aon Hewitt
HC10 | N/A (HC10-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Ownership/purging of data history strategy | Both | TRUE | 2015-12-31 | 23 |  | 0% | TRUE | Assumption is that both companies will retain history and purging is not required | Lowry, Kerekes | Not Started | Need decision from Legal |  |  |  | 2015-12-31
HC10 | N/A (HC10-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Payroll Provider / Split Contract | Up. Co. | TRUE | 2015-12-31 | 23 |  | 0% | TRUE | Assumption is that both companies will continue to use Aon Hewitt hosted PeopleSoft, requiring contract split | Lowry, Kerekes | Not Started | Need decision from Legal and Procurement |  |  |  | 2015-12-31 | [5 empty] | 2015-12-31
HC10 | N/A (HC10-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | LOW - Review scope and SLA for each company | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | Customers will be involved in the process to validate future SLA and scope | Lowry, Kerekes | Not started | [31 empty] | X | Customers
HC10 | N/A (HC10-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Define and implement controls regarding access to data on fileshare, SharePoint, emails, and with vendors | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | IT and Procurement needs to support the process | Lowry, Kerekes | Not started | [6 empty] | X |  |  |  | X
HC10 | N/A (HC10-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | LOW - Create location and HR listings, as well as standard metrics, for each company | Both | FALSE | 2016-06-30 | 181 | 2016-01-01 | 0% | FALSE | N/A | Lowry, Kerekes | Not started
HC10 | N/A (HC10-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Work with People Systems Solutions to guarantee the testing process | Both | TRUE | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Lowry, Kerekes | Not Started | [8 empty] | X
HC10 | N/A (HC10-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Work with HRDTA to guarantee the testing process | Both | TRUE | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Lowry, Kerekes | Not Started | [8 empty] | X
HC10 | N/A (HC10-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Implement the new help chain model - Remedy | Both | TRUE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Lowry, Kerekes | Not Started
HC10 | N/A (HC10-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | LOW - Create new mailbox for one of the companies | Both | TRUE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Lowry, Kerekes | Not Started
HC10 | N/A (HC10-23) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | LOW - Create location and HR listings, as well as standard metrics, for each company | Both | FALSE | 2016-06-30 | 181 | 2016-01-01 | 0% | FALSE | N/A | Lowry, Kerekes | Not started
HC10 | N/A (HC10-24) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM - Create new fileshare, SharePoint site, email shared mailboxes | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not started | [6 empty] | X |  |  |  | X
HC10 | N/A (HC10-25) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | MEDIUM -Determine approach to split & secure Seibel ticketing system | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE |  | Lowry, Kerekes | Not started | [31 empty] | X | Vendor Aon Hewitt
HC10 | N/A (HC10-26) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Replicate secured Payroll Reuest Form technology and proess for Upstream Co | Up. Co. | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not started | [6 empty] | X
HC10 | N/A (HC10-27) | Hank Cochran_HR_Benefits, Payroll, T&A | Payroll | HIGH - Determine if trailing payments will occur (equity, performance pay, incentive comp) and if so how those will be handled (charged back, split) | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | IT needs to support the process | Lowry, Kerekes | Not started | [6 empty] | X
HC13 | 85 (HC 13-01) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Understand the size of GPP organization to be supported (potential employees to be served) | Up. Co | TRUE | 2016-01-31 | 30 | 2016-01-01 | 0% | TRUE | GPP leadership needs to define the size of the organization that will be supported in the future | Freier, Marcelo | Not started | [31 empty] | X | GPP
HC13 | 85 (HC 13-02) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Define the systems that will be used by each of the companies (GPS, Workbrain, Web Based Reports, Equifax, Case Builder, ASP and Brassring) | Both | TRUE | 2016-07-31 | 212 | 2016-01-01 | 0% | TRUE | IT needs to define the systems that will be used to support both groups | Freier, Marcelo | Not started | [6 empty] | X
HC13 | 85 (HC 13-03) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Define the organization in Hungary that will support both companies, including GSS for Compliances activities. | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | FALSE | N/A | Freier, Marcelo | Not started
HC13 | 85 (HC 13-04) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Define the organization in US that will support both companies | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | FALSE | N/A | Freier, Marcelo | Not started
HC13 | 85 (HC 13-05) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Confirm if the same ASAT protocols will be applied for both companies | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | TRUE | Audit needs to define the program that will be used in the future to support both companies | Freier, Marcelo | Not started | [24 empty] | X
HC13 | 85 (HC 13-06) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Confirm the plans for Safe Harbor for both companies | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | TRUE | Legal and IT (security) need to define the document that will allow support from Hungary | Freier, Marcelo | Not started |  |  |  |  | X |  | X
HC13 | 85 (HC 13-07) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Review scope and SLA for each one of the customers. | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | Customers will be involved in the process to validate future SLA and scope | Freier, Marcelo | Not started | [31 empty] | X | Customers
HC13 | 85 (HC 13-08) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Review procedures to reflect the new reality | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | FALSE | N/A | Freier, Marcelo | Not started
HC13 | 85 (HC 13-09) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Define and implement controls regarding access to data on fileshare, SharePoint, emails, and with vendors | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | IT and Procurement needs to support the process | Freier, Marcelo | Not started | [6 empty] | X |  |  |  | X
HC13 | 85 (HC 13-10) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Create location and HR listings, as well as standard metrics, for each company | Both | FALSE | 2016-06-30 | 181 | 2016-01-01 | 0% | FALSE | N/A | Freier, Marcelo | Not started
HC13 | 85 (HC 13-11) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Separate the documents (physical or electronic) for both companies | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | TRUE | IT and Records Management need to support the process | Freier, Marcelo | Not started | [6 empty] | X |  | X
HC13 | 85 (HC 13-12) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Knowledge transfer plan to guarantee the organization skill and capabilities. | Both | TRUE | 2016-06-30 | 181 | 2016-01-01 | 0% | FALSE | N/A | Freier, Marcelo | Not started
HC13 | 85 (HC 13-13) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Involve Procurement to negotiate the contracts - separation | Both | TRUE | 2016-06-30 | 180 | 2016-01-02 | 0% | TRUE | Work with procurement on the commerical side of the program | Freier, Marcelo | Not Started | [10 empty] | X
HC13 | 85 (HC 13-14) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Communicate the main changes to the customers | Both | TRUE | 2016-09-30 | 30 | 2016-08-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-15) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Define and start the transition process among the team members | Both | TRUE | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-16) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Work with People Systems Solutions to guarantee the testing process | Both | TRUE | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Freier, Marcelo | Not Started | [8 empty] | X
HC13 | 85 (HC 13-17) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Work with HRDTA to guarantee the testing process | Both | TRUE | 2016-05-30 | 90 | 2016-03-01 | 0% | TRUE | Testing process with People Services | Freier, Marcelo | Not Started | [8 empty] | X
HC13 | 85 (HC 13-18) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Implement new controls to manage the process | Both | TRUE | 2016-07-30 | 30 | 2016-06-30 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-19) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Implement actions to evaluate and measure the productivity for USBS based on the new reality | Both | TRUE | 2016-07-30 | 60 | 2016-05-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-20) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Perform an assessment to evaluate risks and opportunities to improve compliance process for USBS | Both | TRUE | 2015-06-30 | 30 | 2015-05-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-21) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Move employees between offices - especially TN, Pittsburgh and Kofem | Both | TRUE | 2015-06-30 | 30 | 2015-05-31 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-22) | Hank Cochran_HR_Other | People Services Transaction Support | MEDIUM - Evaluate opportunities after the transition to move further activities to Hub (Kofem) | Both | TRUE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-23) | Hank Cochran_HR_Other | People Services Transaction Support | HIGH - Implement the new help chain model - Remedy | Both | TRUE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-24) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Create new mailbox for one of the companies | Both | TRUE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13 | 85 (HC 13-25) | Hank Cochran_HR_Other | People Services Transaction Support | LOW - Create a new terminology for USBS | Both | TRUE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Freier, Marcelo | Not Started
HC13
HC14 | 88 (HC 14-01) | Hank Cochran_Records Management | Records Management | MEDIU M - Define the organization in US that will support both companies | Both | TRUE | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-02) | Hank Cochran_Records Management | Records Management | MEDIUM - Tracking system (Jordan Lawrence). If the system will continue for both companies. | Both | TRUE | 2016-06-30 | 180 | 2016-01-02 | 0% | TRUE | Legal & Ethics and Compliance to determine if continue with Jordan Lawrence | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-03) | Hank Cochran_Records Management | Records Management | HIGH - Strategy to separate documents for both companies - according to Legal, recommendation is that records that are truly “corporate” and can’t be split stay with Value-Add | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | TRUE | Legal to provide direction | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X
HC14 | 88 (HC 14-04) | Hank Cochran_Records Management | Records Management | MEDIUM - Confirm if the same ASAT protocols will be applied for both companies | Both | TRUE | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | Audit needs to define the program that will be used in the future to support both companies | Freire, Marcelo Steve Snyder | Not Started | [24 empty] | X
HC14 | 88 (HC 14-05) | Hank Cochran_Records Management | Records Management | LOW - Review scope and SLA for each one of the customers. | Both | TRUE | 2016-06-30 | 180 | 2016-01-02 | 0% | TRUE | Legal and Ethis and Compliance will be involved in the process to validate future SLA and scope | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-06) | Hank Cochran_Records Management | Records Management | LOW - Review procedures to reflect the new reality | Both | TRUE | 2016-02-28 | 60 | 2015-12-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-07) | Hank Cochran_Records Management | Records Management | HIGH - Involve Procurement to negotiate the contracts - separation | Both | TRUE | 2016-06-30 | 180 | 2016-01-02 | 0% | TRUE | Work with procurement on the commerical side of the program | Freire, Marcelo Steve Snyder | Not Started | [10 empty] | X
HC14 | 88 (HC 14-08) | Hank Cochran_Records Management | Records Management | MEDIUM - Define the funding for the program - Corporate for both Companies? | Both | TRUE | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-09) | Hank Cochran_Records Management | Records Management | MEDIUM - Confirm if the retention schedule should be applied for both companies - according to Legal, recommendation is to clone existing Policy, Procedures and (new) Retention Schedules | Both | TRUE | 2016-02-28 | 60 | 2015-12-30 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-10) | Hank Cochran_Records Management | Records Management | MEDIUM - Confirm the strategy for the International Retention Schedules | Both | TRUE | 2016-02-28 | 60 | 2015-12-30 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-11) | Hank Cochran_Records Management | Records Management | HIGH - Work with RUs to ensure they understand that Records Segregation is one of their work streams, and what can and should be done pre-separation | Both | TRUE | 2016-04-30 | 120 | 2016-01-01 | 0% | TRUE | Customers will need to be involved in this review | Freire, Marcelo Steve Snyder | Not Started |  | X | X | X | X | X | X | X |  |  | X | X | X | X |  | X | X | [6 empty] | X |  |  | X
HC14 | 88 (HC 14-12) | Hank Cochran_Records Management | Records Management | HIGH - Set Access Ground Rules for after the Separation | Both | TRUE | 2016-06-30 | 180 | 2016-01-02 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-13) | Hank Cochran_Records Management | Records Management | LOW - Define Steering Team(s) and escalation plans (tax, legal, ethics and compliance) for each company | Both | TRUE | 2016-09-30 | 180 | 2016-04-03 | 0% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | Not Started |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-14) | Hank Cochran_Records Management | Records Management | MEDIUM - Partner with IT regarding guidance and protocols for electronic storage | Both | TRUE | 2016-09-30 | 270 | 2016-01-04 | 0% | TRUE | IT needs to support the process | Freire, Marcelo Steve Snyder | Not Started | [6 empty] | X
HC14 | 88 (HC 14-15) | Hank Cochran_Records Management | Records Management | MEDIUM - Define and implement controls regarding access to data on fileshare, SharePoint, emails, and with vendors | Both | TRUE | 2016-09-30 | 270 | 2016-01-04 | 0% | TRUE | IT needs to support the process | Freire, Marcelo Steve Snyder | Not Started | [6 empty] | X
HC14 | 88 (HC 14-16) | Hank Cochran_Records Management | Records Management | LOW - Create location and custodian listings, as well as standard metrics, for each company | Both | FALSE | 2016-03-31 | 90 | 2016-01-01 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-17) | Hank Cochran_Records Management | Records Management | MEDIUM - Complete to identify the Orphaned Boxes | Both | TRUE | 2016-03-31 | 121 | 2015-12-01 | 89% | TRUE | Legal and Ethis and Compliance will be involved in this definition | Freire, Marcelo Steve Snyder | In progress |  |  |  |  | X | [26 empty] | X | Ethics and Compliance
HC14 | 88 (HC 14-18) | Hank Cochran_Records Management | Records Management | MEDIUM - Communicate the main changes to the customers | Both | TRUE | 2016-06-30 | 61 | 2016-04-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-19) | Hank Cochran_Records Management | Records Management | MEDIUM - Define and start the transition process among the team members | Both | TRUE | 2016-06-30 | 61 | 2016-04-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-20) | Hank Cochran_Records Management | Records Management | LOW - Implement actions to evaluate and measure the productivity for Records Management based on the new reality | Both | TRUE | 2016-06-30 | 61 | 2016-04-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-21) | Hank Cochran_Records Management | Records Management | MEDIUM - Perform an assessment to evaluate risks and opportunities to improve compliance process for Records Management | Both | TRUE | 2016-06-30 | 61 | 2016-04-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-22) | Hank Cochran_Records Management | Records Management | LOW - Involve Steering Group Meeting to evaluate results after the separation | Both | TRUE | 2016-06-30 | 61 | 2016-04-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC14 | 88 (HC 14-23) | Hank Cochran_Records Management | Records Management | LOW - Define the Records Coordinators network after separation | Both | TRUE | 2016-09-30 | 428 | 2015-07-30 | 0% | FALSE | N/A | Freire, Marcelo Steve Snyder | Not Started
HC01 | FSS-HC01-01 | Hank Cochran_Finance | Finance System Support | Create / Update SOPs and Training Documents | Both | FALSE | 2016-03-31 | 75 | 2016-01-16 | 0% | FALSE |  | Ridilla | Not started | In preparation for an organization separation, create/update training documents and SOPs to be use for cross-training and future reference. Also, ensure SharePoint site and Fileshare data will be available for both companies.
HC01 | FSS-HC01-02 | Hank Cochran_Finance | Finance System Support | SharePoint/FileShare strategy | Both | FALSE | 2016-03-31 |  |  | 0% | TRUE | Identify strategy for replication of SharePoint sites/fileshares in order to store documentation and information | IT | Not started | [6 empty] | 2016-03-31
HC01 | FSS-HC01-03 | Hank Cochran_Finance | Finance System Support | Resolve Software Licensing | Both | TRUE | 2016-01-31 |  |  | 0% | TRUE | Procurement and Legal need to negotiate with system providers for licenses, support, etc. for the two separate companies/systems. | Procurement | Not started |  |  |  |  | 2016-01-31 | [5 empty] | 2016-01-31
HC01 | FSS-HC01-04 | Hank Cochran_Finance | Finance System Support | Separation of Cloud Solution Environments | Both | TRUE | 2016-01-31 |  |  | 0% | TRUE | Identify SPAs for Cloud Solutions and, once Procurement/Legal arranges licensing, work with our vendors to create a second environment for the Upstream company. This includes but is not limited to Ariba/Quadrem, Vinimaya, Walmedian, ACS, Standard Register, IQN, IPS, PiLog | GSS, Procurement & COE | Not started | [6 empty] | 2016-01-31 |  | 2016-01-31 |  | 2016-01-31
HC01 | FSS-HC01-05 | Hank Cochran_Finance | Finance System Support | Separation of Data within Systems | Both | TRUE | 2016-04-30 |  |  | 0% | TRUE | Data within our systems which is shared across companies (e.g. POs, Contracts, Assets, Projects, GL Balances, Asset Blue Sheets, etc.) needs to be separated by the process owners to position us for the clone of software. Also, a strategy needs to be established for what to do with existing data (i.e. bleed out or convert). | GSS & Procurement | Not started |  | 2016-04-30 | 2016-04-30 | 2016-04-30 |  | 2016-04-30 | 2016-04-30 |  | 2016-04-30 |  | 2016-04-30 | [6 empty] | 2016-04-30 | [7 empty] | 2016-04-30
HC01 | FSS-HC01-06 | Hank Cochran_Finance | Finance System Support | Shared OU/Inventory Orgs | Both | TRUE | 2016-04-30 |  |  | 0% | TRUE | Define process to move data from one OU/Inventory Org to another for those that share both future companies' data. | Business Units | Not started | [6 empty] | 2016-03-31 |  | 2016-03-31 |  | 2016-03-31 | [20 empty] | 2016-04-30 | BUs, RUs, Canada
HC01 | FSS-HC01-07 | Hank Cochran_Finance | Finance System Support | NON Operating Unit | Both | TRUE | 2016-04-30 |  |  | 0% | TRUE | Define process to move data from the NON operating unit from one of the two future companies. | Procurement | Not started | [8 empty] | 2016-03-31 |  | 2016-03-31 | [20 empty] | 2016-04-30 | BUs, RUs, Canada
HC01 | FSS-HC01-08 | Hank Cochran_Finance | Finance System Support | AR Shared Services Orgs | Both | TRUE | 2016-04-30 |  |  | 0% | FALSE |  | GSS | Not started | Determine a strategy for how to handle the data in the three AR Shared Services Operating Units in EBS | [30 empty] | 2016-04-30 | BUs, RUs, Canada
HC01 | FSS-HC01-09 | Hank Cochran_Finance | Finance System Support | Legal entities and L-Parents | Both | TRUE | 2016-03-31 |  |  | 0% | TRUE | Legal entities and L-Parents need to be established for both companies | Legal | Not started |  | 2016-03-31
HC01 | FSS-HC01-10 | Hank Cochran_Finance | Finance System Support | Establish new Bank Accounts | Both | TRUE | 2016-03-31 |  |  | 0% | TRUE | Establish and configure new AP, AR and SWIFT bank accounts and arrangements/configurations in time for testing so as not to risk rework and retesting. | Treasury | Not started |  |  |  | 2016-03-31 |  |  |  |  | 2016-03-31
HC01 | FSS-HC01-11 | Hank Cochran_Finance | Finance System Support | Intercompany and IICS | Both | TRUE | 2016-03-31 |  |  | 0% | FALSE | Plans need to be made for how Intercompany and IICS will be handled with the new companies and when the intercompany vs. third party designation will be changed in the system. | Finance | Not started |  | 2016-03-31 | 2016-03-31 |  | 2016-03-31
HC01 | FSS-HC01-12 | Hank Cochran_Finance | Finance System Support | Prepare Testing Strategy | Both | FALSE | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Ridilla | Not started | Prepare a Test Plan for each application that ensures adequate testing within GSC, TCS and Alcoans and consider whether or not this can be an opportunity to cross-train resources in the process. Also ensure resource availability for production support to be maintained during the Separation process. | [27 empty] | 2016-03-31
HC01 | FSS-HC01-13 | Hank Cochran_Finance | Finance System Support | Identify System Configuration Changes | Both | FALSE | 2016-03-31 | 75 | 2016-01-16 | 0% | FALSE |  | Ridilla | Not started | Identify configuration changes that will be need to be made in the system once the clone is complete. Examples include links and trusted internet access to external sites (e.g. ACS, PiLog), ship-to address, GL Cross Validations rules, MOAC Setups, Projects OU Structure, etc.
HC01 | FSS-HC01-14 | Hank Cochran_Finance | Finance System Support | Rules of Engagement between OD1 and LD1 | Both | FALSE | 2016-04-30 |  |  | 0% | TRUE | Need to better understand how we will operation on Operational Day 1 so that we can configure the systems properly (e.g. Will Oplinger need approval capability in both companies until LD1?) | Separtion Office | Not started |  | 2016-04-30 |  |  | 2016-04-30
HC01 | FSS-HC01-15 | Hank Cochran_Finance | Finance System Support | IT Code Remediation | Both | TRUE | 2016-03-31 |  |  | 0% | TRUE | GIS needs to identify any company/org-specific coding that should be remediated for the separation. This includes but is not limited to Customer Facing documents/logos, Terms and Conditions, references to instance ids, alcoa.com and AP Check signatures. Also need to understand plan for updating e-mail addresses across the systems when alcoa.com changes to a new domain. | IT | Not started | [6 empty] | 2016-03-31
HC01 | FSS-HC01-16 | Hank Cochran_Finance | Finance System Support | Taxware Software Configuration | Both | FALSE | 2016-03-31 |  |  | 0% | TRUE | Taxware engine needs to be functional and accurate. This includes but is not limited to Direct Pay Permits, Goods and Services Codes and Entity Codes. Also, a sales tax exemption certificate is needed in order to make tax-free purchases of items and services that are taxable. Each company will need its own. This is currently handled by Taxware (Sovos). | Tax & IT | Not started |  |  | 2016-03-31 |  |  |  | 2016-03-31
HC01 | FSS-HC01-17 | Hank Cochran_Finance | Finance System Support | System Interfaces | Both | FALSE | 2016-03-31 |  |  | 0% | TRUE | All system interfaces for Upstream will need to be identified and repointed to the appropriate new environment and interfaces to both companies' systems will need to be tested | IT & GSS | Not started | [6 empty] | 2016-03-31 |  | 2016-03-31 | [22 empty] | 2016-03-31 | BUs and RUs
HC01 | FSS-HC01-18 | Hank Cochran_Finance | Finance System Support | Create new RTP Hierarchies | Both | FALSE | 2016-05-13 | 60 | 2016-03-14 | 0% | TRUE | The new organization structures will need to be finalized in order to populate the new hierarchies | Ridilla | Not started | Due to all of the Organization Changes, new RTP Hierarchies will need to be created in EBS
HC01 | FSS-HC01-19 | Hank Cochran_Finance | Finance System Support | Alcoa-Hosted Systems Ready for Testing | Both | TRUE | 2016-03-01 |  |  | 0% | TRUE | GIS must deliver a test-ready system in enough time to perform "solutions" level testing and remediation before funtional user testing occurs. We are expect 2-3 rounds of such testing. If dependency not fulfilled, there is a risk of not have proper separation of systems or error/omission in the financials, or being unable to transact business across all applications. | GSS, Procurement & COE | Not started | [6 empty] | 2016-03-01 |  | 2016-03-31 |  | 2016-03-31
HC01 | FSS-HC01-20 | Hank Cochran_Finance | Finance System Support | EBS Unit Testing | Both | TRUE | 2016-04-11 | 41 | 2016-03-01 | 0% | FALSE |  | GSS & Procurement | Not started | Test all systems (EBS, non-EBS and hosted) in light with GBS-IS Dev, CRP and UAT timelines | [5 empty] | 2016-03-01
HC01 | FSS-HC01-21 | Hank Cochran_Finance | Finance System Support | EBS CRP Testing | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0% | FALSE |  | GSS & Procurement | Not started | Test all systems (EBS, non-EBS and hosted) in light with GBS-IS Dev, CRP and UAT timelines | [5 empty] | 2016-04-25
HC01 | FSS-HC01-22 | Hank Cochran_Finance | Finance System Support | EBS UAT Testing | Both | TRUE | 2016-07-04 | 35 | 2016-05-30 | 0% | FALSE |  | GSS & Procurement | Not started | Test all systems (EBS, non-EBS and hosted) in light with GBS-IS Dev, CRP and UAT timelines | [5 empty] | 2016-05-30
HC01 | FSS-HC01-23 | Hank Cochran_Finance | Finance System Support | Software Vendor Assistance | Both | FALSE | 2016-03-31 |  |  | 0% | FALSE |  | IT | Not started | Working in conjunction with GIS, we will need prompt resolution of showstopper issues. Vendors include: Oracle, TCS, Sovos, etc. Without critical support from vendors, the overall solution will be jeopardized. | [5 empty] | 2016-03-31
HC01 | FSS-HC01-24 | Hank Cochran_Finance | Finance System Support | Train Future IT Support & Developers | Both | FALSE | 2016-04-30 |  |  | 0% | TRUE | GIS needs to identify our support model for the two companies going forward and ensure personnel are trained to function effectively on OD1. | IT | Not started | [6 empty] | 2016-04-30
HC01 | FSS-HC01-25 | Hank Cochran_Finance | Finance System Support | Global Solution Coordination | Both | FALSE | On-Going |  |  | 0% | FALSE |  | Ridilla | Not started | Need close connection with GSS support and functional counterparts around the world for global solutions.
HC01 | FSS-HC01-26 | Hank Cochran_Finance | Finance System Support | ATC Projects Superuser | Both | FALSE | On-Going |  |  | 0% | FALSE |  | Ridilla | Not started | ATC is a special location which is a Projects superuser, has special processes, and some they orchestrate and maintain themselves. Strong connection will be key, else the solution could be damaged.
HC01 | FSS-HC01-27 | Hank Cochran_Finance | Finance System Support | Identify new Solutions orgs and cross-train personnel | Both | TRUE | 2016-05-13 |  |  | 0% | FALSE |  | Ridilla | Not started | The new Solutions organizations need to be determined and personnel need to be trained so that all applicable solutions can be supported in both new companies. | [7 empty] | 2016-05-13 | [19 empty] | 2016-05-13
HC01 | FSS-HC01-28 | Hank Cochran_Finance | Finance System Support | Develop Cutover Plan | Both | TRUE | 2016-05-13 |  |  | 0% | FALSE |  | GSS, Procurement, COE & IT | Not started | Define Cutover plan for any changes that need to be orchestrated within and across applications (e.g. GL structures/period, concurrent program schedules, configuration changes, Reconciliation process, etc.) | [5 empty] | 2016-05-13 |  | 2016-05-13
HC01 | FSS-HC01-29 | Hank Cochran_Finance | Finance System Support | EBS Archive Instance Strategy | Both | FALSE | 2016-06-30 |  |  | 0% | TRUE | GBS-IS will need to identify and implement a plan for the data currently stored in the EBS Archive Instance | IT | Not started | [6 empty] | 2016-06-30
HC01 | FSS-HC01-30 | Hank Cochran_Finance | Finance System Support | Application Security | Both | FALSE | 2016-05-13 |  |  | 0% | FALSE |  | GSS & IT | Not started | EBS and Non-EBS Application Security will need to be reviewed to ensure (1) individuals can do what they need to and (2) can't do what they should be able to any longer. Also, new owners will need to be identified for shared accounts (e.g. Scheduling Accounts) and we need to ensure that we are SOD-compliant. In addition, LBC Security rules will need to be manipulated (which directly links to Responsbilities). This impacts all applications. | [5 empty] | 2016-05-13 |  | 2016-05-13
HC01 | FSS-HC01-31 | Hank Cochran_Finance | Finance System Support | MOAC Setups | Both | FALSE | 2016-05-13 |  |  | 0% | FALSE |  | GSS & IT | Not started | Review/revise Multi-Org Access setups for new company structures | [7 empty] | 2016-05-13
HC01 | FSS-HC01-32 | Hank Cochran_Finance | Finance System Support | Go Live with New Systems | Both | TRUE | 2016-08-01 |  |  | 0% | TRUE |  | All | Not started | Execute Cutover Plan and go live with New Systems
HC01 | FSS-HC01-33 | Hank Cochran_Finance | Finance System Support | Deactivation Plan / Purge System Data | Both | FALSE | 2016-05-13 |  |  | 0% | TRUE | Determine if there is a legal need to purge data from either/both systems once cloned | GSS, Procurement & IT | Not started | Prepare a plan for deactivating obsolete data within each instance of each application once the clone is complete (to avoid errant data being entered). Potentially consider security controls as an alternative. | [5 empty] | 2016-05-13 |  | 2016-05-13
HC05 | N/A (HC05-01) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on ERP & AR applications solution | Both | TRUE | 2016-01-15 |  | 2015-12-15 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Clone and remediate data? | [5 empty] | 2016-01-15
HC05 | N/A (HC05-02) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on approach for separating/segregating data in the cloned environments | Both | TRUE | 2016-01-30 |  | 2016-01-01 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Will current/open transactions be removed from each respective instance? What about history data? | [5 empty] | 2016-01-15
HC05 | N/A (HC05-03) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on approach for handling archived instance and related transactions at time of separation | Both | TRUE | 2016-01-31 |  | 2016-01-01 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell |  | What is the plan for supporting archived data for both entities at time of separation? | [5 empty] | 2016-01-15
HC05 | N/A (HC05-04) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on approach for handling intercompany transactions at time of separation | Both | TRUE | 2016-01-31 |  | 2016-01-01 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | What is the plan for eliminating intercompany transactions and relationships at time of separation? (POs/Sos/Invoices/etc.) | [5 empty] | 2016-01-15
HC05 | N/A (HC05-05) | Hank Cochran_Finance | Accounts Receivable | Identify and develop test approach for ensuring post-clone processing is restricted to only the respective entity's transactions | Both | TRUE | 2016-02-15 |  | 2016-01-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | What is the plan for excluding the other's transactions during post-separation processing? | [5 empty] | 2016-01-15
HC05 | N/A (HC05-06) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on OTC invoicing solution | Both | TRUE | 2016-02-15 |  | 2016-01-15 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell |  | Will both entities leverage current model? If so, need new contracts with Standard Register along with new interface testing and implementation. | [5 empty] | 2016-01-15
HC05 | N/A (HC05-07) | Hank Cochran_Finance | Accounts Receivable | Validate current AR configurations and OU operating model will support future solution | Both | TRUE | 2016-02-22 |  | 2016-01-15 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Will both entities employ SSAR OU structure? Does upstream have a need for the shared AR OU structure going forward? | [5 empty] | 2016-01-15
HC05 | N/A (HC05-08) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on legal entity names | Both | TRUE | 2016-02-28 |  | 2015-11-01 |  | TRUE | Decision by EC/Legal on new entity name and alignment of existing entities by 2/28/16. | Caldwell/Antli |  | Prerequisite to testing invoice changes and establishing new bank accounts. |  |  |  | 2016-02-28
HC05 | N/A (HC05-09) | Hank Cochran_Finance | Accounts Receivable | Decision on future organization structure & staffing approach | Both | TRUE | 2016-03-31 |  | 2015-12-01 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli |  | Understand organizational direction and develop plan to align AR staffing accordingly. | [7 empty] | 2016-03-31
HC05 | N/A (HC05-10) | Hank Cochran_Finance | Accounts Receivable | Establish/create target systems environment to enable configuration udpates and testing activities | Both | TRUE | 2016-03-31 |  | 2016-01-01 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Replicate EBS environment for all BU and RU groups to perform any configuration changes needed along with full cycle testing activities | [5 empty] | 2016-01-15
HC05 | N/A (HC05-11) | Hank Cochran_Finance | Accounts Receivable | Strategic decision on banking relationships and account structures | Both | TRUE | 2016-03-31 |  | 2015-11-01 |  | TRUE | Decision by Treasury on banking relationships and account structures by 3/31/16. | Caldwell/Antli |  | Will same or different institutions be involved? If different, more testing of payment interfaces will be required. |  |  | 2016-03-31
HC05 | N/A (HC05-12) | Hank Cochran_Finance | Accounts Receivable | Create duplicate EDI environment to support new trading partner arrangements | Both | TRUE | 2016-04-01 |  | 2016-01-01 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Replicate e-commerce environment for all transaction sets and update/modify data setups to reflect new entities/trading partner relationships. | [5 empty] | 2016-01-31
HC05 | N/A (HC05-13) | Hank Cochran_Finance | Accounts Receivable | Configurations - custom processes | Both | TRUE | 2016-04-15 |  | 2016-03-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Final pricing, summary billing, IICS, adjustments, bolt-on parameters, etc. | [5 empty] | 2016-01-31
HC05 | N/A (HC05-14) | Hank Cochran_Finance | Accounts Receivable | Configurations - tax regimes | Both | TRUE | 2016-04-15 |  | 2016-03-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Ensure Taxware in place for US.; EBTax for CA/MX | [5 empty] | 2016-01-31
HC05 | N/A (HC05-15) | Hank Cochran_Finance | Accounts Receivable | Configurations - Trade Management | Both | TRUE | 2016-04-15 |  | 2016-03-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell |  | Replicate and/or modify claim types, routing and approval rules, write-off codes, etc. | [5 empty] | 2016-01-31
HC05 | N/A (HC05-16) | Hank Cochran_Finance | Accounts Receivable | Update and test configurations to enable printing new entity name on invoices | Both | TRUE | 2016-04-15 |  | 2016-03-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Update related setups to enable invoice printing. | [5 empty] | 2016-01-31
HC05 | N/A (HC05-17) | Hank Cochran_Finance | Accounts Receivable | Update and test configurations to enable processing payment data from new bank accounts | Both | TRUE | 2016-04-15 |  | 2016-03-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Create new banks, accounts, payment methods, etc. |  |  | 2016-03-31 |  |  | 2016-01-31
HC05 | N/A (HC05-18) | Hank Cochran_Finance | Accounts Receivable | Obtain guidance on potential changes to current AR securitization programs due to separation | Both | TRUE | 2016-04-15 |  | 2016-01-31 |  | TRUE | Decision by Treasury on banking relationships and account structures by 3/31/16. | Caldwell |  | Determine impact of separation on existing securitization programs as well as evaluate efforts needed to support any new program that may be proposed by Treasury. |  |  | 2016-03-31
HC05 | N/A (HC05-19) | Hank Cochran_Finance | Accounts Receivable | Identify customers of both businesses that will need to be contacted to alert them to processing changes. | Both | FALSE | 2016-04-30 |  | 2016-04-01 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli |  | Identify those customers which buy from both future entities and develop communication process to ensure alignment with future process and transactional flows. | [7 empty] | 2016-03-31
HC05 | N/A (HC05-20) | Hank Cochran_Finance | Accounts Receivable | Develop training and cross-training plan to ensure both organizations have sufficient expertise to sustain operations | Both | FALSE | 2016-04-30 |  | 2016-04-01 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli |  | Identify skillset needs of future organizations and develop training plan to ensure both teams have knowledgable resources for all aspects of processing. | [7 empty] | 2016-03-31
HC05 | N/A (HC05-21) | Hank Cochran_Finance | Accounts Receivable | Establish AR operational approval limits for both entities (adjustments, refunds, etc.) | Both | TRUE | 2016-05-15 |  | 2016-04-30 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli |  | Update AR configurations for operations teams in line with new management guidelines. | [5 empty] | 2016-01-31 |  | 2016-03-31
HC05 | N/A (HC05-22) | Hank Cochran_Finance | Accounts Receivable | Identify destination for replication of key process documentation | Both | TRUE | 2016-05-31 |  | 2016-01-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli |  | Determine new file server structure for storage of replicated and new process documentation. | [5 empty] | 2016-01-31
HC05 | N/A (HC05-23) | Hank Cochran_Finance | Accounts Receivable | Notify customers of new remittance instructions | Both | TRUE | 2016-06-01 |  | 2016-04-30 |  | TRUE | Decision by Treasury on banking relationships and account structures by 3/31/16. | Caldwell/Antli |  | Need to send notices to customers of new remittance guidance 30-60 days in advance of effective date of change. |  |  | 2016-03-31
HC05 | N/A (HC05-24) | Hank Cochran_Finance | Accounts Receivable | Notify shared customers of impact of impending split as it relates to invoicing, payment, and customer service processing. | Both | TRUE | 2016-06-01 |  | 2016-04-30 |  | TRUE | Decision on AR service organization structure by GSS PMO and EC by 3/31/16. | Caldwell/Antli |  | Ned to send alerts to customers of potential, pending changes in invoicing, payment, and customer service/inquiry processes 30-60 days in advance of change. | [7 empty] | 2016-03-31
HC05 | N/A (HC05-25) | Hank Cochran_Finance | Accounts Receivable | Configurations - update customer records to reflect external vs. internal status | Both | TRUE | 2016-07-01 |  | 2016-04-30 |  | TRUE | Identification of impacted intercompany customers by 4/30/16 | Caldwell/Antli |  | Customer master changes needed on both sides. | [7 empty] | 2016-04-30
HC05 | N/A (HC05-26) | Hank Cochran_Finance | Accounts Receivable | Define approach & process for handling post-split activity (cash from customers, etc.). | Both | FALSE | 2016-05-31 |  | 2016-02-15 |  | TRUE | SPMO/Finance decision on transactional data strategy needed by 1/30/16. | Caldwell/Antli | AR Operations | Determine plan and process to ensure cash received from customers by one entity belonging to the other entity is handled appropriately. | 2016-01-30
HC05 | N/A (HC05-27) | Hank Cochran_Finance | Accounts Receivable | Understand approach and develop processes to accommodate 2-month window between OD1 and LD1 | Both | FALSE | 2016-05-31 |  | 2016-02-15 |  | TRUE | SPMO/Finance decision on transactional data strategy needed by 1/30/16. | Caldwell/Antli | AR Operations | Will both entities run entirely separately or can a bleed-out approach be employed? Key considerations are directing cash from customers to proper entity, creation & use of second operations structure (e.g. AR mailbox, staff, etc.) | 2016-01-30
HC05 | N/A (HC05-28) | Hank Cochran_Finance | Accounts Receivable | Identify and assess impact of permanent configuration settings (e.g OU settings, etc.) | Both | FALSE | 2016-03-31 |  | 2016-01-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli | AR configuration & testing | Will desired or required changes in configurations be feasible based on Oracle AR design and current settings | [5 empty] | 2016-01-31
HC05 | N/A (HC05-29) | Hank Cochran_Finance | Accounts Receivable | Identify and assess impact of changes to the alcoa.com domain | Both | FALSE | 2016-03-31 |  | 2016-01-31 |  | TRUE | IT ERP Decision required by 1/15/16; testing schedule to be provided by 1/31/16 | Caldwell/Antli | AR Operations | AR operations will be significantly impacted due to link to receipt of remittance data from customers, AR invoicing, etc. | [5 empty] | 2016-01-31
HC06 | N/A (HC06-01) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Credit Reporting ( D&B, CRM, Elipru) | Both | TRUE | 2015-09-01 | 10 | 2015-07-01 |  | TRUE | Procurement need to work through this to determine how the D&B, CRM contract will be impacted and split at the time of separation. | Helga |  | We need to move current contract fro Alcoa Kofem to the new Value add co, prepare document to follow the entity changes ensuring no distruption in report usuage and history. We need analysze the amount of report needs. For Primary we need a new contract and review if exitsing monitoring services of the year could be pulled in the new user id | [9 empty] | 2016-07-01
HC06 | N/A (HC06-02) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Coface collection agent contract | Both | TRUE | [5 empty] | Procurement need to work through this to determine how the contract will be impacted and split at the time of separation. | Helga |  | Provide list open cases to proc that will be open at the time of separation. | [9 empty] | 2016-07-01
HC06 | N/A (HC06-03) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Delegation of Authorities / Bad Debt approval authorities / | Both | FALSE | 2016-06-30 |  | 2015-04-01 |  |  |  | Cochran/Lintner |  | define responsibilities according to new roles
HC06 | N/A (HC06-04) | Hank Cochran_Credit | Credit (NOA, Europe, China) | charge out re-run model - SLA and charge agreement | Both | [7 empty] | Cochran |  | Request Finance Director to rerun the chargeback model for the new structure.
HC06 | N/A (HC06-05) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Credit Suiss L/C - Treasury | Both | TRUE | 2016-07-31 |  | 2016-01-01 |  |  | Work with Treasury in order to make sure that contract for L/C accounts are transfered /negociated and we have new account for the differnt 2 entities in place | Eli |  |  |  |  | 2016-03-31
HC06 | N/A (HC06-06) | Hank Cochran_Credit | Credit (NOA, Europe, China) | US Bank L/C - Treasury | Both | TRUE | 2016-07-31 |  | 2016-01-01 |  |  | Work with Treasury to identify the new LC advising bank and negotiate agreements | Eisler |  | Currently with US Bank but will depend on core banks for new entity. |  |  | 2016-03-31
HC06 | N/A (HC06-07) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Treasury Bank accounts: 1) Citibank access, 2) new bank accounts when to inform customers | Both | TRUE | 2016-07-31 |  | 2016-01-01 |  |  | work to be done in agreement with Treasury, BU / PLANT, Controllers, IT | Eli |  | be linked with treasury to make sure that our citicard access will remain and that we will be informed on new bank accounts/name changes in a appropriate way. Coordinate with BU's and controller in order to make sure that customer recieves right info on time on where to pay, and that the invoices will report correct bank name and account number for payments |  |  | 2016-03-31 |  |  | 2016-03-31 |  | 2016-03-31
HC06 | N/A (HC06-08) | Hank Cochran_Credit | Credit (NOA, Europe, China) | vendor portal access |  | FALSE | [8 empty] | After the new names are known and being registered we must ensure our Team updates customer vendor portal access to be inlign with the company they represent. Need to create a list of All vendor portals split by Value Add/Upstream or both
HC06 | N/A (HC06-09) | Hank Cochran_Credit | Credit (NOA, Europe, China) | MDM new set up | Both | TRUE | 2016-06-01 |  | 2016-04-01 |  |  | Connect with MDM Team and confirm on the current process if it is a copy past
HC06 | N/A (HC06-10) | Hank Cochran_Credit | Credit (NOA, Europe, China) | receiving BU-Credit Reporting | Both
HC06 | N/A (HC06-11) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Bad debt Tool | Both | TRUE | 2016-06-30 |  |  |  |  | Work with Data center to split tool for the 2 companies | Ben |  | Need to split the 2 companies by LBC, will there new LBC's established or will we use existing ones ? Will names of BU's change ? Check authorisation levels and develop new set of names for approvals (write off etc.). For Kofem, we need to make the split in documentation for the 2 companies (evidence). Advisable is to develop test database with Data center when framework is known for the 2 companies. | [5 empty] | 2016-03-31 |  | 2016-03-31
HC06 | N/A (HC06-12) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Statement Service | Both | TRUE | 2015-05-30 | 12 | 2015-05-01 |  | TRUE | Statement Service while ran by Credit, the macro writing is done by ETC, we need to ensure for both entities there is resouce available to continue to run the service on both ETC and Credit level. | Helga |  | ETC to create 2 control file for both entities in their own Oracle settings Statement team to work with Credit staff and split the communication template, rework the wording of the template including signitures, requesting in both outlook environment a general mailbox set up, ensure there is knowledge in both entities to run the program, have the required legacy access in place for invoice copy | [7 empty] | 2016-03-31
HC06 | N/A (HC06-13) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Global Credit shared folder 1) review what needs to be split other than containder folder 2) container folder - split, | Both | TRUE | 2016-08-01 | 30 | 2016-07-01 |  | FALSE | Identifiy the folder that need to be separated (some are only UP CO other are only V-A CO and some are common) and identify the report that are in it that as well need to be separated | Eli / Caldwell |  | deep dive in the Global credit Europe file move the info that need to be splitted, check and make sure that we are aligned with ETC for having separated report in case of common report saved (work with DSG) | [7 empty] | 2016-03-31
HC06 | N/A (HC06-14) | Hank Cochran_Credit | Credit (NOA, Europe, China) | customer container file | Both | TRUE | 2016-08-31 |  | 2016-01-01 |  |  | check with legal wich kind of info can be copied / reported historical data for both new entities | Eli |  | understand clearly legal position on the transfert of historical data (what will be done behind the scene as comunication to the customers) this work can be done in // of te other 2 tasks |  |  |  | 2016-03-31
HC06 | N/A (HC06-15) | Hank Cochran_Credit | Credit (NOA, Europe, China) | customer container file | Both | TRUE | 2016-08-31 | 60 | 2016-06-01 |  |  | Create new customer container file and copy all customer from Up Co in it (this has to be done in once in order to avoid to miss something.) make sure that from Sep. 1st all data are in 1 specific folder only | Eli |  | see if this can be done inside credit / DSG or we need a student | [7 empty] | 2016-03-31
HC06 | N/A (HC06-16) | Hank Cochran_Credit | Credit (NOA, Europe, China) | customer container file | Both | TRUE | 2016-08-31 |  | 2016-07-01 |  |  | work with DSG to idetify : common customer (same oracle number invoiced by both new cos) and to indetify the CL given on group level that includes both new CO. | Eli |  | work with DSG on lists, review | [7 empty] | 2016-03-31
HC06 | N/A (HC06-17) | Hank Cochran_Credit | Credit (NOA, Europe, China) | ASAT testing, keeping report on Brazil sharedpoint, mailbox, compliance calendar
HC06 | N/A (HC06-18) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Split Global Credit portal | Both | TRUE | 2015-09-01 |  | 2015-08-01 |  | TRUE | Waiting for direction from IT. | Ibolya |  | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | [5 empty] | 2016-01-31
HC06 | N/A (HC06-19) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Legal documents ; bank guarantee, corp guarantee | Both | [9 empty] | Review all legal document and make necessary step to update with new co names
HC06 | N/A (HC06-20) | Hank Cochran_Credit | Credit (NOA, Europe, China) | ERP (Collection Module, order release, customer, account details), Hyperion applications solution. | Both | TRUE | 2016-06-30 |  | 2016-01-01 |  | TRUE | Waiting for direction from IT and EBS Support | Ben |  | Task: UAT/Dev resouces need (vacations)Question to clarify: how many resources are required and to check availability. New set of OU's to establish. Deep authorisation check to be performed by IT / Credit | [5 empty] | 2016-01-31
HC06 | N/A (HC06-21) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Oracle | Both | TRUE | 2016-06-30 |  | 2016-01-01 |  | TRUE | Waiting for direction from IT and EBS Support | Ben / Melissa |  | Are we going to continue with the current collector codes or will we create new process for this as this is used for our Hold order panels as well ? Can we continue to use current customer number(ing) and/or need to setup additional ones for shared customers. Check need for reports running from Discoverer, do we need to create specific reports for the split ? IT / Credit need to look to the authorisation split System/ banking Interfaces testing | [5 empty] | 2016-01-31
HC06 | N/A (HC06-22) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Collection Module | Both | TRUE | 2016-06-30 |  | 2016-01-01 |  | TRUE | Waiting for direction from IT and EBS Support | Ben / Melissa |  | Need to create 2 testing teams for the Oracle collection module. RPC3 testing Aug.2015-Feb. 2016. Do we have resources available to establish another testing team, to be discussed. Is ETC able to continue support for both companies | [5 empty] | 2016-01-31
HC06 | N/A (HC06-23) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Hyperion | Both | TRUE | 2016-06-30 |  | 2016-01-01 |  | TRUE | Waiting for direction from IT and EBS Support | Ben |  | Will both companies make use of Hyperion and would there be a need for specific ones. IT/Credit need to check authorisation as BU's are having access as well. New set of OU's to be established | [5 empty] | 2016-01-31
HC06 | N/A (HC06-24) | Hank Cochran_Credit | Credit (NOA, Europe, China) | System testing | Both
HC06 | N/A (HC06-25) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Alcoa Direct | Both
HC06 | N/A (HC06-26) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Server ? | [10 empty] | need to know destination
HC06 | N/A (HC06-27) | Hank Cochran_Credit | Credit (NOA, Europe, China) | SRMC reporting split
HC06 | N/A (HC06-28) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Split the Credit Location | both | TRUE | 2016-03-30 |  | Jan 15th 2016 |  |  | To determine which Credit Locations remain in scope of Global credit ASAT | Lintner/Caldwell | [9 empty] | 2016-03-31
HC06 | N/A (HC06-29) | Hank Cochran_Credit | Credit (NOA, Europe, China) | to determine and train the ASAT Coordinators | both | TRUE | 2016-04-30 |  | 2016-09-30 |  |  | Suggestion is to have training sessions during the testing cycles each month | Lintner/Caldwell | [9 empty] | 2016-03-31
HC06 | N/A (HC06-30) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Compliance Calendar | both | TRUE | June 30th 2016 |  | May 15th 2016 |  |  | To prepare as normally and split before go live | Lintner/Caldwell | [9 empty] | 2016-03-31
HC06 | N/A (HC06-31) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Sample selection/Evalaution on testing/Access to Brazilian Share Point where test templates are stored. /Global Credit ASAT Mailbox - owner is the SOA COE ASAT Group | both | TRUE | Aug 15th 2016 |  | May 15th 2016 |  |  | Sample selection and testing evaluation is done by SOA COE ASAT for Global Credit testing it should be determined who will perform this task for both companies. To determine where to store data by the time of splitting company. New owner of the Mailbox is to be determined | Lintner/Caldwell | [9 empty] | 2016-03-31
HC06 | N/A (HC06-32) | Hank Cochran_Credit | Credit (NOA, Europe, China) | to check with Internal Audit if there is any new diretion of scheduling Audits | both | TRUE | 2016-03-01 |  | 2016-03-01 |  |  |  | Lintner/Caldwell
HC06 | N/A (HC06-33) | Hank Cochran_Credit | Credit (NOA, Europe, China) | ISDA Negotiation | Up. Co | TRUE | 2016-08-01 | 180 | 2016-02-03 |  | TRUE | Treasurer sets negotiation parameters | Eisler |  | Up Co treasurer needs to set parameters for the new agreements and the trading desks need to ID the brokers they wish to use. |  |  | 2016-03-31
HC06 | N/A (HC06-34) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Transfer Derivitive trading knowledge | Up. Co | FALSE | 2015-08-01 | 14 | 2016-01-01 |  | FALSE |  | Eisler |  | The credit risk will need to be coverd by the other company and currently only Eisler, Cochran and Caldwell have background in this area
HC06 | N/A (HC06-35) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Collateral Security Agreement | Up. Co | FALSE | 2015-08-01 | 14 | 2016-01-01 |  | FALSE |  | Eisler |  | Understanding of the CSA agreements and the market will need to be transferred.
HC06 | N/A (HC06-36) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Transfer Eneergy Trading Knowledge | Up. Co | FALSE | 2015-08-01 | 14 | 2016-01-01 |  | FALSE |  | Eisler |  | Currently Eisler sets credit limits and approves trading activity for Electricity trading activity and NG retail purchases with no backup.
HC06 | N/A (HC06-37) | Hank Cochran_Credit | Credit (NOA, Europe, China) | Treasury Bank accounts: 1) PNC and Mellon access, 2) new bank accounts when to inform customers | Both | TRUE | 2016-07-31 |  | 2016-01-01 |  |  | work to be done in agreement with Treasury and IT | Caldwell |  | Open new accounts for new legal entity and build feeds into the cash application module |  |  | 2016-03-31
HC15 | 89 (HC15-01) | Hank Cochran_EHS | EHS | HIGH - ORG STRUCTURE - Determine how EHS Support resources will be split between companies | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | GBS/GSS/EHS will need to determine how the EHS Support teams will look in the new companies | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | Waiting for direction from GBS/GSS/EHS | [7 empty] | 2016-03-31 |  |  | 2016-03-31
HC15 | 89 (HC15-02) | Hank Cochran_EHS | EHS | HIGH - IT SYSTEMS STRATEGY - Determine how systems will be split between companies. | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | IT will need to determine how the EHS Support systems will look in the new companies | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | Waiting for direction from IT | [5 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31
HC15 | 89 (HC15-03) | Hank Cochran_EHS | EHS | MED - DEVELOP PROCEDURES | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-04-30 |  | 2016-04-30 |  |  | 2016-04-30
HC15 | 89 (HC15-04) | Hank Cochran_EHS | EHS | LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-04-30 |  | 2016-04-30 |  |  | 2016-04-30
HC15 | 89 (HC15-05) | Hank Cochran_EHS | EHS | LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE | 2016-07-31 | 237 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-07-31 |  | 2016-07-31 |  |  | 2016-07-31
HC15 | 89 (HC15-06) | Hank Cochran_EHS | EHS | HIGH - EHS SYSTEMS - Identify which EHS systems (IHS, SEM, OHM, etc.) each company (Upstream or Value Add) will use after the split. | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | GBS/GSS/EHS will need to identify which systems will be used in the new companies. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31
HC15 | 89 (HC15-07) | Hank Cochran_EHS | EHS | HIGH - EHS SYSTEMS - how will upgrades to OHM and Comply Plus be handled? | Both | TRUE | 2016-01-31 | 47 |  | 0% | TRUE | EHS will need to provide plan of moving forward and role GSS plays in supporting these systems. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [11 empty] | 2016-01-31
HC15 | 89 (HC15-08) | Hank Cochran_EHS | EHS | LOW - EHS SYSTEM SUPPORT - how will shared inboxes (IHS Help, EHS Help, etc.) be split - what happens to the archived, historical data? | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | GBS/GSS/EHS will need to determine how support will be done in the new company - split existing inboxes? Create new support structure? Etc. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31
HC15 | 89 (HC15-09) | Hank Cochran_EHS | EHS | MED - IHS REPORTS - Determine how existing custom excel reports will be split. | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | EHS will need to provide plan on how reports will be handled for both companies. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [11 empty] | 2016-03-31
HC15 | 89 (HC15-10) | Hank Cochran_EHS | EHS | MED - QBR PROCESS - Determine how the QBR process will be completed for both companies. Does the process remain the same? | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | EHS will need to provide plan on how the QBR will be generated and provided for both companies. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [11 empty] | 2016-03-31
HC15 | 89 (HC15-11) | Hank Cochran_EHS | EHS | LOW - WELLNESS PROGRAM - Identify which company (Upstream or Value Add) will use the current Wellness program(s). | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | GBS/GSS/EHS/Wellness will need to identify which programs both new companies will continue to complete and the role GSS plays for analyses. | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31
HC15 | 89 (HC15-12) | Hank Cochran_EHS | EHS | MED - WELLNESS PROGRAM - Determine how Wellness programs (GCC, PROCAM, Lighten Up, etc.) historical analyses are split. | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | GBS/GSS/EHS/Wellness will need to decide how historical data will be split for future analsyes. Will both companies be required to view all historical data for trending purposes? | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson | Not started | [6 empty] | 2016-03-31 |  | 2016-03-31 |  |  | 2016-03-31
HC12 | 84 (HC12-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE | 2015-12-31 | 27 |  | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, Natalie Thomas | In progress | Waiting for direction from Plan Design |  |  |  |  | 2015-12-31
HC12 | 84 (HC12-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | Waiting for direction from GBS/GSS | [7 empty] | 2016-03-31
HC12 | 84 (HC12-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Determine how the benefit plans will be split. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | Waiting for direction from Plan Design, Legal and Tax. |  | 2015-12-31 |  | 2015-12-31 | 2015-12-31
HC12 | 84 (HC12-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, BNY Mellon, Buck Consulting, Buck Suriname, Millenium Trust, Aetna, etc. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | Waiting for direction from Procurement and Legal. | [9 empty] | 2015-12-31
HC12 | 84 (HC12-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | MED - Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2015-12-31 | 2015-12-31 | [25 empty] | 2015-12-31 | Industrial Relations
HC12 | 84 (HC12-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | Waiting for direction from IT. | [5 empty] | 2015-12-31
HC12 | 84 (HC12-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | MED - DEVELOP PROCEDURES | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | [8 empty] | 2016-04-30
HC12 | 84 (HC12-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | [8 empty] | 2016-04-30
HC12 | 84 (HC12-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE | 2016-07-31 | 237 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started | [8 empty] | 2016-07-31
HC12 | 84 (HC12-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | MED - DB Claims/Appeals - Process needs to be split and training is needed. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Month End Funding (pension payroll), Off Cycles, and MetLife funding - Process will need to be done at Upstream and Value Add companies. Training needed. Access needs to be granted to additional analyst to BNY Mellon Work Bench site, reports, contacts. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, BNY Mellon, Alcoa Legal to sign/review contracts for additional business, Upper Management Signatures needed for any additional signature cards and contracts, and Treasury Department | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - PwC Audit - Independent annual audit requirement that outside auditors review plan procedures, payments, documents, calculations, etcetera. Works closely with DB and Benefits Accounting. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits and Benefits Accounting (DB works very closely with Benefits Accounting during audit and the relationship is very dependent) | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - Monthly and Annual Overpayment Processes. IRS requires some process to reimburse the Trust accounts for uncollectible pension amounts paid to participants in error. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, Aon Hewitt, Alcoa Legal, Benefit Appeals Committee (Aon Hewitt sends files to DB, DB reviews and sends data to Alcoa Legal, annual uncollectibles go to BAC for decisions). | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - Suriname is a major part of month end funding. If the company goes with the Upstream or Value Add, the entire month end funding process will have to be changed. Also, process to reissue pension payment returns/rejects. |  | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, Benefits Accounting, BNY Mellon, Buck Suriname. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - Data Dump - Aon Hewitt sends updated participant data feed to DB Admin monthly. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Aon Hewitt and Defined Benefits. Aon Hewitt will need to send data to both companies. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Disability Pension Process - Before participants can go on disability retirement need to go through the process for approval with Aetna and Aon Hewitt. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, Aon Hewitt, and Aetna. Aon Hewitt is the gatekeeper and Aetna determines the medical approvals or denials. DB handles additional level of appeal for denials. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Trust Accounts will need to be split between companies and not just based on the cash value, but also will need new accounts (Holding accounts, General asset account, disbursement accounts, non-qualified account), at BNY Mellon and new signature cards and signers at the new company Treasury department and Human Resource signer. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, BNY Mellon, Alcoa Legal to sign/review contracts for additional business, Upper Management Signatures needed for any additional signature cards and contracts, and Treasury Department | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | MED - Valid Values/Plan Mapping - When there are new locations, Ben Admin receives notification to determine impacts on beenfits. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Benefits Administration (all 3 services), Defined Benefits, HRMS | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, Aetna, Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Vendor Data Feeds - Data is passed from USBS and Alcoa locations to update participant records on a daily basis. Aon Hewitt also provides Actuarial Valuation files to Buck/Xerox Consultants for active, DV, and retiree data. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | USBS, Company Locations, Aon Hewitt, Buck/Xerox Consultants-participant changes and updates are submitted to Aon Hewitt nightly through a system feed from USBS and from Co Locations | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | LOW - BRM/Richmond Pension Files - Will these files need to be split by Value Add vs. Upstream? Users at either company will need to have authorization to request files. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Benefits, Global Records Mgt, BRM | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started
HC12 | 84 (HC12-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DB | HIGH - Plan Documents, SPD's, Requirements, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Angela Lowry, Joseph Adamietz, Natalie Thomas | Not started |  |  |  |  | 2016-02-29 | 2016-02-29
HC19 | N/A (HC19-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE | 2015-12-31 | 27 |  | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | In progress | Waiting for direction from Plan Design |  |  |  |  | 2015-12-31
HC19 | N/A (HC19-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from GBS/GSS | [7 empty] | 2016-03-31
HC19 | N/A (HC19-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - Determine how the benefit plans will be split. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from Plan Design, Legal and Tax. |  | 2015-12-31 |  | 2015-12-31 | 2015-12-31
HC19 | N/A (HC19-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, Truven Analytics, Solenture, Benefit Wallet, Highmark, Caremark, UCCI, Davis Vision, MetLife, Aetna, etc. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from Procurement and Legal. | [9 empty] | 2015-12-31
HC19 | N/A (HC19-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | MED - There is one union for the 4/1/16 enrollment - Kingston NY. They went thru negotiations in November. There is one union negotiating in 2016 and it is for Chandler, AZ. Hampton may be ready in 2016, but unsure. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2015-12-31 | 2015-12-31 | [25 empty] | 2015-12-31 | Industrial Relations
HC19 | N/A (HC19-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from IT. | [5 empty] | 2015-12-31
HC19 | N/A (HC19-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | MED - What will be done with the 2017 Annual Enrollment? | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Plan Design (HR), GBS/GSS and Legal need to work through this to determine how how 2017 Annual Enrollment needs to be executed by the different companies. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from Plan Design, Legal and Tax. |  | 2015-12-31 |  | 2015-12-31 | 2015-12-31
HC19 | N/A (HC19-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | MED - DEVELOP PROCEDURES | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | [8 empty] | 2016-04-30
HC19 | N/A (HC19-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | [8 empty] | 2016-04-30
HC19 | N/A (HC19-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE | 2016-07-31 | 237 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | [8 empty] | 2016-07-31
HC19 | N/A (HC19-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - VENDOR FEEDS | Both | TRUE | 2016-01-31 | 147 |  | 0% | TRUE | Will need to be set up for medical (Highmark), Rx (Caremark), dental (UCCI), vision (Davis), life (MetLife), disability (Aetna), AD&D (MetLife), tuition (GP), HMOs, HSA (Benefit Wallet), analytics (Truven), etc. Decisions to be made by Plan Design (HR) | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from Plan Design
HC19 | N/A (HC19-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - PAYROLL DEDUCTION FEEDS | Both | TRUE | 2016-01-31 | 147 |  | 0% | TRUE | Will need to be established for payroll deduction codes. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started | Waiting for direction from Plan Design
HC19 | N/A (HC19-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - INTERNAL WEB SITES | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE | MyAlcoabenefits.com website and HR SharePoint websites will need to be updated/split for the two companies. Decisions to be made by HR and IT | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | MED - ONEEXCHANGE | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE | Retirees and future retirees will need to be splt between the two companies. This also effects feeds from Hewitt to OneExchange (Towers Watson) which are sent monthly. Also, Account Administration will need to be set up for both companies. Decisions needed by HR as to which company the retirees will go. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - SURVIVING SPOUSE PAYMENTS | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE | Typically done in last month of the year. Will need to be set up for both companies with Hewitt. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - DOMESTIC PARTNER SOLICITATION | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE | Typically done in 3rd/4th quarter. Will need to be set up for both companies with Hewitt. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - MEDICARE PART B PROJECT | Both | TRUE | 2016-07-31 |  |  | 0% | TRUE | This kicks off in February. But, retirees could be in separate company at the end of the year when project ends. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - ELIGIBILITY RECORDS | Both | TRUE | 2016-03-31 |  |  | 0% | TRUE | Will both companies have history of employees in TBA? | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | HIGH - Plan Documents, SPD's, Requirements, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started |  |  |  |  | 2016-02-29 | 2016-02-29
HC19 | N/A (HC19-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - Data Dump - Aon Hewitt sends updated participant data feed to HW Admin monthly. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Aon Hewitt and Health & Welfare. Aon Hewitt will need to send data to both companies. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC19 | N/A (HC19-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - HW | LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | H&W, Truven and Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Kathleen Viazanko | Not started
HC21 | N/A (HC21-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE | 2015-12-31 | 27 |  | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, David Carozza | In progress | Waiting for direction from Plan Design |  |  |  |  | 2015-12-31
HC21 | N/A (HC21-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting for direction from GBS/GSS | [7 empty] | 2016-03-31
HC21 | N/A (HC21-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - Determine how the benefit plans will be split. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting for direction from Plan Design, Legal and Tax. |  | 2015-12-31 |  | 2015-12-31 | 2015-12-31
HC21 | N/A (HC21-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, BNY Mellon, Millenium Trust, Aon Financial Advisors, Solenture, etc. | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting for direction from Procurement and Legal. | [9 empty] | 2015-12-31
HC21 | N/A (HC21-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | MED - Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2015-12-31 | 2015-12-31 | [25 empty] | 2015-12-31 | Industrial Relations
HC21 | N/A (HC21-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting for direction from IT. | [5 empty] | 2015-12-31
HC21 | N/A (HC21-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | MED - DEVELOP PROCEDURES | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, David Carozza | Not started | [8 empty] | 2016-04-30
HC21 | N/A (HC21-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, David Carozza | Not started | [8 empty] | 2016-04-30
HC21 | N/A (HC21-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE | 2016-07-31 | 237 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, David Carozza | Not started | [8 empty] | 2016-07-31
HC21 | N/A (HC21-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - AON FEED TO BNY MELLON | BOTH | TRUE | 2016-04-30 | 147 |  | 0% | FALSE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | Not started | need to know what the plans will look like prior to creating a feed between Aon and BNY Mellon
HC21 | N/A (HC21-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - AON FEED TO MILLENNIUM TRUST | BOTH | TRUE | 2016-07-31 | 237 |  | 0% | FALSE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | Not started | need to know what the plans will look like prior to creating a feed between Aon and Millennium Trust
HC21 | N/A (HC21-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - BNY MELLON FEED TO MILLENNIUM TRUST | BOTH | TRUE | 2016-07-31 | 237 |  | 0% | FALSE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | Not started | need to know what the plans will look like prior to creating a feed between BNY Mellon and Millennium Trust
HC21 | N/A (HC21-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - FUND LINEUP FOR BOTH PLANS | BOTH | TRUE | 2016-03-31 | 118 |  | 0% | FALSE | Fund lineup will be identical for both plans, however, the new plan will need all the funds establsihed. Waiting for BMC approval | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting on Confirmation on Fund Lineups from BMC
HC21 | N/A (HC21-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - WRAP CONTRACTS SET UP FOR BOTH PLANS | BOTH | TRUE | 2016-03-31 | 118 |  | 0% | FALSE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting on Confirmation on Fund Lineups from BMC
HC21 | N/A (HC21-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - BASIS POINT FEE ANALYSIS | BOTH | TRUE | 2016-04-30 | 147 |  | 0% | FALSE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting on projected Plan Cost Analysis Associated with Fund Lineup
HC21 | N/A (HC21-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - CREATE DEFERRED COMPENSATION PLAN AND DISTRIBUTION OPTION ELECTIONS FOR BOTH PLANs | BOTH | TRUE | 2016-03-31 | 118 |  | 0% | FALSE | Waiting on Determination from Plan Design | Angela Lowry, Joseph Adamietz, David Carozza | Not started | Waiting on Determination from Plan Design
HC21 | N/A (HC21-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | HIGH - Plan Documents, SPD's, Requirements, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | We will need to work with Plan Design and legal to ensure both companies benefit plans have the completed and accurate plan document, requirements, SPD's, etc. in place. | Angela Lowry, Joseph Adamietz, David Carozza | Not started |  |  |  |  | 2016-02-29 | 2016-02-29
HC21 | N/A (HC21-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | LOW - Data Dump - Aon Hewitt sends updated participant data feed to DC Admin monthly. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Aon Hewitt and Defined Contributions. Aon Hewitt will need to send data to both companies. | Angela Lowry, Joseph Adamietz, David Carozza | Not started
HC21 | N/A (HC21-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - DC | LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Defined Contributions and Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, David Carozza | Not started
HC22 | N/A (HC22-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE | 2015-12-31 | 27 |  | 20% | TRUE | Plan Design (HR) is working through this to determine where each companies impacted employees/retirees will go. This is necessary to split benefits when the companies split. | Angela Lowry, Joseph Adamietz, Karen Heuber | In progress | Waiting for direction from Plan Design |  |  |  |  | 2015-12-31
HC22 | N/A (HC22-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | Waiting for direction from GBS/GSS | [7 empty] | 2016-03-31
HC22 | N/A (HC22-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - Determine how the benefit plans will be split. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | Waiting for direction from Plan Design, Legal and Tax. |  | 2015-12-31 |  | 2015-12-31 | 2015-12-31
HC22 | N/A (HC22-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: Aon Hewitt, Solenture, etc. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | Waiting for direction from Procurement and Legal. | [9 empty] | 2015-12-31
HC22 | N/A (HC22-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2015-12-31 | 2015-12-31 | [25 empty] | 2015-12-31 | Industrial Relations
HC22 | N/A (HC22-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | IT needs to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | Waiting for direction from IT. | [5 empty] | 2015-12-31
HC22 | N/A (HC22-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - DEVELOP PROCEDURES | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | [8 empty] | 2016-04-30
HC22 | N/A (HC22-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | [8 empty] | 2016-04-30
HC22 | N/A (HC22-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE | 2016-07-31 | 237 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started | [8 empty] | 2016-07-31
HC22 | N/A (HC22-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - ISSUE TRACKING SYSTEMS (SIEBEL AND REMEDY)- how will access to information be shared between the companies? Seems as though the sytems will need to be duplicated. | Both | TRUE | 2016-01-31 |  |  | 0% | TRUE | IT and Hewitt will need to work thorugh how access will be granted and issues will be stored in the future | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - CUSTOMER SERVICE CENTERS - how will dedicated cernters be handled. Will both companies have access to same customer service centers? | Both | TRUE | 2016-01-31 |  |  | 0% | TRUE | Once centers have been created, IT may need to be involved with arrangeing access | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - REVIEW AND ACCESS TO BENEFITS COMMUNICATIONS - will need to be able to access historic documentation including enrollment guides, SPDs, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Plan Design, Legal and Benefits Communiation | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | LOW - CALL CALIBRATIONS - will need to coordinate with vendors to ensure that company-specific calls are provided to persons responsible for review | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Plan Design and vendors. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - ACCESS TO POAs, QDROs and QMCSOs - how will this information be shared? Will one company own theinformation and the other have to reach out to get what is needed? | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Hewitt | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | LOW - ADOPTION ASSISTANCE, EXECUTIVE LIFE INSURANCE PROCESSES | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Payroll | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-16) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - EXPAT BENEFIT ADMINISTRATION | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Global Mobility and Plan Design | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-17) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - HIPAA PROCESS | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent upon Plan Design | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-18) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - SOLENTURE SERVICES - Will Solenture handle benefits for both Company's Execs? | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Plan Design | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-19) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | MED - LAW SUITS/GRIEVENCES/ARBITRATION CASES - how and where will this information be stored? | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Legal | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-20) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | LOW - JOINT HEALTH CARE MTGS - who will handle facilitation of these required meetings? | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Legal and IR | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-21) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | HIGH - APPEALS COMMITTEE | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Dependent on Legal | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC22 | N/A (HC22-22) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Benefits Admin Customer Service | LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | Customer Service and Aon Hewitt. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Karen Heuber | Not started
HC20 | N/A (HC20-01) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Identify which company (Upstream or Value Add) each person with a curent or future benefit in TBA will go to. There are 111,000+ employees and retirees who are receiving a current benefit or entitled to a future benefit. | Both | TRUE | 2015-12-31 | 27 |  | 20% | TRUE | This is necessary to split benefits when the companies split. This will determined based on decisions made by Plan Design (HR) as to which company employees will go. | Angela Lowry, Joseph Adamietz, Paula Bustinger | In progress | Waiting for direction from Plan Design |  |  |  |  | 2015-12-31
HC20 | N/A (HC20-02) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - ORG STRUCTURE - Identify the Benefits Administration Team for each new company (Upstream or Value Add). | Both | TRUE | 2016-03-31 | 118 |  | 0% | TRUE | This will be determined by GBS/GSS and is necessary to maintain current benefit plans, so that there is no disruption of service and that all new plans are compliant with the law. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | Waiting for direction from GBS/GSS | [7 empty] | 2016-03-31
HC20 | N/A (HC20-03) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Determine how the benefit plans will be split. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Plan Design (HR), Legal and Tax need to work through this to determine how each benefit plan will be split at the time of separation. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | Waiting for direction from Plan Design, Legal and Tax. |  | 2015-12-31 |  | 2015-12-31 | 2015-12-31
HC20 | N/A (HC20-04) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - PROCUREMENT CONTRACT STRATEGY - What will be done with vendor contracts? | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Procurement and Legal need to work through this to determine how each benefit plan vendor contract will be impacted and split at the time of separation. These vendors include the following: GP Strategies, etc. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | Waiting for direction from Procurement and Legal. | [9 empty] | 2015-12-31
HC20 | N/A (HC20-05) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | MED - Will there be any impact due to union negotiations? Two unions will be negotiating next year with a 4/1/2016 benefits enrollment date. | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | Industrial Relations, Legal and Plan Design (HR) is working through this to determine how each benefit plan union contract will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | Waiting for direction from Industrial Relations, Legal and Plan Design. |  |  |  | 2015-12-31 | 2015-12-31 | [25 empty] | 2015-12-31 | Industrial Relations
HC20 | N/A (HC20-06) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - IT SYSTEM STRATEGY - What will be done with the GPS Portal and the link to UPoint? Also, questions surrounding Single Sign-on need to be addressed. Also will need to know how systems will be separated, including the daily file from Oracle HR to TBA (Hewitt). | Both | TRUE | 2015-12-31 | 27 |  | 0% | TRUE | IT and GP Strategies need to work through this to determine how each portal, link, connection, etc. will be impacted and split at the time of separation. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | Waiting for direction from IT. | [5 empty] | 2015-12-31
HC20 | N/A (HC20-07) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | MED - DEVELOP PROCEDURES | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | [8 empty] | 2016-04-30
HC20 | N/A (HC20-08) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | LOW - DEVELOP TRAINING DOCUMENTS | Both | TRUE | 2016-04-30 | 147 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | [8 empty] | 2016-04-30
HC20 | N/A (HC20-09) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | LOW - COMPLETE KNOWLEDGE TRANSFER | Both | TRUE | 2016-07-31 | 237 |  | 0% | FALSE |  | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started | [8 empty] | 2016-07-31
HC20 | N/A (HC20-10) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Funding for courses. | Both | TRUE | 2016-03-31 |  |  |  |  | Funding for courses. GP sends a bi-weekly file requesting funds to pay tuition to the schools. Will need to know how to separate and charge back appropriately. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started
HC20 | N/A (HC20-11) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Payroll deductions. | Both |  | 2016-03-31 |  |  |  |  | Payroll deductions. When an ee has courses that are taxable or they did not get the required grade for reimbursement, a file is sent by GP to payroll. These files would need to be split depending on which company the employee works for. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started
HC20 | N/A (HC20-12) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Approval matrix. | Both |  | 2016-03-31 |  |  |  |  | There is an approval matrix that is used to route applications, and most businesses have 4 levels of approval for tuition applications. Will the approval structure remain the same, and if so, it would need to be determined who would be in the approval chain based on the new management structures. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started
HC20 | N/A (HC20-13) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Repayment terms | Both |  | 2016-03-31 |  |  |  |  | There are repayment terms if an employee leaves the company. Will this be the same for both companies. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started
HC20 | N/A (HC20-14) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | HIGH - Hewitt sends a weekly demographic feed to GP | Both |  | 2016-03-31 |  |  |  |  | Hewitt sends a weekly demographic feed to GP which identifies employees who are eligible to particpate in the tuition plan. This file will need to be separated. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started
HC20 | N/A (HC20-15) | Hank Cochran_HR_Benefits, Payroll, T&A | Benefits Admin - Tuition Assistance | LOW - Quarterly ASATS - audit completed to insure that DB has processes in place regarding controls, fraud, etc. | Both | TRUE | 2016-02-29 |  |  | 0% | TRUE | GP Strategies and H&W. Data is gathered from these groups to ensure that processes and requirements are working as they should be. | Angela Lowry, Joseph Adamietz, Paula Bustinger | Not started
HC09 | N/A (HC09-01) | Hank Cochran_HR_Other | Global Mobility | HIGH - Identify the Global Mobility team members for each company | Both | TRUE | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | Level 2 Management needs to determine split between Value-Add and Upstream | Lowry, McCleary | Not Started | Waiting for split determination | [7 empty] | X
HC09 | N/A (HC09-02) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Obtain the new accounting structure for both entities and ensure that these structures are set up properly in the all vendors sytems for which information is transferred (i.e. Weichert, Fragomen, Suddath, Deloitte, Celergo, Nuss, Santa Fe) | Both | TRUE | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | Tax and Accounting | Lowry, McCleary | Not Started |  | X | X | [5 empty] | X
HC09 | N/A (HC09-03) | Hank Cochran_HR_Other | Global Mobility | LOW - Duplicate the Global Mobility Share Drive, Outook Mailbox, Archives, Sharepoint for both FAS access and outside vendor access, | Both | FALSE | 2016-10-01 | 60 | 2016-08-02 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [6 empty] | X |  | X
HC09 | N/A (HC09-04) | Hank Cochran_HR_Other | Global Mobility | MEDIUM: Amend both the domestic and International repayment agreements to specify the separate organizations. Amend the international Letters of Understanding (LOUs) to specify the separate organizations. Amend any Tax Secondment agreements. | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started |  |  | X |  | X |  |  |  | X
HC09 | N/A (HC09-05) | Hank Cochran_HR_Other | Global Mobility | MEDIUM: Clone the existing 4 domestic and 6 international policies. As part of the cloning/revisions the additional 3 Primary Ma'aden specific policies will need to be amended to reflect Upsteam only. | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC09 | N/A (HC09-06) | Hank Cochran_HR_Other | Global Mobility | LOW - Reveiow scope and SLA for each entity | Both | FALSE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL BUs
HC09 | N/A (HC09-07) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Transfer of relocation specific knowledge, transfer or create training documents, transfer and/or revise SOPs | Both | TRUE | 2016-10-01 | 150 | 2016-05-04 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC09 | N/A (HC09-08) | Hank Cochran_HR_Other | Global Mobility | LOW - Configure International SOS feeds for expats | Both | FALSE | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC09 | N/A (HC09-09) | Hank Cochran_HR_Other | Global Mobility | LOW - Clone all ASAT testing documents and determine to which entity historical information will be transferred to. | Both | FALSE | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC09 | N/A (HC09-10) | Hank Cochran_HR_Other | Global Mobility | HIGH - Identify which company, Upstream or Value-Add, each relocating employee record will be transferred to, including historical records | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL GROUPS
HC09 | N/A (HC09-11) | Hank Cochran_HR_Other | Global Mobility | HIGH - Clone all Weichert systems for both international and domestic relocating employees including the MyWin relocation tracking system , the comp and benefits system, host expense reporting, expense management system and others | Both | TRUE | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | WEICHERT
HC09 | N/A (HC09-12) | Hank Cochran_HR_Other | Global Mobility | HIGH - Identify remaining accruals for active relocations to determine which entity, Upstream or Value-Add, will need to recognize the liabllity (Deloitte, Fragomen, Weichert, Celergo, etc.) | Both | TRUE | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL OUTSIDE VENDORS
HC09 | N/A (HC09-13) | Hank Cochran_HR_Other | Global Mobility | HIGH - Proper allocation of ledger accounts to either Upstream or Value-Add. Domestically, this would be focused around mortage and equity for home sales and any properties in inventory. On the international side, this would primarily focus on tax equalization payments or receipts. | Both | TRUE | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started |  | X | [6 empty] | X | [22 empty] | X | DELOITTE AND WEICHERT
HC09 | N/A (HC09-14) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Determine appropriate process for payment of Weichert invoices ($50-$60M), along with appropriate process for funding multiple payroll via Celergo. | Both | TRUE | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE | N/A | Lowry, McCleary | Not Started |  | X |  | X |  |  |  |  | X | [22 empty] | X | ALL OUTSIDE VENDORS
HC09 | N/A (HC09-15) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - For Celergo, Fragomen and Deloitte, determine under which company the record will be assigned to. | Both | TRUE | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | ALL OUTSIDE VENDORS
HC09 | N/A (HC09-16) | Hank Cochran_HR_Other | Global Mobility | HIGH - Will need to clone all home / host / cash payroll feeds through Celergo | Both | TRUE | 2015-04-30 | 60 | 2015-03-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | CELERGO
HC09 | N/A (HC09-17) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Document proceedure(s) for filing of tax returns that will take place after the sparation. Will need to work with Deloitte on this. | Both | TRUE | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | DELOITTE
HC09 | N/A (HC09-18) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Update / Change / or Revise login details specific to the Celergo payroll system to esure all employees maintain access to their payroll information under only ONE company. | Both | TRUE | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | CELERGO
HC09 | N/A (HC09-19) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Evaluate opportunities for transfer of work to KOFEM | Both | TRUE | 2016-10-01 | 200 | 2016-03-15 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC09 | N/A (HC09-20) | Hank Cochran_HR_Other | Global Mobility | HIGH - IT system strategy for Global People Systems (GPS), server space, computers, general eldger, telephones, VPN, etc. | Both | TRUE | 2016-01-31 | 21 | 2016-01-10 | 0% | TRUE | This will be determined by GSS/IS and the BU. | Lowry, McCleary | Not Started | Waiting for decision on the HR application solution - includes portal pages, GPS, GL, Outlook, Share Drives etc. | [5 empty] | X
HC09 | N/A (HC09-21) | Hank Cochran_HR_Other | Global Mobility | HIGH - Procurement contract strategy for all vendors | Both | TRUE | 2016-01-31 | 52 | 2015-12-10 | 0% | TRUE | Assumption - no changes in 3rd party vendors. Dependencies relate to vendor feeds from GPS, Payroll, and funding sources. | Lowry, McCleary | Not Started | Waiting for procurement to provide assistance |  |  | X |  |  | X |  |  |  | X
HC09 | N/A (HC09-22) | Hank Cochran_HR_Other | Global Mobility | MEDIUM - Key Partner Summit to identify and review deliverables and develop detailed implementation plans | Both | TRUE | 2016-02-15 | 60 | 2015-12-17 | 0% | TRUE | Dependent upon determinations made for IT Systems and Procurement | Lowry, McCleary | Not Started | IT and Procurement decisions need to be made in order to structure the summit discussion and determine next steps |  |  | X |  |  | X |  |  |  | X
HC09 | N/A (HC09-23) | Hank Cochran_HR_Other | Global Mobility | HIGH - Global Visa Determinations for Upstream vs. Value-Add with recommendations and action plans for finalization of compliance with each country's immigration requirements | Both | TRUE | 2016-01-31 | 52 | 2015-12-10 | 0% | TRUE | Level 2 Management, Legal, HR. BU Level decision making | Lowry, McCleary | Not Started | Critical decision to ensure onging employment - post-separation |  |  |  | X | X | [25 empty] | X | Fragomen and all Business Units
HC07 | 80 - (HC07-01) | Hank Cochran_HR_Other | T&E | HIGH - Hewitt payroll splits between companies and all associated functionalities will need to be known. | Both | TRUE | 2015-05-31 | 30 | 2015-05-01 | 0% | TRUE | Dependent upon local payroll determinations which will impact how we proceed | Lowry, McCleary | Not Started | Critical to ensure cash reimbursments are set up properly | [7 empty] | X | [22 empty] | 2016-01-31
HC07 | 80 - (HC07-02) | Hank Cochran_HR_Other | T&E | HIGH - Identify the T&E team members for each company | Both | TRUE | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | Level 2 Management needs to determine split between Value-Add and Upstream | Lowry, McCleary | Not Started | Waiting for split determination - must include Hungary support group | [7 empty] | X
HC07 | 80 - (HC07-03) | Hank Cochran_HR_Other | T&E | MEDIUM - Obtain the new accounting structure for both entities and ensure that these structures are set up properly in the all vendors sytems for which information is transferred (i.e. Concur, Citibank, American Express) | Both | TRUE | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | Tax and Accounting | Lowry, McCleary | Not Started |  | X | X | [5 empty] | X
HC07 | 80 - (HC07-04) | Hank Cochran_HR_Other | T&E | LOW - Duplicate the T&E Share Drive, Outook Mailbox, Archives, Sharepoint, | Both | TRUE | 2016-10-01 | 90 | 2016-07-03 | 0% | FALSE | N/A | Lowry, McCleary | Not started | [6 empty] | X |  | X
HC07 | 80 - (HC07-05) | Hank Cochran_HR_Other | T&E | MEDIUM: Clone the existing T&E and LVPl policies. | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-06) | Hank Cochran_HR_Other | T&E | LOW - Reveiow scope and SLA for each entity | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-07) | Hank Cochran_HR_Other | T&E | MEDIUM - Transfer of specified T&E knowledge, transfer or create training documents, transfer and/or revise SOPs | Both | TRUE | 2016-10-01 | 150 | 2016-05-04 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-08) | Hank Cochran_HR_Other | T&E | LOW - Clone all ASAT testing documents and determine to which entity historical information will be transferred to. | Both | TRUE | 2016-10-01 | 30 | 2016-09-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-09) | Hank Cochran_HR_Other | T&E | HIGH - Identify which company, Upstream or Value-Add, each employee record will be transferred to, including historical records | Both | TRUE | 2016-03-31 | 90 | 2016-01-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X
HC07 | 80 - (HC07-10) | Hank Cochran_HR_Other | T&E | HIGH - Clone Concur travel and expense systems | Both | TRUE | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X
HC07 | 80 - (HC07-11) | Hank Cochran_HR_Other | T&E | MEDIUM - Update / Change / or Revise login details specific to the Concur system | Both | TRUE | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X
HC07 | 80 - (HC07-12) | Hank Cochran_HR_Other | T&E | HIGH - Reconcile all open accounts and distribute appropriate communications for next steps to the employees for account clean-up | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X
HC07 | 80 - (HC07-13) | Hank Cochran_HR_Other | T&E | HIGH - Review automated and standardized reporting to determine necessity and any potential revisions dependent upon the separation; including any changes in email addresses | Both | TRUE | 2016-08-01 | 120 | 2016-04-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X | [22 empty] | X | CONCUR
HC07 | 80 - (HC07-14) | Hank Cochran_HR_Other | T&E | MEDIUM - For Concur, Citibank, and American Express, determine under which company the record will be assigned to. | Both | TRUE | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | Concur is the expense system so the accounts and any changes in Supervisory approval will need to be captured. Citiback issues the credit cards so the proper entity and acocunting codes will need to be determined. AMEX relates to the travel profile and appropriate credit card set ups. Waiting for split determination | [7 empty] | X | [22 empty] | X
HC07 | 80 - (HC07-15) | Hank Cochran_HR_Other | T&E | MEDIUM - Evaluate opportunities for transfer of work to KOFEM | Both | TRUE | 2016-10-01 | 200 | 2016-03-15 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-16) | Hank Cochran_HR_Other | T&E | HIGH - IT system strategy for Global People Systems (GPS), server space, computers, general eldger, telephones, VPN, etc. | Both | TRUE | 2016-01-31 | 21 | 2016-01-10 | 0% | TRUE | This will be determined by GSS/IS and the BU. | Lowry, McCleary | Not Started | [6 empty] | X
HC07 | 80 - (HC07-17) | Hank Cochran_HR_Other | T&E | HIGH - Procurement contract strategy for all vendors | Both | TRUE | 2016-01-31 | 52 | 2015-12-10 | 0% | TRUE | Assumption - no changes in 3rd party vendors. Dependencies relate to vendor feeds from GPS, Payroll, and funding sources. | Lowry, McCleary | Not Started | Waiting for procurement to provide assistance |  |  | X |  |  | X |  |  |  | X
HC07 | 80 - (HC07-18) | Hank Cochran_HR_Other | T&E | MEDIUM - Key Partner Summit to identify and review deliverables and develop detailed implementation plans | Both | TRUE | 2016-02-15 | 60 | 2015-12-17 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | IT and Procurement decisions need to be made in order to structure the summit discussion and determine next steps |  |  | X |  |  | X |  |  |  | X
HC07 | 80 - (HC07-19) | Hank Cochran_HR_Other | T&E | MEDIUM - Establish cutoff for separation related to credit card and payroll expense processing and revise schedule prospectively | Both | TRUE | 2016-10-01 | 90 | 2016-07-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-20) | Hank Cochran_HR_Other | T&E | HIGH - Issue new corporate credit cards to those assigned to Upstream and cancel old cards | Up. Co. | TRUE | 2016-10-01 | 90 | 2016-07-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | Issue new card, reconcile/clean up old account, cancel previous card | [7 empty] | X
HC07 | 80 - (HC07-21) | Hank Cochran_HR_Other | T&E | MEDIUM - Establish necessary proceedures and accouting allocation for Citibank rebates | Both | TRUE | 2016-10-01 | 90 | 2016-07-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-22) | Hank Cochran_HR_Other | T&E | MEDIUM - Establish new process related to the auditing and rebates related to VAT receipts | Both | TRUE | 2016-10-01 | 90 | 2016-07-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-23) | Hank Cochran_HR_Other | T&E | MEDIUM - Establish process and ownership for Business Records Management | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | TRUE | Identification of allocations of employees to Value-Add or Upstream | Lowry, McCleary | Not Started | [8 empty] | X
HC07 | 80 - (HC07-24) | Hank Cochran_HR_Other | T&E | MEDIUM - Establish process for customer support and inquiries related to the Remedy system and the emergency phone support | Both | TRUE | 2016-10-01 | 120 | 2016-06-03 | 0% | FALSE | N/A | Lowry, McCleary | Not Started | [8 empty] | X
HC04 | PSC-CRP-01 | Hank Cochran_Finance | PSC | CRP testing: Modified responsibilities | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-02 | Hank Cochran_Finance | PSC | CRP testing: Buyer setup updates | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-03 | Hank Cochran_Finance | PSC | CRP testing: Approval hierarchy changes | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-04 | Hank Cochran_Finance | PSC | CRP testing: Intercompany process and purchase orders for the new companies to do business with each other. New supplier setup needed. | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-05 | Hank Cochran_Finance | PSC | CRP testing: B2B testing - Split of Quadrem B2B functionality | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-06 | Hank Cochran_Finance | PSC | CRP testing: eCM Bulkload Tool | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-07 | Hank Cochran_Finance | PSC | CRP End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. Taxware system needed. |  | 42485 |  |  |  | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-08 | Hank Cochran_Finance | PSC | CRP testing -Capital End to End Testing | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system CRP testing. Once CRP dates are known, this due date will be adjusted. Taxware system needed. This task is copied onto the Procurement Separation Project Plan. |  | 2016-04-25 |  |  |  | 2016-04-25 |  | 2016-04-25
HC04 | PSC-CRP-09 | Hank Cochran_Finance | PSC | CRP testing: Duplicate NON OU | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system CRP testing. Once CRP dates are known, this due date will be adjusted. Taxware system needed. This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-04-25
HC04 | PSC-CRP-10 | Hank Cochran_Finance | PSC | CRP testing: B2B testing direct connections | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system CRP testing. Once CRP dates are known, this due date will be adjusted. Taxware system needed. This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-04-25
HC04 | PSC-CRP-11 | Hank Cochran_Finance | PSC | CRP testing: B2B Test PullPay direct connections and PullPay converter tool | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | Tool used for uploading to Pull Pay | [7 empty] | 2016-04-25
HC04 | PSC-CRP-12 | Hank Cochran_Finance | PSC | CRP testing: eCM testing Alcoa Services link in iProcurement will need to be duplicated | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Solutions will need to duplicate the system in iProcurement | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-13 | Hank Cochran_Finance | PSC | CRP testing: eCM testing Common table of rate mapping | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Solutions will need to duplicate tables | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-14 | Hank Cochran_Finance | PSC | CRP testing: eCM Problem Reporting link in iClaims | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Alcoa Direct Duplicating iClaims | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-15 | Hank Cochran_Finance | PSC | CRP testing: Duplicate Remedy | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-16 | Hank Cochran_Finance | PSC | CRP testing: BPA testing Infopath tool for submitting changes to CTT | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-17 | Hank Cochran_Finance | PSC | CRP testing: PO History - would be helpful to keep for looking up past price | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-18 | Hank Cochran_Finance | PSC | CRP testing: Split Infopath form for Remedy | Both | TRUE | 2016-06-01 | 60 | 2016-04-02 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | IT decision for creation of Remedy system each company and availability of system. | [5 empty] | 2016-04-02 |  | 2016-04-25
HC04 | PSC-CRP-19 | Hank Cochran_Finance | PSC | CRP testing: eCM testing Bulk Load Notifications (Successful and Errors) | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-20 | Hank Cochran_Finance | PSC | CRP testing: eCM iClaim users will need to be duplicated | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | 1 email address per supplier name | [7 empty] | 2016-04-25
HC04 | PSC-CRP-21 | Hank Cochran_Finance | PSC | CRP testing: Mall testing Alcoa Mall link in iProcurement will need to be duplicated | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-22 | Hank Cochran_Finance | PSC | CRP testing: Mall testing Alcoa Mall punchout sites and internal catalogs will need split | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Vinamaya assistance. Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-23 | Hank Cochran_Finance | PSC | CRP testing: Mall testing Alcoa Mall Filter Groups will need updated and split | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Vinamaya assistance. Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-24 | Hank Cochran_Finance | PSC | CRP testing: eCM testing Auto Receive Open ASN PO Program will need to be split | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-25 | Hank Cochran_Finance | PSC | CRP testing: Discoverer and Pi2P reports | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-26 | Hank Cochran_Finance | PSC | CRP testing: Duplicate and test all macros and other non-Oracle automation tools used by USBPC | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | New networks and domain names are created and accessible. Oracle platform is maintained in both companies or similar data is available from new platform. | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-27 | Hank Cochran_Finance | PSC | CRP testing: eCM testing Control Report (Mismatch / Rejections) | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | POSCHED: XXECM: Claims Control Report | [7 empty] | 2016-04-25
HC04 | PSC-CRP-28 | Hank Cochran_Finance | PSC | CRP testing: eCM testing Workflows | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-29 | Hank Cochran_Finance | PSC | CRP testing: Relink MSIS contracts to BPA's | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-30 | Hank Cochran_Finance | PSC | CRP testing: Intercompany PO's will need to be set up for business across the companies | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-31 | Hank Cochran_Finance | PSC | CRP testing: eCM testing invoices pay from submission date (not approval date) | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-32 | Hank Cochran_Finance | PSC | CRP testing: Bulk Upload Template | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-33 | Hank Cochran_Finance | PSC | CRP Testing: Suppliers and Supplier Sites updated with new SCO's and SAM's | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Procurement decisions need to have been made | Koenig, Miller | Not started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-06-12 |  | 2016-06-12
HC04 | PSC-CRP-34 | Hank Cochran_Finance | PSC | CRP testing: B2B testing Connection to Quadrem from each new Oracle instance | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-35 | Hank Cochran_Finance | PSC | Delta Process flat file testing | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Availability of knowledgeable resource | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-CRP-36 | Hank Cochran_Finance | PSC | CRP testing eCM testing: - Every new MSIS contract will require a new Oracle contract and table of rates | Both | TRUE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Procurement / GBS COE needs to have completed the work in MSIS. Alcoa Direct needs to be split and ready to use. | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-04-01 |  | 2016-04-01
HC04 | PSC-PRD-01 | Hank Cochran_Finance | PSC | Updates to PO's to align with contractual changes, including new terms and conditions, attachments, and standard notes | Both | TRUE | 2016-07-22 | 40 | 2016-06-12 | 0 | TRUE | New T&C's and Contractual changes to PO's by Procurement | Koenig, Miller | Not started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-06-12 |  | 2016-06-12
HC04 | PSC-PRD-02 | Hank Cochran_Finance | PSC | Updates to BPA's to align with contractual changes, including new terms and conditions, attachments, and standard notes. | Both | TRUE | 2016-07-22 | 40 | 2016-06-12 | 0 | TRUE | New T&C's and Contractual changes to PO's by Procurement | Koenig, Miller | Not started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-06-12 |  | 2016-06-12
HC04 | PSC-PRD-03 | Hank Cochran_Finance | PSC | Manufacturing Part Number tool needs to be split (Access Database) | Both | FALSE | 2016-05-31 | 40 | 2016-04-21 | 0 | TRUE | Need to find a resource, likely on Data & Reporting team, with knowledge to work on this tool. | Koenig, Miller | Not started | Estimated due date and days needed to accomplish - will be discussed with Data & Reporting Team | [7 empty] | 2016-04-21 | [22 empty] | 2016-04-21 | GBS COE D&R Team
HC04 | PSC-PRD-04 | Hank Cochran_Finance | PSC | Master Req Pool Tool needs to be split (Access Database) | Both | FALSE | 2016-05-31 | 40 | 2016-04-21 | 0 | TRUE | Need to find a resource, likely on Data & Reporting team, with knowledge to work on this tool. | Koenig, Miller | Not started | Estimated due date and days needed to accomplish - will be discussed with Data & Reporting Team | [7 empty] | 2016-04-21 | [22 empty] | 2016-04-21 | GBS COE D&R Team
HC04 | PSC-PRD-40 | Hank Cochran_Finance | PSC | Master Req Pool Consolidator Tool needs to be split (Access Database) | Both | FALSE | 2016-05-31 | 40 | 2016-04-21 | 0 | TRUE | Need to find a resource, likely on Data & Reporting team, with knowledge to work on this tool. | Koenig, Miller | Not started | Estimated due date and days needed to accomplish - will be discussed with Data & Reporting Team | [7 empty] | 2016-04-21 | [22 empty] | 2016-04-21 | GBS COE D&R Team
HC04 | PSC-PRD-05 | Hank Cochran_Finance | PSC | Review org structure, roles and responsibilities with Hungary Team | Both | FALSE | 2016-06-01 | 30 | 2016-05-02 | 0 | TRUE |  | Koenig, Miller | Not started | [8 empty] | 2016-04-21
HC04 | PSC-PRD-06 | Hank Cochran_Finance | PSC | Capital Testing - Capital PMO SharePoint site separated for use by both companies | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Decision by Mike Petro concerning use of the Sharepoint site by both companies | Koenig, Miller | Not started | This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-05-02 |  | 2016-05-02
HC04 | PSC-PRD-07 | Hank Cochran_Finance | PSC | Capital Testing - Communication method for new projects | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Decision is needed by Mike Petro (Cap Proc) to determine what communication methods will be used to relay capital projects to the procurement team. | Koenig, Miller | Not started | This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-05-02 |  | 2016-05-02
HC04 | PSC-PRD-08 | Hank Cochran_Finance | PSC | Duplicate shared drives for collection of reports needed for buy and pay processes | Both | FALSE | 2016-05-31 | 90 | 2016-03-02 | 0 | TRUE | Networks / Windows available for both companies, IT decision | Koenig, Miller | Not started | Folders are used not only for manually storing materials, but are also designated in Discoverer report output as the default storage. | [5 empty] | 2016-03-02 |  | 2016-03-02
HC04 | PSC-PRD-09 | Hank Cochran_Finance | PSC | Distribute Histroical data from shared drives to appropriate company | Both | FALSE | 2016-05-31 | 30 | 2016-05-01 | 0 | TRUE | IT decision for data storage and legal for ownership | Koenig, Miller | Not started |  |  |  |  | 2016-05-01 |  | 2016-05-01 |  | 2016-05-01
HC04 | PSC-PRD-10 | Hank Cochran_Finance | PSC | Updates to our new operating units | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Need data on naming convention | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-11 | Hank Cochran_Finance | PSC | Duplicate email boxes | Both | FALSE | 2016-05-31 | 60 | 2016-04-01 | 0 | TRUE | Creation of mailbox and accesses | Koenig, Miller | Not started | [6 empty] | 2016-04-01 |  | 2016-04-01
HC04 | PSC-PRD-12 | Hank Cochran_Finance | PSC | Separate Sharepoint sites for pull Pay and PSC | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Creation of sites and accesses | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-13 | Hank Cochran_Finance | PSC | Separate buyers | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Setup of responsibilities | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-14 | Hank Cochran_Finance | PSC | Telephone numbers | Both | FALSE | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE | Creation of new phone numbers | Koenig, Miller | Not started | [8 empty] | 2016-05-31
HC04 | PSC-PRD-15 | Hank Cochran_Finance | PSC | Split Keep it Common | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Work with PIT EBS | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-16 | Hank Cochran_Finance | PSC | Safety prequalification process | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Access to all for Capital and who will work the GPP PSQ | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-17 | Hank Cochran_Finance | PSC | Supplier education on how to work with new companies | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Training documentation created as well as communication | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-18 | Hank Cochran_Finance | PSC | UPS Codes are provided by locations - will need to be separated | Both | FALSE | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE | Follow-up with location procurement | Koenig, Miller | Not started | [8 empty] | 2016-05-31
HC04 | PSC-PRD-19 | Hank Cochran_Finance | PSC | Duplicate item numbers | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | FALSE |  | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-20 | Hank Cochran_Finance | PSC | Bleed out period for open PO's and Invoices across companies | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | FALSE |  | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-21 | Hank Cochran_Finance | PSC | Cross training | Both | TRUE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Training documentation created as well as communication | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-22 | Hank Cochran_Finance | PSC | Separate Daily Management Boards | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Determination of needs and updated macros | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-23 | Hank Cochran_Finance | PSC | Split / duplicate SLA | Both | TRUE | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE |  | Koenig, Miller | Not started | Organizational decisions | [7 empty] | 2016-05-31
HC04 | PSC-PRD-24 | Hank Cochran_Finance | PSC | People assignments | Both | TRUE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Training documentation created as well as communication | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-25 | Hank Cochran_Finance | PSC | Setup new printers | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Icon/IT assistance and purchase of new printers | Koenig, Miller | Not started | [6 empty] | 2016-04-01 |  | 2016-04-01
HC04 | PSC-PRD-26 | Hank Cochran_Finance | PSC | Create/split USBPC Portal page for each company | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | IT intranet | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-27 | Hank Cochran_Finance | PSC | Recurring Data Requests | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Work with COE | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-28 | Hank Cochran_Finance | PSC | Delta Process flat file testing | Both | TRUE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE |  | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-29 | Hank Cochran_Finance | PSC | Update Outlook DL lists | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Who wil lbe in each group. Ticket creation | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-30 | Hank Cochran_Finance | PSC | Archiving of Mailboxes | Both | FALSE | 2016-05-31 | 60 | 2016-04-01 | 0 | TRUE | Location of archive | Koenig, Miller | Not started |  |  |  |  | 2016-04-01 |  | 2016-04-01 |  | 2016-04-01
HC04 | PSC-PRD-31 | Hank Cochran_Finance | PSC | Duplicate Progress Payment Tracker for new company | Both | TRUE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE |  | Koenig, Miller | Not started | [8 empty] | 2016-05-02
HC04 | PSC-PRD-32 | Hank Cochran_Finance | PSC | New SPQ access for new company | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE |  | Koenig, Miller | Not started | Who will determine | [7 empty] | 2016-05-02
HC04 | PSC-PRD-33 | Hank Cochran_Finance | PSC | B2B testing: Contracts between Quadrem and the suppliers need to be updated | Both | TRUE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Need updated contracts from COE | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-PRD-34 | Hank Cochran_Finance | PSC | eCM testing - Separate Sharepoint site for eCM Onboarding and Update requests | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Sharepoint needs to be available for both companies | Koenig, Miller | Not started | This task is copied onto the Procurement Separation Project Plan. SharePoint team to create new site for new company. Site Owner to create new forms on the new site. | [5 empty] | 2016-05-02 |  | 2016-05-02
HC04 | PSC-PRD-35 | Hank Cochran_Finance | PSC | Reassignment of PO's to new buyers | Both | FALSE | 2016-07-22 | 16 | 2016-07-06 | 0 | TRUE | Contractual changes to PO's by Procurement | Koenig, Miller | Not started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-07-06 |  | 2016-07-06
HC04 | PSC-PRD-36 | Hank Cochran_Finance | PSC | Duplicate Work Instructions | Both | FALSE | 2016-05-31 | 60 | 2016-04-01 |  | FALSE |  | Koenig, Miller | Not started
HC04 | PSC-UAT-01 | Hank Cochran_Finance | PSC | UAT Testing: Modified responsibilities | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-05-30 |  | 2016-05-30
HC04 | PSC-UAT-02 | Hank Cochran_Finance | PSC | UAT Testing: Buyer setup updates | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-05-30 |  | 2016-05-30
HC04 | PSC-UAT-03 | Hank Cochran_Finance | PSC | UAT Testing: Approval hierarchy changes | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-05-30 |  | 2016-05-30
HC04 | PSC-UAT-04 | Hank Cochran_Finance | PSC | UAT Testing: Intercompany process and purchase orders for the new companies to do business with each other. New supplier setup needed. | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability; Supplier Maintenance Team does setup | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-05-30 |  | 2016-05-30
HC04 | PSC-UAT-05 | Hank Cochran_Finance | PSC | UAT Testing: Split of Quadrem B2B functionality | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle QA testing schedule and instance availability, Quadrem split | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-05-30 |  | 2016-05-30
HC04 | PSC-UAT-06 | Hank Cochran_Finance | PSC | CRP testing: eCM Bulkload Tool | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Availability of knowledgeable resource | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-07 | Hank Cochran_Finance | PSC | CRP End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle QA testing schedule and instance availability, Need to determine if Bulkload Tool needs updating and by whom | Koenig, Miller | Not started | Dependent on CRP testing results |  | 2016-05-30 |  |  |  | 2016-05-30 |  | 2016-05-30
HC05 | PSC-UAT-08 | Hank Cochran_Finance | PSC | UAT testing-Capital End to End Testing | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT Capital testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results |  | 2016-05-30 |  |  |  | 2016-05-30 |  | 2016-05-30
HC04 | PSC-UAT-09 | Hank Cochran_Finance | PSC | UAT testing: Duplicate NON OU | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-10 | Hank Cochran_Finance | PSC | UAT testing: B2B testing direct connections | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-11 | Hank Cochran_Finance | PSC | UAT testing: B2B testing PullPay direct connections and PullPay converter tool | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-12 | Hank Cochran_Finance | PSC | UAT testing: eCM testing Services link in iProcurement will need to be duplicated | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Solutions will need to duplicate the system in iProcurement | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-13 | Hank Cochran_Finance | PSC | UAT testing: eCM testing Common table of rate mapping | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Solutions will need to duplicate tables | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-14 | Hank Cochran_Finance | PSC | UAT testing: eCM testing Problem Reporting link in iClaims | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Alcoa Direct Duplicating iClaims | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-15 | Hank Cochran_Finance | PSC | UAT testing: Duplicate Remedy | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-16 | Hank Cochran_Finance | PSC | UAT testing: BPA testing Infopath tool for submitting changes to CTT | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-17 | Hank Cochran_Finance | PSC | UAT testing: PO History - would be helpful to keep for looking up past price | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-18 | Hank Cochran_Finance | PSC | UAT testing: Split Infopath form for Remedy | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-19 | Hank Cochran_Finance | PSC | UAT testing: eCM testing Bulk Load Notifications (Successful and Errors) | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-20 | Hank Cochran_Finance | PSC | UAT testing: eCM testing iClaim users will need to be duplicated | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-21 | Hank Cochran_Finance | PSC | UAT testing: Mall testing Alcoa Mall link in iProcurement will need to be duplicated | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-22 | Hank Cochran_Finance | PSC | UAT testing: Mall Alcoa Mall punchout sites and internal catalogs will need split | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Vinamaya assistance. Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-23 | Hank Cochran_Finance | PSC | UAT testing: Mall Alcoa Mall Filter Groups will need updated and split | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-24 | Hank Cochran_Finance | PSC | UAT testing: eCM testing Auto Receive Open ASN PO Program will need to be split | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-25 | Hank Cochran_Finance | PSC | UAT testing: Discoverer and Pi2P reports | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-26 | Hank Cochran_Finance | PSC | UAT testing: Duplicate and test all macros and other non-Oracle automation tools used by USBPC | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | New networks and domain names are created and accessible. Oracle platform is maintained in both companies or similar data is available from new platform. | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-27 | Hank Cochran_Finance | PSC | UAT testing: eCM testing Control Report (Mismatch / Rejections) | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-28 | Hank Cochran_Finance | PSC | UAT testing: eCM Workflows | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-29 | Hank Cochran_Finance | PSC | UAT Testing: BPA testing Relink MSIS contracts to BPA's | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-30 | Hank Cochran_Finance | PSC | UAT Testing: Intercompany PO's will need to be set up for business across the companies | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-31 | Hank Cochran_Finance | PSC | UAT testing: eCM testing invoices pay from submission date (not approval date) | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-32 | Hank Cochran_Finance | PSC | UAT Testing: Bulk Upload Template | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-33 | Hank Cochran_Finance | PSC | UAT Testing: Supplier testing: Suppliers and Supplier Sites updated with new SCO's and SAM's | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Procurement decisions need to have been made | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-06-12 |  | 2016-06-12
HC05 | PSC-UAT-34 | Hank Cochran_Finance | PSC | UATtesting: B2B testing Connection to Quadrem from each new Oracle instance | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Procurement decisions need to have been made |  |  | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-UAT-35 | Hank Cochran_Finance | PSC | Delta Process flat file testing | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Availability of knowledgeable resource | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-UAT-36 | Hank Cochran_Finance | PSC | UAT testing: eCM testing: - Every new MSIS contract will require a new Oracle contract and table of rates | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Procurement / GBS COE needs to have completed the work in MSIS. Alcoa Direct needs to be split and ready to use. Oracle must be duplicated and MSIS contracts must be finalized before eCM contract purchase agreement with table of rates can be created by Central Transaction Team | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-04-01 |  | 2016-04-01
HC04 | PSC-UNI-01 | Hank Cochran_Finance | PSC | UNI testing: Modified responsibilities | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-02 | Hank Cochran_Finance | PSC | UNI testing: Buyer setup updates | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-03 | Hank Cochran_Finance | PSC | UNI testing: Approval hierarchy changes | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-04 | Hank Cochran_Finance | PSC | UNI testing: Intercompany process and purchase orders for the new companies to do business with each other. New supplier setup needed. | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-05 | Hank Cochran_Finance | PSC | UNI testing: B2B testing - Split of Quadrem B2B functionality | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-06 | Hank Cochran_Finance | PSC | UNI testing: eCM Bulkload Tool | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. | [5 empty] | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-07 | Hank Cochran_Finance | PSC | UNI End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system UAT testing. Once UAT dates are known, this due date will be adjusted. Taxware system needed. |  | 42485 |  |  |  | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-08 | Hank Cochran_Finance | PSC | UNI testing -Capital End to End Testing | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system CRP testing. Once CRP dates are known, this due date will be adjusted. Taxware system needed. This task is copied onto the Procurement Separation Project Plan. |  | 2016-04-25 |  |  |  | 2016-04-25 |  | 2016-04-25
HC04 | PSC-UNI-09 | Hank Cochran_Finance | PSC | UNI testing: Duplicate NON OU | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system CRP testing. Once CRP dates are known, this due date will be adjusted. Taxware system needed. This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-04-25
HC04 | PSC-UNI-10 | Hank Cochran_Finance | PSC | UNI testing: B2B testing direct connections | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | This is part of the Oracle system CRP testing. Once CRP dates are known, this due date will be adjusted. Taxware system needed. This task is copied onto the Procurement Separation Project Plan. | [7 empty] | 2016-04-25
HC04 | PSC-UNI-11 | Hank Cochran_Finance | PSC | UNI testing: B2B Test PullPay direct connections and PullPay converter tool | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | Tool used for uploading to Pull Pay | [7 empty] | 2016-04-25
HC04 | PSC-UNI-12 | Hank Cochran_Finance | PSC | UNI testing: eCM testing Alcoa Services link in iProcurement will need to be duplicated | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Solutions will need to duplicate the system in iProcurement | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-13 | Hank Cochran_Finance | PSC | UNI testing: eCM testing Common table of rate mapping | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Solutions will need to duplicate tables | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-14 | Hank Cochran_Finance | PSC | UNI testing: eCM Problem Reporting link in iClaims | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Alcoa Direct Duplicating iClaims | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-15 | Hank Cochran_Finance | PSC | UNI testing: Duplicate Remedy | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-16 | Hank Cochran_Finance | PSC | UNI testing: BPA testing Infopath tool for submitting changes to CTT | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-17 | Hank Cochran_Finance | PSC | UNI testing: PO History - would be helpful to keep for looking up past price | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-18 | Hank Cochran_Finance | PSC | UNI testing: Split Infopath form for Remedy | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-19 | Hank Cochran_Finance | PSC | UNI testing: eCM testing Bulk Load Notifications (Successful and Errors) | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-20 | Hank Cochran_Finance | PSC | UNI testing: eCM iClaim users will need to be duplicated | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | 1 email address per supplier name | [7 empty] | 2016-04-25
HC04 | PSC-UNI-21 | Hank Cochran_Finance | PSC | UNI testing: Mall testing Alcoa Mall link in iProcurement will need to be duplicated | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-22 | Hank Cochran_Finance | PSC | UNI testing: Mall testing Alcoa Mall punchout sites and internal catalogs will need split | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Vinamaya assistance. Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-23 | Hank Cochran_Finance | PSC | UNI testing: Mall testing Alcoa Mall Filter Groups will need updated and split | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Vinamaya assistance. Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-24 | Hank Cochran_Finance | PSC | UNI testing: eCM testing Auto Receive Open ASN PO Program will need to be split | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-25 | Hank Cochran_Finance | PSC | UNI testing: Discoverer and Pi2P reports | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-26 | Hank Cochran_Finance | PSC | UNI testing: Duplicate and test all macros and other non-Oracle automation tools used by USBPC | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | New networks and domain names are created and accessible. Oracle platform is maintained in both companies or similar data is available from new platform. | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-27 | Hank Cochran_Finance | PSC | UNI testing: eCM testing Control Report (Mismatch / Rejections) | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | POSCHED: XXECM: Claims Control Report | [7 empty] | 2016-04-25
HC04 | PSC-UNI-28 | Hank Cochran_Finance | PSC | UNI testing: eCM testing Workflows | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-29 | Hank Cochran_Finance | PSC | UNI testing: Relink MSIS contracts to BPA's | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-30 | Hank Cochran_Finance | PSC | UNI testing: Intercompany PO's will need to be set up for business across the companies | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-31 | Hank Cochran_Finance | PSC | UNI testing: eCM testing invoices pay from submission date (not approval date) | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-32 | Hank Cochran_Finance | PSC | UNI testing: Bulk Upload Template | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-UNI-33 | Hank Cochran_Finance | PSC | UNI Testing: Suppliers and Supplier Sites updated with new SCO's and SAM's | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Procurement decisions need to have been made | Koenig, Miller | Not started | Both Oracle systems will need to be available and ready for Prod changes | [5 empty] | 2016-06-12 |  | 2016-06-12
HC04 | PSC-UNI-34 | Hank Cochran_Finance | PSC | UNI testing: B2B testing Connection to Quadrem from each new Oracle instance | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-04-25
HC04 | PSC-CRP-35 | Hank Cochran_Finance | PSC | Delta Process flat file testing | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Availability of knowledgeable resource | Koenig, Miller | Not started | [8 empty] | 2016-04-01
HC04 | PSC-UNI-36 | Hank Cochran_Finance | PSC | UNI testing: eCM testing: - Every new MSIS contract will require a new Oracle contract and table of rates | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Procurement / GBS COE needs to have completed the work in MSIS. Alcoa Direct needs to be split and ready to use. Oracle must be duplicated and MSIS contracts must be finalized before eCM contract purchase agreement with table of rates can be created by Central Transaction Team | Koenig, Miller | Not started | Dependent on CRP testing results | [5 empty] | 2016-04-01 |  | 2016-04-01
HC04 | PSC-PRD-36 | Hank Cochran_Finance | PSC | UNI testing: Split Infopath form for Remedy | Both | TRUE | 2016-07-03 | 21 | 2016-06-12 | 0 | TRUE | Oracle CRP testing schedule and instance availability | Koenig, Miller | Not started | [8 empty] | 2016-06-12
HC04 | PSC-PRD-37 | Hank Cochran_Finance | PSC | UAT testing: Discoverer and Pi2P reports | Both | TRUE | 2016-07-03 | 34 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability | Koenig, Miller | Not started | Dependent on CRP testing results | [7 empty] | 2016-05-30
HC04 | PSC-PRD-38 | Hank Cochran_Finance | PSC | UNI testing: Discoverer and Pi2P reports | Both | TRUE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | COE/IT | Koenig, Miller | Not started | [8 empty] | 2016-07-04
HC04 | PSC-PRD-39 | Hank Cochran_Finance | PSC | UNI testing: Duplicate and test all macros and other non-Oracle automation tools used by USBPC | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | FALSE |  | Koenig, Miller | Not started | [8 empty] | 2016-07-04
HC03 | AP-UNI-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | We will need to determine if both companies with to use Alcoa direct as a vendor portal. There are also several purchasing/payment processes which flow through AD. | [5 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-01 | Hank Cochran_Finance | Accounts Payable | Alcoa Direct Split and Testing | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04
HC03 | AP-PRD-02 | Hank Cochran_Finance | Accounts Payable | Assign bank account access to payment team for manual payments | Both | FALSE | 2016-07-01 | 30 | 2016-06-01 | 0 | TRUE | Treasury needs to make decisions on the bank accounts for both companies for manual payments. | Koenig,Verardi | Not started |  |  |  | 2016-06-01
HC03 | AP-UNI-03 | Hank Cochran_Finance | Accounts Payable | Bank and Bank Account setup + technical connection to banks: EBS, FMW, FundTech, SWIFT, Bank | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT testing schedule and instance availability; Supplier Maintenance Team and Solutions complete most setups. Treasury must create the bank accounts and ensure availability of bank testing resources and bank testing environment. | Koenig,Verardi | Not started | Treasury will need to develop the bank account stragegy here and will also be key in obtaining testing resources at the given banks for end to end testing. IT support teams will also be key in making the connection to the banks and adjusting coding in payment files and processes as needed. Solutions will be completing many of the functional setups for payments and will need to support testing in general. |  |  | 2016-02-29 |  |  | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-03 | Hank Cochran_Finance | Accounts Payable | Bank and Bank Account setup + technical connection to banks: EBS, FMW, FundTech, SWIFT, Bank | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability; Supplier Maintenance Team and Solutions complete most setups. Treasury must create the bank accounts and ensure availability of bank testing resources and bank testing environment. | Koenig,Verardi | Not started |  |  |  | 2016-04-25 |  |  | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-03 | Hank Cochran_Finance | Accounts Payable | Bank and Bank Account setup + technical connection to banks: EBS, FMW, FundTech, SWIFT, Bank | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability; Supplier Maintenance Team and Solutions complete most setups. Treasury must create the bank accounts and ensure availability of bank testing resources and bank testing environment. | Koenig,Verardi | Not started |  |  |  | 2016-05-30 |  |  | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-03 | Hank Cochran_Finance | Accounts Payable | Bank and Bank Account setup + technical connection to banks: EBS, FMW, FundTech, SWIFT, Bank | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD testing schedule and instance availability; Supplier Maintenance Team and Solutions complete most setups. Treasury must create the bank accounts and ensure availability of bank testing resources and bank testing environment. | Koenig,Verardi | Not started |  |  |  | 2016-06-30 |  |  | 2016-06-30 |  | 2016-06-30
HC03 | AP-UNI-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-04 | Hank Cochran_Finance | Accounts Payable | Connection to Siemens Customer Care for Global Energy invoices to Cyber to Alcoa via Pull Pay | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Siemens collects energy invoices to provide customer care and data to the Energy Group in Procurement. Need decision that both companies will use this service. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04 |  | 2016-07-04
HC03 | AP-PRD-05 | Hank Cochran_Finance | Accounts Payable | Create ARM (approval listing and limits) list for upstream and downstream | Both | FALSE | 2016-07-01 | 45 | 2016-05-17 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-UNI-06 | Hank Cochran_Finance | Accounts Payable | Create emergency check proceedures for each company including setting up of printers, etc. | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-06 | Hank Cochran_Finance | Accounts Payable | Create emergency check proceedures for each company including setting up of printers, etc. | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-06 | Hank Cochran_Finance | Accounts Payable | Create emergency check proceedures for each company including setting up of printers, etc. | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-06 | Hank Cochran_Finance | Accounts Payable | Create emergency check proceedures for each company including setting up of printers, etc. | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04
HC03 | AP-PRD-07 | Hank Cochran_Finance | Accounts Payable | Create/Split USBPC portal page for each company | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | Intranet availability and creation by IT | Koenig,Verardi | Not started | [6 empty] | 2016-05-02
HC03 | AP-UNI-08 | Hank Cochran_Finance | Accounts Payable | Create/test flat file uploads for processes other than B of A | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNI instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-08 | Hank Cochran_Finance | Accounts Payable | Create/test flat file uploads for processes other than B of A | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-08 | Hank Cochran_Finance | Accounts Payable | Create/test flat file uploads for processes other than B of A | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-08 | Hank Cochran_Finance | Accounts Payable | Create/test flat file uploads for processes other than B of A | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04
HC03 | AP-UNI-09 | Hank Cochran_Finance | Accounts Payable | Create/test intercompany PO and invoicing process | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNI instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-09 | Hank Cochran_Finance | Accounts Payable | Create/test intercompany PO and invoicing process | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-09 | Hank Cochran_Finance | Accounts Payable | Create/test intercompany PO and invoicing process | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-09 | Hank Cochran_Finance | Accounts Payable | Create/test intercompany PO and invoicing process | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04
HC03 | AP-PRD-10 | Hank Cochran_Finance | Accounts Payable | Determine ownership of AP Microfiche reader and documents or obtain 2nd reader for records. | Both | FALSE | 2016-07-01 | 30 | 2016-06-01 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-PRD-11 | Hank Cochran_Finance | Accounts Payable | Determine ownership of materials in AP safe and determine if a second safe is needed. | Both | FALSE | 2016-07-01 | 30 | 2016-06-01 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-PRD-12 | Hank Cochran_Finance | Accounts Payable | Distribute Historical data from shared drives to appropriate company | Both | FALSE | 2016-05-31 | 30 | 2016-05-01 | 0 | TRUE | IT decision for data storage and Legal decision on ownersip of shared documentation and reports. | Koenig,Verardi | Not started |  |  |  |  | 2016-05-01 |  | 2016-05-01
HC03 | AP-UNI-13 | Hank Cochran_Finance | Accounts Payable | Duplicate and test invoicing connections including Pullpay, B2B, ECM, PFR | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor availability of testing instances. Solutions support for testing. | Koenig,Verardi | Not started | 90% of our invoicing comes in through electronically. This is a key milestone to verifty that the critical connections are working as needed. End to end testing would include the full spectrum of IT and GSS while significant work would need to be done to ensure that our vendors support the testing in line with the established testing windows. | [5 empty] | 2016-02-29 |  | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-13 | Hank Cochran_Finance | Accounts Payable | Duplicate and test invoicing connections including Pullpay, B2B, ECM | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor availability of testing instances. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-13 | Hank Cochran_Finance | Accounts Payable | Duplicate and test invoicing connections including Pullpay, B2B, ECM | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor availability of testing instances. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-13 | Hank Cochran_Finance | Accounts Payable | Duplicate and test invoicing connections including Pullpay, B2B, ECM | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD instance and FMW ready for setups and testing. Procurement work to separate relevant contracts (ARIBA) and vendor coordination. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04 |  | 2016-07-04
HC03 | AP-PRD-14 | Hank Cochran_Finance | Accounts Payable | Duplicate email boxes | Both | FALSE | 2016-05-31 | 60 | 2016-04-01 | 0 | TRUE | IT decision for data storage and network access | Koenig,Verardi | Not started | [6 empty] | 2016-04-01
HC03 | AP-PRD-15 | Hank Cochran_Finance | Accounts Payable | Duplicate shared drives for collection of reports needed for buy and pay processes | Both | FALSE | 2016-05-31 | 90 | 2016-03-02 | 0 | TRUE | IT decision for data storage | Koenig,Verardi | Not started | [6 empty] | 2016-03-02
HC03 | AP-PRD-16 | Hank Cochran_Finance | Accounts Payable | Duplicate/update work instructions | Both | FALSE | 2016-05-31 | 60 | 2016-04-01 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-UNI-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | A huge amount of AP compliance, analysis and support tasks are done with the support of Discoverer and Pi2P reporting. These tools must be in working order for both companies in order to administer the AP function. | [5 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-17 | Hank Cochran_Finance | Accounts Payable | Duplication and testing of all Discoverer + Pi2P reports | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PRD instance ready for setups and testing. Pi2P system set up and ready for testing. Solutions support for setups | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04 | [22 empty] | 2016-07-04 | GBS COE
HC03 | AP-UNI-18 | Hank Cochran_Finance | Accounts Payable | End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNI testing schedule and instance availability. Any changes, if needed, made in Taxware. | Koenig,Verardi | Not started | Tax is a known/difficult area as it relates to AP as well as critical to AP operations. |  | 2016-02-29 |  |  |  | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-18 | Hank Cochran_Finance | Accounts Payable | End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability. Any changes, if needed, made in Taxware. | Koenig,Verardi | Not started |  |  | 2016-04-25 |  |  |  | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-18 | Hank Cochran_Finance | Accounts Payable | End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability. Any changes, if needed, made in Taxware. | Koenig,Verardi | Not started |  |  | 2016-05-30 |  |  |  | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-18 | Hank Cochran_Finance | Accounts Payable | End to End Testing - details should be on Solutions / IT project plan. On here specifically to test Tax calculations. | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance availability. Any changes, if needed, made in Taxware. | Koenig,Verardi | Not started |  |  | 2016-07-04 |  |  |  | 2016-07-04 |  | 2016-07-04
HC03 | AP-CRP-19 | Hank Cochran_Finance | Accounts Payable | Macro and automation tool updates for all applicable processes and reports | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-UAT-19 | Hank Cochran_Finance | Accounts Payable | Macro and automation tool updates for all applicable processes and reports | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-PRD-19 | Hank Cochran_Finance | Accounts Payable | Macro and automation tool updates for all applicable processes and reports | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-UNI-20 | Hank Cochran_Finance | Accounts Payable | Payment program updates | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT instance availability. Solutions support for testing | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-20 | Hank Cochran_Finance | Accounts Payable | Payment program updates | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP instance availability. Solutions supoort for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-20 | Hank Cochran_Finance | Accounts Payable | Payment program updates | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-20 | Hank Cochran_Finance | Accounts Payable | Payment program updates | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance ready for setups. Solutions support for setups. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04
HC03 | AP-PRD-21 | Hank Cochran_Finance | Accounts Payable | People assignments and training | Both | TRUE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | GSS decision regarding ORG structure for each company | Koenig,Verardi | Not started | [8 empty] | 2016-05-01
HC03 | AP-PRD-22 | Hank Cochran_Finance | Accounts Payable | Remap PO boxes at ACS and Pittsburgh post offices to correct ACS instance | Both | FALSE | 2016-07-04 | 90 | 2016-04-05 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. | Koenig,Verardi | Not started | [10 empty] | 2016-04-05
HC03 | AP-UNI-23 | Hank Cochran_Finance | Accounts Payable | RtP Sched Changes | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNIT testing schedule and instance availability. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-23 | Hank Cochran_Finance | Accounts Payable | RtP Sched Changes | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-23 | Hank Cochran_Finance | Accounts Payable | RtP Sched Changes | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT instance ready for setups. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PROD-23 | Hank Cochran_Finance | Accounts Payable | RtP Sched Changes | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance availability. Solutions support for setups. | Koenig,Verardi | Not started | [6 empty] | 2016-07-24 |  | 2016-07-24
HC03 | AP-PRD-24 | Hank Cochran_Finance | Accounts Payable | Set up new printers | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | TRUE | Working EBS produciton environment | Koenig,Verardi | Not started | [6 empty] | 2016-04-01
HC03 | AP-PRD-25 | Hank Cochran_Finance | Accounts Payable | Split / duplicate Accounts Payable SLA | Both | TRUE | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE | IT EBS decision, and organizational decisions by both businesses. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-UNI-26 | Hank Cochran_Finance | Accounts Payable | Split Xerox contract and duplicate/test interface and connections to Oracle | Both | TRUE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for testing. | Koenig,Verardi | Not started | The Xerox/ACS interface is used for roughly 10k invoices per month. Both companies will need access to a similar invoice imaging system in order to continue AP operations. ACS is also connected to Oracle so that field users can queiry invoice images directly from EBS. | [5 empty] | 2016-02-29 |  | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-26 | Hank Cochran_Finance | Accounts Payable | Split Xerox contract and duplicate/test interface and connections to Oracle | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-26 | Hank Cochran_Finance | Accounts Payable | Split Xerox contract and duplicate/test interface and connections to Oracle | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-26 | Hank Cochran_Finance | Accounts Payable | Split Xerox contract and duplicate/test interface and connections to Oracle | Both | FALSE | 2016-07-31 | 30 | 2016-07-01 | 0 | TRUE | Procurement action to facilitate splitting of contract and development costs of split. IT resources to duplicate invoice connection between Oracle and invoice image. Solutions support for setup. | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-04 |  | 2016-07-04
HC03 | AP-UNI-27 | Hank Cochran_Finance | Accounts Payable | Supplier and supplier site changes | Both | FALSE | 2016-04-11 | 42 | 2016-02-29 | 0 | TRUE | Oracle UNI testing schedule and instance availability; Supplier Maintenance Team does setup | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-27 | Hank Cochran_Finance | Accounts Payable | Supplier and supplier site changes | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle CRP testing schedule and instance availability; Supplier Maintenance Team does setup | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-27 | Hank Cochran_Finance | Accounts Payable | Supplier and supplier site changes | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle UAT testing schedule and instance availability; Supplier Maintenance Team does setup | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-27 | Hank Cochran_Finance | Accounts Payable | Supplier and supplier site changes | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle PROD instance availability; Supplier Maintenance Team does setup | Koenig,Verardi | Not started | [6 empty] | 2016-07-04 |  | 2016-07-05
HC03 | AP-PRD-28 | Hank Cochran_Finance | Accounts Payable | Update USBPC Infopath form (Remedy) | Both | FALSE | 2016-06-01 | 60 | 2016-04-02 | 0 | TRUE | IT decision for creation of Remedy system each company and availability of system. | Koenig,Verardi | Not started | [6 empty] | 2016-04-02
HC03 | AP-PRD-29 | Hank Cochran_Finance | Accounts Payable | Communicate updates to AP related changes to vendors such as PO box and Alcoa Direct changes | Both | FALSE | 2016-07-01 | 60 | 2016-05-02 | 0 | FALSE |  | Koenig,Verardi | Not started
HC03 | AP-PRD-30 | Hank Cochran_Finance | Accounts Payable | Splitting of all contracts including FSG and AP recoveries | Both | FALSE | 2016-07-01 | 60 | 2016-05-02 | 0 | TRUE | Procurement action to split contracts | Koenig,Verardi | Not started | [10 empty] | 2016-05-02
HC03 | AP-UNI-31 | Hank Cochran_Finance | Accounts Payable | Test AP Subledger Closing for each company | Both | FALSE | 2016-05-16 | 21 | 2016-04-25 | 0 | TRUE | Oracle UNIT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-02-29 |  | 2016-02-29
HC03 | AP-CRP-31 | Hank Cochran_Finance | Accounts Payable | Test AP Subledger Closing for each company | Both | FALSE | 2016-07-04 | 35 | 2016-05-30 | 0 | TRUE | Oracle CRP instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-04-25 |  | 2016-04-25
HC03 | AP-UAT-31 | Hank Cochran_Finance | Accounts Payable | Test AP Subledger Closing for each company | Both | FALSE | 2016-07-31 | 27 | 2016-07-04 | 0 | TRUE | Oracle UAT instance ready for setups, connection to alcoa direct and duplication of alcoa direct for each company ready for testing. Solutions support for testing. | Koenig,Verardi | Not started | [6 empty] | 2016-05-30 |  | 2016-05-30
HC03 | AP-PRD-32 | Hank Cochran_Finance | Accounts Payable | Duplicate/update pullpay sharepoint | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0 | TRUE | IT decision for sharepoint | Koenig,Verardi | Not started | [6 empty] | 2016-05-02
HC03 | AP-PRD-33 | Hank Cochran_Finance | Accounts Payable | Review org structure, roles and responsibilities with Hungary Team | Both | FALSE | 2016-06-01 | 30 | 2016-05-02 | 0 | TRUE | GSS decision regarding ORG structure for each company | Koenig,Verardi | Not started | [8 empty] | 2016-05-02
HC03 | AP-PRD-34 | Hank Cochran_Finance | Accounts Payable | Create/Duplicate Telephone (Hotline) numbers | Both | FALSE | 2016-06-30 | 30 | 2016-05-31 | 0 | TRUE | IT support to create phone lines | Koenig,Verardi | Not started | [6 empty] | 2016-05-31
HC03 | AP-PRD-35 | Hank Cochran_Finance | Accounts Payable | Split/duplicate DMBs | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | FALSE |  | Koenig,Verardi | Not started | [6 empty] | 2016-05-31
HC03 | AP-PRD-36 | Hank Cochran_Finance | Accounts Payable | Create/Update Outlook DLs | Both | FALSE | 2016-06-30 | 90 | 2016-04-01 | 0 | FALSE |  | Koenig,Verardi | Not started | [6 empty] | 2016-05-31
HC-16 | TRN-TDW-01 | Hank Cochran_Other | Transportation Support | TDW - setup new interface/vpn (to/from BestTransport and to/from IPS, Pi2P?) | Both | FALSE | 2016-07-31 | 200 | 2016-01-13 | 0% | TRUE |  | Devware/McWilliams | not started | To/from Alcoa (pi2P - GBS CoE Data & Reporting) can be different timeframe. Dependent on when IPS & BT are set up also. | [5 empty] | 2016-01-13 | [24 empty] | 2016-06-30 | GBS CoE Data & Reporting
HC-16 | TRN-TDW-02 | Hank Cochran_Other | Transportation Support | TDW split - create new corp ID structure - QA environment | Both | FALSE | 2016-04-30 | 90 | 2016-01-31 | 0% | TRUE | Transportation contracts | Devware/McWilliams | not started | TDW 75% ready to handle multiple customers as of 12/2015. Intend to use January to complete the functionality. | [5 empty] | 2016-01-31 |  | 2016-01-31 | [16 empty] | 2016-01-31
HC-16 | TRN-IPS-03 | Hank Cochran_Other | Transportation Support | IPS - Identify 'go-forward' plan with UPS small package contract. Will we need to cancel and re-issue shipper numbers and new corp plan codes. | Both | FALSE | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE |  | K. Carver/B. Carraway/McWilliams | not started | Dependent upon GBS TRN negotiating the new contract & if UPS will be renewed, knowing if UPS will cancel existing shipper #'s and re-issue all new, knowing what the new CPP codes are, when can UPS set up new ones, etc. | [24 empty] | 2016-03-01
HC-16 | TRN-BST-04 | Hank Cochran_Other | Transportation Support | Best Transport - identify locations to 'move', Set up new location accounts - DEV (copy to PROD by 8/1/16) | Both | FALSE | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE |  | Williams/McWilliams | not started | review the 'shared' locations and determine if new locations need to be setup. DEV first
HC-16 | TRN-IPS-05 | Hank Cochran_Other | Transportation Support | IPS - Split IPS - IPS to confirm how split will be managed by them | Both | FALSE | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | Oracle instance required | McWilliams | not started | [6 empty] | 2016-04-02 |  | 2016-04-02
HC-16 | TRN-PRD-06 | Hank Cochran_Other | Transportation Support | Procurement contracts for IPS, Best Transport, QTS and DevWare | Both | FALSE | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | Procurement for both businesses to be identified and able to begin contract negotiations | M. Dausch/McWilliams | not started | start working the new contracts ASAP. | [9 empty] | 2016-04-02
HC-16 | TRN-TDW-07 | Hank Cochran_Other | Transportation Support | TDW - identify "how" to identify the data by business | Both | FALSE | 2016-04-30 | 14 | 2016-04-16 | 0% | FALSE |  | McWilliams/Williams | not started | BT data, IPS data, rates
HC-16 | TRN-IPS-08 | Hank Cochran_Other | Transportation Support | IPS - Ensure BOLs & PO's reflect 'new' name for IPS mailing - communicate to locations | Both | FALSE | 2016-05-16 | 20 | 2016-04-26 | 0% | TRUE | OM & PO systems need to be up | Brock/McWilliams | not started | need to provide mailing address to locations so they can update their systems - need to know their lead time expectations | [5 empty] | 2016-04-26
HC-16 | TRN-IPS-09 | Hank Cochran_Other | Transportation Support | IPS - Successful test of new interfaces - "new" consolidator to/from IPS, "new" consolidator to ledger, TDW. Accruals, payments, receipts and BOLs | Both | FALSE | 2016-05-16 | 20 | 2016-04-26 | 0% | TRUE | Oracle "Consolidator" interfaces must be in place GSS Ledger needs to be setup for both businesses | E. Strawn/McWilliams | not started | [6 empty] | 2016-04-26 |  | 2016-04-26
HC-16 | TRN-BST-10 | Hank Cochran_Other | Transportation Support | BestTransport - test interfaces to/from ERP systems | Both | FALSE | 2016-05-16 | 20 | 2016-04-26 | 0% | TRUE | ERP interfaces must be in place | D. Benner/McWilliams | not started | GBS Transportation needs to have contracts & rates in TDW and BT prior to testing | [5 empty] | 2016-04-26 | [18 empty] | 2016-04-26
HC-16 | TRN-TDW-11 | Hank Cochran_Other | Transportation Support | TDW - create new user accounts for all users, based on business, add new as necessary | Both | FALSE | 2016-05-30 | 30 | 2016-04-30 | 0% | TRUE |  | Devware/McWilliams | not started | dependent upon new name being announced and knowing new email addresses Includes the data group access (Nick Winter, Giacomo Ferrari) | [5 empty] | 2016-04-30
HC-16 | TRN-TDW-12 | Hank Cochran_Other | Transportation Support | TDW - identify data by business and purge/copy (run scripts) | Both | FALSE | 2016-05-30 | 30 | 2016-04-30 | 0% | TRUE |  | Devware | not started | will need to know if copying any data, will have to 'clean up' any outlier data, apply ID rules to new data coming in. This is included in QA environment testing. | [5 empty] | 2016-04-30
HC-16 | TRN-BST-13 | Hank Cochran_Other | Transportation Support | BestTransport - confirm data setups and update as necessary (such 'dock' location) | Both | FALSE | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE |  | Williams | not started | may not change from today, needs to be setup with interface testing though | [5 empty] | 2016-05-01
HC-16 | TRN-TDW-14 | Hank Cochran_Other | Transportation Support | TDW - train new TDW SPA | Both | FALSE | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | McWilliams | not started
HC-16 | TRN-PRD-15 | Hank Cochran_Other | Transportation Support | MISC: train new "ALSO" group | Both | FALSE | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Brock/Williams/McWilliams | not started | ALSO needs to be identified by 4/30/16
| TRN-TDW-16 |  |  | TDW split - create new corp ID structure - PROD | Both | FALSE | 2016-07-31 | 91 | 2016-05-01 | 0% | TRUE | Transportation contracts | Devware/McWilliams | not started | this is the testing of QA environment | [5 empty] | 2016-05-01
HC-16 | TRN-BST-16 | Hank Cochran_Other | Transportation Support | BestTransport - determine how to 'move' load history to 'new' accounts and properly update load that are status of 'in process' at cut-over (tendered - not picked up, etc), load modifications, reschedules | Both | FALSE | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Williams/McWilliams | not started
HC-16 | TRN-IPS-18 | Hank Cochran_Other | Transportation Support | IPS - Review business rules by location and set up as appropriate under new corp code | Both | FALSE | 2016-06-15 | 30 | 2016-05-16 | 0% | FALSE |  | Brock/McWilliams | not started
HC-16 | TRN-IPS-19 | Hank Cochran_Other | Transportation Support | IPS - Identify new BOL structures and provide to IPS | Both | FALSE | 2016-06-15 | 30 | 2016-05-16 | 0% | FALSE |  | Brock/McWilliams | not started
HC-16 | TRN-TDW-20 | Hank Cochran_Other | Transportation Support | BestTransport - test interface to/from TDW (rates, load extract) | Both | FALSE | 2016-07-15 | 60 | 2016-05-16 | 0% | TRUE |  | McWilliams | not started | TDW must be 'split' prior | [5 empty] | 2016-05-01
HC-16 | TRN-IPS-21 | Hank Cochran_Other | Transportation Support | IPS - update Oracle tables as appropriate (GL accts, etc) | Both | FALSE | 2016-05-31 | 14 | 2016-05-17 | 0% | TRUE | GSS Ledger needs to provide new ledger codes New 'Consolidator' needs to be in place to enter the GL code into | Brock/McWilliams | not started | Depending on how much changes, may take less than 2 weeks | [5 empty] | 2016-05-17 |  | 2016-05-17
HC-16 | TRN-IPS-22 | Hank Cochran_Other | Transportation Support | IPS - Provide new account code structures/codes | Both | FALSE | 2016-05-31 | 14 | 2016-05-17 | 0% | TRUE | GSS Ledger needs to provide new ledger codes Confirm with Locations of agreement IPS needs to update location profiles | Brock, McWilliams | not started | [6 empty] | 2016-05-17 |  | 2016-05-17
HC-16 | TRN-BST-23 | Hank Cochran_Other | Transportation Support | Best Transport - Train BT SPA | Both | FALSE | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Williams/McWilliams | not started | Need to know new ALSO org
HC-16 | TRN-IPS-24 | Hank Cochran_Other | Transportation Support | IPS - Provide new small package shipper numbers | Both | FALSE | 2016-07-15 | 45 | 2016-05-31 | 0% | TRUE |  | Brock, McWilliams | not started | Dependent upon GBS TRN negotiating the new contract & if UPS will be renewed, knowing if UPS will cancel existing shipper #'s and re-issue all new, knowing what the new CPP codes are, when can UPS set up new ones, etc. | [9 empty] | 2016-05-31 | [14 empty] | 2016-05-31
HC-16 | TRN-IPS-25 | Hank Cochran_Other | Transportation Support | IPS to create new Corp Code for Value Add | Both | FALSE | 2016-06-15 | 14 | 2016-06-01 | 0% | FALSE |  | McWilliams | not started | Discuss with IPS how long to split and test
HC-16 | TRN-IPS-26 | Hank Cochran_Other | Transportation Support | IPS - identify locations by new Corp Code | Both | FALSE | 2016-06-15 | 14 | 2016-06-01 | 0% | FALSE |  | Brock/McWilliams | not started | Most locations are easily identified, need to 'split'/setup the 'shared' locations (ex MAS, WAR)
HC-16 | TRN-IPS-27 | Hank Cochran_Other | Transportation Support | IPS -Ensure we maintain "Alcoa" and new business specific support teams at IPS (incl Keyers, QA, etc) | Both | FALSE | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | McWilliams | not started | Determine if splitting current team, having new? Train team under new businesses.
HC-16 | TRN-IPS-28 | Hank Cochran_Other | Transportation Support | IPS - Provide training to any new users | Both | FALSE | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Brock/McWilliams/IPS | not started | dependent on when 'new' users are identified and what their roles are
HC-16 | TRN-PRD-29 | Hank Cochran_Other | Transportation Support | ASATs split | Both | FALSE | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | McWilliams | not started | identify who/how ASATs are being carried forward
HC-16 | TRN-PRD-30 | Hank Cochran_Other | Transportation Support | QTS | Both | FALSE | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE |  | K. Carver/McWilliams | not started | Locations pay for the QTS tracking services and reports | [24 empty] | 2016-06-01
| TRN-TDW-31 |  |  | TDW - Contract Renewals (rates) | Both | FALSE | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE |  | GBS TRN/Devware/McWilliams | not started | Automated contract renewal process exists, the time to do this is 'admin' time and will need to occur in PROD. Will require new contracts to be in place. -- WILL we have new contract in August or October, when LEGALLY split? | [9 empty] | 2016-03-01 | [14 empty] | 2016-03-01
HC-16 | TRN-PRD-32 | Hank Cochran_Other | Transportation Support | MISC: create/update new ALSO webpages | Both | FALSE | 2016-07-31 | 45 | 2016-06-16 | 0% | TRUE | Web applications need to be up for both companies | McWilliams | not started | Need to know who will help us and move them. Currently maintained by Clarence McCaskill (GBS TRN) | [5 empty] | 2016-06-16 | [24 empty] | x | web aps
HC-16 | TRN-BST-33 | Hank Cochran_Other | Transportation Support | BestTransport - set up new location user accounts, update existing accounts as appropriate | Both | FALSE | 2016-06-30 | 10 | 2016-06-20 | 0% | FALSE |  | Williams/McWilliams | not started
HC-16 | TRN-PRD-34 | Hank Cochran_Other | Transportation Support | MISC: Create new mailbox/DL for both businesses for "ALSO" | Both | FALSE | 2016-07-01 | 10 | 2016-06-21 | 0% | TRUE | RemedyWeb'/help desk process needs to be in place | McWilliams | not started | need to know new name, email structure and how to create 'tickets' | [5 empty] | 2016-06-21 | [24 empty] | x | HelpDesk/ticketing process
HC-16 | TRN-PRD-35 | Hank Cochran_Other | Transportation Support | MISC: create new name for ALSO | Both | FALSE | 2016-07-01 | 10 | 2016-06-21 | 0% | FALSE |  | Koenig/McWilliams | not started
HC-16 | TRN-IPS-36 | Hank Cochran_Other | Transportation Support | IPS - Provide carriers with new 'location/customer/patron' codes for EDI | Both | FALSE | 2016-07-01 | 2 | 2016-06-29 | 0% | FALSE |  | Brock/McWilliams/IPS | not started | provide info to carriers and test (IPS)
HC-16 | TRN-IPS-37 | Hank Cochran_Other | Transportation Support | IPS - Communicate new location names to carriers and new IPS billing info | Both | FALSE | 2016-07-01 | 2 | 2016-06-29 | 0% | FALSE |  | Brock/McWilliams | not started | need to mail/email letter to carriers.
HC-16 | TRN-IPS-38 | Hank Cochran_Other | Transportation Support | IPS - Review current report distribution and split as appropriate (new emails) | Both | FALSE | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE |  | Brock/McWilliams | not started
HC-16 | TRN-IPS-39 | Hank Cochran_Other | Transportation Support | IPS - Identify who will be set up for suspense approvals and set up at IPS | Both | FALSE | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE |  | Brock/McWilliams | not started | need to know from locations who to set up (specifically for the 'shared' locations ex MAS & WAR), approx 2 weeks to set up at IPS
HC-16 | TRN-PRD-40 | Hank Cochran_Other | Transportation Support | GBS Transportation SharePoint split - create new for new business; identify owner | Both | FALSE | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | McWilliams | not started | Sharepoint infrastructure ready | [5 empty] | 2016-05-01
HC-16 | TRN-IPS-41 | Hank Cochran_Other | Transportation Support | IPS - Determine how to process bills prior to split date | Both | FALSE | 2016-07-31 | 14 | 2016-07-17 | 0% | FALSE |  | Brock/McWilliams | not started
HC-16 | TRN-BST-42 | Hank Cochran_Other | Transportation Support | BestTransport - confirm and setup as appropriate business tender strategies | Both | FALSE | 2016-07-31 | 14 | 2016-07-17 | 0% | TRUE |  | GBS TRN Sourcing Mgr/Williams | not started | GBS TRN to provide the strategies to have loaded | [24 empty] | 2016-07-17
HC-16 | TRN-TDW-43 | Hank Cochran_Other | Transportation Support | TDW - train new users | Both | FALSE | 2016-07-31 | 14 | 2016-07-17 | 0% | FALSE |  | Devware/McWilliams/Williams | not started
HC-16 | TRN-BST-44 | Hank Cochran_Other | Transportation Support | BestTransport - set up carriers in new accounts | Both | FALSE | 2016-07-31 | 10 | 2016-07-21 | 0% | TRUE | GBS TRN needs to have contracts and rates and advise so we can set up | Williams | not started | [25 empty] | 2016-07-21
HC-16 | TRN-IPS-45 | Hank Cochran_Other | Transportation Support | IPS - Copy W-8/W-9 for carriers, ensure both businesses have copies | Both | FALSE | 2016-07-31 | 7 | 2016-07-24 | 0% | FALSE |  | Brock/McWilliams | not started | Identify GPP carriers and make copies to provide to them.
HC-16 | TRN-IPS-46 | Hank Cochran_Other | Transportation Support | IPS - Identify who receives invoice discs (records retention) | Both | FALSE | 2016-07-31 | 1 | 2016-07-30 | 0% | FALSE |  | McWilliams | not started | dependent upon when new 'ALSO' team is identified.
x
Formulas:
Start Date (Calculated) = [Required Completion Date]-[Days to Accomplish]
Start Date (Calculated) = IF(ISBLANK([Required Completion Date]),"",[Required Completion Date]-[Days to Accomplish])
IT = [Start Date (Calculated)]
Global Shared Services (GSS) = [Start Date (Calculated)]
Transportation = [Start Date (Calculated)]

## Day 1 Project Costs_HC
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Project Costs
| As Of | 2016-02-02 11:34
| Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale
HC12 | 84 | Benefits admin - DB | Provide benefits administration for U.S. based programs for all 26K active employees, 100K+ retirees and active/retiree dependents. DB includes 8 pension plans with 80 structures. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | TRUE | FALSE | Angela Lowry, Joseph Adamietz, Natalie Thomas |  | This cost is necessary to separate/clone the benefit plans for each company in a manner that is in compliance as outlined by direction from HR (Plan Design), Legal, Tax and Industrial Relations. This would include additional resources, doubling of work and/or additional vendors, multiple interface changes
HC15 | 89 | EHS | Provide IHS Systems Support and the running of reports as needed for all businesses in all regoins. | FALSE | TRUE | Angela Lowry, Joseph Adamietz, Kris Koeppl, James Peterson |  | This cost is necessary to separate the EHS Support function as outlined by direction from GSS and EHS.
HC19 | N/A | Benefits admin - H&W | Provide benefits administration for U.S. based programs for all 26K active employees, 40K+ retirees and active/retiree dependents. H&W for 3 active, 10 pre-65 retiree and 10 post-65 retiree H&W Plans that cover 57K+ active and retired employees, plus another 18K+ at One Exchange. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | TRUE | FALSE | Angela Lowry, Joseph Adamietz, Kathleen Viazanko |  | This cost is necessary to separate/clone the benefit plans for each company in a manner that is in compliance as outlined by direction from HR (Plan Design), Legal, Tax and Industrial Relations. This would include additional resources, doubling of work and/or additional vendors, multiple interface changes
HC20 | N/A | Benefits admin - Tuition Assistance | Provide tuition reimbursement assistance and processes for approxiamtely employees. We use GP as our tuition assistance vendor. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | TRUE | FALSE | Angela Lowry, Joseph Adamietz, Paula Bustinger |  | This cost is necessary to separate/clone the benefit plans for each company in a manner that is in compliance as outlined by direction from HR (Plan Design), Legal, Tax and Industrial Relations. This would include additional resources, doubling of work and/or additional vendors, multiple interface changes
HC21 | N/A | Benefits admin - DC | Provide benefits administration for U.S. based programs for all 26K active employees plus 10K inactives with an account balance. DC includes 5 plans when RTI is added on for the value add company, and will need to split out 2 additional plans for the upstream business. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | TRUE | FALSE | Angela Lowry, Joseph Adamietz, David Carozza |  | This cost is necessary to separate/clone the benefit plans for each company in a manner that is in compliance as outlined by direction from HR (Plan Design), Legal, Tax and Industrial Relations. This would include additional resources, doubling of work and/or additional vendors, multiple interface changes
HC22 | N/A | Benefits admin - Benefits Admin Customer Service | Provide benefits administration for U.S. based programs for all 26K active employees, 100K+ retirees and active/retiree dependents. DB includes 8 pension plans with 80 structures. DC includes 5 plans. H&W for 3 active, 10 pre-65 retiree and 10 post-65 retiree H&W Plans that cover 57K+ active and retired employees, plus another 18K+ at One Exchange. We also have a call center run by our vendor that supports over 170K+ monthly hits to the website, plus an additional 12K+ monthly calls to the service center, including escalations and appeals. Additionally, this group is responsible for the production of all benefits communication materials, including, but not limited to, all AE, legislative, standard and non-standard benefits communications. Decisions need to be made as to how these plans will be split and look after separation. I would expect plans would look the same as they do now for the value add, but uncertain for the upstream business. | TRUE | FALSE | Angela Lowry, Joseph Adamietz, Karen Heuber |  | This cost is necessary to separate/clone the benefit plans for each company in a manner that is in compliance as outlined by direction from HR (Plan Design), Legal, Tax and Industrial Relations. This would include additional resources, doubling of work and/or additional vendors, multiple interface changes

## Data Validation (hide) (hidden)
Master Function List | Sub-function list
Legal | Legal | HumanResources | FinanceandAccounting | OCIO | InvestorRelations | Communications | GPI | GlobalBilling | BusinessUnitFunctions | Yes/No | Day 1 Target State | TSA Feasibility | TSA Exit Activities
Human Resources | Benefits | HR Systems | Treasury | PMO | Investor Relations | Inc. PR | Business Office | Operational | Strategy | Yes | Replicate (Clone) | Possible - Low/Medium Complexity | Replicate (Clone)
Finance and Accounting | Stock Systems | GTA | FP&A | Facilities |  | Internal | Operations | Systems | Sales & Business Development | No | Give and Go | Possible - Very Complex | Give and Go
OCIO | Competition | MyHR | Tax | HR Systems |  | Brand / EVP | Tools |  | Marketing |  | New Build | Impossible | New Build
Investor Relations | Corporate | Comp/Ben/M&A | AP | Other Enabling Sys |  | Social Innovation | Services |  | Risk |  | Forward TSA | Not Required | Standalone
Communications | Employment | L&OD | Travel | Finance Systems |  |  | Platform |  | Trust & Safety |  | Reverse TSA |  | Discontinue
GPI | Compliance | Diversity | Purchasing | CS Systems |  |  | Data |  | CS |  | Standalone |  | Operating Agreement
Global Billing | Government Relations |  | Payroll | Traditional IT Systems |  |  | Infrastructure/Cloud |  | PD / Arch |  | Discontinue
Business Unit Functions | IP |  | Finance Separation |  |  |  | Data Center |  | Product |  | Operating Agreement
| Privacy |  | Accounting Policy | [5 empty] | Data
| Litigation |  | SEC Reporting | [5 empty] | Info Security
| Real Estate |  | SOX | [5 empty] | Regulatory
Finance Trans
Procurement

## Countries (hidden)
# | Location Country | Total Employees
1 | USA Total |  | USA | USA | FRA | GBR | CAN | DEU | IND | AUS | SWE | MEX | BEL | HKG | SGP | CHE | ARG | NLD | DNK | TWN | POL | NOR | THA | CZE | GRC | HUN | MCO | ESP | LUX | FIN | JPN | NZL | BRA | CHN | IRL | MYS | RUS
2 | FRA Total |  | FRA | USA: USA,FRA,GBR,CAN,DEU,IND,AUS,SWE,MEX,BEL,HKG,SGP,CHE,ARG,NLD,DNK,TWN,POL,NOR,THA,CZE,GRC,HUN,MCO,ESP,LUX,FIN,JPN,NZL,BRA,CHN,IRL,MYS,RUS
3 | GBR Total |  | GBR
4 | CAN Total |  | CAN
5 | DEU Total |  | DEU
6 | IND Total |  | IND
7 | AUS Total |  | AUS
8 | SWE Total |  | SWE
9 | MEX Total |  | MEX
10 | BEL Total |  | BEL
11 | HKG Total |  | HKG
12 | SGP Total |  | SGP
13 | CHE Total |  | CHE
14 | ARG Total |  | ARG
15 | NLD Total |  | NLD
16 | DNK Total |  | DNK
17 | TWN Total |  | TWN
18 | POL Total |  | POL
19 | NOR Total |  | NOR
20 | THA Total |  | THA
21 | CZE Total |  | CZE
22 | GRC Total |  | GRC
23 | HUN Total |  | HUN
24 | MCO Total |  | MCO
25 | ESP Total |  | ESP
26 | LUX Total |  | LUX
27 | FIN Total |  | FIN
28 | JPN Total |  | JPN
29 | NZL Total |  | NZL
30 | BRA Total |  | BRA
31 | CHN Total |  | CHN
32 | IRL Total |  | IRL
33 | MYS Total |  | MYS
34 | RUS Total |  | RUS
Grand Total