## Instructions and Descriptions
Project Elevation
High-Level Separation Workplan - Instructions, Descriptions, and Examples
Below are instructions for the high-level separation workplan template
This template comprises of three tabs: one focused a list of Day 1 projects, the second focused on capturing the tasks and milestones required to complete those projects, and final focused on capturing project-associated costs
1) Follow the directions in the light grey rows of example tables below. There is an example table for each of the three tabs; example line items are provided in italics.
2) This template is designed to be modular - if you need to create multiple Project Plan tabs to break up workplanning, please do so. Indicate your tab divisions by renaming the tab where it says "{Project}"
3) Please refer any questions to your separation counterpart or contact. Leverage your contact for help with submission and plan consolidation
| Day 1 Project List Tab | Orange fields due for completion by 4 December 2015
| Activity-Level Description | [14 empty] | Dependency Resolution Checklist
| Project ID (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | Day 1 Project Description | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with a workstream-defined three letter code for WS & SWS and a unique 3 digit code for the activity within | List the name of the Resource Unit, Function, or division acting as a workstream with the separation | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Provide a detailed description (what, why and where) of the Day 1 Project | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Provide the date by which this project must be completed | Provide an estimate of the number of calendar days it will take to complete the entire project | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the project is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
x | HRD-LRL-001 | Human Resources | Labor Relations | French Works Council Approval | Adjusting organizations in France requires gaining approval from the Works Council via a formal proposal | Both | 2016-06-01 | 132 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Will require input from X, Y, and Z | [27 empty] | 2016-01-15
| HRD-LRL-002 | Human Resources | Labor Relations | German Works Council Approval | Adjusting organizations in Germany requires gaining approval from the Works Council via a series of formal meetings | Both | 2016-06-01 | 102 | 2016-02-20 | 0% | FALSE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Will require input from X, Y, and Z | [27 empty] | 2015-10-31
| Project Plan Tab | Fields due for completion by 17 December 2015
| Task-Level Description | [14 empty] | Dependency Resolution Checklist
| Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with workstream-defined three letter code for SWS, the unique 3 digit code for the activity, and a two digit code for the task | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Identify the name of the task that must be done to complete the project. Only list one task per row | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Mark whether or not this task is a milestone for a project. Milestones are the most critical tasks within a project, which are often time-sensitive. | Provide the date by which this task must be completed | Provide an estimate of the number of calendar days it will take to complete the entire task | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the task is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, important subtasks that must be captured, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
| LRL-001-01 | Labor Relations | French Works Council Approval | -Draft Proposal | Both | FALSE | 2016-02-20 | 30 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-001-02 | Labor Relations | French Works Council Approval | -Submit Proposal | Both | TRUE | 2016-03-01 | 10 | 2016-02-20 | 0% | FALSE |  | Dominique Bordeaux | Not Started
| LRL-001-03 | Labor Relations | French Works Council Approval | -Follow up after 3 months | Both | FALSE | 2016-06-01 | 90 | 2016-03-03 | 0% | FALSE |  | Dominique Bordeaux | Not Started
x | LRL-002-01 | Labor Relations | German Works Council Approval | -Draft Proposal | Both | FALSE | 2016-03-20 | 30 | 2016-02-19 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-002-02 | Labor Relations | German Works Council Approval | -Submit Proposal | Both | TRUE | 2016-04-01 | 10 | 2016-03-22 | 0% | FALSE |  | Petra Schmidt | Not Started
| LRL-002-03 | Labor Relations | German Works Council Approval | -Follow up after 2 months | Both | FALSE | 2016-06-01 | 60 | 2016-04-02 | 0% | FALSE |  | Petra Schmidt | Not Started
Project Costs Tab
| Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale
| Provide the unique ID for the project defined on the Day 1 Projects tab | Provided the name of the Day 1 project defined on the Day 1 Projects tab | Provide a description of what the cost is and why it exists | Indicate if this cost is a dis-synergy (incl stranded cost) (True/False) | Indicate if this cost is a one-time cost (True/False) | Indicate who will own the plan to minimize and address this cost | Provide an estimated cost for all or part of this Day 1 Project | Briefly describe rationale (business case) for cost estimate
| HRD-LRL-002 | German Works Council Approval | Lobbying - Gaining approval often requires spending money to lobby key officials | No | Yes | Peter Schmidt | 10000 | Spending this money will reduce risk and speed transition for German Org
x
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Instructions and Descriptions'!$[Required Completion Date]),"",'Instructions and Descriptions'!$[Required Completion Date]-'Instructions and Descriptions'!$[Days to Accomplish])

## Day 1 Project List_AT
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Projects
| As Of | 2016-02-19 09:54
Project-Level Description | [17 empty] | Dependency Resolution Checklist
Project # | Project ID Blueprint # (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | In scope sub processes | Day 1 Project Description | Country of Service Delivery | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) PLEASE INSERT DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | Total # Tasks in Project | # of Tasks for Review | % Project Tasks For review | Project For GSS PMO Review? | Start Date Review | Completion Date Review | % Complete Progression Review | % Tasks for Review Flag | Off Track or at risk
AT01 | 94 | GSS | Alain Taillefer_Canada People Services | Payroll Kronos | Acquisition/Divestiture Services General Ledger Accounting Government Compliance Reporting | Establish organization structure, name changes, review contracts, new tax ID, notify to government new names, change bank contract and bank account numbers. | Mexico | V-A Co. | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Tax, Legal, Treasury. Legal department has to confirm the new names for locations. IT: GBS system will need to be updated for name | Alain Taillefer | Not Started | In conjuction with Tax, corporate consolidation, FP&A, Financial transactions and BU controllers review and implement new LEC/LBC/BU structure for each company. |  | 2016-02-08 |  | 2016-01-08 | [11 empty] | 2016-05-01 | [16 empty] | 7 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT02 | 94 | GSS | Alain Taillefer_Mexico Finance | FAS Mexico | Acquisition/Divestiture Services General Ledger Accounting Government Compliance Reporting | Establish organization structure, name changes, review contracts, new tax ID, notify to government new names, change bank contract and bank account numbers. | Mexico | V-A Co. | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Tax, Legal, Treasury. Legal department has to confirm the new names for Mexican locations. IT: GBS system will need to be updated for name | Pedro Rosas | Not Started | In conjuction with Tax, corporate consolidation, FP&A, Financial transactions and BU controllers review and implement new LEC/LBC/BU structure for each company. |  | 2016-02-08 |  | 2016-01-08 | [11 empty] | 2016-05-01 | [16 empty] | 5 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT03 | 95 | GSS | Alain Taillefer_Mexico Finance | Accounts Payable Mexico | Invoice processing Payment processing Holds resolution Customer service AP subledger closing | Communication with vendors for names changes and change names and bank account numbers, checks. | Mexico | V-A Co. | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Tax, Legal, Procurement, Treasury. Legal department has to confirm the new names for Mexican locations. Tresury will need to open new bank accounts with new names and IT system setup to link the new bank accounts. Procurment has to review their contract accordingly | Pedro Rosas | Not Started |  |  | 2016-02-08 | 2016-03-08 | 2016-01-08 | [5 empty] | 2016-06-08 | [5 empty] | 2016-07-01 | [16 empty] | 3 | 0 | 0% | No Review | REVIEW | REVIEW | - |  | -
AT04 | 97 | GSS | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Preparation of invoices for all Mexican locations, send fiscal invoices to customers, create fiscal invoice | Notified change name to customers and provide VAT taxes numbers, change bank account numbers. | Mexico | V-A Co. | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Tax, Legal. Legal department has to confirm the new names for Mexican locations. | Pedro Rosas | Not Started |  |  | 2016-02-08 | 2016-03-08 | 2016-01-08 | [11 empty] | 2016-05-31 | [16 empty] | 3 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT05 | 98 | GSS | Alain Taillefer_Mexico Finance | T&E Mexico | Management of all T&E precess including the customer services, issuance of credit card etc - Annual reconciliation - T&E audit - Customer service desk - Escalation management - LVP admin | Name change on contract with CITI related to Credit Cards for travelers. | Mexico | V-A Co. | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Tax, Legal. Legal department has to confirm the new names for Mexican locations. | Pedro Rosas | Not Started |  |  | 2016-02-08 | 2016-03-08 | 2016-01-08 | [11 empty] | 2016-07-01 | [16 empty] | 2 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT06 | 100 | GSS | Alain Taillefer_Canada People Services Other | GPS | Domestic Payroll Production, Payroll Tax Administration, Garnishment Administration, SUB Payroll Production, Payroll Accounting & Account Reconciliation, | Work with Mexican lawyers to change the social benefits ID number to new company names. Change contract with payroll vendor system. | Mexico | V-A Co. | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Tax, Legal. Legal department has to confirm the new names for Mexican locations. | Pedro Rosas | Not Started |  |  | 2016-02-08 | 2016-03-08 | 2016-01-08 | [11 empty] | 2016-07-01 | [16 empty] | 3 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT07 | 101 | GSS | Alain Taillefer_Mexico People Services | Compensation & Benefits admin | Health & welfare contract management customers services Pension and insurance | Change suppliers contract for employees benefits ( insurance and pension ) | Mexico | V-A Co. | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Tax, Legal. Legal department has to confirm the new names for Mexican locations. | Pedro Rosas | Not Started |  |  | 2016-02-08 |  | 2016-01-08 | [11 empty] | 2016-07-01 | [16 empty] | 2 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT08 | 103 | GSS | Alain Taillefer_Mexico Finance | Corporate & VAT taxes Mexico | Income Tax and Tax claim for VAT Tax Planning Tax Returns and Reporting Manage governement audit Transfer pricing study Support BU with all tax questions | Obtain all new tax ID numbers for corporate and VAT taxes. Change bank account numbers. | Mexico | V-A Co. | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Tax, Legal. Legal department has to confirm the new names for Mexican locations. | Pedro Rosas | Not Started |  |  | 2016-02-08 |  | 2016-01-08 | [11 empty] | 2016-07-01 | [16 empty] | 2 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT09 | 106 | GSS | Alain Taillefer_Canada Finance | FAS Canada | Acquisition/Divestiture Services General Ledger Accounting Government Compliance Reporting Intercompany Accounting Account reconciliation Customer services | Establish organization structure, name changes, review contracts, new tax ID, notify to government new names, change bank contract and bank account numbers. | Canada | Both | 2016-02-28 | 75 | 2015-12-15 | 15% | TRUE | Tax and legal department has to confirm the new corporate structure and names for Canadian locations. IT: GBS system will need to be updated for name . Agreed with consolidation and international tax for the Canadian structure for BU, RU reportingchanges | Alain and Pedro | On Track | In conjuction with Tax, corporate consolidation, FP&A, Financial transactions and BU controllers review and implement new LEC/LBC/BU structure for each company. | 2015-12-15 | 2015-12-15 |  | 2015-12-15 |  | 2015-12-15 | [9 empty] | 2015-12-15 | [16 empty] | 5 | 0 | 0% | No Review | - | REVIEW | REVIEW | - | -
AT10 | 107 | GSS | Alain Taillefer_Canada Finance | Accounts Payable Canada | Invoice processing Payment processing Holds resolution Customer service AP subledger closing GRNI Reporting | Notified change name to customers and provide VAT taxes numbers, change bank account numbers. Procurement will have to manage the PO accordingly to the new orgs. | Canada | Both | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly | Alain and Pedro | Not Started |  |  | 2016-02-08 | 2016-03-08 | 2016-01-08 |  | 2016-05-08 |  |  |  | 2016-06-08 | [5 empty] | 2016-05-31 | [16 empty] | 4 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT11 | 109 | GSS | Alain Taillefer_Canada Finance | Accounts Receivable Canada | Liaison with locations for invoice preparation | Notified change name to customers and provide VAT taxes numbers, change bank account numbers. | Canada | Both | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Tax department has to confirm the corporate structure and new names for locations. Treasury will need to open new bank accounts and GSS Hungary will need to modify the invoices layout and system setup to link the new bank accounts | Alain and Pedro | Not Started |  |  | 3-30-16 | 5-31-16 |  |  |  |  | 6-31-16 | [7 empty] | 2016-07-01 | [16 empty] | 3 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT12 | 112 | GSS | Alain Taillefer_Canada Finance | T&E Canada | Management of all T&E precess including the customer services, issuance of credit card etc - Annual reconciliation - T&E audit - Customer service desk - Escalation management - LVP admin | Name change on contract with CITI and Amex Canada related to Credit Cards for travelers. Contract split, split concur in two | Canada | Both | 2016-07-31 | 40 | 2016-06-21 | 0% | TRUE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly | Alain and Pedro | Not Started |  |  | 3-30-16 | [7 empty] | 2016-04-30 | [5 empty] | 2016-06-21 | [16 empty] | 2 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT13 | 113 | GSS | Alain Taillefer_Canada People Services | Payroll | Domestic Payroll Production, Payroll Tax Administration, Garnishment Administration, Payroll Accounting & Account Reconciliation, Expatriate Payroll Production | Separate contract ( Desjardins, Kronos) Should be done in Canada Hire pay master for value Add create new Cloud and Kronos environment for value add GL Reconciliation Work with Canadian lawyers to change legal entity names. Change contract with payroll vendor system. REview payroll with following the new corporate structure | Canada | Both | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly. IT will work with us to separte payroll and T&A system | Mariano | Not Started |  |  | 3-30-16 | [7 empty] | 2016-04-30 | [5 empty] | 2016-05-02 | [16 empty] | 5 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT14 | 114 | GSS | Alain Taillefer_Canada People Services | T&A | Kronos Time & Attendance Support | split the agreement with Kronos and two clouds Integrate RTI -Laval before the split standardize processes train the trainer implement GPS | Canada | Both | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly. IT will work with us to separte payroll and T&A system | Mariano | Not Started | [10 empty] | 2016-04-30 | [5 empty] | 2016-05-02 | [16 empty] | 3 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT15 | 115 | GSS | Alain Taillefer_Canada People Services | Benefits and Administration | Health & welfare | Change suppliers contract for employees benefits ( insurance and pension ) | Canada | Both | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | HR will assist in communication with employees and Legal will review new contracts | Mariano | Not Started |  |  |  |  | 2016-06-01 | 2016-06-01 | [10 empty] | 2016-05-02 | [16 empty] | 4 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT16 | 116 | GSS | Alain Taillefer_Canada People Services | People Services Transaction Support | GPS data management | duplicate GPS train IT SPA on HCMCA | Canada | Both | 2016-06-01 | 60 | 2016-04-02 | 0% | TRUE | IT and or GBS US will work on separation of the database of GPS | Mariano | Not Started | [6 empty] | 6-30-16 |  | 6-30-16 | [7 empty] | 2016-04-02 | [16 empty] | 1 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT17 | 118 | GSS | Alain Taillefer_Canada People Services Other | Global Mobility | Expatriate assignments as well as extended business travelers, Provide support for Payroll, Health Care and taxes | Knowledge and procedure transfert to value add SPA | Canada | Both | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Agreed with HR on the policy to used for transfer of employees | Alain and Pedro | Not Started | [5 empty] | 6-30-15 | [10 empty] | 2016-07-01 | [16 empty] | 1 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT18 | 119 | GSS | Alain Taillefer_Canada Compliance and reporting | Compliance | #NAME? | Transfer knowledge to new SPA, Integrate RTI-Laval in the process Establish updated contract with Hungary will continue to support value add F03, F05, F07, F08' F09, F10, F11 | Canada | Both | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Split the ASP system and agreed on Hub services with Hungary | Alain and Pedro | Not Started | [6 empty] | 6-30-16 | [9 empty] | 2016-06-01 |  |  |  | 6-30-16 | [12 empty] | 2 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT19 | 120 | GSS | Alain Taillefer_Canada Finance | Corporate & VAT taxes Canada | Corporate and VAT taxe return preparation | Obtain all new tax ID numbers for corporate and VAT taxes. | Canada | Both | 2016-07-31 | 180 | 2016-02-02 | 4% | TRUE | Agreed with consolidation and international tax for the Canadian structure for BU, RU reporting | Alain and Pedro | On Track |  | 3-31-16 | [14 empty] | 2016-02-02 | [16 empty] | 1 | 0 | 0% | No Review | - | REVIEW | REVIEW | - | -
AT20 | 124 | GSS | Alain Taillefer_Canada Finance | Pension funds accounting and Admin | Pension accounting , audited financial statement Managing the assets | Agree on TCA Split the defined benefits plan Obtain government approval Coordinate with actuaries, corporate and PWC | Canada | Both | 2016-07-31 | 180 | 2016-02-02 | 10% | TRUE | Work with Benefit accounting group for F/S reporting, Legal and procurment will assist with the separation of pension funds and required suppliers contracts | Alain and Pedro | On Track |  | 1-15-16 |  |  | 5-31-16 | [5 empty] | 5-31-16 | [5 empty] | 2016-02-02 | [16 empty] | 2 | 0 | 0% | No Review | - | REVIEW | - | - | -
AT21 | 125 | GSS | Alain Taillefer_Canada Other | Corporate affair | Archive,gov stat, legal books etc | Seperate archves Updates minutes books responsability transfer to new book SPA | Canada | Both | 2016-07-31 | 180 | 2016-02-02 | 4% | TRUE | Legal will prepare corporate books when names changes when they are confirm by tax department | Alain and Pedro | On Track |  |  | 3-31-16 |  | 5-31-16 | [11 empty] | 2016-02-02 | [16 empty] | 3 | 0 | 0% | No Review | - | REVIEW | REVIEW | - | -
AT22 | 126 | GSS | Transformation_Facilities | Shared Facilities | Physical location of office and all supporting infrastructure | Project to address all infrastructure to support both orgs | Mexico and Canada | Both | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | Facilities for upstram already in place no change. For Value add, it should be in Howmet Laval facilitites, we need to review if we are missing anything IT will need to review if servers are available to cover the need for shared services. Finally HR will assist to hire employees if required | Lisa Marie | Not Started | [5 empty] | 4-30-16 | 5-31-16 | [9 empty] | 2016-03-03 | [16 empty] | 9 | 0 | 0% | No Review | REVIEW | REVIEW | - | - | -
AT23 | 131 | GSS | Alain Taillefer_Canada Finance | Archive,gov stat, legal books etc |  |  |  |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Alain and Pedro | Not Started | [16 empty] | 2016-05-02 | [16 empty] | 3 | 0 | 0 |  | REVIEW | REVIEW | - | - | -
AT24 | 134 | GSS | Alain Taillefer_Canada Finance | Benefits accounting |  |  |  |  | 2016-07-31 | 210 | 2016-02-08 | 10% | FALSE |  | Alain Taillefer | On Track | [16 empty] | 2016-01-03 | [17 empty] | 0 | #DIV/0! |  | - | REVIEW | - | - | -
AT25 | 136 | GSS | Alain Taillefer_Mexico People Services | Payroll TRESS |  |  |  |  | 2016-05-31 | 90 | 2016-03-31 | 0% | FALSE |  | Pedro Rosas | Not Started | [16 empty] | 2016-03-02 | [16 empty] | 6 | 0 | 0 |  | REVIEW | REVIEW | - | - | -
AT26 | 137 | GSS | Alain Taillefer_Canada People Services | Insurance |  |  |  |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Alain Taillefer | Not Started | [16 empty] | 2016-06-01 | [16 empty] | 6 | 0 | 0 |  | REVIEW | REVIEW | - | - | -
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Day 1 Project List_AT'!$[Required Completion Date]),"",'Day 1 Project List_AT'!$[Required Completion Date]-'Day 1 Project List_AT'!$[Days to Accomplish])
Gov't Affairs = IF(ISBLANK('Day 1 Project List_AT'!$[Required Completion Date]),"",'Day 1 Project List_AT'!$[Required Completion Date]-'Day 1 Project List_AT'!$[Days to Accomplish])
Project For GSS PMO Review? = IF(AND('Day 1 Project List_AT'!$[Status]<>"On Track",'Day 1 Project List_AT'!$[Start Date (Calculated)]<TODAY()+7),"Review",IF(OR('Day 1 Project List_AT'!$BA10>0.25),"Review","No Review"))
Start Date Review = IFERROR(IF(ProjectsTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF(ProjectsTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Finance = IF(ISBLANK('Day 1 Project List_AT'!$[Required Completion Date]),"",'Day 1 Project List_AT'!$[Required Completion Date]-'Day 1 Project List_AT'!$[Days to Accomplish])
Tax = IF(ISBLANK('Day 1 Project List_AT'!$[Required Completion Date]),"",'Day 1 Project List_AT'!$[Required Completion Date]-'Day 1 Project List_AT'!$[Days to Accomplish])
Legal = IF(ISBLANK('Day 1 Project List_AT'!$[Required Completion Date]),"",'Day 1 Project List_AT'!$[Required Completion Date]-'Day 1 Project List_AT'!$[Days to Accomplish])
IT = IF(ISBLANK('Day 1 Project List_AT'!$[Required Completion Date]),"",'Day 1 Project List_AT'!$[Required Completion Date]-'Day 1 Project List_AT'!$[Days to Accomplish])

## Risk Register
Date risk recorded | Project Number | Day 1 Project Name | Sub-Workstream (SWS) | Related project Task ID(s) | Risk Title | Mitigating Action(s) | Probability of occurance (0-100%) 0% being less probable | Degree of Impact (1-10) 1 being low impact | Risk rating (Probability x Impact) | For discussion in GSS PMO? (Y/N) | Status | Weekly Status Comments (enter date DD-MON-YYYY (06-JAN-2016) then comment) | Person recording risk (Last name, First name) | Date Reviewed in PMO DD-MON-YYYY (06-JAN-2016) | Track in Deloitte tool? | SPO escalation?
2016-01-14 | All | All | All | All | Risk of system clones not completing on time and delaying integrated functional testing (data, applications, interfaces) and remediation. | Participate with GIS, and deliver needed inputs and knowledge…prepare for timely and thorough testing. |  |  | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
2016-01-14 | All | All | All | All | Need to ensure sufficient testing resources are in place to support functional testing. Extra resources need to be brought with proper lead time so as to be productive during testing and remediation. | Resources for growth/sweeps need to be hired earlier so that we have resources freed up for testing. |  |  | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
2016-01-18 | All | All | All | All | Risk of filling dis-synergie positions too late. There are a number of key open positions, where we need to start hiring asap. E.g. Payment team member, US-AUS-CAN AP Team Lead, Functional Support PO/Inv, TBO team members | Discuss whether we can start posting jobs and seeking for candidates. Need approval for these positions asap. |  |  | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[5 empty] | Pension Fund – It will take more than two years to get all government approvals |  |  |  | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[5 empty] | Get the final corporate structure by 2/2/016 for both companies and name change for 3/31/2016 |  |  |  | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[5 empty] | Alcoa GIS resources availability on time |  |  |  | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>

## Project Plan(s) - {AT}
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 09:54
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) PLEASE INSERT DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours | Start Date Review | Completion Date Review | % Complete Progression Review
AT01 | PAY-001-00 | Alain Taillefer_Canada People Services | Payroll Kronos | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-28 |  | 2016-01-15 | 15% |  |  | Cote, Mariano | On Track | [33 empty] | No Review | [5 empty] | - | REVIEW | -
AT01 | PAY-001-22 |  |  | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-04-15 |  | 2016-03-01 | 0% |  |  | Cote, Mariano | Not Started | [39 empty] | REVIEW | REVIEW | -
AT01 | PAY-001-23 |  |  | Obtain IT sign off for vendor owned system scope of work | Both | TRUE | MPS_5 | 2016-05-01 |  | 2016-04-01 | 0% |  |  | Cote, Mariano | Not Started | [39 empty] | REVIEW | REVIEW | -
AT01 | PAY-001-08 | Alain Taillefer_Canada People Services | Payroll Kronos | Align IT systems strategy with IT organization | Both | FALSE | MPS_3 | 2016-03-30 |  | 2016-02-15 | 10% |  |  | Cote, Mariano | Off Track | [33 empty] | Review | [5 empty] | - | REVIEW | -
AT01 | PAY-001-01 | Alain Taillefer_Canada People Services | Payroll Kronos | Split payroll Desjardins contract Procurement to execute vendor owned system scope of work for standing up second system | Both | FALSE | MPS_6 | 2016-03-31 | 30 | 2016-03-01 | 10% | TRUE | Tax department has to confirm the corporate structure and new names for locations. . IT will work with us to split payroll and T&A system | Cote, Mariano | On Track | kronos will go with upstream. TSA for H2-2016. | [32 empty] | No Review | 12 | CSS LEAD | 12 | HR |  | REVIEW | REVIEW | -
AT01 | PAY-001-02 | Alain Taillefer_Canada People Services | Payroll Kronos | Agree TSA for payroll for H2-16 | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly. IT will work with us to separte payroll and T&A system | Cote, Mariano | Not Started | [8 empty] | 2016-05-30 | [24 empty] | No Review | 12 | CSS LEAD | 12 | Payroll |  | REVIEW | REVIEW | -
AT01 | PAY-001-03 | Alain Taillefer_Canada People Services | Payroll Kronos | Create V-A Co structure payroll system (LBC) | V-A Co. | TRUE | MPS_10 | 2016-05-01 | 90 | 2016-02-01 | 5% | TRUE |  | Taillefer Alain | On Track | [33 empty] | No Review | 120 | System support | 380 | Payroll |  | - | REVIEW | REVIEW
AT01 | PAY-001-10 | Alain Taillefer_Canada People Services | Payroll Kronos | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-03-01 |  | 2016-02-15 | 5% |  |  | Taillefer Alain | On Track | [33 empty] | No Review | [5 empty] | - | REVIEW | -
AT01 | PAY-001-04 | Alain Taillefer_Canada People Services | Payroll Kronos | Government ID# change V-A Co | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | for 2017. It will cost 5k per employee to do it within the year | Langlois, Diane | Not Started |  |  | 2016-03-31 | [30 empty] | No Review | 12 | Tax | 12 | Payroll |  | REVIEW | REVIEW | -
AT01 | PAY-001-05 | Alain Taillefer_Canada People Services | Payroll Kronos | Create Icloud Value Add | V-A Co. | FALSE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | FALSE | Tax: Canadian Tax | Couillard, Guillaume | Not Started | [31 empty] | 2016-05-01 | Kronos (vendor) | No Review | 80 | System support | 20 | Payroll |  | REVIEW | REVIEW | -
AT01 | PAY-001-07 | Alain Taillefer_Canada People Services | Payroll Kronos | Duplicate and create set of procedures for Value Add | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Johane Goulet | Not Started | [33 empty] | No Review | 40 | Payroll |  |  |  | REVIEW | REVIEW | -
AT01 | PAY-001-06 | Alain Taillefer_Canada People Services | Payroll Kronos | Create / Update SOPs and Training Documents | Both | FALSE |  | 2016-04-30 | 90 | 2016-01-31 | 10% | FALSE |  | Cote, Mariano | On Track | [33 empty] | No Review | 30 | Payroll |  |  |  | - | REVIEW | REVIEW
AT14 | T&A-001-01 | Alain Taillefer_Canada People Services | T&A | Split Kronos contract Procurement to execute vendor owned system scope of work for standing up second system | Both | FALSE | MPS_6 | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly. IT will work with us to separte payroll and T&A system | Cote, Mariano | Not Started | [33 empty] | No Review | 12 | CSS LEAD | 12 | Payroll |  | REVIEW | REVIEW | -
AT14 | T&A-001-02 | Alain Taillefer_Canada People Services | T&A | Create V-A Co structure in the system | V-A Co. | TRUE |  | 2016-05-01 | 60 | 2016-03-02 | 0% | TRUE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly. IT will work with us to separte payroll and T&A system | Cote, Mariano | Not Started | [33 empty] | No Review | 20 | System support | 80 | Payroll |  | REVIEW | REVIEW | -
AT14 | T&A-001-02 | Alain Taillefer_Canada People Services | T&A | Vendor commences work to stand-up separate system | V-A Co. |  | MPS_7 | 2016-04-01 |  | 2016-02-28 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT14 | T&A-001-05 | Alain Taillefer_Canada People Services | T&A | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. |  | MPS_8 | 2016-05-01 |  | 2016-04-01 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT14 | T&A-001-06 | Alain Taillefer_Canada People Services | T&A | Agree TSA for payroll for H2-2016 | Both | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE | Tax department has to confirm the corporate structure and new names for locations. Procurment has to review their contract accordingly. IT will work with us to separte payroll and T&A system | Cote, Mariano | Not Started | [8 empty] | 2016-05-30 | [24 empty] | No Review | 12 | CSS LEAD | 12 | Payroll |  | REVIEW | REVIEW | -
AT20 | BEN-001-01 | Alain Taillefer_Canada Finance | Pension funds accounting and Admin | Agree 2-years TSA (DB) | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | HR will assist in communication with employees and Legal will review new contracts | Taillefer Alain | Not Started | [5 empty] | 2016-06-01 | [27 empty] | No Review | 12 | CSS LEAD |  |  |  | REVIEW | REVIEW | -
AT20 | BEN-001-02 | Alain Taillefer_Canada Finance | Pension funds accounting and Admin | Split saving plan (401K)(DC) | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | Work with Benefit accounting group for F/S reporting, Legal and procurment will assist with the separation of pension funds and required suppliers contracts | Methot, Stephane | Not Started | [5 empty] | 2016-06-01 | [27 empty] | No Review | 12 | CSS LEAD | 12 | Pension Funds |  | REVIEW | REVIEW | -
AT26 | BEN-002-01 | Alain Taillefer_Canada People Services | Insurance | Split benefits contract | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | HR will assist in communication with employees and Legal will review new contracts | Methot, Stephane | Not Started | [5 empty] | 2016-06-01 | [27 empty] | No Review | 40 | Benefits Admin | 20 | CSS Lead |  | REVIEW | REVIEW | -
AT26 | BEN-002-02 | Alain Taillefer_Canada People Services | Insurance | Integrate RTI-Laval into Canadian contract | V-A Co. | TRUE |  | 2016-06-01 | 60 | 2016-04-02 | 10% | FALSE |  | Methot, Stephane | Not Started | [5 empty] | 2016-06-01 | [27 empty] | No Review | 24 | Benefits Admin | 20 | Benefits accounting |  | REVIEW | REVIEW | -
AT06 | PST-001-001 | Alain Taillefer_Canada People Services Other | GPS | TCA for GPS for Day 1 | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Couillard, Guillaume | Not Started | Assumption is GPS goes with value add | [7 empty] | 2016-05-30 | [24 empty] | No Review | 40 | System support | 20 | Benefits admin |  | REVIEW | REVIEW | -
AT06 | PST-001-002 | Alain Taillefer_Canada People Services Other | GPS | Create clone in UpStream | Both | FALSE |  | 2016-05-30 | 90 | 2016-03-01 | 0% | FALSE | IT and or GBS US will work on separation of the database of GPS | Couillard, Guillaume | Not Started | Assumption is GPS goes with value add | [5 empty] | 2016-03-01 |  | 2016-03-01 | [24 empty] | No Review | 40 | System support |  |  |  | REVIEW | REVIEW | -
AT06 | PST-001-003 | Alain Taillefer_Canada People Services Other | GPS | Duplicate HCMCa for value add in Canada | Both | FALSE |  | 2016-05-30 | 90 | 2016-03-01 | 0% | FALSE | IT and or GBS US will work on separation of the database of GPS | Couillard, Guillaume | Not Started | [6 empty] | 2016-03-01 |  | 2016-03-01 | [24 empty] | No Review | 40 | System support |  |  |  | REVIEW | REVIEW | -
AT25 | PAY-001-21 | Alain Taillefer_Mexico People Services | Payroll TRESS | Adjust contract with new entity name | V-A Co. | TRUE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | FALSE |  | Rosas, Pedro | Not Started | [8 empty] | 2016-06-30 | [24 empty] | No Review | 12 | GSS Lead | 12 | Tax |  | REVIEW | REVIEW | -
AT25 | PAY-001-03 | Alain Taillefer_Mexico People Services | Payroll TRESS | Government ID# change V-A Co | V-A Co. | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Rosas, Pedro | Not Started | [33 empty] | No Review | 12 | Tax | 12 | GSS Lead |  | REVIEW | REVIEW | -
AT07 | BEN-001-01 | Alain Taillefer_Mexico People Services | Compensation & Benefits admin | Pension Funds - Change name on saving plan (DC) contract | V-A Co. | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | Change name | Rosas, Pedro | Not Started |  |  |  |  | 2016-06-01 | 2016-06-01 | [27 empty] | No Review | 12 | GSS Lead | 12 | HR |  | REVIEW | REVIEW | -
AT07 | BEN-002-01 | Alain Taillefer_Mexico People Services | Compensation & Benefits admin | Insurance - Change benefits contract name | V-A Co. | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE | HR will assist in communication with employees and Legal will review new contracts | Rosas, Pedro | Not Started |  |  |  |  | 2016-01-05 | 2016-06-01 | [27 empty] | No Review | 12 | GSS Lead | 12 | HR |  | REVIEW | REVIEW | -
AT09 | FAS-001-01 | Alain Taillefer_Canada Finance | FAS Canada | Establish organization structure, name changes, BU entity hierarchy | Both | TRUE | FS_2 | 2016-02-12 | 105 | 2015-10-30 | 10% | TRUE | All other process depend on mane changes and corpoarte structure | Taillefer Alain | On Track | Working with Tax depratment and laywers Stickman | 2016-02-05 | 2016-02-05 |  | 2016-02-05 |  |  |  | 2016-02-05 | 2016-02-05 | [6 empty] | 2016-01-05 | [16 empty] | No Review | 800 | Tax | 80 | CSS Lead |  | - | - | REVIEW
AT09 | FAS-001-02 | Alain Taillefer_Canada Finance | FAS Canada | Review contracts | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started | Will work with Procurment Isabelle Foster. | [32 empty] | No Review | 80 | CSS LEAD | 80 | HR |  | REVIEW | REVIEW | -
AT09 | FAS-001-03 | Alain Taillefer_Canada Finance | FAS Canada | New tax ID, notify to government new names, | Both | TRUE | FS_3 | 2016-03-31 | 60 | 2016-01-31 | 5% | TRUE |  | Langlois Diane | On Track |  |  | 2016-02-01 | [30 empty] | No Review | 200 | Tax | 40 | CSS Lead |  | - | REVIEW | REVIEW
AT09 | FAS-001-04 | Alain Taillefer_Canada Finance | FAS Canada | Change bank contract and bank account numbers. | Both | TRUE | FS_11 | 2016-04-30 | 90 | 2016-01-31 | 5% | TRUE |  | Taillefer Alain | On Track |  |  |  | 2016-05-01 | [29 empty] | No Review | 40 | CSS LEAD |  |  |  | - | REVIEW | REVIEW
AT09 | FAS-001-05 | Alain Taillefer_Canada Finance | FAS Canada | Create / Update SOPs and Training Documents | Both | FALSE | FS_24 | 2016-09-30 | 80 | 2016-07-12 | 0% | FALSE |  | Taillefer Alain | Not Started | [33 empty] | No Review | 60 | FAS |  |  |  | REVIEW | REVIEW | -
AT10 | A/P-001-01 | Alain Taillefer_Canada Finance | Accounts Payable Canada | Notified change name to suppliers and provide VAT taxes numbers, | Both | TRUE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE |  | Lagacé Alain | Not Started | [10 empty] | 2016-05-01 | [22 empty] | No Review | 80 | RtP |  |  |  | REVIEW | REVIEW | -
AT10 | A/P-001-02 | Alain Taillefer_Canada Finance | Accounts Payable Canada | Procurement will have to manage the PO accordingly to the new orgs/names. | Both | TRUE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE |  | Isabelle Foster | Not Started | [10 empty] | 2016-05-01 | [22 empty] | No Review | 120 | RtP | 80 | CoE-Proc.ops |  | REVIEW | REVIEW | -
AT10 | A/P-001-03 | Alain Taillefer_Canada Finance | Accounts Payable Canada | Change bank account numbers. | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started |  |  |  | 2016-05-01 | [29 empty] | No Review | 20 | CSS LEAD |  |  |  | REVIEW | REVIEW | -
AT10 | A/P-001-04 | Alain Taillefer_Canada Finance | Accounts Payable Canada | Create people assignments and complete training | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started | [33 empty] | No Review | 40 | RtP |  |  |  | REVIEW | REVIEW | -
AT11 | A/R-001-01 | Alain Taillefer_Canada Finance | Accounts Receivable Canada | Notified change name to customers and provide VAT taxes numbers, | Both | TRUE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Global A/R and credit departement will need to work with us | Theriault Marielle | Not Started |  |  | 2016-05-01 | 2016-05-01 |  |  |  |  | 2016-05-01 | [24 empty] | No Review | 40 | FAS |  |  |  | REVIEW | REVIEW | -
AT11 | A/R-001-02 | Alain Taillefer_Canada Finance | Accounts Receivable Canada | Work with Hungary GSS to modify set up for this process | Both | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Misc. A/R Canadian process is handle by Hungary shared servives | Theriault Marielle | Not Started | [31 empty] | 2016-07-01 | Hungary | No Review | 40 | FAS | 40 | AR Hun |  | REVIEW | REVIEW | -
AT11 | A/R-001-03 | Alain Taillefer_Canada Finance | Accounts Receivable Canada | Change bank account numbers. | Both | TRUE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | TRUE |  | Theriault Marielle | Not Started |  |  |  | 2016-06-01 | [27 empty] | 2016-07-01 | Hungary | No Review | 20 | CSS LEAD |  |  |  | REVIEW | REVIEW | -
AT12 | T&E-001-01 | Alain Taillefer_Canada Finance | T&E Canada | Name change on contract with CITI and Amex Canada related to Credit Cards for travelers. | Both | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE |  | Lagacé Alain | Not Started | [8 empty] | 2016-06-01 |  | 2016-06-01 | [22 empty] | No Review | 10 | US T&E |  |  |  | REVIEW | REVIEW | -
AT12 | T&E-001-02 | Alain Taillefer_Canada Finance | T&E Canada | Contract split, split concur in two | Both | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE |  | Lagacé Alain | Not Started | [8 empty] | 2016-06-01 |  | 2016-06-01 | [22 empty] | No Review | 10 | US T&E |  |  |  | REVIEW | REVIEW | -
AT17 | GM-001-01 | Alain Taillefer_Canada People Services Other | Global Mobility | Knowledge and procedures transfert to value add SPA | Both | TRUE |  | 2016-09-30 | 60 | 2016-08-01 | 0% | TRUE |  | Petit Karine | Not Started | [8 empty] | 2016-06-01 | [24 empty] | No Review | 20 | Benefits Admin |  |  |  | REVIEW | REVIEW | -
AT18 | ASP-001-01 | Alain Taillefer_Canada Other | Compliance | Transfer knowledge to new SPA, | Both | TRUE |  | 2016-09-30 | 90 | 2016-07-02 | 0% | TRUE |  | Lahaie André | Not Started | [33 empty] | No Review | 40 | Compliance Admin |  |  |  | REVIEW | REVIEW | -
AT18 | ASP-001-03 | Alain Taillefer_Canada Other | Compliance | Establish updated contract with Hungary will continue to support value add 'F03, F05, F07, F08' F09, F10, F11 | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started | [31 empty] | 2016-07-01 | Hungary | No Review | 80 | CSS LEAD | 80 | HR |  | REVIEW | REVIEW | -
AT19 | TAX-001-01 | Alain Taillefer_Canada Finance | Corporate & VAT taxes Canada | Obtain all new tax ID numbers for corporate and VAT taxes. | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Langlois Diane | Not Started |  |  | 2016-05-01 | [30 empty] | No Review | 40 | Tax |  |  |  | REVIEW | REVIEW | -
AT15 | PEN-001-01 | Alain Taillefer_Canada People Services | Benefits and Administration | Agree on TCA | Both | TRUE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Taillefer Alain | Not Started | It will take more than 2 years to get government approval. So we will have to put in place a TCA that will cover it during that period of time | [7 empty] | 2016-06-30 | [24 empty] | No Review | 12 | CSS LEAD | 12 | Benefits accounting |  | REVIEW | REVIEW | -
AT15 | PEN-001-02 | Alain Taillefer_Canada People Services | Benefits and Administration | Split the defined benefits plan | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 10% | FALSE |  | Taillefer Alain | On Track | [33 empty] | No Review | 120 | Benefits Accounting | 40 | CSS Lead |  | REVIEW | REVIEW | -
AT15 | PEN-001-03 | Alain Taillefer_Canada People Services | Benefits and Administration | Obtain government approval | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 10% | FALSE |  | Taillefer Alain | On Track | [31 empty] | 2015-12-31 | Government | No Review | 40 | Benefits Accounting |  |  |  | REVIEW | REVIEW | -
AT24 | PEN-001-04 | Alain Taillefer_Canada Finance | Benefits accounting | Coordinate with actuaries, corporate and PWC | Both | TRUE |  | 2016-07-31 | 150 | 2016-03-03 | 10% | FALSE |  | Taillefer Alain | On Track | [31 empty] | 2015-12-31 | Actuaries | No Review | 40 | Benefits Accounting |  |  |  | REVIEW | REVIEW | -
AT23 | GOV-001-01 | Alain Taillefer_Canada Finance | Archive,gov stat, legal books etc | Seperate archves | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started |  |  |  |  | 2016-04-30 | [28 empty] | No Review | 120 | Archive |  |  |  | REVIEW | REVIEW | -
AT23 | GOV-001-02 | Alain Taillefer_Canada Finance | Archive,gov stat, legal books etc | Updates minutes books | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started |  |  |  |  | 2016-04-30 | [28 empty] | No Review | 24 | CSS LEAD |  |  |  | REVIEW | REVIEW | -
AT23 | GOV-001-03 | Alain Taillefer_Canada Finance | Archive,gov stat, legal books etc | responsability transfer to new book SPA | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Taillefer Alain | Not Started |  |  |  |  | 2016-01-05 | [28 empty] | No Review | 24 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT02 | FAS-001-01 | Alain Taillefer_Mexico Finance | FAS Mexico | Establish name changes | V-A Co. | TRUE |  | 2016-04-30 | 80 | 2016-02-10 | 10% | TRUE | All other process depend on name changes and corporate structure | Rosas, Pedro | On Track | Working with Tax depratment and laywers Stickman |  | 2016-01-05 |  | 2016-01-05 |  |  |  | 2016-01-05 | [7 empty] | 2016-01-05 | [16 empty] | No Review | 24 | GSS Lead |  |  |  | - | REVIEW | REVIEW
AT02 | FAS-001-02 | Alain Taillefer_Mexico Finance | FAS Mexico | Review contracts | V-A Co. | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Rosas, Pedro | Not Started | Will work with Procurement | [9 empty] | 2016-05-01 | [22 empty] | No Review | 80 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT02 | FAS-001-03 | Alain Taillefer_Mexico Finance | FAS Mexico | New tax ID, notify to government new names, | V-A Co. | TRUE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  | 2016-03-31 | [30 empty] | No Review | 100 | GSS Lead | 40 | Tax |  | REVIEW | REVIEW | -
AT02 | FAS-001-04 | Alain Taillefer_Mexico Finance | FAS Mexico | Change bank contract and bank account numbers. | V-A Co. | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  |  | 2016-05-01 | [29 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT04 | A/P-001-01 | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Notified change name to suppliers and provide TAX ID numbers, | V-A Co. | TRUE | FS_3 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Rosas, Pedro | Not Started | [10 empty] | 2016-05-01 | [22 empty] | No Review | 80 | RtP |  |  |  | REVIEW | REVIEW | -
AT04 | A/P-001-02 | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Procurement will have to manage the PO accordingly to the new orgs. | V-A Co. | TRUE |  | 2016-03-31 | 60 | 2016-01-31 | 5% | TRUE |  | Rosas, Pedro | On Track | [10 empty] | 2016-05-01 | [22 empty] | No Review | 40 | RtP |  |  |  | - | REVIEW | REVIEW
AT04 | A/P-001-03 | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Change bank account numbers. | V-A Co. | TRUE | FS_11 | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  |  | 2016-05-01 | [6 empty] | 2016-05-01 | [22 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT04 | A/R-001-01 | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Notified change name to suppliers and provide TAX ID numbers, | V-A Co. | TRUE | FS_3 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Global A/R and credit departement will need to work with us | Rosas, Pedro | Not Started |  |  | 2016-05-01 | [5 empty] | 2016-05-01 | [24 empty] | No Review | 80 | AR |  |  |  | REVIEW | REVIEW | -
AT04 | A/R-001-02 | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Work with GSS & location to modify set up for this process | V-A Co. | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Global A/R and credit departement will need to work with us | Rosas, Pedro | Not Started | ? Has to be validated to whom it will be worked out | [32 empty] | No Review | 80 | AR |  |  |  | REVIEW | REVIEW | -
AT04 | A/R-001-03 | Alain Taillefer_Mexico Finance | Accounts Receivable Mexico | Change bank account numbers. | V-A Co. | TRUE | FS_11 | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  |  | 2016-06-01 | [29 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT05 | T&E-001-01 | Alain Taillefer_Mexico Finance | T&E Mexico | Name change on contract with CITI and Amex Mexico related to Credit Cards for travelers. | V-A Co. | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  | 2016-06-01 | [5 empty] | 2016-06-01 |  | 2016-06-01 | [22 empty] | No Review | 24 | US T&E |  |  |  | REVIEW | REVIEW | -
AT05 | T&E-001-02 | Alain Taillefer_Mexico Finance | T&E Mexico | Contract with concur | V-A Co. | TRUE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  | 2016-06-01 | [5 empty] | 2016-06-01 |  | 2016-06-01 | [22 empty] | No Review | 12 | US T&E |  |  |  | REVIEW | REVIEW | -
AT08 | TAX-001-01 | Alain Taillefer_Mexico Finance | Corporate & VAT taxes Mexico | Obtain all new tax ID numbers for corporate and VAT taxes. | V-A Co. | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  | 2016-05-01 | [30 empty] | No Review | 120 | GSS Lead | 80 | Tax |  | REVIEW | REVIEW | -
AT08 | TAX-001-02 | Alain Taillefer_Mexico Finance | Corporate & VAT taxes Mexico | Archive,gov stat, legal books etc - Updates minutes books | V-A Co. | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE |  | Rosas, Pedro | Not Started |  |  |  |  | 2016-04-30 | [28 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT09 | FAS-002-01 | Alain Taillefer_Canada | FAS Canada | Oracle Set up | Both | TRUE | FS_15 | 2016-05-31 | 90 | 2016-03-02 | 0% | TRUE |  | Gauthier, Carole | Not Started | Mirrors set up L Parent. 5 new companies to settle up and 5 to temrinated | [5 empty] | 2016-07-31 |  | 2016-04-01 | [24 empty] | No Review | 500 | FAS | 200 | FIN System solution |  | REVIEW | REVIEW | -
AT22 | VAD-001-01 | Transformation_Facilities | Shared Facilities | Agree with Howmet on the future office space required for GSS Canada ( including rent) | V-A Co. | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | TRUE |  | Alain Taillefer | Not Started | [8 empty] | 2016-05-31 | [24 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT22 | VAD-001-02 | Transformation_Facilities | Shared Facilities | Agree with Howmet on the future SLA agreements for GSS supports ( Local IT, Procurement, HR services , etc) | V-A Co. | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | TRUE |  | Alain Taillefer | Not Started | [8 empty] | 2016-05-31 | [24 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT15 | PEN-001-06 | Alain Taillefer_Canada People Services | Benefits and Administration | Contract Separation Training for GSS Team Members | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE |  | Jennifer Kintzel | Not Started | [10 empty] | 2016-01-19 | [22 empty] | No Review | 4 | HR |  |  |  | REVIEW | REVIEW | -
AT15 | PEN-001-07 | Alain Taillefer_Canada People Services | Benefits and Administration | Contact suppliers and agreed on split contract and if possible on potential additional saving | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 100 | HR | 100 | GSS Lead |  | REVIEW | REVIEW | -
AT15 | PEN-001-08 | Alain Taillefer_Canada People Services | Benefits and Administration | Introduce GSS lead to all sub contractor/ specialist ( Lawyers, accountant, Actuaries, Insurance and saving admistrators ) | V-A Co. | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 40 | GSS Lead | 20 | HR |  | REVIEW | REVIEW | -
AT22 | VAD-001-03 | Transformation_Facilities | Shared Facilities | Agree with Value Add GGS lead on the proposed structure/org-chart for future GSS Canada | V-A Co. | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 60 | GSS Lead | 40 | HR |  | REVIEW | REVIEW | -
AT22 | VAD-001-04 | Transformation_Facilities | Shared Facilities | Identify required workforce for Value-add GSS Canada and prepare posting. • Agreed on Permanent vs. contractual employees with GSS lead Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | V-A Co. | FALSE | MPS_24 | 2016-05-31 | 30 | 2016-05-01 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 40 | GSS Lead | 40 | HR |  | REVIEW | REVIEW | -
AT22 | VAD-001-05 | Transformation_Facilities | Shared Facilities | Cross training on all task to be transferred | V-A Co. | FALSE | MPS_25 | 2016-09-30 | 30 | 2016-08-31 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 200 | FAS | 80 | Benefits and Administration |  | REVIEW | REVIEW | -
AT22 | VAD-001-06 | Transformation_Facilities | Shared Facilities | Reduce workforce at upstream GSS Canada base on agreed plan with GPP Canada | Up. Co. | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 120 | GSS Lead | 120 | HR |  | REVIEW | REVIEW | -
AT22 | VAD-001-07 | Transformation_Facilities | Shared Facilities | Identify orphelin employees that need to be transferred from GPP to Value-add corporate ledger ( Wheels, AFS, AMP, aerospace , GSS, etc) • Transfer those employees to Howmet payroll new corporate LBC and agree on charge back to Value add BU | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 40 | GSS Lead |  |  |  | REVIEW | REVIEW | -
AT22 | VAD-001-08 | Transformation_Facilities | Shared Facilities | Agree/ Maximize what will be transferred to Hungary ( define the model with Hob ) | V-A Co. | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 80 | GSS Lead | 80 | HR |  | REVIEW | REVIEW | -
AT16 | PEO-001-01 | Alain Taillefer_Canada People Services | People Services Transaction Support | IT infrastructure , work with IT Canada representative on a detail plan for Ppoeple System for the Carve out | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 40 | GSS Lead | 200 | HR |  | REVIEW | REVIEW | -
AT15 | PEN-001-05 | Alain Taillefer_Canada People Services | Benefits and Administration | Create or adjust the Policy of Benefits according to the rules | V-A Co. | FALSE |  | 2016-03-31 | 50 | 2016-02-10 | 5% | FALSE |  | Alain Taillefer | On Track | [33 empty] | No Review | 80 | BENEFITS AND ADMINISTRATION |  |  |  | - | REVIEW | REVIEW
AT15 | PEN-001-06 | Alain Taillefer_Canada People Services | Benefits and Administration | Setup the Payroll system to apply the Benefits Policies of New Co. (duplicate the rules of workflows, parameters of benefits discount files, default and rules to discount the benefits) | V-A Co. | TRUE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | TRUE |  | Alain Taillefer | Not Started | [8 empty] | 2016-02-28 | [24 empty] | No Review | 120 | Payroll |  |  |  | REVIEW | REVIEW | -
AT15 | PEN-001-07 | Alain Taillefer_Canada People Services | Benefits and Administration | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | TRUE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 80 | Payroll |  |  |  | REVIEW | REVIEW | -
AT15 | PEN-001-08 | Alain Taillefer_Canada People Services | Benefits and Administration | Create or adjust the flows and procedures regarding Benefits process | V-A Co. | FALSE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | FALSE |  | Alain Taillefer | Not Started | [33 empty] | No Review | 80 | BENEFITS AND ADMINISTRATION | 40 | HR |  | REVIEW | REVIEW | -
AT15 | PEN-001-10 | Alain Taillefer_Canada People Services | Benefits and Administration | Create the New Co. in the Global People System (GPS) and associate the LBC, Department and Fiscal Code to allocate the employess | V-A Co. | TRUE |  | 2016-03-31 | 50 | 2016-02-10 | 5% | TRUE |  | Alain Taillefer | On Track | [33 empty] | No Review | 200 | Poeple System Support | 120 | Finance |  | - | REVIEW | REVIEW
AT22 | VAD-001-09 | Transformation_Facilities | Shared Facilities | Define/confirm target organization for MEX and CAN | Both | TRUE | MPS_1 | 2016-02-29 | 20 | 2016-02-09 | 5% | TRUE |  | Alain Taillefer | On Track | [8 empty] | 2016-01-31 | [24 empty] | No Review | 80 | GSS Lead | 80 | HR |  | - | REVIEW | REVIEW
AT18 | ASP-001-04 | Alain Taillefer_Canada Other | Compliance | Review and update ASAT process and content | Up. Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Andre Lahaie | Not Started | [33 empty] | No Review | 80 | ASAT | 40 | HR |  | REVIEW | REVIEW | -
AT22 | VAD-001-10 | Transformation_Facilities | Shared Facilities | Validate the Support Model is in place prior to the separation (Kiosks, HR Portal, HR Call Center and Escalation Level) | Both | TRUE | MPS_26 | 2016-06-30 | 30 | 2016-05-31 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT22 | VAD-001-11 | Transformation_Facilities | Shared Facilities | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both |  | MPS_20 | 2016-07-31 |  | 2016-04-01 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-12 | Alain Taillefer_Canada People Services | Payroll | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | Both |  | MPS_11 | 2016-04-15 |  | 2016-03-15 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-13 | Alain Taillefer_Canada People Services | Payroll | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both |  | MPS_12 | 2016-05-20 |  | 2016-04-04 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-14 | Alain Taillefer_Canada People Services | Payroll | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both |  | MPS_13 | 2016-07-08 |  | 2016-05-23 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-15 | Alain Taillefer_Canada People Services | Payroll | Vendor owned IT System/Application testing | Both |  | MPS_17 | 2016-07-08 |  | 2016-05-01 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-16 | Alain Taillefer_Canada People Services | Payroll | Complete employee physical and electronic data purging | Both |  | MPS_19 | 2016-07-31 |  | 2016-07-01 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-17 | Alain Taillefer_Canada People Services | Payroll | Complete the Testing of critical processes for Compensation (Hourly performance pay, compensation planning) and Talent Management (goal reporting, end cycle). | Both |  | MPS_20 | 2016-07-31 |  | 2016-05-01 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT13 | PAY-001-18 | Alain Taillefer_Canada People Services | Payroll | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both |  | MPS_21 | 2016-07-31 |  | 4/31/2016 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [6 empty] | REVIEW | -
AT13 | PAY-001-19 | Alain Taillefer_Canada People Services | Payroll | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both |  | MPS_22 | 2016-07-31 |  | 2016-07-15 | 0% |  |  | Cote, Mariano | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT09 | FAS-003-01 | Alain Tailler_Finance | FAS | Finalize implementation and testing plans with banks | Both |  | FS_12 | 2016-05-30 |  | 2016-03-31 | 0% |  |  | Alain Taillefer | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT08 |  | Alain Tailler_Finance | FAS | Obtain needed separation resources to assist with acitvities suc as system testing | Both |  | FS_4 | 2016-04-15 |  | 2016-03-15 | 0% |  |  | Alain Taillefer | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT23 |  | Alain Tailler_Finance | FAS | Stakeholder Sign off on vendor completion of standing up second system which is ready for testing | Both |  | FS_7 | 2016-03-31 |  | 2016-03-01 | 0% |  |  | Alain Taillefer | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT09 | FAS-001-06 | Alain Tailler_Finance | FAS | Obtain approval hierarchies for purchasing for each location from BU and RU controllership | Both |  | FS_9 | 2016-03-31 |  | 2016-03-15 | 0% |  |  | Alain Taillefer | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT23 |  | Alain Tailler_Finance | FAS | Obtain legal entity and BU entity hierarchy structures from Transaction Execution | Both |  | FS_10 | 2016-03-31 |  | 2016-02-15 | 20% |  |  | Alain Taillefer | On Track | [33 empty] | No Review | [5 empty] | - | REVIEW | -
AT21 |  | Alain Tailler_Finance | FAS | Finalize and execute comingled data strategy for shared organizations | Both |  | FS_8 | 2016-04-15 |  | 2016-02-15 | 5% |  |  | Alain Taillefer | On Track | [33 empty] | No Review | [5 empty] | - | REVIEW | -
AT09 | FAS-003-02 | Alain Tailler_Finance | FAS | Test Event 1- Internal testing (3/15- 4/15) | Both |  | FS_14 | 2016-04-15 |  | 2016-03-15 | 0% |  |  | Alain Taillefer | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT22 |  | Alain Tailler_Finance | FAS | Create cutover plan between end of system clone and OD 1 | Both |  | FS_15 | 2016-05-31 |  | 2016-03-15 | 0% |  |  | Alain Taillefer | Not Started | [33 empty] | No Review | [5 empty] | REVIEW | REVIEW | -
AT09 | FAS-003-03 | Alain Tailler_Finance | FAS | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both |  | FS_16 | 2016-05-20 |  | 2016-04-18 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT09 | FAS-003-04 | Alain Tailler_Finance | FAS | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both |  | FS_17 | 2016-07-08 |  | 2016-05-23 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT09 | FAS-004-01 | Alain Tailler_Finance | FAS | Complete confidential physical and electronic data purging | Both |  | FS_19 | 2016-06-30 |  | 2016-06-01 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT09 | FAS-001-07 | Alain Tailler_Finance | FAS | Close intercompany transactions and update customer information for Value Add Co and Upstream Co. | Both |  | FS_21 | 2016-07-31 |  | 2016-06-01 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT19 |  | Alain Tailler_Finance | FAS | Operational readiness checkpoint | Both |  | FS_22 | 2016-07-15 |  | 2016-06-15 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT23 |  | Alain Tailler_Finance | FAS | Legal Day 1 Go live- system and functional requirements complete | Both |  | FS_23 | 2016-08-01 |  | 2016-07-07 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT09 | FAS-005-01 | Alain Tailler_Finance | FAS | Complete any GSS knowledge transfer/training required for Value Add and Upstream Co | Both |  | FS_24 | 2016-09-30 |  | 2016-07-31 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT22 |  | Alain Tailler_Finance | FAS | Implement target GSS organization for Value Add Co. and Upstream Co. | Both |  | FS_25 | 2016-08-01 |  | 2016-05-01 | 0% |  |  | Alain Taillefer | Not Started | [39 empty] | REVIEW | REVIEW | -
AT09 | FAS-005-02 | Alain Tailler_Finance | FAS | Define/confirm GSS Finance scope of services for BU's and locations | Both |  | FS_1 | 2016-01-31 |  | 2016-01-15 | 100% |  |  | Alain Taillefer | Complete | [39 empty] | - | - | -
x
Formulas:
For GSS PMO Review? = IF(AND('Project Plan(s) - {AT}'!$[Status]<>"On Track",'Project Plan(s) - {AT}'!$[Start Date (Calculated)]<TODAY()+7),"Review","No Review")
Start Date Review = IFERROR(IF(TasksTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF(TasksTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Start Date (Calculated) = 'Project Plan(s) - {AT}'!$[Required Completion Date]-'Project Plan(s) - {AT}'!$[Days to Accomplish]
Note on S18: cotem: Canadian Tax Melanie Dolbec
Note on V27: cotem: Canadian HR
Note on V28: cotem: Canadian HR
Note on V29: cotem: Canadian HR
Note on V30: cotem: Canadian HR
Note on W32: cotem: Canadian IT
Note on W33: cotem: Canadian IT
Note on U36: cotem: Mexican Laywer
Note on V36: cotem: Maxican HR
Note on U37: cotem: Mexican Laywer
Note on V37: cotem: Mexican HR
Note on S38: cotem: canadian Tax
Note on U38: cotem: Canadian Legal
Note on S40: cotem: Canadian Tax
Note on AA43: cotem: Isbelle Foster
Note on S55: cotem: Canadian Tax
Note on U60: cotem: Canadian Legal
Note on U61: cotem: Canadian Legal
Note on U62: cotem: Canadian Legal
Note on S63: cotem: Mexican TAx
Note on U63: cotem: Mexica Legal
Note on U76: cotem: Mexican Legal

## Day 1 Project Costs_AT
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Project Costs
As Of | 2016-02-19 09:54
Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale

## MPS
|  | CAN | MEX
| Payroll Model (Vendor or In-house) / System | Des Jardins
T&A Model (Vendor or In-house)
| UP Co # Employees | 2600
| VA Co # Employees | 1000 | 2400
# | People Services Separation Strategy Milestone
MPS_1 | Define/confirm target GSS organization structures to support scope of services for both companies. | 2016-02-12 | 2016-02-12
# | IT System Separation Milestone
MPS_2 | Determine IT system requirements and strategy by country | 2016-02-28 | N/A
MPS_3 | Align IT systems strategy with IT organization | 2016-03-30 | N/A
MPS_4 | Obtain system scope of work and timeline from vendor to stand- up second system | N/A | N/A
MPS_5 | Obtain IT sign off for vendor owned system scope of work | N/A | N/A
MPS_6 | Procurement to execute vendor owned system scope of work for standing up second system | 2016-03-31 | 2016-03-31
MPS_7 | Vendor commences work to stand-up separate system | 2016-04-01 | N/A
MPS_8 | Stakeholder Sign off on vendor completion of standing up second system | 2016-05-01 | N/A
MPS_9 | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | 2016-03-01 | N/A
MPS_10 | Complete IT system configuration with target condition in preparation for testing | 2016-07-31 | N/A
MPS_11 | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | 2016-04-15 | 2016-04-15
MPS_12 | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | 2016-05-20 | 2016-05-20
MPS_13 | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | 2016-07-08 | 2016-07-08
MPS_14 | Vendor owned IT System/Application testing | 2016-07-08 | 2016-07-08
MPS_15 | Work with Legal on the Safe Harbor agreement - especially for the locations in Europe and US that have the services provided from the HUB | N/A | N/A
MPS_16 | Complete employee physical and electronic data purging | 2016-07-31 | 2016-07-31
MPS_17 | Complete the Testing of critical processes for Compensation (Hourly performance pay, compensation planning) and Talent Management (goal reporting, end cycle). | 2016-07-31 | 2016-07-31
MPS_18 | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | 2016-07-31 | 2016-07-31
MPS_19 | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | 2016-07-31 | 2016-07-31
MPS_20 | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | 2016-07-31 | 2016-07-31
# | GSS People Services Organization Separation Milestones
MPS_21 | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | 2016-05-31 | 2016-05-31
MPS_22 | Complete GSS employee knowledge transfer/training required for the new GSS Value Add and Upstream organizations. | 2016-06-30 | 2016-06-30
MPS_23 | Validate the Support Model is in place prior to the separation (Kiosks, HR Portal, HR Call Center and Escalation Level) | 2016-06-30 | 2016-06-30

## Data Validation (hide) (hidden)
Master Function List | Sub-function list
Legal | Legal | HumanResources | FinanceandAccounting | OCIO | InvestorRelations | Communications | GPI | GlobalBilling | BusinessUnitFunctions | Yes/No | Day 1 Target State | TSA Feasibility | TSA Exit Activities
Human Resources | Benefits | HR Systems | Treasury | PMO | Investor Relations | Inc. PR | Business Office | Operational | Strategy | Yes | Replicate (Clone) | Possible - Low/Medium Complexity | Replicate (Clone)
Finance and Accounting | Stock Systems | GTA | FP&A | Facilities |  | Internal | Operations | Systems | Sales & Business Development | No | Give and Go | Possible - Very Complex | Give and Go
OCIO | Competition | MyHR | Tax | HR Systems |  | Brand / EVP | Tools |  | Marketing |  | New Build | Impossible | New Build
Investor Relations | Corporate | Comp/Ben/M&A | AP | Other Enabling Sys |  | Social Innovation | Services |  | Risk |  | Forward TSA | Not Required | Standalone
Communications | Employment | L&OD | Travel | Finance Systems |  |  | Platform |  | Trust & Safety |  | Reverse TSA |  | Discontinue
GPI | Compliance | Diversity | Purchasing | CS Systems |  |  | Data |  | CS |  | Standalone |  | Operating Agreement
Global Billing | Government Relations |  | Payroll | Traditional IT Systems |  |  | Infrastructure/Cloud |  | PD / Arch |  | Discontinue
Business Unit Functions | IP |  | Finance Separation |  |  |  | Data Center |  | Product |  | Operating Agreement
| Privacy |  | Accounting Policy | [5 empty] | Data
| Litigation |  | SEC Reporting | [5 empty] | Info Security
| Real Estate |  | SOX | [5 empty] | Regulatory
Finance Trans
Procurement

## Countries (hidden)
# | Location Country | Total Employees
1 | USA Total |  | USA | USA | FRA | GBR | CAN | DEU | IND | AUS | SWE | MEX | BEL | HKG | SGP | CHE | ARG | NLD | DNK | TWN | POL | NOR | THA | CZE | GRC | HUN | MCO | ESP | LUX | FIN | JPN | NZL | BRA | CHN | IRL | MYS | RUS
2 | FRA Total |  | FRA | USA: USA,FRA,GBR,CAN,DEU,IND,AUS,SWE,MEX,BEL,HKG,SGP,CHE,ARG,NLD,DNK,TWN,POL,NOR,THA,CZE,GRC,HUN,MCO,ESP,LUX,FIN,JPN,NZL,BRA,CHN,IRL,MYS,RUS
3 | GBR Total |  | GBR
4 | CAN Total |  | CAN
5 | DEU Total |  | DEU
6 | IND Total |  | IND
7 | AUS Total |  | AUS
8 | SWE Total |  | SWE
9 | MEX Total |  | MEX
10 | BEL Total |  | BEL
11 | HKG Total |  | HKG
12 | SGP Total |  | SGP
13 | CHE Total |  | CHE
14 | ARG Total |  | ARG
15 | NLD Total |  | NLD
16 | DNK Total |  | DNK
17 | TWN Total |  | TWN
18 | POL Total |  | POL
19 | NOR Total |  | NOR
20 | THA Total |  | THA
21 | CZE Total |  | CZE
22 | GRC Total |  | GRC
23 | HUN Total |  | HUN
24 | MCO Total |  | MCO
25 | ESP Total |  | ESP
26 | LUX Total |  | LUX
27 | FIN Total |  | FIN
28 | JPN Total |  | JPN
29 | NZL Total |  | NZL
30 | BRA Total |  | BRA
31 | CHN Total |  | CHN
32 | IRL Total |  | IRL
33 | MYS Total |  | MYS
34 | RUS Total |  | RUS
Grand Total