## Instructions and Descriptions
Project Elevation
High-Level Separation Workplan - Instructions, Descriptions, and Examples
Below are instructions for the high-level separation workplan template
This template comprises of three tabs: one focused a list of Day 1 projects, the second focused on capturing the tasks and milestones required to complete those projects, and final focused on capturing project-associated costs
1) Follow the directions in the light grey rows of example tables below. There is an example table for each of the three tabs; example line items are provided in italics.
2) This template is designed to be modular - if you need to create multiple Project Plan tabs to break up workplanning, please do so. Indicate your tab divisions by renaming the tab where it says "{Project}"
3) Please refer any questions to your separation counterpart or contact. Leverage your contact for help with submission and plan consolidation
| Day 1 Project List Tab | Orange fields due for completion by 7 december 2015
| Activity-Level Description | [14 empty] | Dependency Resolution Checklist
| Project ID (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | Day 1 Project Description | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with a workstream-defined three letter code for WS & SWS and a unique 3 digit code for the activity within | List the name of the Resource Unit, Function, or division acting as a workstream with the separation | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Provide a detailed description (what, why and where) of the Day 1 Project | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Provide the date by which this project must be completed | Provide an estimate of the number of calendar days it will take to complete the entire project | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the project is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
x | HRD-LRL-001 | Human Resources | Labor Relations | French Works Council Approval | Adjusting organizations in France requires gaining approval from the Works Council via a formal proposal | Both | 2016-06-01 | 132 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Will require input from X, Y, and Z | [27 empty] | 2016-01-15
| HRD-LRL-002 | Human Resources | Labor Relations | German Works Council Approval | Adjusting organizations in Germany requires gaining approval from the Works Council via a series of formal meetings | Both | 2016-06-01 | 102 | 2016-02-20 | 0% | FALSE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Will require input from X, Y, and Z | [27 empty] | 2015-10-31
| Project Plan Tab | Fields due for completion by 17 December 2015
| Task-Level Description | [14 empty] | Dependency Resolution Checklist
| Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with workstream-defined three letter code for SWS, the unique 3 digit code for the activity, and a two digit code for the task | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Identify the name of the task that must be done to complete the project. Only list one task per row | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Mark whether or not this task is a milestone for a project. Milestones are the most critical tasks within a project, which are often time-sensitive. | Provide the date by which this task must be completed | Provide an estimate of the number of calendar days it will take to complete the entire task | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the task is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, important subtasks that must be captured, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
| LRL-001-01 | Labor Relations | French Works Council Approval | -Draft Proposal | Both | FALSE | 2016-02-20 | 30 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-001-02 | Labor Relations | French Works Council Approval | -Submit Proposal | Both | TRUE | 2016-03-01 | 10 | 2016-02-20 | 0% | FALSE |  | Dominique Bordeaux | Not Started
| LRL-001-03 | Labor Relations | French Works Council Approval | -Follow up after 3 months | Both | FALSE | 2016-06-01 | 90 | 2016-03-03 | 0% | FALSE |  | Dominique Bordeaux | Not Started
x | LRL-002-01 | Labor Relations | German Works Council Approval | -Draft Proposal | Both | FALSE | 2016-03-20 | 30 | 2016-02-19 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-002-02 | Labor Relations | German Works Council Approval | -Submit Proposal | Both | TRUE | 2016-04-01 | 10 | 2016-03-22 | 0% | FALSE |  | Petra Schmidt | Not Started
| LRL-002-03 | Labor Relations | German Works Council Approval | -Follow up after 2 months | Both | FALSE | 2016-06-01 | 60 | 2016-04-02 | 0% | FALSE |  | Petra Schmidt | Not Started
Project Costs Tab
| Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale
| Provide the unique ID for the project defined on the Day 1 Projects tab | Provided the name of the Day 1 project defined on the Day 1 Projects tab | Provide a description of what the cost is and why it exists | Indicate if this cost is a dis-synergy (incl stranded cost) (True/False) | Indicate if this cost is a one-time cost (True/False) | Indicate who will own the plan to minimize and address this cost | Provide an estimated cost for all or part of this Day 1 Project | Briefly describe rationale (business case) for cost estimate
| HRD-LRL-002 | German Works Council Approval | Lobbying - Gaining approval often requires spending money to lobby key officials | No | Yes | Peter Schmidt | 10000 | Spending this money will reduce risk and speed transition for German Org
x
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Instructions and Descriptions'!$[Required Completion Date]),"",'Instructions and Descriptions'!$[Required Completion Date]-'Instructions and Descriptions'!$[Days to Accomplish])

## Risk Register
To be filled out by Lisa in PMO
Date risk recorded | Project Number | Day 1 Project Name | Sub-Workstream (SWS) | Related project Task ID(s) | Risk Title | Mitigating Action(s) | Probability of occurance (0-100%) 0% being less probable | Degree of Impact (1-10) 1 being low impact | Risk rating (Probability x Impact) | For discussion in GSS PMO? (Y/N) | Status | Weekly Status Comments (enter date DD-MON-YYYY (06-JAN-2016) then comment) | Person recording risk (Last name, First name) | Date Reviewed in PMO DD-MON-YYYY (06-JAN-2016) | Track in Deloitte tool? | SPO escalation?
2016-01-18 | TN12-TN21 | Payroll, T&A, Benefits Admin, Global Mobility, Person. Admin, Recuiting, Comp., HR Global Services, HR Call Center & Performance | Tania Nossa_HR | TN12-TN21 | Sufficient resources to carry on project tasks while keeping services level and delivery | People Services identifying possible external resource sources as well as realigning internal resource workloads and Service Level |  | 4 | 0 | N | OnTrack |  |  |  | <Select> | <Select>
2016-01-18 | TN12-TN21 | Payroll, T&A, Benefits Admin, Global Mobility, Person. Admin, Recuiting, Comp., HR Global Services, HR Call Center & Performance | Tania Nossa_HR | TN12-TN21 | Alcoa GIS: Risk of system clones not completing on time | In the event of not having core systems available for the New Co, a contingency measure could be processing only essential services (payroll and benefits) using the manual spreadsheets that we currently use for double check . Another possibility is to repeat previous month payroll calculations |  | 6 | 0 | N | OnTrack |  |  |  | <Select> | <Select>
2016-01-18 | TN12-TN21 | Payroll, T&A, Benefits Admin, Global Mobility, Person. Admin, Recuiting, Comp., HR Global Services, HR Call Center & Performance | Tania Nossa_HR | TN12-TN21 | Vendor not having enough resources to meet the project timelines | People Services and Procurement will doing constant follow-ups and escalate if needed |  | 6 | 0 | N | OnTrack |  |  |  | <Select> | <Select>
2016-01-18 | TN01 | General Ledger, Cost Accounting | Tania Nossa_Finance | TN01 | Delay on the VA Capital structure definition by Legal and Tax departments | Do the follow up and escalate if needed | 10% | 10 | 1 | N | OnTrack |  |  |  | <Select> | <Select>
2016-01-18 | TN06 | Finance System Support | Tania Nossa_Finance | TN06 | Delay on Oracle and Legacies Systems setup due to lack of VA Legal Structure definition | Corporate Controllership is doing the follow up to guarantee the task will be completed on time | 10% | 10 | 1 | N | OnTrack |  |  |  | <Select> | <Select>
2016-01-18 | TN08 | Foreign Trade | Tania Nossa_Finance | TN08 | Lack of Custom brokers to represent V-A Co with government agencies | Use the same Alcoa’s brokers to VA, avoiding new bid and FCPA process | 5% | 8 | 0.4 | N | OnTrack |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>

## Project Plan(s) - {TN}
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-18 13:34
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) PLEASE INSERT DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours | Start Date Review | Completion Date Review | % Complete Progression Review
TN12 | TN12 - 01 | Tania Nossa_People Services | Payroll | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Marcos Souza | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN12 | TN12 - 02 | Tania Nossa_People Services | Payroll | Vendor Contract - Negotitation | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate benefits contrats | Marcos Souza | Not Started | [6 empty] | 2016-02-01 |  |  |  | 2016-02-01 | [22 empty] | No Review | 150 | Procurement Team | [5 empty] | -
TN12 | TN12 - 03 | Tania Nossa_People Services | Payroll | Create new Database - Employee history and calculations, internal controls and other files | V-A Co. | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-03-01 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN12 | TN12 - 04 | Tania Nossa_People Services | Payroll | Setup legislation and Payroll parameters | V-A Co. | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Marcos Souza | Not Started |  |  |  |  | 2016-03-01 | [28 empty] | No Review | 200 | Payroll Team | [5 empty] | -
TN12 | TN12 - 05 | Tania Nossa_People Services | Payroll | Setup Alimony parameters | V-A Co. | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE |  | Marcos Souza | Not Started | [33 empty] | No Review | 150 | Payroll Team | [5 empty] | -
TN12 | TN12 - 06 | Tania Nossa_People Services | Payroll | Setup Social charges parameters | V-A Co. | FALSE |  | 2016-08-30 | 30 | 2016-07-31 | 0% | TRUE | Tax - define legal entity | Marcos Souza | Not Started | [33 empty] | No Review | 15 | SAM TAX | 15 | Payroll Team |  |  |  | -
TN12 | TN12 - 07 | Tania Nossa_People Services | Payroll | Create Financial interface | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Treasury - open banking account | Marcos Souza | Not Started |  |  |  | 2016-03-01 | [29 empty] | No Review | 150 | SAM TBO | 50 | Payroll Team |  |  |  | -
TN12 | TN12 - 08 | Tania Nossa_People Services | Payroll | Create Financial interface | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-03-01 | [24 empty] | 2016-03-01 | Apdata (Vendor - Payroll) | No Review | 100 | IT Team | [5 empty] | -
TN12 | TN12 - 09 | Tania Nossa_People Services | Payroll | Create Payroll Reports | V-A Co. | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE |  | Marcos Souza | Not Started | [31 empty] | 2016-03-01 | Apdata (Vendor - Payroll) | No Review | [7 empty] | -
TN12 | TN12 - 10 | Tania Nossa_People Services | Payroll | Setup Payroll accounting | V-A Co. | FALSE |  | 2016-09-17 | 30 | 2016-08-18 | 0% | TRUE | Finance - provide parameter payroll accounting | Marcos Souza | Not Started | [33 empty] | No Review | 5 | SAM GL | 5 | Payroll Team |  |  |  | -
TN12 | TN12 - 11 | Tania Nossa_People Services | Payroll | Setup Union Collective Agreement | V-A Co. | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Legal & Latam Region - Labor Relationship and Union Agreement | Marcos Souza | Not Started | It will be defined by legal |  |  |  | 2016-03-01 | [28 empty] | No Review | 50 | Payroll Team | [5 empty] | -
TN12 | TN12 - 12 | Tania Nossa_People Services | Payroll | Create Policies, Procedures and Flows | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Marcos Souza | Not Started | [5 empty] | 2016-03-01 | [15 empty] | 2016-03-01 | [11 empty] | No Review | 15 | Payroll Team | [5 empty] | -
TN12 | TN12 - 13 | Tania Nossa_People Services | Payroll | Parallel Payroll processing (clone) | V-A Co. | TRUE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Apdata - provide payroll services | Marcos Souza | Not Started | at least two parallel (previews month and current month) |  |  |  | 2016-03-01 | [26 empty] | 04/30/16 | Apdata (Vendor - Payroll) | No Review | [7 empty] | -
TN12 | TN12 - 14 | Tania Nossa_People Services | Payroll | Create Controls and Tests | V-A Co. | FALSE |  | 2016-05-31 | 90 | 2016-03-02 | 0% | FALSE |  | Marcos Souza | Not Started | [33 empty] | No Review | 100 | Payroll Team | [5 empty] | -
TN12 | TN12 - 15 | Tania Nossa_People Services | Payroll | Setup Monthly / Annual obligations | Both | FALSE |  | 2016-09-30 | 90 | 2016-07-02 | 0% | FALSE |  | Marcos Souza | Not Started | [33 empty] | No Review | 200 | Payroll Team | [5 empty] | -
TN12 | TN12 - 16 | Tania Nossa_People Services | Payroll | Creat Monthly and Annual payroll schedule | V-A Co. | FALSE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Marcos Souza | Not Started | [33 empty] | No Review | 5 | Payroll Team | [5 empty] | -
TN12 | TN12 - 17 | Tania Nossa_People Services | Payroll | Monthly Payroll - processing | Both | FALSE |  | 2016-08-30 | 30 | 2016-07-31 | 0% | FALSE |  | Marcos Souza | Not Started | [33 empty] | No Review | 30 | Payroll Team | [5 empty] | -
TN12 | TN12 - 18 | Tania Nossa_People Services | Payroll | Identify and setup Union fees | V-A Co. | FALSE |  | 2016-09-30 | 30 | 2016-08-31 | 0% | FALSE |  | Marcos Souza | Not Started |  |  | 2016-03-01 |  | 2016-03-01 | [28 empty] | No Review | 5 | Payroll Team | [5 empty] | -
TN12 | TN12 - 19 | Tania Nossa_People Services | Payroll | Create employee Records storage | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started |  |  |  |  | 2016-02-01 | [28 empty] | No Review | 100 | IT Team | [5 empty] | -
TN12 | TN12 - 20 | Tania Nossa_People Services | Payroll | Payroll System Upgrade | Both | FALSE |  | 2016-02-29 | 30 | 2016-01-30 | 0% | FALSE |  | Marcos Souza | On Track | [31 empty] | 2016-02-01 | Apdata (Vendor - Payroll) | No Review | [7 empty] | REVIEW
TN12 | TN12 - 21 | Tania Nossa_People Services | Payroll | Create Payroll and Benefits data batchs for Operational Plan | V-A Co. | FALSE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE | Global Services - Define Operation Plan | Marcos Souza | Not Started |  | 2016-03-01 |  |  |  | 2016-03-01 | [27 empty] | No Review | 50 | Global Services Team | 150 | Payroll Team |  |  |  | -
TN12 | TN12 - 22 | Tania Nossa_People Services | Payroll | Implement E- Social rules | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Marcos Souza | Not Started | compliance with legislation | 2016-03-01 | 2016-03-01 |  | 2016-03-01 | 2016-03-01 | 2016-03-01 |  |  |  | 2016-03-01 | 2016-03-01 | [19 empty] | 2016-03-01 | Apdata (Vendor - Payroll) | No Review | 100 | Payroll Team | [5 empty] | -
TN12 | TN12 - 23 | Tania Nossa_People Services | Payroll | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Marcos Souza | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN12 | TN12 - 24 | Tania Nossa_People Services | Payroll | Align IT systems strategy with IT organization | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 80% | TRUE | IT - implement IT Infrastructure | Marcos Souza | On Track | [6 empty] | 2016-03-04 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 25 | Tania Nossa_People Services | Payroll | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 5% | TRUE | IT - implement IT Infrastructure | Marcos Souza | On Track | 15-Feb-2016 Initial contact made with vendor explaining request and scope and asked to send estimate timeline for splitting system | [5 empty] | 2016-03-15 | [26 empty] | No Review | [7 empty] | REVIEW
TN12 | TN12 - 26 | Tania Nossa_People Services | Payroll | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Marcos Souza | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN12 | TN12 - 27 | Tania Nossa_People Services | Payroll | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 28 | Tania Nossa_People Services | Payroll | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Marcos Souza | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN12 | TN12 - 29 | Tania Nossa_People Services | Payroll | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 30 | Tania Nossa_People Services | Payroll | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 31 | Tania Nossa_People Services | Payroll | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 32 | Tania Nossa_People Services | Payroll | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 33 | Tania Nossa_People Services | Payroll | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 34 | Tania Nossa_People Services | Payroll | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 35 | Tania Nossa_People Services | Payroll | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN12 | TN12 - 36 | Tania Nossa_People Services | Payroll | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 01 | Tania Nossa_People Services | Benefits admin | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Luciane Moraes | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN14 | TN14 - 02 | Tania Nossa_People Services | Benefits admin | Renegotiate benefits vendors contracts | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate benefits contrats | Luciane Moraes | Not Started | [10 empty] | 2016-02-01 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN14 | TN14 - 03 | Tania Nossa_People Services | Benefits admin | Create or adjust the Policy of Benefits according to the rules of each Co. | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - benefits definition | Luciane Moraes | Not Started | [5 empty] | 02/29/16 | [15 empty] | 02/29/16 | [11 empty] | No Review | 50 | Benefits Team | [5 empty] | -
TN14 | TN14 - 04 | Tania Nossa_People Services | Benefits admin | Open a request for Procurement team to add amount in vendors contracts in the EBS system | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate benefits contrats | Luciane Moraes | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN14 | TN14 - 05 | Tania Nossa_People Services | Benefits admin | Split both companies in the database of benefits vendors (Private Pension Plan, Medical Care, Dental Care, Pharmacy, Life Insurance, Special Consumer Discounts, Food and Subsistance tickets, Employee Country Club, Employee Credit Union, Transportation Allowance) | Both | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | Procurement - renegotiate benefits contrats | Luciane Moraes | Not Started | [33 empty] | No Review | 150 | Procurement Team | [5 empty] | -
TN14 | TN14 - 06 | Tania Nossa_People Services | Benefits admin | Setup the Payroll system to apply the Benefits Policies of New Co. (duplicate the rules of workflows, parameters of benefits discount files, default and rules to discount the benefits) | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Apdata - employee records IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 04/30/16 | [24 empty] | 04/30/16 | Apdata (Vendor - Payroll) | No Review | 75 | IT Team | [5 empty] | -
TN14 | TN14 - 07 | Tania Nossa_People Services | Benefits admin | Implement the IT Infrastructure and split the systems (Payroll, GPS, legacy systems) | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN14 | TN14 - 08 | Tania Nossa_People Services | Benefits admin | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 150 | Benefits Team | [5 empty] | -
TN14 | TN14 - 09 | Tania Nossa_People Services | Benefits admin | Create or adjust the flows and procedures regarding Benefits process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Benefits Team | [5 empty] | -
TN14 | TN14 - 10 | Tania Nossa_People Services | Benefits admin | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Benefits Team | [5 empty] | -
TN14 | TN14 - 11 | Tania Nossa_People Services | Benefits admin | Setup the New Co. in Worker Food Program (PAT) regarding food and subsistence tickets offered for the employees | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | [7 empty] | -
TN14 | TN14 - 12 | Tania Nossa_People Services | Benefits admin | Create a new contract with Bank regarding the setup of loan for discount in payroll | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE | Finance - payroll accounting Treasury - open banking account | Luciane Moraes | Not Started |  | 2016-02-01 |  | 2016-02-01 | [27 empty] | 02/29/16 | Bradesco (Bank) | No Review | 10 | SAM TBO | 10 | Benefits Team |  |  |  | -
TN14 | TN14 - 13 | Tania Nossa_People Services | Benefits admin | Double Check the parameters and rules implemented for New Co. And guarantee the accuracy of discounts of benefits | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Apdata - provide payroll services | Luciane Moraes | Not Started | [31 empty] | 2016-06-30 | Apdata (Vendor - Payroll) | No Review | [7 empty] | -
TN14 | TN14 - 14 | Tania Nossa_People Services | Benefits admin | Define if the reports including diversity, headcount, turnover and management indicators are generated by BUs will be used for New Co. | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Latam Region - HR Reporting definition | Luciane Moraes | Not Started | [21 empty] | 04/30/16 | [11 empty] | No Review | 100 | Benefits Team | [5 empty] | -
TN14 | TN14 - 15 | Tania Nossa_People Services | Benefits admin | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN14 | TN14 - 16 | Tania Nossa_People Services | Benefits admin | Align IT systems strategy with IT organization | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | 15-feb-2016 - Waiting for Comp & Benefits CoE to confirm that current benefits systems will be kept "as it is" for both companies | [5 empty] | 2016-03-04 | [26 empty] | Review | [7 empty] | -
TN14 | TN14 - 17 | Tania Nossa_People Services | Benefits admin | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | 15-feb-2016 - Waiting for Comp & Benefits CoE to confirm that current benefits systems will be kept "as it is" for both companies | [5 empty] | 2016-03-15 | [26 empty] | Review | [7 empty] | REVIEW
TN14 | TN14 - 18 | Tania Nossa_People Services | Benefits admin | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Luciane Moraes | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN14 | TN14 - 19 | Tania Nossa_People Services | Benefits admin | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 20 | Tania Nossa_People Services | Benefits admin | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Luciane Moraes | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN14 | TN14 - 21 | Tania Nossa_People Services | Benefits admin | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 22 | Tania Nossa_People Services | Benefits admin | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 23 | Tania Nossa_People Services | Benefits admin | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 24 | Tania Nossa_People Services | Benefits admin | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 25 | Tania Nossa_People Services | Benefits admin | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 26 | Tania Nossa_People Services | Benefits admin | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 27 | Tania Nossa_People Services | Benefits admin | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN14 | TN14 - 28 | Tania Nossa_People Services | Benefits admin | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 01 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Juliana Lima | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN21 | TN21 - 02 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Renegotiate with HR Call Center vendor (Stefanini) contract | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [20 empty] | 04/30/16 | Stefanini Vendor | No Review | 30 | Procurement Team | [5 empty] | -
TN21 | TN21 - 03 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Setting if the supplier will be shared between the two companies as well as the physical structure | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [20 empty] | 04/30/16 | Stefanini Vendor | No Review | 15 | HR Call Center Team | [5 empty] | -
TN21 | TN21 - 04 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Implement the IT Infrastructure and split the systems (Global Remedy) for new Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN21 | TN21 - 05 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Review Service Level Management and Service Level Agreement for New Co | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Latam Region - Metrics definition | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [15 empty] | 04/30/16 | [11 empty] | No Review | 100 | HR Call Center Team | [5 empty] | -
TN21 | TN21 - 06 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create and adjust the flows, procedures and Scripts regarding all HR process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 7.5 | HR Global Services Team | 7.5 | Performance Team |  |  |  | -
TN21 | TN21 - 07 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Provide trainings of process for HR Call Center Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 50 | HR Call Center Team | [5 empty] | -
TN19 | TN19 - 01 | Tania Nossa_People Services | Compensation | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Luciane Moraes | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN19 | TN19 - 02 | Tania Nossa_People Services | Compensation | Renegotiate benefits vendors contracts | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate benefits contrats | Luciane Moraes | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN19 | TN19 - 03 | Tania Nossa_People Services | Compensation | Open a request for Procurement team to add amount in vendors contracts in the EBS system | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate benefits contrats | Luciane Moraes | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN19 | TN19 - 04 | Tania Nossa_People Services | Compensation | Create or adjust the Policy of Compensation according with rule of each Co. | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - benefits definition | Luciane Moraes | Not Started | [21 empty] | 02/29/16 | [11 empty] | No Review | 50 | Compensation Team | [5 empty] | -
TN19 | TN19 - 05 | Tania Nossa_People Services | Compensation | Create the New Co. in the Global People System (GPS) and associate the LBC, Department and Fiscal Code to allocate the employess | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Finance - setup the accounting | Luciane Moraes | Not Started |  | 2016-02-01 | [31 empty] | No Review | 15 | SAM GL | 15 | Compensation Team |  |  |  | -
TN19 | TN19 - 06 | Tania Nossa_People Services | Compensation | Setup the Payroll system to apply the Compensation Policies of New Co. (duplicate the rules of parameters for compensation payments or reserve if aplicable - IC, PP, Stock Option, Transfers Allowances, etc.) | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Apdata - employee records IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 04/30/16 | [24 empty] | 04/30/16 | Apdata (Vendor - Payroll) | No Review | 75 | IT Team | [5 empty] | -
TN19 | TN19 - 07 | Tania Nossa_People Services | Compensation | Create the table of job and salaries structures for New Co. on GPS | V-A Co. | FALSE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started |  | 2016-02-01 |  |  |  |  | 04/30/16 | [26 empty] | No Review | 15 | IT Team | 15 | Compensation Team |  |  |  | -
TN19 | TN19 - 08 | Tania Nossa_People Services | Compensation | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Compensation Team | [5 empty] | -
TN19 | TN19 - 09 | Tania Nossa_People Services | Compensation | Create or adjust the flows and procedures regarding Compensation process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Compensation Team | [5 empty] | -
TN19 | TN19 - 10 | Tania Nossa_People Services | Compensation | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Compensation Team | [5 empty] | -
TN19 | TN19 - 11 | Tania Nossa_People Services | Compensation | Double check the parameters and rules implemented for New Co. And guarantee the accuracy of payments | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Apdata - provide payroll services | Luciane Moraes | Not Started | [31 empty] | 2016-06-30 | Apdata (Vendor - Payroll) | No Review | [7 empty] | -
TN19 | TN19 - 13 | Tania Nossa_People Services | Compensation | Setup the Payroll system to apply the rules of pension plan for New Co. (duplicate the parameters for payroll discounts and reports) | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Apdata - employee records IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 04/30/16 | [24 empty] | 04/30/16 | Apdata (Vendor - Payroll) | No Review | 75 | IT Team | [5 empty] | -
TN19 | TN19 - 14 | Tania Nossa_People Services | Compensation | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN19 | TN19 - 15 | Tania Nossa_People Services | Compensation | Align IT systems strategy with IT organization | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | 15-feb-2016 - Compensation definition depends on GPS global strategy decision for borh companies | [5 empty] | 2016-03-04 | [26 empty] | Review | [7 empty] | -
TN19 | TN19 - 16 | Tania Nossa_People Services | Compensation | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | 15-feb-2016 - Compensation definition depends on GPS global strategy decision for borh companies | [5 empty] | 2016-03-15 | [26 empty] | Review | [7 empty] | REVIEW
TN19 | TN19 - 17 | Tania Nossa_People Services | Compensation | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Luciane Moraes | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN19 | TN19 - 18 | Tania Nossa_People Services | Compensation | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 19 | Tania Nossa_People Services | Compensation | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Luciane Moraes | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN19 | TN19 - 20 | Tania Nossa_People Services | Compensation | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 21 | Tania Nossa_People Services | Compensation | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 22 | Tania Nossa_People Services | Compensation | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 23 | Tania Nossa_People Services | Compensation | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 24 | Tania Nossa_People Services | Compensation | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 25 | Tania Nossa_People Services | Compensation | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 15 | 2016-07-16 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 26 | Tania Nossa_People Services | Compensation | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | Both | TRUE | MPS_11 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE | MPS_12 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE | MPS_13 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Participate in GPS Testing- Test Test Event 1 | Both | TRUE | MPS_14 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Participate in GPS Testing - CRP testing | Both | TRUE | MPS_15 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Participate in GPS Testing - UAT testing | Both | TRUE | MPS_16 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN19 | TN19 - 27 | Tania Nossa_People Services | Compensation | Complete the Testing of critical processes for Compensation (Hourly performance pay, compensation planning) and Talent Management (goal reporting, end cycle). | Both | TRUE | MPS_20 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN15 | TN15 - 01 | Tania Nossa_People Services | Global Mobility | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Luciane Moraes | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN15 | TN15 - 02 | Tania Nossa_People Services | Global Mobility | Renegotiate vendor contract (EMDOC) | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate global mobility contrats | Luciane Moraes | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN15 | TN15 - 03 | Tania Nossa_People Services | Global Mobility | Open a request for Procurement team to add amount in vendors contracts in the EBS system | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate global mobility contrats | Luciane Moraes | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN15 | TN15 - 04 | Tania Nossa_People Services | Global Mobility | Define the global mobility policy for both companies | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - benefits definition | Luciane Moraes | Not Started | [8 empty] | 02/29/16 | [24 empty] | No Review | 50 | Compensation Team | [5 empty] | -
TN15 | TN15 - 05 | Tania Nossa_People Services | Global Mobility | Implement the IT Infrastructure and split the systems (Payroll, GPS) | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Luciane Moraes | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN15 | TN15 - 06 | Tania Nossa_People Services | Global Mobility | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Compensation Team | [5 empty] | -
TN15 | TN15 - 07 | Tania Nossa_People Services | Global Mobility | Create or adjust the flows and procedures regarding Mobility process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Compensation Team | [5 empty] | -
TN15 | TN15 - 08 | Tania Nossa_People Services | Global Mobility | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Luciane Moraes | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Compensation Team | [5 empty] | -
TN21 | TN21 - 08 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Implement the IT Infrastructure and split the systems (GPS and Kenexa) for New Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [24 empty] | 04/30/16 | Kenexa vendor | No Review | 100 | IT Team | [5 empty] | -
TN21 | TN21 - 09 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Validation of the GPS model (Global access control, Global Share Point, PMO, etc.), Tests about Talent Report and Global Voices Methodology for New Co | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | GSS - reassure GVS, GPS and Talent Report models. | Juliana Lima | Not Started | [8 empty] | 02/29/16 | [24 empty] | No Review | 100 | GSS & Latam Region | [5 empty] | -
TN21 | TN21 - 10 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | HR Global Services Team | 15 | HR Call Center Team |  |  |  | -
TN21 | TN21 - 11 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create reports regarding GPS, Global Voices and Talent process for New Co | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 100 | HR Global Services Team | [5 empty] | -
TN21 | TN21 - 12 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create Monthly and Annual schedule | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 2.5 | HR Global Services Team | 2.5 | HR Call Center Team |  |  |  | -
TN21 | TN21 - 13 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Definition of asessment methodology for New Co (Will be the same criteria?) | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - recruitment definition | Juliana Lima | Not Started | [5 empty] | 02/29/16 | [15 empty] | 02/29/16 | [11 empty] | No Review | 30 | HR Global Services Team | [5 empty] | -
TN21 | TN21 - 14 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Implement the IT Infrastructure and split the systems (GPS and Fusion) for New Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN21 | TN21 - 15 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Setup the systems to apply the evaluation methodology for New Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN21 | TN21 - 16 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create reports regarding Performance process for New Co | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 100 | Performance Team | [5 empty] | -
TN21 | TN21 - 17 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 7.5 | HR Global Services Team | 7.5 | Performance Team |  |  |  | -
TN21 | TN21 - 18 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create and adjust the flows and procedures regarding Performance process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 7.5 | HR Global Services Team | 7.5 | Performance Team |  |  |  | -
TN21 | TN21 - 19 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Training Team | [5 empty] | -
TN21 | TN21 - 20 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create Monthly and Annual schedule | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 5 | Training Team | [5 empty] | -
TN16 | TN16 - 01 | Tania Nossa_People Services | Personnel Administration | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Juliana Lima | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN16 | TN16 - 02 | Tania Nossa_People Services | Personnel Administration | Renegotiate with Personnel Administration vendors contracts for New Co | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [20 empty] | 02/29/16 | Apdata (Vendor - Payroll); Nexo (Vendor- Healthy) | No Review | 30 | Procurement Team | [5 empty] | -
TN16 | TN16 - 03 | Tania Nossa_People Services | Personnel Administration | Open a request for Procurement team to add amount in vendor contract in the EBS system | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN16 | TN16 - 04 | Tania Nossa_People Services | Personnel Administration | Create new Database - Employee history and calculations | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-01-03 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN16 | TN16 - 05 | Tania Nossa_People Services | Personnel Administration | Implement the IT Infrastructure and split the systems (Antares, GPS, Nexo) for New Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN16 | TN16 - 06 | Tania Nossa_People Services | Personnel Administration | Create Interface HR systems to Portal | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-03-01 | [24 empty] | 2016-03-01 | Apdata (Vendor - Payroll) | No Review | 100 | IT Team | [5 empty] | -
TN16 | TN16 - 07 | Tania Nossa_People Services | Personnel Administration | Setup legislation and Parameters (invalid pension, Closed Companies) | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started |  |  |  |  | 2016-03-01 | [28 empty] | No Review | [7 empty] | -
TN16 | TN16 - 08 | Tania Nossa_People Services | Personnel Administration | Setup parameters and rules into the vendor system regarding vacation, hire, termination, absence, retirement document, pension and internal | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-30 | [24 empty] | 2016-04-30 | Apdata (Vendor - Payroll); Nexo (Vendor- Healthy) | No Review | 100 | IT Team | [5 empty] | -
TN16 | TN16 - 09 | Tania Nossa_People Services | Personnel Administration | Create and adjust the Terminantion Policy according with rule of each Co. | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - recruitment definition | Juliana Lima | Not Started | [5 empty] | 02/29/16 | [15 empty] | 02/29/16 | [11 empty] | No Review | 50 | Personnel Admin Team | [5 empty] | -
TN16 | TN16 - 10 | Tania Nossa_People Services | Personnel Administration | Check the parameters and rules implemented for New Co. and guarantee the accuracy of absences and termination | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Apdata - provide payroll services | Juliana Lima | Not Started | [31 empty] | 06/30/2016 | Apdata (Vendor - Payroll); | No Review | [7 empty] | -
TN16 | TN16 - 11 | Tania Nossa_People Services | Personnel Administration | Create reports regarding Personnel Administration process for New Co | V-A Co. | FALSE |  | 2016-05-31 | 60 | 2016-04-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 100 | Personnel Admin Team | [5 empty] | -
TN16 | TN16 - 12 | Tania Nossa_People Services | Personnel Administration | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Personnel Admin Team | [5 empty] | -
TN16 | TN16 - 13 | Tania Nossa_People Services | Personnel Administration | Create and adjust the flows and procedures regarding Recruitment process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Personnel Admin Team | [5 empty] | -
TN16 | TN16 - 14 | Tania Nossa_People Services | Personnel Administration | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Personnel Admin Team | [5 empty] | -
TN16 | TN16 - 15 | Tania Nossa_People Services | Personnel Administration | Create Monthly and Annual schedule | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 5 | Personnel Admin Team | [5 empty] | -
TN16 | TN16 - 16 | Tania Nossa_People Services | Personnel Administration | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Juliana Lima | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN16 | TN16 - 17 | Tania Nossa_People Services | Personnel Administration | Align IT systems strategy with IT organization | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 30% | TRUE | IT - implement IT Infrastructure | Juliana Lima | On Track | 15-feb-2016 - Part of Personnel definition depends on GPS global strategy decision for borh companies | [5 empty] | 2016-03-04 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 18 | Tania Nossa_People Services | Personnel Administration | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 40% | TRUE | IT - implement IT Infrastructure | Juliana Lima | On Track | 15-Feb-2016 Local legacy systems scope and timeline definitions ongoing. GPS portion dependingo on global decision for both companies | [5 empty] | 2016-03-15 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 19 | Tania Nossa_People Services | Personnel Administration | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Juliana Lima | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN16 | TN16 - 20 | Tania Nossa_People Services | Personnel Administration | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 21 | Tania Nossa_People Services | Personnel Administration | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Juliana Lima | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN16 | TN16 - 22 | Tania Nossa_People Services | Personnel Administration | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 23 | Tania Nossa_People Services | Personnel Administration | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 24 | Tania Nossa_People Services | Personnel Administration | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 25 | Tania Nossa_People Services | Personnel Administration | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 26 | Tania Nossa_People Services | Personnel Administration | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 27 | Tania Nossa_People Services | Personnel Administration | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 28 | Tania Nossa_People Services | Personnel Administration | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 29 | Tania Nossa_People Services | Personnel Administration | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 30 | Tania Nossa_People Services | Personnel Administration | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | Both | TRUE | MPS_11 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 31 | Tania Nossa_People Services | Personnel Administration | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE | MPS_12 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 32 | Tania Nossa_People Services | Personnel Administration | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE | MPS_13 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 33 | Tania Nossa_People Services | Personnel Administration | Participate in GPS Testing- Test Test Event 1 | Both | TRUE | MPS_14 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 34 | Tania Nossa_People Services | Personnel Administration | Participate in GPS Testing - CRP testing | Both | TRUE | MPS_15 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN16 | TN16 - 35 | Tania Nossa_People Services | Personnel Administration | Participate in GPS Testing - UAT testing | Both | TRUE | MPS_16 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 01 | Tania Nossa_People Services | Recruiting | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Juliana Lima | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN18 | TN18 - 02 | Tania Nossa_People Services | Recruiting | Renegotiate with Recruitment vendors contracts | Both | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN18 | TN18 - 03 | Tania Nossa_People Services | Recruiting | Open a request for Procurement team to add amount in vendor contract in the EBS system | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN18 | TN18 - 04 | Tania Nossa_People Services | Recruiting | Create and adjust the Recruitment Policy according to therule of each Co. | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - recruitment definition | Juliana Lima | Not Started | [5 empty] | 02/29/16 | [15 empty] | 02/29/16 | [11 empty] | No Review | 50 | Recruiting Team | [5 empty] | -
TN18 | TN18 - 05 | Tania Nossa_People Services | Recruiting | Implement the IT Infrastructure and split the systems (GPS - I-recruitment) for New Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN18 | TN18 - 06 | Tania Nossa_People Services | Recruiting | Setup the systems to apply the Recruitment Policies for New Co. | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN18 | TN18 - 07 | Tania Nossa_People Services | Recruiting | Create Recruiting reports for New Co. | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 100 | Recruiting Team | [5 empty] | -
TN18 | TN18 - 08 | Tania Nossa_People Services | Recruiting | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Recruiting Team | [5 empty] | -
TN18 | TN18 - 09 | Tania Nossa_People Services | Recruiting | Create and adjust the flows and procedures regarding Recruitment process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Recruiting Team | [5 empty] | -
TN18 | TN18 - 10 | Tania Nossa_People Services | Recruiting | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Recruiting Team | [5 empty] | -
TN18 | TN18 - 11 | Tania Nossa_People Services | Recruiting | Create Monthly and Annual schedule | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 5 | Recruiting Team | [5 empty] | -
TN18 | TN18 - 12 | Tania Nossa_People Services | Recruiting | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Juliana Lima | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN18 | TN18 - 13 | Tania Nossa_People Services | Recruiting | Align IT systems strategy with IT organization | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | 15-feb-2016 - R&S definition depends on GPS global strategy decision for borh companies | [5 empty] | 2016-03-04 | [26 empty] | Review | [7 empty] | -
TN18 | TN18 - 14 | Tania Nossa_People Services | Recruiting | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | 15-feb-2016 - R&S definition depends on GPS global strategy decision for borh companies | [5 empty] | 2016-03-15 | [26 empty] | Review | [7 empty] | REVIEW
TN18 | TN18 - 15 | Tania Nossa_People Services | Recruiting | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Juliana Lima | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN18 | TN18 - 16 | Tania Nossa_People Services | Recruiting | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 17 | Tania Nossa_People Services | Recruiting | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Juliana Lima | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN18 | TN18 - 18 | Tania Nossa_People Services | Recruiting | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 19 | Tania Nossa_People Services | Recruiting | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 20 | Tania Nossa_People Services | Recruiting | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 21 | Tania Nossa_People Services | Recruiting | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 22 | Tania Nossa_People Services | Recruiting | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 23 | Tania Nossa_People Services | Recruiting | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 24 | Tania Nossa_People Services | Recruiting | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 25 | Tania Nossa_People Services | Recruiting | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 26 | Tania Nossa_People Services | Recruiting | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | Both | TRUE | MPS_11 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 27 | Tania Nossa_People Services | Recruiting | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE | MPS_12 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 28 | Tania Nossa_People Services | Recruiting | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE | MPS_13 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 29 | Tania Nossa_People Services | Recruiting | Participate in GPS Testing- Test Test Event 1 | Both | TRUE | MPS_14 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 30 | Tania Nossa_People Services | Recruiting | Participate in GPS Testing - CRP testing | Both | TRUE | MPS_15 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN18 | TN18 - 31 | Tania Nossa_People Services | Recruiting | Participate in GPS Testing - UAT testing | Both | TRUE | MPS_16 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 01 | Tania Nossa_People Services | T&A | Define organization | Both | TRUE | MPS_1 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE |  | Marcos Souza | On Track | 01-FEB-2016 Updated the org charts and need to seek approval 18-JAN-2016 Need to seek approval for draft org charts 12-JAN-2016 Draft org chart was designed | [7 empty] | 2016-02-28 | [24 empty] | No Review | 5 | People Services Lead Team | [5 empty] | -
TN13 | TN13 - 02 | Tania Nossa_People Services | T&A | Vendor Contract - Negotitation | V-A Co. | FALSE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Marcos Souza | Not Started | [6 empty] | 2016-02-01 |  |  |  | 2016-02-01 | [20 empty] | 2016-02-01 | Senior (Vendor - T&A) | No Review | 50 | Procurement Team | [5 empty] | -
TN13 | TN13 - 03 | Tania Nossa_People Services | T&A | Setup legislation and Parameters | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Marcos Souza | Not Started |  |  |  |  | 2016-04-01 | 2016-04-01 | 2016-04-01 | [24 empty] | 2016-03-01 | Senior (Vendor - T&A) | No Review | [7 empty] | -
TN13 | TN13 - 04 | Tania Nossa_People Services | T&A | Create Policies, Procedures and Flows | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Marcos Souza | Not Started | [5 empty] | 2016-04-01 | 2016-04-01 | [26 empty] | No Review | 15 | T&A Team | [5 empty] | -
TN13 | TN13 - 05 | Tania Nossa_People Services | T&A | Create T&A Reports | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | FALSE |  | Marcos Souza | Not Started | [5 empty] | 2016-05-01 | 2016-05-01 | [24 empty] | 2016-04-01 | Senior (Vendor - T&A) | No Review | [7 empty] | -
TN13 | TN13 - 06 | Tania Nossa_People Services | T&A | Create new Database - Employee history and calculations, internal controls and other files | V-A Co. | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started |  |  |  |  | 2016-04-01 | [28 empty] | No Review | 100 | IT Team | [5 empty] | -
TN13 | TN13 - 07 | Tania Nossa_People Services | T&A | Create journey Management and Control rules | V-A Co. | FALSE |  | 2016-09-17 | 30 | 2016-08-18 | 0% | FALSE |  | Marcos Souza | Not Started |  |  |  |  | 2016-04-01 | 2016-06-01 | [27 empty] | No Review | 5 | T&A Team | [5 empty] | -
TN13 | TN13 - 08 | Tania Nossa_People Services | T&A | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Marcos Souza | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN13 | TN13 - 09 | Tania Nossa_People Services | T&A | Align IT systems strategy with IT organization | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 80% | TRUE | IT - implement IT Infrastructure | Marcos Souza | On Track | [6 empty] | 2016-03-04 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 10 | Tania Nossa_People Services | T&A | Obtain system scope of work and timeline from vendor to stand- up second system | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 5% | TRUE | IT - implement IT Infrastructure | Marcos Souza | On Track | 15-Feb-2016 Initial contact made with vendor explaining request and scope and asked to send estimate timeline for splitting system | [5 empty] | 2016-03-15 | [26 empty] | No Review | [7 empty] | REVIEW
TN13 | TN13 - 11 | Tania Nossa_People Services | T&A | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Marcos Souza | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN13 | TN13 - 12 | Tania Nossa_People Services | T&A | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 13 | Tania Nossa_People Services | T&A | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Marcos Souza | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN13 | TN13 - 14 | Tania Nossa_People Services | T&A | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 15 | Tania Nossa_People Services | T&A | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 16 | Tania Nossa_People Services | T&A | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 17 | Tania Nossa_People Services | T&A | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 18 | Tania Nossa_People Services | T&A | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 19 | Tania Nossa_People Services | T&A | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 20 | Tania Nossa_People Services | T&A | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN13 | TN13 - 21 | Tania Nossa_People Services | T&A | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | IT - implement IT Infrastructure | Marcos Souza | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 21 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Renegotiate with Training vendor (Paradigm) contract | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN21 | TN21 - 22 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Open a request for Procurement team to add amount in vendor contract in the EBS system | V-A Co. | FALSE |  | 2016-04-01 | 30 | 2016-03-02 | 0% | TRUE | Procurement - renegotiate recruitment contrats | Juliana Lima | Not Started | [10 empty] | 02/29/16 | [22 empty] | No Review | 30 | Procurement Team | [5 empty] | -
TN21 | TN21 - 23 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create and adjust the Training and School Tuition Reimbursement Policy according with rule of each Co. | Both | FALSE |  | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | Latam Region - recruitment definition | Juliana Lima | Not Started | [5 empty] | 02/29/16 | [15 empty] | 02/29/16 | [11 empty] | No Review | 50 | Training Team | [5 empty] | -
TN21 | TN21 - 24 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Implement the IT Infrastructure and split the systems and database (SRE, TBG, Alcoa Learn and Paradigm) for new Co | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [24 empty] | 04/30/16 | Paradigm Vendor | No Review | 200 | IT Team | [5 empty] | -
TN21 | TN21 - 25 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create Financial interface for the School Tuition Reimbursement | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Accounts Payable - Pay the School Tuition Reimbursement | Juliana Lima | Not Started |  | 04/30/16 |  |  |  | 04/30/16 | [27 empty] | No Review | 30 | SAM AP | [5 empty] | -
TN21 | TN21 - 26 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Setup the systems to apply the Training and School Tuition Reimbursement Policies for New Co. | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 04/30/16 | [26 empty] | No Review | 200 | IT Team | [5 empty] | -
TN21 | TN21 - 27 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create reports regarding Training and School Tuition Reimbursement for New Co. | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Training Team | [5 empty] | -
TN21 | TN21 - 28 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Duplicate the internal controls for New Co. to guarantee the acuracy of process | V-A Co. | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Training Team | [5 empty] | -
TN21 | TN21 - 29 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create and adjust the flows and procedures regarding Training and School Tuition Reimbursement process | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 15 | Training Team | [5 empty] | -
TN21 | TN21 - 30 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Provide trainings of process for HR Team according the split of Departments | Both | TRUE | MPS_25 | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 30 | Performance Team | [5 empty] | -
TN21 | TN21 - 31 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Create Monthly and Annual schedule | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Juliana Lima | Not Started | [5 empty] | 04/30/16 | [27 empty] | No Review | 5 | Performance Team | [5 empty] | -
TN21 | TN21 - 32 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Determine IT system requirements and strategy by country | Both | TRUE | MPS_2 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | IT - implement IT Infrastructure | Juliana Lima | On Track | [6 empty] | 2016-02-29 | [26 empty] | No Review | [7 empty] | REVIEW
TN21 | TN21 - 33 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Align IT systems strategy with IT organizationHR Global Services, HR Call Center & Performance and Training) | Both | TRUE | MPS_3 | 2016-03-04 | 15 | 2016-02-18 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | 15-feb-2016 - definition depends on GPS global strategy decision for borh companies. Also, waiting for regional leaders to decide on HR Call Center applicability for Value Add Co. | [5 empty] | 2016-03-04 | [26 empty] | Review | [7 empty] | -
TN21 | TN21 - 34 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Align IT systems strategy with IT organizationHR Global Services, HR Call Center & Performance and Training) | Both | TRUE | MPS_4 | 2016-03-15 | 30 | 2016-02-14 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | 15-feb-2016 - definition depends on GPS global strategy decision for borh companies. Also, waiting for regional leaders to decide on HR Call Center applicability for Value Add Co. | [5 empty] | 2016-03-15 | [26 empty] | Review | [7 empty] | REVIEW
TN21 | TN21 - 35 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Procurement to execute vendor owned system scope of work for standing up second system | V-A Co. | TRUE | MPS_6 | 2016-02-29 | 30 | 2016-01-30 | 10% | TRUE | Procurement - renegotiate Payroll contrats | Juliana Lima | On Track | [10 empty] | 2016-02-29 | [22 empty] | No Review | [7 empty] | REVIEW
TN21 | TN21 - 36 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Vendor commences work to stand-up separate system | Both | TRUE | MPS_7 | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-01 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 37 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Stakeholder Sign off on vendor completion of standing up second system | V-A Co. | TRUE | MPS_8 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | Procurement - renegotiate Payroll contrats | Juliana Lima | Not Started | [10 empty] | 2016-06-30 | [22 empty] | No Review | [7 empty] | -
TN21 | TN21 - 38 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | Both | TRUE | MPS_9 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 39 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Complete IT system configuration with target condition in preparation for testing | Both | TRUE | MPS_10 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 40 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Vendor owned IT System/Application testing | Both | TRUE | MPS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 41 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Complete employee physical and electronic data purging | Both | TRUE | MPS_19 | 2016-06-30 | 30 | 2016-05-31 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 42 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | Both | TRUE | MPS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 43 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | MPS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 44 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | Both | TRUE | MPS_23 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 45 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | Both | TRUE | MPS_24 | 2016-07-31 | 30 | 2016-07-01 | 0% | FALSE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 46 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | Both | TRUE | MPS_11 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 47 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE | MPS_12 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 48 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE | MPS_13 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 49 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in GPS Testing- Test Test Event 1 | Both | TRUE | MPS_14 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 50 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in GPS Testing - CRP testing | Both | TRUE | MPS_15 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 51 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Participate in GPS Testing - UAT testing | Both | TRUE | MPS_16 | 2016-07-08 | 60 | 2016-05-09 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 52 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Complete the Testing of critical processes for Compensation (Hourly performance pay, compensation planning) and Talent Management (goal reporting, end cycle). | Both | TRUE | MPS_20 | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN21 | TN21 - 53 | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Validate the Support Model is in place prior to the separation (Kiosks, HR Portal, HR Call Center and Escalation Level) | Both | TRUE | MPS_26 | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE | IT - implement IT Infrastructure | Juliana Lima | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN08 | TN08-01 | Tania Nossa_Finance | Foreign Trade | Define Foreign Trade Organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 45% | FALSE |  | Mateus Sousa | On Track | Identify key activities and required skills and its their owner and owner backups; provide the appropriate training 18-Jan-2016 - Volumes and scope for 2016 being assessd with the Bus | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 270 | Foreign Trade Leadership | [5 empty] | -
TN08 | TN08-02 | Tania Nossa_Finance | Foreign Trade | Request Power of Attorney for V-A Co. employees to represent the Company with government agencies | V-A Co. | TRUE |  | 2016-04-30 | 45 | 2016-03-16 | 0% | TRUE | Having opened all branches CNPJ (IDs local companies) =>Tax Having the local board defined (President and Directors) to enable them as legal representatives => Legal Ensure that the new company is empowered to act as Imp/Exp (including all local branches) => Trade Compliance | Mateus Sousa | Not Started | 18-Jan-2016 - No comments |  | 2016-04-30 |  | 2016-04-30 | [26 empty] | 2016-03-15 |  | No Review |  | Foreign Trade Leadership |  | Legal Department |  |  |  | -
TN08 | TN08-03 | Tania Nossa_Finance | Foreign Trade | Custom brokers to represent V-A Co. | V-A Co. | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | We need the definition if the current custom brokers that have already represent Alcoa will be able for represent V-A as well => Legal Having the Commercial agreement assigned by brokers => Transportation | Mateus Sousa | Not Started | If FCPA investigations will be need to appoint the custom brokers for V-A, the processes must be started asap 18-Jan-2016 - This action depends first on Legal Structure for Value Add Company and then by Brokers definition |  |  |  | 2016-07-31 | [20 empty] | 2016-07-31 | [7 empty] | No Review |  | Foreign Trade Leadership |  | Legal Department |  |  |  | -
TN08 | TN08-04 | Tania Nossa_Finance | Foreign Trade | Ensure that Softway applilcations will properly work for Up and V-A Co. | Both | FALSE | FS_18 | 2016-06-30 | 120 | 2016-03-02 | 0% | FALSE | IT Team will define the best way to replicate he legacy system and suggest a schedule for the project => IT | Mateus Sousa | Not Started | An extremely critical item is to be defined by Softway Comany and IT Dept if the system to be implemented for V-A will be the same version currently used by Alcoa. If it will be required the new version, we can have problems once recently Sfw had asked seven months to update the versions 18-Jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review |  | Foreign Trade Leadership |  | IT Team | Softway |  |  | -
TN22 | TN22-01 | Tania Nossa_Compliance and Reporting | Compliance | Define ASAT Resources | Both | FALSE |  | 2016-03-31 | 30 | 2016-03-01 | 0% | FALSE |  | Fernando Campos | Not Started | # of Testers to attend each business. 18-jan-2016 - No comments | [32 empty] | No Review | 270 | CoE ASAT Leadership | [5 empty] | -
TN22 | TN22-02 | Tania Nossa_Compliance and Reporting | Compliance | Provide ASAT Training for transition | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Fernando Campos | Not Started | All testers should be trained and capable to attend the business. 18-jan-2016 - No comments | [32 empty] | No Review | 1620 | CoE ASAT Leadership | [5 empty] | -
TN22 | TN22-03 | Tania Nossa_Compliance and Reporting | Compliance | ASAT Storage Data | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | IT Servers | Fernando Campos | Not Started | Keep the ASAT documentation independent and available for 5 years. 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review | 180 | CoE ASAT Leadership | [5 empty] | -
TN22 | TN22-04 | Tania Nossa_Compliance and Reporting | Compliance | ASAT Internal Tools | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | IT Development | Fernando Campos | Not Started | Access Database to manage ASAT internal activities. 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review | 180 | CoE ASAT Leadership | [5 empty] | -
TN22 | TN22-05 | Tania Nossa_Compliance and Reporting | Compliance | ASAT Reporting | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT Development | Fernando Campos | Not Started | Compliance Dashboard should be running for all Business. 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review | 180 | CoE ASAT Leadership | [5 empty] | -
TN22 | TN22-06 | Tania Nossa_Compliance and Reporting | Compliance | ASP Sytem - Access | Both | FALSE |  | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Alcoa Audit System to manage the ASATs and Action Plans. | Fernando Campos | Not Started | Provide access to the Testers based on the TN22-01 action plan definitions 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [17 empty] | 2016-07-31 | [8 empty] | No Review |  | CoE ASAT Leadership |  | IT Team |  |  |  | -
TN22 | TN22-07 | Tania Nossa_Compliance and Reporting | Compliance | ASP Sytem - Database | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | Alcoa Audit System to manage the ASATs and Action Plans. | Fernando Campos | Not Started | Understand how would be the impact of the new ASP system to each business. 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [17 empty] | 2016-07-31 | [8 empty] | No Review |  | CoE ASAT Leadership |  | IT Team |  |  |  | -
TN22 | TN22-08 | Tania Nossa_Compliance and Reporting | Compliance | ASAT Testing Methodology | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Fernando Campos | Not Started | Follow a methodology of testing for each business in case is not possible to use a standard process. 18-jan-2016 - No comments | [32 empty] | No Review | 360 | CoE ASAT Leadership | [5 empty] | -
TN22 | TN22-09 | Tania Nossa_Compliance and Reporting | Compliance | SLAs (Service Level Agreement) | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Fernando Campos | Not Started | Develop a master SLA for each business regarding ASATs. 18-jan-2016 - No comments | [32 empty] | No Review | 360 | CoE ASAT Leadership | [5 empty] | -
TN23 | TN23-01 | Tania Nossa_Other | Commercial Backoffice | Reassure scope of service for Commercial Backoffice | V-A Co. | TRUE |  | 2016-03-31 | 60 | 2016-01-31 | 20% | TRUE | Reassure with Latin maerica GRP and LAE the strategy for CBO | Sergio Caldeira | On Track | 18-Jan-2016 - First discussion with LAE and GRP in Brazil to reassure scope for 2016 | [20 empty] | 2016-03-31 | [11 empty] | No Review | 90 | Commercial Backoffice | [5 empty] | REVIEW
TN23 | TN23-02 | Tania Nossa_Other | Commercial Backoffice | Define Commercial Backoffice Resources | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Sergio Caldeira | Not Started | 11-Jan-2016 - Based on current scope the organization is dedicated to value Add | [32 empty] | No Review | 45 | Commercial Backoffice | [5 empty] | -
TN23 | TN23-03 | Tania Nossa_Other | Commercial Backoffice | Provide access to the Commercial Backoffice systems | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Access to the BUs Systems with IT | Sergio Caldeira | Not Started | 18-Jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review |  | IT Team | [5 empty] | -
TN24 | TN24-01 | Tania Nossa_Other | Other process (Communication;Controllership; People Services Business Partner) | Controllership - Define GBS Controllership Organization | Both | TRUE |  | 2016-03-31 | 60 | 2016-01-31 | 0% | FALSE |  | Karen Guariza | Not Started | Define Org.design for both companies 18-Jan-2016 - No comments | [32 empty] | Review | 45 | GBS Controller | [5 empty] | REVIEW
TN24 | TN24-02 | Tania Nossa_Other | Other process (Communication;Controllership; People Services Business Partner) | Controllership - Provide Training to the GBS Controllership Processes transition | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Karen Guariza | Not Started | Provide training on GBS Controllership processes 18-Jan-2016 - No comments | [32 empty] | No Review | 720 | GBS Controller | [5 empty] | -
TN24 | TN24-03 | Tania Nossa_Other | Other process (Communication;Controllership; People Services Business Partner) | Controllership - Provide Access to the GBS Controllership Systems | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - implement IT Infrastructure | Karen Guariza | Not Started | 18-Jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review |  | GBS Controller |  | IT Team |  |  |  | -
TN24 | TN24-04 | Tania Nossa_Other | Other process (Communication;Controllership; People Services Business Partner) | BBHR & Communications - Define GBS HR Organization | Both | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 0% | FALSE |  | Karen Guariza | Not Started | Define Org.design for both companies 1`8-jan-2016 - No comments | [32 empty] | Review |  | ELGSS | [5 empty] | REVIEW
TN24 | TN24-05 | Tania Nossa_Other | Other process (Communication;Controllership; People Services Business Partner) | BBHR & Communications - Define GBS HR Organization | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Karen Guariza | Not Started | Provide training on GBS Controllership processes 18-jan-2016 - No comments | [32 empty] | No Review |  | ELGSS | [5 empty] | -
TN27 | TN27-01 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Reporting - Define Reporting Organization | Both | FALSE |  | 2016-02-28 | 60 | 2015-12-30 | 15% | FALSE |  | Carlos H.L.Silva | On Track | Define Org.design for both companies - Brazil and Europe 18-Jan-2016 - No comments | [32 empty] | No Review | 180 | CoE Reporting Leadership | [5 empty] | REVIEW
TN27 | TN27-02 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Reporting - Provide Reporting activities training for transition | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 25% | FALSE |  | Carlos H.L.Silva | On Track | Provide training based on Organizations designed for both Companies - Brazil and Europe 18-Jan-2016 - No comments | [32 empty] | No Review | 180 | CoE Reporting Leadership | [5 empty] | -
TN27 | TN27-03 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Reporting - Provide access to the systems and folders | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | IT - Provide system and infrastructure for FP&A and Reporting activites | Carlos H.L.Silva | Not Started | Based on the Organization split - Action plan TN27-01 - Brazil and Europe 18-Jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review |  | IT Team | [5 empty] | -
TN27 | TN27-04 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | FP&A GPP - Reassure scope of services with LATAM Regional Corporate and GPP organizations | Up. Co. | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | GPP FP&A - Finance and Latam region - reassure scope of services | Priscila Justiniano | Not Started | Brazil and Europe 18-jan-2016 - No comments | [20 empty] | 2016-03-31 | [11 empty] | Review | 180 | FP&A GPP Leadership | [5 empty] | REVIEW
TN27 | TN27-05 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | FP&A GPP - Define GPP FP&A Organization | Up. Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Priscila Justiniano | Not Started | Brazil and Europe 18-jan-2016 - No comments | [32 empty] | No Review | 45 | FP&A GPP Leadership | [5 empty] | -
TN27 | TN27-06 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | FP&A GRP and EPS - Define organization and provide access to the systems | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - Provide system and infrastructure for FP&A activites | Mitilha Silva | Not Started | Brazil and Europe 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review | 180 | FP&A GRP and EPS Leadership |  | IT Team |  |  |  | -
TN27 | TN28-01 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Reporting - Define Reporting Organization | Both | FALSE |  | 2016-02-28 | 60 | 2015-12-30 | 20% | FALSE |  | Carlos H.L.Silva | On Track | Define Org.design for both companies - US 18-Jan-2016 - No comments | [32 empty] | No Review | 270 | CoE Reporting Leadership | [5 empty] | REVIEW
TN27 | TN28-02 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Reporting - Provide Reporting training | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 25% | FALSE |  | Carlos H.L.Silva | On Track | Provide cross training based on Organizations designed for both Companies - US 18-jan-2016 - No comments | [32 empty] | No Review | 1080 | CoE Reporting Leadership | [5 empty] | -
TN27 | TN28-03 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Reporting - Provide access to the systems | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - Provide system and infrastructure for FP&A and Reporting activites | Carlos H.L.Silva | Not Started | Based on the Organization split - Action plan TN27-01 - US 18-jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review |  | IT Team | [5 empty] | -
TN27 | TN28-04 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | FP&A Global - Define organization | Both | FALSE |  | 2016-02-28 | 30 | 2016-01-29 | 90% | TRUE | GSS - Reassure scope of service and Customer (Company) to be attended | Thais Carvalho | On Track | US 18-Jan-2016 - Still waiting on Global FP&A definition regarding to the separation project | [7 empty] | 2016-02-28 | [24 empty] | No Review | 90 | FP&A Global | [5 empty] | -
TN27 | TN28-05 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | FP&A Global - Provide access to the systems | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - Provide system and infrastructure for FP&A and Reporting activites | Thais Carvalho | Not Started | US 18-Jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review | 90 | FP&A Global | [5 empty] | -
TN27 | TN28-06 | Tania Nossa_Compliance and Reporting | Reporting + FP&A | FP&A GRP and EPS - Provide access to the systems | V-A Co. | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | TRUE | IT - Provide system and infrastructure for FP&A activites | Mitilha Silva | Not Started | US 18-Jan-2016 - No comments | [5 empty] | 2016-07-31 | [26 empty] | No Review | 180 | FP&A GRP and EPS Leadership |  | IT Team |  |  |  | -
TN29 | TN29-01 | Transformation_Facilities | Shared Facilities | Define GSS organization | Both | TRUE |  | 2016-02-29 | 59 | 2016-01-01 | 5% | TRUE | GSS - Define organization for both Companies | Tania Nossa | On Track | 11-Jan-2016 - First level of Leadership already defined 18-JAN-2016 - Org charts depends on the 2nd level of Leadership definition | [7 empty] | 2016-02-28 | [24 empty] | No Review | 360 | GSS leadership | [5 empty] | REVIEW
TN29 | TN29-02 | Transformation_Facilities | Shared Facilities | Define IT organization | Both | TRUE |  | 2016-02-29 | 59 | 2016-01-01 | 0% | TRUE | IT - Define organization for both Companies | Tania Nossa | Not Started | 11-jan-2016 - depend on IT Leadership 18-Jan-2016 - Pendency was escalateds to Gael and Nancy | [5 empty] | 2016-02-28 | [26 empty] | Review |  | IT Leadership | [5 empty] | REVIEW
TN29 | TN29-03 | Transformation_Facilities | Shared Facilities | Define Procurement organization | Both | TRUE |  | 2016-02-29 | 59 | 2016-01-01 | 0% | TRUE | Procurement - Define organization for both Companies | Rodolfo Carvalho | Not Started | 11-jan-2016 - depend on Procurement Leadership 18-Jan-2016 - Pendency was escalateds to Gael and Nancy | [9 empty] | 2016-02-28 | [22 empty] | Review |  | Procurement Leadership | [5 empty] | REVIEW
TN29 | TN29-04 | Transformation_Facilities | Shared Facilities | Define Transportation organization | Both | TRUE |  | 2016-02-29 | 59 | 2016-01-01 | 0% | TRUE | Transportation - Define organization for both Companies | Hercules Schweter | Not Started | 11-jan-2016 - depend on Transportation Leadership 18-Jan-2016 - Pendency was escalateds to Gael and Nancy | [24 empty] | 2016-02-28 | [7 empty] | Review |  | Transportation leadership | [5 empty] | REVIEW
TN29 | TN29-05 | Transformation_Facilities | Shared Facilities | Map positions availability at GBS Facilities Offices (Pocos Plant and PDA) | Both | FALSE |  | 2016-01-31 | 30 | 2016-01-01 | 90% | FALSE |  | Tania Nossa | On Track | 11-Jan-2016 - Business Case being prepared 18-Jan-2016 - first draft under review with GBS leadership | [32 empty] | No Review | 540 | GSS leadership | [5 empty] | REVIEW
TN29 | TN29-06 | Transformation_Facilities | Shared Facilities | Evaluate potential facilities out of the Plant for Value Add Office | Both | FALSE |  | 2016-02-29 | 59 | 2016-01-01 | 90% | FALSE |  | Tania Nossa | On Track | 18-Jan-2016 - Two options evaluated, but the recommended option seems to be current Downtown Office refurbishment | [32 empty] | No Review | 90 | GSS leadership | [5 empty] | -
TN29 | TN29-07 | Transformation_Facilities | Shared Facilities | Submit and Approve BC for both Facilities | Both | TRUE |  | 2016-03-31 | 30 | 2016-03-01 | 40% | TRUE | GSS/Procurement/Transportation - Final decision on Facilities for both Companies | Tania Nossa | On Track | 11-Jan-2016 - Business Case being prepared 18-Jan-2016 - first draft under review with GBS leadership | [7 empty] | 2016-03-31 |  | 2016-03-31 | [14 empty] | 2016-03-31 | [7 empty] | No Review | 180 | GSS leadership | [5 empty] | -
TN29 | TN29-08 | Transformation_Facilities | Shared Facilities | Detailed plan for Facility adequacy and transition | Up. Co. | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | IT - Evaluate required Infrastructure for the Office 11-Jan-2016 - Depends on the actions 5 to 7 | Tania Nossa | Not Started | Supporting Infrastructure needed based on Action Plan TN29-07 18-Jan-2016 - To be develop after actions 5-7 | [5 empty] | 2016-03-31 | [26 empty] | Review | 90 | GSS leadership | [5 empty] | REVIEW
TN29 | TN29-09 | Transformation_Facilities | Shared Facilities | Detailed plan for Facility adequacy and transition | V-A Co. | FALSE |  | 2016-03-31 | 60 | 2016-01-31 | 0% | TRUE | IT - Evaluate required Infrastructure for the Office | Tania Nossa | Not Started | Supporting Infrastructure needed based on Action Plan TN29-07 18-Jan-2016 - To be develop after actions 5-7 | [5 empty] | 2016-03-31 | [26 empty] | Review | 180 | GSS leadership | [5 empty] | REVIEW
TN29 | TN29-10 | Transformation_Facilities | Shared Facilities | Perform facility adequacy | Up. Co. | TRUE |  | 2016-06-30 | 120 | 2016-03-02 | 0% | TRUE | IT - Provide required Infrastructure for the Office | Tania Nossa | Not Started | Supporting Infrastructure needed based on Action Plan TN29-07 18-Jan-2016 - To be develop after actions 5-7 | [5 empty] | 2016-06-30 | [26 empty] | No Review |  | GSS leadership | [5 empty] | -
TN29 | TN29-11 | Transformation_Facilities | Shared Facilities | Perform facility adequacy | V-A Co. | TRUE |  | 2016-06-30 | 120 | 2016-03-02 | 0% | TRUE | IT - Provide required Infrastructure for the Office | Tania Nossa | Not Started | Supporting Infrastructure needed based on Action Plan TN29-07 18-Jan-2016 - To be develop after actions 5-7 | [5 empty] | 2016-06-30 | [26 empty] | No Review |  | GSS leadership | [5 empty] | -
TN29 | TN29-12 | Transformation_Facilities | Shared Facilities | Accommodate the final organization in the definitive Office | Up. Co. | FALSE |  | 2016-07-31 | 59 | 2016-06-02 | 0% | FALSE |  | Tania Nossa | Not Started | Supporting Infrastructure needed based on Action Plan TN29-07 18-Jan-2016 - To be develop after actions 5-7 | [32 empty] | No Review |  | GSS leadership | [5 empty] | -
TN29 | TN29-13 | Transformation_Facilities | Shared Facilities | Accommodate the final organization in the definitive Office | V-A Co. | FALSE |  | 2016-07-31 | 59 | 2016-06-02 | 0% | FALSE |  | Tania Nossa | Not Started | Supporting Infrastructure needed based on Action Plan TN29-07 18-Jan-2016 - To be develop after actions 5-7 | [32 empty] | No Review |  | GSS leadership | [5 empty] | -
TN01 | TN01 - 01 | Tania Nossa_Finance | General Ledger, Cost Accounting | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN01 | TN01 - 02 | Tania Nossa_Finance | General Ledger, Cost Accounting | Define strategy between LD1 and OD 1 in collaboration with Transaction Execution | Both | TRUE | FS_3 | 2016-07-20 | 30 | 2016-06-20 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN01 | TN01 - 03 | Tania Nossa_Finance | General Ledger, Cost Accounting | Obtain needed separation resources to assist with acitvities suc as system testing | Both | TRUE | FS_4 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN01 | TN01 - 04 | Tania Nossa_Finance | General Ledger, Cost Accounting | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 25% | TRUE | GSS & Latam Region- Define organization for both Companies | Celso Baccini | On Track | 04-JAN-2016 - The discusson about the new organização was started in. 12-FEB-2016 - It was defined what type of LBC structure will be nedded to New Co. | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 40 | SAM GL | [5 empty] | -
TN01 | TN01 - 05 | Tania Nossa_Finance | General Ledger, Cost Accounting | Definition about the type of spilt (details about what assets/liabities will be transferred) | Both | TRUE |  | 2016-03-30 | 89 | 2016-01-01 | 15% | TRUE | Legal and Financial Accounting - Define type of split | Celso Baccini | On Track | 04-JAN-2016 - The discusson about the new organização was started in. 12-FEB-2016 - It was defined what type of LBC structure will be nedded to New Co. |  |  |  | 2016-03-30 | [26 empty] | 2016-03-30 | Financial Accounting and LAC Controllership | No Review | 132 | SAM GL | [5 empty] | REVIEW
TN01 | TN01 - 06 | Tania Nossa_Finance | General Ledger, Cost Accounting | Prepare the accounting data basis to transfer assets/liabilities from Alcoa to New Co (Value-Add) | Both | TRUE | FS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE | Legal and Financial Accounting - Define type of split | Celso Baccini | Not Started |  |  |  |  | 2016-03-30 | [26 empty] | 2016-03-30 | Financial Accounting and LAC Controllership | No Review | 300 | SAM GL | [5 empty] | -
TN01 | TN01 - 07 | Tania Nossa_Finance | General Ledger, Cost Accounting | Trainings | Both | FALSE | FS_22 | 2016-07-31 | 152 | 2016-03-01 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 60 | SAM GL | [5 empty] | -
TN01 | TN01 - 08 | Tania Nossa_Finance | General Ledger, Cost Accounting | Review Policies and Procedures | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 30 | SAM GL | [5 empty] | -
TN01 | TN01 - 9 | Tania Nossa_Finance | General Ledger, Cost Accounting | Access to the Systems | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Celso Baccini | Not Started | 04-JAN-2016 - Define which legacies systems will be used, setup and test them. | [32 empty] | No Review | 30 | SAM GL | [5 empty] | -
TN01 | TN01 - 10 | Tania Nossa_Finance | General Ledger, Cost Accounting | ABM&C Contract | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Procurement - renegotiate vendor contract (ABM&C) | Celso Baccini | Not Started | 04-JAN-2016 - Regociation with ABM&C (contractor to support about some legal obligations) to both companies | [9 empty] | 2016-04-30 | [22 empty] | No Review | 10 | SAM GL | [5 empty] | -
TN01 | TN01 - 11 | Tania Nossa_Finance | General Ledger, Cost Accounting | Reassessement of the Legacies Systems utilization for both sides | Both | FALSE |  | 2016-07-31 | 152 | 2016-03-01 | 10% | FALSE |  | Celso Baccini | On Track | 04-FEB-2016 - The Reassessement of the Legacies Systems utilization for both sides was started. | [32 empty] | No Review | 30 | SAM GL | [5 empty] | -
TN01 | TN01 - 12 | Tania Nossa_Finance | General Ledger, Cost Accounting | Review of Macros/Massalocation/Links to atend both companies | Both | TRUE |  | 2016-07-31 | 121 | 2016-04-01 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 60 | SAM GL | [5 empty] | -
TN01 | TN01 - 13 | Tania Nossa_Finance | General Ledger, Cost Accounting | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN02 | TN02 - 01 | Tania Nossa_Finance | Accounts Payable | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Matheus C. Martins | Not Started | [33 empty] | No Review | [7 empty] | -
TN02 | TN02 - 02 | Tania Nossa_Finance | Accounts Payable | Define strategy between LD1 and OD 1 in collaboration with Transaction Execution | Both | TRUE | FS_3 | 2016-07-20 | 30 | 2016-06-20 | 0% | FALSE |  | Matheus C. Martins | Not Started | [33 empty] | No Review | [7 empty] | -
TN02 | TN02 - 03 | Tania Nossa_Finance | Accounts Payable | Obtain needed separation resources to assist with acitvities suc as system testing | Both | TRUE | FS_4 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Matheus C. Martins | Not Started | [33 empty] | No Review | [7 empty] | -
TN02 | TN02 - 04 | Tania Nossa_Finance | Accounts Payable | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | GSS & Latam Region- Define organization for both Companies | Matheus C. Martins | Not Started | 12-JAN-2016 - Not started. Depends on Corporate definition | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 40 | SAM AP | [5 empty] | -
TN02 | TN02 - 05 | Tania Nossa_Finance | Accounts Payable | System Set Up and test (EBS and CambioSys) | Both | TRUE | FS_18 | 2016-06-30 | 120 | 2016-03-02 | 0% | TRUE | IT - implement IT Infrastructure | Matheus C. Martins | Not Started | 12-JAN-2016 - Not started. Depends on IT strategy. Execute all tests in EBS environment prior to Go Live. New company ID implementation on May'2015 and split to be completed on August'15. All interfaces from legacy systems to AP and IR module. Guarantee that all accounts payable set up was properly performed by GSS-Finance Set Up. | 2016-01-04 |  |  |  |  | 2016-04-03 | [26 empty] | No Review | 350 | SAM AP | [5 empty] | -
TN02 | TN02 - 06 | Tania Nossa_Finance | Accounts Payable | People training and back up development for all activities and positions | Both | TRUE | FS_22 | 2016-07-31 | 90 | 2016-05-02 | 2% | FALSE |  | Matheus C. Martins | On Track | 12-JAN-2016 - We started the initial mapping for key activities that requires back up development. | [32 empty] | No Review | 350 | SAM AP | [5 empty] | -
TN02 | TN02 - 07 | Tania Nossa_Finance | Accounts Payable | Duplicate Policies, Procedures and Flows | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Matheus C. Martins | Not Started | 12-JAN-2016 - Not Started | [32 empty] | No Review | 88 | SAM AP | [5 empty] | -
TN02 | TN02 - 08 | Tania Nossa_Finance | Accounts Payable | Bank Account and Foreign Trade Payments set up (Citibank, Bradesco and Bank of Brasil) | V-A Co. | TRUE |  | 2016-06-30 | 30 | 2016-05-31 | 50% | TRUE | Treasury - open banking account | Matheus C. Martins | On Track | 12-JAN-2016 - New bank account and access rights to accounts payable team. Treasury started the discussion on bank account and AP is providing data to the analysis. |  |  | 2016-03-31 |  |  | 2016-04-01 | [24 empty] | 2016-05-01 | Bank | No Review | 30 | SAM AP | [5 empty] | -
TN02 | TN02 - 09 | Tania Nossa_Finance | Accounts Payable | Supplier agreement for outsourced resources | Both | TRUE |  | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | Depends on the Contract Negotiation by Procurement | Matheus C. Martins | Not Started | 12-JAN-2016 - Not started. Depends on Procurement to review supplier contract. | [9 empty] | 2016-05-01 | [22 empty] | No Review | 20 | SAM AP | [5 empty] | -
TN02 | TN02 - 10 | Tania Nossa_Finance | Accounts Payable | Bradesco Bank System Set Up for tax payments - OBB and PTI | V-A Co. | TRUE |  | 2016-05-01 | 60 | 2016-03-02 | 0% | TRUE | Treasury - open banking account and Bradesco Bank | Matheus C. Martins | Not Started | 12-JAN-2016 - Not started. Depends on IT and bank strategy definition. | [5 empty] | 2016-03-02 | [24 empty] | 2016-05-01 | Bank | No Review | 88 | SAM AP | [5 empty] | -
TN02 | TN02 - 11 | Tania Nossa_Finance | Accounts Payable | Freight system Tests - CTMS | Both | TRUE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE | IT - implement IT Infrastructure and Transportation to support on Set Up | Matheus C. Martins | Not Started | 12-JAN-2016 - Not started. Depends on IT and Transportation team to determine the strategy for freight system. | [5 empty] | 2016-02-01 | [18 empty] | 2016-02-01 | [7 empty] | No Review | 150 | SAM AP | [5 empty] | -
TN02 | TN02 - 12 | Tania Nossa_Finance | Accounts Payable | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Matheus C. Martins | Not Started | [33 empty] | No Review | [7 empty] | -
TN03 | TN03 - 01 | Tania Nossa_Finance | FAPA | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN03 | TN03 - 02 | Tania Nossa_Finance | FAPA | Define strategy between LD1 and OD 1 in collaboration with Transaction Execution | Both | TRUE | FS_3 | 2016-07-20 | 30 | 2016-06-20 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN03 | TN03 - 03 | Tania Nossa_Finance | FAPA | Obtain needed separation resources to assist with acitvities suc as system testing | Both | TRUE | FS_4 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN03 | TN03 - 04 | Tania Nossa_Finance | FAPA | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 10% | TRUE | GSS & Latam Region- Define organization for both Companies | Celso Baccini | On Track | 04-JAN-2016 - The discusson about the new organização was started. | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 40 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 05 | Tania Nossa_Finance | FAPA | Transfer assets/liabilities from Alcoa to New Co (Value-Add) | Both | TRUE | FS_21 | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Legal and Financial Accounting - Support on accounting data. | Celso Baccini | Not Started | Prepare the accounting data basis to effective transferring assets/liabilities from Alcoa to New Co (Value-Add) |  |  |  | 2016-06-30 | [26 empty] | 2016-06-30 | Financial Accounting and LAC Controllership | No Review | 198 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 06 | Tania Nossa_Finance | FAPA | FAPA Training | Both | FALSE | FS_22 | 2016-07-31 | 152 | 2016-03-01 | 0% | FALSE |  | Celso Baccini | Not Started | Provide trainning for whole FAPA team in order to be prepared for Separation. | [32 empty] | No Review | 462 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 07 | Tania Nossa_Finance | FAPA | Review FAPA Policies and Procedures | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Celso Baccini | Not Started | Review the Accounting/FAPA Policies to both companies (FMHB for US-Gaap and Local) | [32 empty] | No Review | 88 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 08 | Tania Nossa_Finance | FAPA | Access to the Systems | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 88 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 09 | Tania Nossa_Finance | FAPA | Reassessement of the Legacies Systems utilization for both sides | Both | FALSE |  | 2016-07-31 | 121 | 2016-04-01 | 5% | FALSE |  | Celso Baccini | On Track | 04-FEB-2016 - The Reassessement of the Legacies Systems utilization for both sides was started. | [32 empty] | No Review | 462 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 10 | Tania Nossa_Finance | FAPA | Review of Macros/Massalocation/Links to atend both companies | Both | TRUE |  | 2016-07-31 | 121 | 2016-04-01 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 88 | SAM FAPA | [5 empty] | -
TN03 | TN03 - 11 | Tania Nossa_Finance | FAPA | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN04 | TN04 - 01 | Tania Nossa_Finance | Accounts Receivable & Credit | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Caroline Almeida | Not Started | [33 empty] | No Review | [7 empty] | -
TN04 | TN04 - 02 | Tania Nossa_Finance | Accounts Receivable & Credit | Define strategy between LD1 and OD 1 in collaboration with Transaction Execution | Both | TRUE | FS_3 | 2016-07-20 | 30 | 2016-06-20 | 0% | FALSE |  | Caroline Almeida | Not Started | [33 empty] | No Review | [7 empty] | -
TN04 | TN04 - 03 | Tania Nossa_Finance | Accounts Receivable & Credit | Obtain needed separation resources to assist with acitvities suc as system testing | Both | TRUE | FS_4 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Caroline Almeida | Not Started | [33 empty] | No Review | [7 empty] | -
TN04 | TN04 - 04 | Tania Nossa_Finance | Accounts Receivable & Credit | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | GSS & Latam Region- Define organization for both Companies | Caroline Almeida | Not Started | 12-JAN-2016 - Not started. Waiting Corporate definition. | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 20 | SAM OTC | [5 empty] | -
TN04 | TN04 - 05 | Tania Nossa_Finance | Accounts Receivable & Credit | Internal training | Both | TRUE | FS_22 | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE | NA | Caroline Almeida | Not Started | Bad debts calculation; AR daily management (domestic and exportation); Cash application; internal controls; cash flow process; receivable sales; closing activvities; Supplier financial analyses; internal controls; management reports 12-JAN-2016 - Not started. Depends on new organization definition. 12-FEB-2016: No additional comments | [32 empty] | No Review | 176 | SAM OTC | [5 empty] | -
TN04 | TN04 - 06 | Tania Nossa_Finance | Accounts Receivable & Credit | Serasa and Merchant Contracts | V-A Co. | TRUE |  | 2016-05-30 | 60 | 2016-03-31 | 0% | TRUE | Procurement - renegotiate vendor contracts (Serasa & Merchant) | Caroline Almeida | Not Started | 12-JAN-2016 - Not started. Depends on Procurement to review supplier contract. 12-FEB-2016: No additional comments | [9 empty] | 2016-04-30 | [22 empty] | No Review | 15 | SAM OTC | [5 empty] | -
TN04 | TN04 - 07 | Tania Nossa_Finance | Accounts Receivable & Credit | Bank Collection | V-A Co. | TRUE |  | 2016-04-30 | 120 | 2016-01-01 | 10% | TRUE | Treasury - renegotiate bank collection service | Caroline Almeida | On Track | 12-JAN-2016 - Treasury stated bank structure analysis and AR is providing data to help on bank definitions. 12-FEB-2016: No additional comments |  |  | 2016-04-30 | [29 empty] | No Review | 88 | SAM OTC | [5 empty] | REVIEW
TN04 | TN04 - 08 | Tania Nossa_Finance | Accounts Receivable & Credit | Credit Systems | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | FALSE | NA | Caroline Almeida | Not Started | Reassure that SAC System will be used by both companies. 12-JAN-2016 - Not started. Depends on system definition. 12-FEB-2016: No additional comments | [32 empty] | No Review | 40 | SAM OTC | [5 empty] | -
TN04 | TN04 - 09 | Tania Nossa_Finance | Accounts Receivable & Credit | Credit Policy | Both | TRUE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | GSS & Latam Region - Review Credit Policy | Caroline Almeida | Not Started | Verify if both companies will follow the current credit policy. 12-JAN-2016 - Not started. Depends on corporate definition. 12-FEB-2016: No additional comments | [7 empty] | 02/28/16 | [12 empty] | 02/28/16 | [11 empty] | No Review | 50 | SAM OTC | [5 empty] | -
TN04 | TN04 - 10 | Tania Nossa_Finance | Accounts Receivable & Credit | Obtain new bank account information from Treasury | V-A Co. | TRUE | FS_11 | 2016-03-31 | 30 | 2016-03-01 | 50% | TRUE | Treasury - Open new banking account | Caroline Almeida | On Track | 04-FEB-2016 - Treasury is opening new banking accounts for V-A. Co. 12-FEB-2016: No additional comments |  |  | 2016-03-31 | [29 empty] | No Review | [7 empty] | -
TN04 | TN04 - 11 | Tania Nossa_Finance | Accounts Receivable & Credit | System Setup and Interfaces | Both | TRUE | FS_13 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | IT - implement IT Infrastructure | Caroline Almeida | Not Started | Setup new banking accounts on EBS Oracle Setup and test Systems Interfaces (EBS/SAC/AOL/SCB) 12-JAN-2016 - Not started. Depends on system definition. 12-FEB-2016: No additional comments | [5 empty] | 04/30/16 | [26 empty] | No Review | 132 | SAM OTC | [5 empty] | -
TN05 | TN05 - 01 | Tania Nossa_PSC | PSC | Define new organization | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | GSS & Latam Region- Define organization for both Companies | Matheus C. Martins | Not Started | 18-JAN-2016 - Not started. Depends on Corporate definition | [7 empty] | 2016-02-28 | [12 empty] | 2016-02-28 | [11 empty] | No Review | 15 | SAM PSC | [5 empty] | -
TN05 | TN05 - 02 | Tania Nossa_PSC | PSC | EBS System - Setup and Tests | Both | FALSE |  | 2016-05-01 | 60 | 2016-03-02 | 0% | TRUE | IT - implement IT Infrastructure and Procurement to provide vendor Master Data | Matheus C. Martins | Not Started | 18-JAN-2016 - Not started. Depends on IT and GL Set Up Team. Execute all tests in EBS environment prior to Go Live. New company ID implementation on May'2015. Set up new vendor master data database. | [5 empty] | 04/30/16 |  |  |  | 04/30/16 | [22 empty] | No Review | 176 | SAM PSC | [5 empty] | -
TN05 | TN05 - 03 | Tania Nossa_PSC | PSC | People training and back up development for all activities and positions | Both | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Matheus C. Martins | Not Started | 18-JAN-2016 - Not started. Depends on organization definition. | [32 empty] | No Review | 132 | SAM PSC | [5 empty] | -
TN05 | TN05 - 04 | Tania Nossa_PSC | PSC | Duplicate Policies, Procedures and Flows | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Matheus C. Martins | Not Started | 18-JAN-2016 - Not started. | [32 empty] | No Review | 40 | SAM PSC | [5 empty] | -
TN05 | TN05 - 05 | Tania Nossa_PSC | PSC | Supplier agreement for outsourced resources | Both | FALSE |  | 2016-05-01 | 30 | 2016-04-01 | 0% | TRUE | Depends on the Contract Negotiation by Procurement | Matheus C. Martins | Not Started | 18-JAN-2016 - Not started. Depends on Procurement to review supplier agreement. | [9 empty] | 03/31/16 | [22 empty] | No Review | 10 | SAM PSC | [5 empty] | -
TN04 | TN04 - 12 | Tania Nossa_Finance | Accounts Receivable & Credit | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Caroline Almeida | Not Started | [33 empty] | No Review | [7 empty] | -
TN06 | TN06 - 01 | Tania Nossa_Finance | Finance System Support | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 10% | TRUE | GSS & Latam Region- Define organization for both Companies | Celso Baccini | On Track | 04-JAN-2016 - The discusson about the new organização was started in. | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 40 | SAM GL | [5 empty] | -
TN06 | TN06 - 02 | Tania Nossa_Finance | Finance System Support | Define strategy between LD1 and OD 1 in collaboration with Transaction Execution | Both | TRUE | FS_3 | 2016-07-20 | 30 | 2016-06-20 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN06 | TN06 - 03 | Tania Nossa_Finance | Finance System Support | Obtain needed separation resources to assist with acitvities suc as system testing | Both | TRUE | FS_4 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN06 | TN06 - 04 | Tania Nossa_Finance | Finance System Support | Obtain new bank account information from Treasury | V-A Co. | TRUE | FS_11 | 2016-03-31 | 30 | 2016-03-01 | 50% | TRUE | Treasury - Open new banking account | Celso Baccini | On Track | 04-FEB-2016 - Treasury is opening new banking accounts for V-A. Co. |  |  | 2016-03-31 | [29 empty] | No Review | [7 empty] | -
TN06 | TN06 - 05 | Tania Nossa_Finance | Finance System Support | Finalize implementation and testing plans with banks | V-A Co. | TRUE | FS_12 | 2016-05-30 | 30 | 2016-04-30 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN06 | TN06 - 06 | Tania Nossa_Finance | Finance System Support | Set-up and interface between EBS/Oracle and Legacies | Both | TRUE | FS_13 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE | IT - Implement IT Infrastructure | Celso Baccini | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | 464.2 | SAM GL | [5 empty] | -
TN06 | TN06 - 07 | Tania Nossa_Finance | Finance System Support | Create new LBC Structure to Value-Add Co (LBC's, SBU's, BU's, Lparent's) | Up. Co. | FALSE | FS_10 | 2016-03-30 | 90 | 2015-12-31 | 15% | TRUE | Legal and Financial Accounting - Define new LBC Structure | Celso Baccini | On Track | 04-JAN-2016 - The discusson about the new organização was started in. 12-FEB-2016 - It was defined what type of LBC structure will be nedded to New Co. |  |  |  | 2016-03-30 | [26 empty] | 2016-03-30 | Financial Accounting | No Review | 198 | SAM GL | [5 empty] | REVIEW
TN06 | TN06 - 08 | Tania Nossa_Finance | Finance System Support | Trainings | Both | FALSE | FS_24 | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 154 | SAM GL | [5 empty] | -
TN06 | TN06 - 09 | Tania Nossa_Finance | Finance System Support | Review Policies and Procedures | Both | FALSE |  | 2016-07-31 | 121 | 2016-04-01 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 30 | SAM GL | [5 empty] | -
TN06 | TN06 - 10 | Tania Nossa_Finance | Finance System Support | Obtain system scope of work and timeline from vendor to stand- up second system and obtain IT sign off for vendor owned system scope of work | Both | TRUE | FS_6 | 2016-02-28 | 30 | 2016-01-29 | 30% | TRUE | IT | Celso Baccini | On Track | 05-FEB-2016 - IT is working on system scope and timeline | [5 empty] | 2016-02-28 | [26 empty] | No Review | [7 empty] | REVIEW
TN06 | TN06 - 11 | Tania Nossa_Finance | Finance System Support | Test Event 1- Internal testing (3/15- 4/15) | Both | TRUE | FS_14 | 2016-04-15 | 30 | 2016-03-16 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-04-15 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 12 | Tania Nossa_Finance | Finance System Support | Create cutover plan between end of system clone and OD 1 | Both | TRUE | FS_15 | 2016-04-30 | 30 | 2016-03-31 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-04-30 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 13 | Tania Nossa_Finance | Finance System Support | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | Both | TRUE | FS_16 | 2016-05-20 | 30 | 2016-04-20 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-05-20 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 14 | Tania Nossa_Finance | Finance System Support | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | Both | TRUE | FS_17 | 2016-07-08 | 30 | 2016-06-08 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-07-08 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 15 | Tania Nossa_Finance | Finance System Support | Vendor owned IT System/Application testing | Both | TRUE | FS_18 | 2016-06-30 | 60 | 2016-05-01 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-06-30 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 16 | Tania Nossa_Finance | Finance System Support | Complete confidential physical and electronic data purging | Both | TRUE | FS_19 | 2016-08-31 | 60 | 2016-07-02 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-08-31 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 17 | Tania Nossa_Finance | Finance System Support | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | Both | TRUE | FS_20 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 18 | Tania Nossa_Finance | Finance System Support | Close intercompany transactions and update customer information for Value Add Co and Upstream Co. | Both | TRUE | FS_21 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 19 | Tania Nossa_Finance | Finance System Support | Operational readiness checkpoint | Both | TRUE | FS_22 | 2016-07-31 | 30 | 2016-07-01 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-07-31 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 21 | Tania Nossa_Finance | Finance System Support | Legal Day 1 Go live- system and functional requirements complete | Both | TRUE | FS_23 | 2016-08-01 | 30 | 2016-07-02 | 0% | TRUE |  | Celso Baccini | Not Started | [6 empty] | 2016-08-01 | [26 empty] | No Review | [7 empty] | -
TN06 | TN06 - 22 | Tania Nossa_Finance | Finance System Support | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN06 | TN06 - 23 | Tania Nossa_Finance | Finance System Support | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | [7 empty] | -
TN06 | TN06 - 24 | Tania Nossa_Finance | Finance System Support | Access to the Systems | Both | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | FALSE |  | Celso Baccini | Not Started | [33 empty] | No Review | 45 | SAM GL | [5 empty] | -
TN07 | TN07 - 01 | Tania Nossa_Finance | T&E | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Matheus C. Martins | Not Started | [33 empty] | No Review | [7 empty] | -
TN07 | TN07 - 02 | Tania Nossa_Finance | T&E | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | GSS & Latam Region- Define organization for both Companies | Matheus C. Martins | Not Started | 12-JAN-2016 - Not started. Depends on Corporate definition | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 20 | SAM T&E | [5 empty] | -
TN07 | TN07 - 03 | Tania Nossa_Finance | T&E | T&E Agreements | V-A Co. | TRUE |  | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Contract negotiation to be performed by procurement and Treasury to determine bank account for the new company | Matheus C. Martins | Not Started | 12-JAN-2106. Not Started. Depends on Procurement and GSS strategy for Travel Agency, Bank that will provide credit cards, airlines, hotels and car rental agreements. |  |  | 02/28/16 | [6 empty] | 2016-02-01 | [22 empty] | No Review | 132 | SAM T&E | [5 empty] | -
TN07 | TN07 - 04 | Tania Nossa_Finance | T&E | Legacy System Set Up and Tests | Both | FALSE | FS_18 | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT - to implement IT infrastructure and third-parties companies that need to support the implementation (Concur, Travel Agency, Bank) | Matheus C. Martins | Not Started | 12-JAN-2106. Not Started. Depends on Travel Agency definition and IT to Set up and tests new employees and credit card master data. Develop interface for employee and GL update. | [5 empty] | 04/30/16 | [24 empty] | 2016-02-01 | Concur, Bank and Travel Agency | No Review | 66 | SAM T&E | [5 empty] | -
TN07 | TN07 - 05 | Tania Nossa_Finance | T&E | T&E and LVP Policy and Procedures | Both | FALSE |  | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | Corporation, HR, EHS, Legal and Procurement to approve T&E and LVP Policy | Matheus C. Martins | Not Started | 12-JAN-2106. Not Started. Depends on global and corporate to determine the new T&E and LVP Policies deploy to all employees and provide training. |  |  |  | 2016-07-01 |  |  |  | 2016-07-01 |  | 2016-07-01 | 2016-07-01 | [9 empty] | 2016-07-01 | [11 empty] | No Review | 100 | SAM T&E | [5 empty] | -
TN07 | TN07 - 06 | Tania Nossa_Finance | T&E | People training and back up development for all activities and positions | Both | TRUE | FS_24 | 2016-07-31 | 120 | 2016-04-02 | 0% | FALSE |  | Matheus C. Martins | Not Started | 12-JAN-2106. Not Started. Depends on organization definition. | [32 empty] | No Review | 132 | SAM T&E | [5 empty] | -
TN07 | TN07 - 07 | Tania Nossa_Finance | T&E | Access to the Systems | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | FALSE |  | Matheus C. Martins | Not Started | 12-JAN-2106. Not Started. | [32 empty] | No Review | 45 | SAM T&E | [5 empty] | -
TN07 | TN07 - 08 | Tania Nossa_Finance | T&E | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Matheus C. Martins | Not Started | [33 empty] | No Review | [7 empty] | -
TN09 | TN09 - 01 | Tania Nossa_Finance | Tax Services | Define/confirm GSS Finance scope of services for BU's and locations | Both | TRUE | FS_1 | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE |  | Fabiana Bianucci | Not Started | [33 empty] | No Review | [7 empty] | -
TN09 | TN09 - 02 | Tania Nossa_Finance | Tax Services | Define strategy between LD1 and OD 1 in collaboration with Transaction Execution | Both | TRUE | FS_3 | 2016-07-20 | 30 | 2016-06-20 | 0% | FALSE |  | Fabiana Bianucci | Not Started | [33 empty] | No Review | [7 empty] | -
TN09 | TN09 - 03 | Tania Nossa_Finance | Tax Services | Obtain needed separation resources to assist with acitvities suc as system testing | Both | TRUE | FS_4 | 2016-03-31 | 30 | 2016-03-01 | 0% | TRUE |  | Fabiana Bianucci | Not Started | [33 empty] | No Review | [7 empty] | -
TN09 | TN09 - 04 | Tania Nossa_Finance | Tax Services | Define new organization | Both | TRUE | FS_2 | 2016-04-30 | 60 | 2016-03-01 | 2% | TRUE | GSS & Latam Region- Define organization for both Companies | Fabiana Bianucci | On Track | 12-JAN-2016 - Pending official document to be provided by legal department. | [7 empty] | 2016-04-30 | [12 empty] | 2016-04-30 | [11 empty] | No Review | 40 | SAM TAX | [5 empty] | -
TN09 | TN09 - 05 | Tania Nossa_Finance | Tax Services | Fiscal book system license (Mastersaf) | Both | TRUE | FS_18 | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT - Implement Mastersaf for both companies Procurement - Renegotiate Mastersaf contract | Fabiana Bianucci | Not Started | 12-JAN-2016 - Depends on TN 09-01 conclusion | [5 empty] | 2016-04-30 |  |  |  | 2016-03-31 | [22 empty] | No Review | 40 | SAM TAX | [5 empty] | -
TN09 | TN09 - 06 | Tania Nossa_Finance | Tax Services | Invoice system licence (Synchro-Nfe) | Both | TRUE | FS_18 | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | IT - Implement Synchro for both companies Procurement - Renegotiate Synchro contract | Fabiana Bianucci | Not Started | 12-JAN-2016 - Depends on TN 09-01 conclusion | [5 empty] | 2016-04-30 |  |  |  | 2016-03-31 | [22 empty] | No Review | 40 | SAM TAX | [5 empty] | -
TN09 | TN09 - 07 | Tania Nossa_Finance | Tax Services | Tax ID for V-A Co. locations | V-A Co. | TRUE | FS_10 | 2016-03-30 | 90 | 2015-12-31 | 50% | TRUE | Legal - Update the Company’s Minutes in the Public Agency | Fabiana Bianucci | On Track | 12-JAN-2016 - Open Tax ID for new company - Pending official document to be provided by legal department |  | 12/31/15 |  | 2016-02-28 | [28 empty] | No Review | 50 | SAM TAX | [5 empty] | REVIEW
TN09 | TN09 - 08 | Tania Nossa_Finance | Tax Services | ABMC Contract | V-A Co. | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | TRUE | Procurement - Renegotiate ABMC contract | Fabiana Bianucci | Not Started | 12-JAN-2016 - Depends on TN 09-01 conclusion | [5 empty] | 2016-04-30 |  |  |  | 2016-03-31 | [22 empty] | No Review | 40 | SAM TAX | [5 empty] | -
TN09 | TN09 - 09 | Tania Nossa_Finance | Tax Services | Alcoa Capital Reduction | Up. Co. | TRUE |  | 2016-08-30 | 150 | 2016-04-02 | 0% | TRUE | Legal - Update the Company’s Minutes in the Public Agency | Fabiana Bianucci | Not Started | 12-JAN-2016 - Depends on TN 09-01 conclusion |  |  |  | 2016-06-30 | [28 empty] | No Review | 40 | SAM TAX | [5 empty] | -
TN09 | TN09 - 10 | Tania Nossa_Finance | Tax Services | Transfer tax benefits | V-A Co. | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Tax Planning - support on this action | Fabiana Bianucci | Not Started | 12-JAN-2016 - Depends on TN 09-01 conclusion |  | 2016-04-30 | [30 empty] | No Review | 180 | SAM TAX | [5 empty] | -
TN09 | TN09 - 11 | Tania Nossa_Finance | Tax Services | Technical training | Both | FALSE | FS_22 | 2016-04-30 | 120 | 2016-01-01 | 5% | FALSE |  | Fabiana Bianucci | On Track | 12-JAN-2016 - Tax started the initial mapping for the activities that requires technical training | [32 empty] | No Review | 350 | SAM TAX | [5 empty] | REVIEW
TN09 | TN09 - 12 | Tania Nossa_Finance | Tax Services | Access to the Systems | Both | TRUE |  | 2016-06-30 | 30 | 2016-05-31 | 0% | FALSE |  | Fabiana Bianucci | Not Started | 12-JAN-2016 - Depends on new system enrironment | [32 empty] | No Review | 264 | SAM TAX | [5 empty] | -
TN10 | TN10 - 01 | Tania Nossa_Treasury | LA Treasury Backoffice | Define new organization | Both | TRUE | MT_2 | 2016-02-28 | 60 | 2015-12-30 | 80% | TRUE | GSS & Latam Region- Define organization for both Companies | Fabrizzia Colozza | On Track | 5-FEB-2016 - We are working on a transition schedule 08-JAN-2016 - We are discussing our organization with Global Treasury | [7 empty] | 2016-02-28 | [12 empty] | 2016-02-28 | [11 empty] | No Review | 80 | SAM TBO | [5 empty] | REVIEW
TN10 | TN10 - 02 | Tania Nossa_Treasury | LA Treasury Backoffice | BackOffice Scope Definition | Both | TRUE | MT_1 | 2016-02-28 | 58 | 2016-01-01 | 50% | TRUE | Treasury & Latam Region- define strategy and organization needed | Fabrizzia Colozza | On Track | 5-FEB-2016 - The backOffice structure is still under discussion, considering timezone for some specific activities 08-JAN-2016 - Back Office structure and scope under discussion with Treasury. Definition of how the backoffice structure will be, considering segregation of duties and controls |  |  | 01/31/16 | [17 empty] | 01/31/16 | [11 empty] | No Review | 44 | SAM TBO | [5 empty] | REVIEW
TN10 | TN10 - 03 | Tania Nossa_Treasury | LA Treasury Backoffice | OD1 And LD1 Transaction Execution | Both | TRUE | MT_3 | 2016-05-31 | 91 | 2016-03-01 | 0% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | Not Started | Obtain strategy for operating between OD1 And LD1 from Transaction Execution |  |  | 2016-05-31 |  |  | 2016-05-31 |  | 2016-05-31 | [24 empty] | No Review | 44 | SAM TBO | [5 empty] | -
TN10 | TN10 - 04 | Tania Nossa_Treasury | LA Treasury Backoffice | Hire & Training | Both | TRUE | MT_15 | 2016-07-31 | 180 | 2016-02-02 | 5% | TRUE | RH - hire new employees | Fabrizzia Colozza | On Track | 5-FEB-2016 - communication to HR area to define the necessary steps for hiring new employees Hire employees according to the demand and train team to activities considering duplication |  |  |  |  | 03/30/16 | [27 empty] | No Review | 264 | SAM TBO | 30 | Recruiting Team |  |  |  | REVIEW
TN10 | TN10 - 05 | Tania Nossa_Treasury | LA Treasury Backoffice | Establish Capital Structure definition | Both | TRUE | MT_5 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE | Legal - Legal Entities need be established / Accounting - Need confirmation of LBC codes | Fabrizzia Colozza | On Track | 5-FEB-2016 - no new information 08-JAN-2016 - Delloitte is evaluating Alcoa's proposal. Structure definitions (new entities, counterparties and accounting) |  | 2015-12-31 | [30 empty] | No Review | 88 | SAM TBO | 44 | SAM TAX |  |  |  | -
TN10 | TN10 - 06 | Tania Nossa_Treasury | LA Treasury Backoffice | Treasury Specific IT | Both | TRUE | MT_6 | 2016-03-18 | 76 | 2016-01-02 | 5% | TRUE | Legal - Legal Entities need be established / Treasury - Bank account numbers for new accounts need to be established / Accounting - Need confirmation of LBC codes | Fabrizzia Colozza | On Track | 5-FEB-2016 - the new enviroment development is due to be completed by the mid of February 08-JAN-2016 - defined that both companies will use Quantum System. Support on Inventory Replication; Setup of New Entities, Bank Accounts, Counterparties and accounting; Interfaces. | [5 empty] | 2016-03-18 | [26 empty] | No Review | 150 | SAM TBO | [5 empty] | REVIEW
TN10 | TN10 - 07 | Tania Nossa_Treasury | LA Treasury Backoffice | SCB - bank reconciliation | Both | TRUE |  | 2016-06-09 | 100 | 2016-03-01 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-04-30 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN10 | TN10 - 08 | Tania Nossa_Treasury | LA Treasury Backoffice | Test Treasury System | Both | TRUE | MT_9 | 2016-06-09 | 82 | 2016-03-19 | 0% | TRUE | Legal - Legal Entities need be established / Treasury - Bank account numbers for new accounts need to be established / Accounting - Need confirmation of LBC codes | Fabrizzia Colozza | Not Started | 5-FEB-2016 - the new enviroment development is due to be completed by the mid of February 08-JAN-2016 - defined that both companies will use Quantum System. Support on Inventory Replication; Setup of New Entities, Bank Accounts, Counterparties and accounting; Interfaces. | [5 empty] | 2016-06-09 | [26 empty] | No Review | 70 | SAM TBO | [5 empty] | -
TN10 | TN10 - 09 | Tania Nossa_Treasury | LA Treasury Backoffice | EBS System - Test Event | Both | TRUE | MT_4 | 2016-04-15 | 31 | 2016-03-15 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-04-15 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN10 | TN10 - 10 | Tania Nossa_Treasury | LA Treasury Backoffice | EBS System - CRP Test | Both | TRUE | MT_8 | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-05-20 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN10 | TN10 - 11 | Tania Nossa_Treasury | LA Treasury Backoffice | EBS System - UAT Tests | Both | TRUE | MT_10 | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-07-08 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN10 | TN10 - 12 | Tania Nossa_Treasury | LA Treasury Backoffice | EBS System - Cutover (if needed) | Both | TRUE | MT_12 | 2016-07-31 | 16 | 2016-07-15 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-07-31 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN10 | TN10 - 13 | Tania Nossa_Treasury | LA Treasury Backoffice | Establish Cash and Banking Structures | V-A Co. | TRUE | MT_7 | 2016-05-04 | 160 | 2015-11-26 | 15% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice received new entities documentation and has already the STA approval for oppening the bank accounts 08-JAN-2016 - LA Treasury has started the process of openning banking accounts. Bank account management (inventory, openning new bank accounts, zero balance and shared services structure, interfaces). |  |  | 2016-02-28 | [29 empty] | No Review | 132 | SAM TBO | [5 empty] | REVIEW
TN10 | TN10 - 14 | Tania Nossa_Treasury | LA Treasury Backoffice | Bloomberg & Intercam contract | V-A Co. | TRUE |  | 2016-04-30 | 60 | 2016-03-01 | 0% | TRUE | Procurement - Renegotiate Bloomberg and Intercam Contract | Fabrizzia Colozza | Not Started | New contract, evaluating interfaces and new access needed | [5 empty] | 2016-03-31 | [26 empty] | No Review | 10 | SAM TBO | [5 empty] | -
TN10 | TN10 - 15 | Tania Nossa_Treasury | LA Treasury Backoffice | Access to the Systems | Both | TRUE |  | 2016-04-30 | 120 | 2016-01-01 | 7% | FALSE |  | Fabrizzia Colozza | On Track | 08/01/2016 - Norht America Treasury is currently working with Sungard on the stablishement of new system envirorment. | [32 empty] | No Review | 45 | SAM TBO | [5 empty] | REVIEW
TN10 | TN10 - 16 | Tania Nossa_Treasury | LA Treasury Backoffice | Test processing bank transfer from new bank accounts | V-A Co. | TRUE | MT_11 | 2016-06-15 | 40 | 2016-05-06 | 0% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | Not Started | 6-FEB-2016 - BackOffice received new entities documentation and has already the STA approval for oppening the bank accounts 08-JAN-2016 - LA Treasury has started the process of openning banking accounts. Bank account management (inventory, openning new bank accounts, zero balance and shared services structure, interfaces). |  |  | 2016-06-15 | [29 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN10 | TN10 - 17 | Tania Nossa_Treasury | LA Treasury Backoffice | Review SLA, Policies and Procedures | Both | TRUE | MT_13 | 2016-09-30 | 120 | 2016-06-02 | 0% | TRUE | Legal (policies definition) | Fabrizzia Colozza | Not Started |  |  |  |  | 2016-06-30 | [28 empty] | No Review | 45 | SAM TBO | [5 empty] | -
TN10 | TN10 - 18 | Tania Nossa_Treasury | LA Treasury Backoffice | Review Controls (ASAT processes) | Both | TRUE | MT_14 | 2016-09-30 | 120 | 2016-06-02 | 0% | TRUE | Legal (policies definition) | Fabrizzia Colozza | Not Started |  |  |  |  | 2016-06-30 | [28 empty] | No Review | 45 | SAM TBO | [5 empty] | -
TN10 | TN10 - 19 | Tania Nossa_Treasury | LA Treasury Backoffice | Operational readiness checkpoint | Both | TRUE | MT_17 | 2016-07-31 | 210 | 2016-01-03 | 2% | FALSE |  | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice is working on a transition schedule | [32 empty] | No Review | 45 | SAM TBO | [5 empty] | REVIEW
TN10 | TN10 - 20 | Tania Nossa_Treasury | LA Treasury Backoffice | Implement target GSS organization | Both | TRUE | MT_16 | 2016-07-31 | 210 | 2016-01-03 | 2% | FALSE |  | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice is working on a transition schedule | [32 empty] | No Review | 45 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 01 | Tania Nossa_Treasury | NA Treasury Backoffice | Define new organization | Both | TRUE | MT_2 | 2016-02-28 | 60 | 2015-12-30 | 80% | TRUE | GSS & Latam Region- Define organization for both Companies | Fabrizzia Colozza | On Track | 5-FEB-2016 - We are working on a transition schedule 08-JAN-2016 - We are discussing our organization with Global Treasury | [7 empty] | 2016-02-28 | [12 empty] | 2016-02-28 | [11 empty] | No Review | 88 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 02 | Tania Nossa_Treasury | NA Treasury Backoffice | BackOffice Scope Definition | Both | TRUE | MT_1 | 2016-02-28 | 58 | 2016-01-01 | 50% | TRUE | NA Treasury, Electricity and AMM Trading Desk | Fabrizzia Colozza | On Track | 5-FEB-2016 - The backOffice structure is still under discussion, considering timezone for some specific activities 08-JAN-2016 - Back Office structure and scope under discussion with Treasury. Definition of how the backoffice structure will be, considering segregation of duties and controls |  |  | 2016-02-01 | [29 empty] | No Review | 44 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 03 | Tania Nossa_Treasury | NA Treasury Backoffice | OD1 And LD1 Transaction Execution | Both | TRUE | MT_3 | 2016-05-31 | 91 | 2016-03-01 | 0% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | Not Started | Obtain strategy for operating between OD1 And LD1 from Transaction Execution |  |  | 2016-05-31 |  |  | 2016-05-31 |  | 2016-05-31 | [24 empty] | No Review | 44 | SAM TBO | [5 empty] | -
TN11 | TN11 - 04 | Tania Nossa_Treasury | NA Treasury Backoffice | Hire & Training | Both | TRUE | MT_15 | 2016-07-31 | 180 | 2016-02-02 | 5% | TRUE | RH - hire new employees | Fabrizzia Colozza | On Track | 5-FEB-2016 - communication to HR area to define the necessary steps for hiring new employees Hire employees according to the demand and train team to activities considering duplication |  |  |  |  | 03/30/16 | [27 empty] | No Review | 264 | SAM TBO | 30 | Recruiting Team |  |  |  | REVIEW
TN11 | TN11 - 05 | Tania Nossa_Treasury | NA Treasury Backoffice | Establish Capital Structure definition | Both | TRUE | MT_5 | 2016-04-30 | 60 | 2016-03-01 | 60% | TRUE | Legal - Legal Entities need be established / Accounting - Need confirmation of LBC codes | Fabrizzia Colozza | On Track | 5-FEB-2016 - no new information 08-JAN-2016 - Delloitte is evaluating Alcoa's proposal. Structure definitions (new entities, counterparties and accounting) |  |  | 2016-05-06 | 2016-05-06 | [28 empty] | No Review | 88 | SAM TBO | [5 empty] | -
TN11 | TN11 - 06 | Tania Nossa_Treasury | NA Treasury Backoffice | Treasury Specific IT | Both | TRUE | MT_6 | 2016-03-18 | 76 | 2016-01-02 | 5% | TRUE | Legal - Legal Entities need be established / Treasury - Bank account numbers for new accounts need to be established / Accounting - Need confirmation of LBC codes | Fabrizzia Colozza | On Track | 5-FEB-2016 - the new enviroment development is due to be completed by the mid of February 08-JAN-2016 - defined that both companies will use Quantum System. Support on Inventory Replication; Setup of New Entities, Bank Accounts, Counterparties and accounting; Interfaces. | [5 empty] | 2016-03-18 | [26 empty] | No Review | 150 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 07 | Tania Nossa_Treasury | NA Treasury Backoffice | Test Treasury System | Both | TRUE | MT_9 | 2016-06-09 | 82 | 2016-03-19 | 0% | TRUE | Legal - Legal Entities need be established / Treasury - Bank account numbers for new accounts need to be established / Accounting - Need confirmation of LBC codes | Fabrizzia Colozza | Not Started | 5-FEB-2016 - the new enviroment development is due to be completed by the mid of February 08-JAN-2016 - defined that both companies will use Quantum System. Support on Inventory Replication; Setup of New Entities, Bank Accounts, Counterparties and accounting; Interfaces. | [5 empty] | 2016-06-09 | [26 empty] | No Review | 70 | SAM TBO | [5 empty] | -
TN11 | TN10 - 08 | Tania Nossa_Treasury | NA Treasury Backoffice | EBS System - Test Event | Both | TRUE | MT_4 | 2016-04-15 | 31 | 2016-03-15 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-04-15 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN11 | TN10 - 09 | Tania Nossa_Treasury | NA Treasury Backoffice | EBS System - CRP Test | Both | TRUE | MT_8 | 2016-05-20 | 32 | 2016-04-18 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-05-20 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN11 | TN10 - 10 | Tania Nossa_Treasury | NA Treasury Backoffice | EBS System - UAT Tests | Both | TRUE | MT_10 | 2016-07-08 | 46 | 2016-05-23 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-07-08 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN11 | TN10 - 11 | Tania Nossa_Treasury | NA Treasury Backoffice | EBS System - Cutover (if needed) | Both | TRUE | MT_12 | 2016-07-31 | 16 | 2016-07-15 | 0% | TRUE | Brazil IT | Fabrizzia Colozza | Not Started | New bank account, interface and accounting setup | [5 empty] | 2016-07-31 | [26 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN11 | TN10 - 12 | Tania Nossa_Treasury | NA Treasury Backoffice | Establish Cash and Banking Structures | V-A Co. | TRUE | MT_7 | 2016-05-04 | 160 | 2015-11-26 | 15% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice received new entities documentation and has already the STA approval for oppening the bank accounts 08-JAN-2016 - LA Treasury has started the process of openning banking accounts. Bank account management (inventory, openning new bank accounts, zero balance and shared services structure, interfaces). |  |  | 2016-02-28 | [29 empty] | No Review | 132 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 13 | Tania Nossa_Treasury | NA Treasury Backoffice | Hedging and Electricity IT | Both | TRUE |  | 2016-07-31 | 210 | 2016-01-03 | 15% | TRUE | AMM IT, AMM and Electricity Trading Desk | Fabrizzia Colozza | On Track | Setup new strategies and give support to IT to duplicate and analyse the system 08-JAN-2016 - the strategy split between both companies. 6-FEB-2016 - no new update | [30 empty] | 2016-07-31 | AMM IT, AMM and Electricity Trading Desk | No Review | 154 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 09 | Tania Nossa_Treasury | NA Treasury Backoffice | Establish Cash and Banking Structures | V-A Co. | TRUE | MT_7 | 2016-05-04 | 160 | 2015-11-26 | 15% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice received new entities documentation and has already the STA approval for oppening the bank accounts 08-JAN-2016 - LA Treasury has started the process of openning banking accounts. Bank account management (inventory, openning new bank accounts, zero balance and shared services structure, interfaces). |  |  | 2016-02-28 | [29 empty] | No Review | 132 | SAM TBO | [5 empty] | REVIEW
TN11 | TN11 - 14 | Tania Nossa_Treasury | NA Treasury Backoffice | Test processing bank transfer from new bank accounts | V-A Co. | TRUE | MT_11 | 2016-06-15 | 40 | 2016-05-06 | 0% | TRUE | Shared Services (AP, AR, RH, COMEX), Treasury and IT | Fabrizzia Colozza | Not Started | 6-FEB-2016 - BackOffice received new entities documentation and has already the STA approval for oppening the bank accounts 08-JAN-2016 - LA Treasury has started the process of openning banking accounts. Bank account management (inventory, openning new bank accounts, zero balance and shared services structure, interfaces). |  |  | 2016-06-15 | [29 empty] | No Review | 132 | SAM TBO | [5 empty] | -
TN11 | TN11 - 15 | Tania Nossa_Treasury | NA Treasury Backoffice | Bloomberg contract | Up. Co. | TRUE |  | 2016-05-06 | 60 | 2016-03-07 | 0% | TRUE | Commercial area | Fabrizzia Colozza | Not Started | new contract, evaluating interfaces and new access needed |  |  | 2016-05-06 | [29 empty] | No Review | 10 | SAM TBO | [5 empty] | -
TN11 | TN11 - 16 | Tania Nossa_Treasury | NA Treasury Backoffice | Access to the Systems | Both | TRUE |  | 2016-04-30 | 120 | 2016-01-01 | 7% | FALSE |  | Fabrizzia Colozza | On Track | 08/01/2016 - Norht America Treasury is currently working with Sungard on the stablishement of new system envirorment. | [32 empty] | No Review | 45 | SAM TBO | [5 empty] | REVIEW
TN11 | TN10 - 17 | Tania Nossa_Treasury | NA Treasury Backoffice | Review SLA, Policies and Procedures | Both | TRUE | MT_13 | 2016-09-30 | 120 | 2016-06-02 | 0% | TRUE | Legal (policies definition) | Fabrizzia Colozza | Not Started |  |  |  |  | 2016-06-30 | [28 empty] | No Review | 45 | SAM TBO | [5 empty] | -
TN11 | TN10 - 18 | Tania Nossa_Treasury | NA Treasury Backoffice | Review Controls (ASAT processes) | Both | TRUE | MT_14 | 2016-09-30 | 120 | 2016-06-02 | 0% | TRUE | Legal (policies definition) | Fabrizzia Colozza | Not Started |  |  |  |  | 2016-06-30 | [28 empty] | No Review | 45 | SAM TBO | [5 empty] | -
TN11 | TN10 - 19 | Tania Nossa_Treasury | NA Treasury Backoffice | Operational readiness checkpoint | Both | TRUE | MT_17 | 2016-07-31 | 210 | 2016-01-03 | 2% | FALSE |  | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice is working on a transition schedule | [32 empty] | No Review | 45 | SAM TBO | [5 empty] | REVIEW
TN11 | TN10 - 20 | Tania Nossa_Treasury | NA Treasury Backoffice | Implement target GSS organization | Both | TRUE | MT_16 | 2016-07-31 | 210 | 2016-01-03 | 2% | FALSE |  | Fabrizzia Colozza | On Track | 6-FEB-2016 - BackOffice is working on a transition schedule | [32 empty] | No Review | 45 | SAM TBO | [5 empty] | REVIEW
TN26 | TN26 - 01 | Tania Nossa_Records Management | Records Management | Transfer records archived onsite from downstream BUs to Alcoa | V-A Co. | TRUE |  | 2016-11-30 | 150 | 2016-07-03 | 5% | TRUE | Project plan should be defined with downstream Bus that have records stored onsite | Matheus C. Martins | On Track | 12-JAN-2016. We started the discussion with Corporate Tax and Legal to determine if the documents currently archived onsite on downstream Bus should be transferred to Alcoa prior to separation process. 18-JAN-2016. Legal aspects being analyzed by Legal area to definie the ownership of the current Value-Add documents under Alcoa's responmsibility |  |  |  | 03/31/16 |  | 04/30/16 | [24 empty] | 2016-03-04 | Downstream BU | No Review | 330 | SAM Records Management | [5 empty] | -
TN26 | TN26 - 02 | Tania Nossa_Records Management | Records Management | Records Management Supplier agreement | V-A Co. | FALSE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | TRUE | Depends on the Contract Negotiation by Procurement | Matheus C. Martins | Not Started | 18-JAN-2106. Not Started. Depends on Procurement to review supplier agreement. | [9 empty] | 03/31/16 | [22 empty] | No Review | 20 | SAM Records Management | [5 empty] | -
TN26 | TN26 - 03 | Tania Nossa_Records Management | Records Management | Duplicate Policies, Procedures and Flows | Both | FALSE |  | 2016-07-31 | 60 | 2016-06-01 | 0% | FALSE |  | Matheus C. Martins | Not Started | 18-JAN-2106. Not Started. | [32 empty] | No Review | 88 | SAM Records Management | [5 empty] | -
TN26 | TN26 - 04 | Tania Nossa_Records Management | Records Management | People training and back up development for all activities and positions | Both | TRUE |  | 2016-06-30 | 90 | 2016-04-01 | 0% | FALSE |  | Matheus C. Martins | Not Started | 18-JAN-2106. Not Started. | [32 empty] | No Review | 132 | SAM Records Management | [5 empty] | -
TN26 | TN26 - 05 | Tania Nossa_Records Management | Records Management | Review Records Management model (Insourcing vs Outsourcing) | Both | TRUE |  | 2016-07-31 | 90 | 2016-05-02 | 0% | FALSE |  | Matheus C. Martins | Not Started | 18-JAN-2106. Not Started. |  |  |  | 03/31/16 |  |  |  | 03/31/16 | [12 empty] | 2016-03-30 | [11 empty] | No Review | 50 | SAM Records Management | [5 empty] | -
TN25 | TN25-01 | Tania Nossa_EHS | EHS | EHS - Define EHS Organization | Both | TRUE |  | 2016-02-28 | 30 | 2016-01-29 | 20% | TRUE | GSS and EHS - Reassure scope of service and Customer (Company) to be attended | Edson Reis | On Track | Define Org.design for both companies | [7 empty] | 2016-02-28 |  |  | 2016-02-28 | [21 empty] | No Review | 20 | SAM EHS |  |  | 0 |  |  | REVIEW
TN25 | TN25-02 | Tania Nossa_EHS | EHS | EHS - Define EHS Systems | Both | TRUE |  | 2016-04-30 | 30 | 2016-03-31 | 0% | FALSE | IT and EHS define the systems | Edson Reis | Not Started | Define EHS Systems for both companies | [5 empty] | 2016-04-30 |  | 2016-04-30 |  |  | 2016-04-30 | [21 empty] | No Review | 20 | SAM EHS |  |  | 0 |  |  | -
TN25 | TN25-03 | Tania Nossa_EHS | EHS | EHS - Provide system and infrastructure | Both | FALSE |  | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | IT - Provide system and infrastructure for EHS | Edson Reis | Not Started | Based on the Organization split - Action plan TN25-01 | [5 empty] | 2016-07-31 | [26 empty] | No Review |  | IT | [5 empty] | -
TN25 | TN25-04 | Tania Nossa_EHS | EHS | EHS - Provide training | Both | FALSE |  | 2016-08-15 | 15 | 2016-07-31 | 0% | FALSE |  | Edson Reis | Not Started | Provide cross training based on Organizations designed for both Companies | [7 empty] | 2016-02-28 |  |  | 2016-02-28 | [21 empty] | No Review | 80 | SAM EHS | [5 empty] | -
TN25 | TN25-05 | Tania Nossa_EHS | EHS | EHS - Define about EHS regional contracts | Both | FALSE |  | 2016-04-30 | 60 | 2016-03-01 | 20% | TRUE | Procurement - Define vendors for EHS Contracts | Edson Reis | Not Started | Based on the Organization split - Action plan TN25-01 | [9 empty] | 2016-02-28 | 2016-02-28 | [21 empty] | No Review | 160 | SAM EHS |  |  | 0 |  |  | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
[49 empty] | Review | [7 empty] | -
TN09 | TN09 - 13 | Tania Nossa_Finance | Tax Services | Implement target GSS organization for Value Add Co. and Upstream Co. | Both | TRUE | FS_25 | 2016-08-01 | 30 | 2016-07-02 | 0% | FALSE |  | Fabiana Bianucci | Not Started | [33 empty] | No Review | [7 empty] | -
x
Formulas:
Start Date (Calculated) = 'Project Plan(s) - {TN}'!$[Required Completion Date]-'Project Plan(s) - {TN}'!$[Days to Accomplish]
For GSS PMO Review? = IF(AND('Project Plan(s) - {TN}'!$[Status]<>"On Track",'Project Plan(s) - {TN}'!$[Start Date (Calculated)]<TODAY()+7),"Review","No Review")
Start Date Review = IFERROR(IF([7]!TasksTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF([7]!TasksTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")

## Day 1 Project List_TN
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Projects
| As Of | 2016-02-18 13:34
| Project-Level Description | [16 empty] | Dependency Resolution Checklist
Project Number | Project ID Blueprint # (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | In scope sub processes | Day 1 Project Description | Country of Service Delivery | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) PLEASE INSERT DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | Total # Tasks in Project | # of Tasks for Review | % Project Tasks For review | Project For GSS PMO Review? | Start Date Review | Completion Date Review | % Complete Progression Review | % Tasks for Review Flag | Off Track or at risk
TN01 | 128, 132 | GSS | Tania Nossa_Finance | General Ledger, Cost Accounting | Closing and account reconciliation; Cost Accounting | Setup new capital structure and entities, reassure Finance&Accounting policies and procedures, prepare accounting database for separation, slipt organization and provide trainings. | Brazil | Both | 2016-07-31 | 210 | 2016-01-03 | 4% | TRUE | IT - implement IT Infrastructure Treasury - open banking account Tax & Latam Region - define capital structure and legal entities Legal - Update the Company’s Minutes in the Public Agency GSS & Latam Region - Reassure Finance&Accounting policies and procedures Procurement - renegotiate vendor contract (ABM&C) | Leonardo Puccini Moreira | On Track | 12-JAN-2016 - Accounting team and finance lead team started the discuntions about the new organization to split purposes and regarding to new LBC's structure to new company (value-add). |  | 12/31/15 | 02/28/16 | 12/31/15 |  | 04/30/16 |  | 02/28/16 |  | 04/30/16 | [10 empty] | 12/31/15 | [11 empty] | 10 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN02 | 129 | GSS | Tania Nossa_Finance | Accounts Payable | Payment processing and invoice processing | Work on banking services, setup banking systems and services, slipt organization and provide trainings. | Brazil | Both | 2016-07-31 | 180 | 2016-02-02 | 4% | TRUE | Treasury - open banking account Procurement: new PO's Banks - provide services and systems IT - implement IT Infrastructure | Leonardo Puccini Moreira | On Track | 12-JAN-2016 - Accounts Payable and Invoice Receiving started initial mapping for key activities that needs back up development, and also started the discussion with Treasury on bank structure strategy, and with Tax and Accounting to determine how balance accrual should be transferred to the new company. |  |  | 02/28/16 |  |  | 04/30/16 |  |  |  | 04/30/16 | [20 empty] | 04/30/16 | Banks | 8 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN03 | 130 | GSS | Tania Nossa_Finance | FAPA | Fixed Assets and Project Accounting | Setup new capital structure and entities, reassure FAPA policies and procedures, transfer assets to New Co., slipt organization and provide trainings. | Brazil | Both | 2016-07-31 | 180 | 2016-02-02 | 1% | TRUE | IT - implement IT Infrastructure Tax & Latam Region - define capital structure and legal entities Legal - Update the Company’s Minutes in the Public Agency GSS & Latam Region - Reassure FAPA policies and procedures | Leonardo Puccini Moreira | On Track | 12-JAN-2016 - Accounting team and finance lead team started the discuntions about the new organization to split purposes and regarding to new LBC's structure to new company (value-add). |  | 12/31/15 |  | 12/31/15 |  | 04/30/16 |  | 02/28/16 | [12 empty] | 12/31/15 | [11 empty] | 7 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN04 | 131, 136 | GSS | Tania Nossa_Finance | Accounts Receivable & Credit | Accounts Receivable and Collection; Credit analysis and sales order release | Reassure Credit Policy for both companies, setup systems, renegotiate bank and vendors contratcs, split organization and provide trainings. | Brazil | Both | 2016-07-31 | 180 | 2016-02-02 | 5% | TRUE | Treasury - open banking account IT - implement IT Infrastructure Banks - bank collection service GSS & Latam Region - Credit Policy Procurement - reassure vendor financial analysis and renegotiate vendor contracts (Serasa and Merchan) | Leonardo Puccini Moreira | On Track | 12-JAN-2016 - Not Started. 05-FEB-2016 - Treasury is opening new bank account |  |  | 02/28/16 |  |  | 04/30/16 |  | 02/28/16 | [12 empty] | 02/28/16 | [9 empty] | 04/30/16 | Banks | 7 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN05 | 133 | GSS | Tania Nossa_PSC | PSC | Purchase Order Maintenance, Vendor data maintanance and Vendor Delivery follow up | Task force for Vendor Master Data Setup , Split PSC organization and provide trainings. | Brazil | Both | 2016-07-31 | 120 | 2016-04-02 | 2% | TRUE | IT - implement IT Infrastructure Procurement - renegociate vendors contracts | Leonardo Puccini Moreira | Not Started | 12-JAN-2016 - Not Started. | [5 empty] | 04/30/16 |  |  |  | 03/31/16 | [22 empty] | 5 | 0 | 0% | No Review |  |  | - | - | -
TN06 | 134 | GSS | Tania Nossa_Finance | Finance System Support | Finance System setup | Setup new capital structure and entities, reassure Finance&Accounting policies and procedures, setup all finance systems (EBS and Legacies), slipt organization and provide trainings. | Brazil | Both | 2016-07-31 | 210 | 2016-01-03 | 5% | TRUE | IT - implement IT Infrastructure Treasury - open banking account Tax & Latam Region - define capital structure and legal entities Legal - Update the Company’s Minutes in the Public Agency GSS & Latam Region - Reassure Finance&Accounting policies and procedures | Leonardo Puccini Moreira | On Track | 12-JAN-2016 - Accounting team and finance lead team started the discuntions about the new organization to split purposes and regarding to new LBC's structure to new company (value-add). |  | 12/31/15 | 02/28/16 | 12/31/15 |  | 04/30/16 |  | 02/28/16 | [12 empty] | 12/31/15 | [11 empty] | 6 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN07 | 135 | GSS | Tania Nossa_Finance | T&E | Credit Card, T&E Compliance, Car Leasing and Travel Management | Define policies and strategy, split organization and provide trainings for internal customers. | Brazil | Both | 2016-07-31 | 120 | 2016-04-02 | 0% | TRUE | Treasury - open banking account Bank - Credit Card Services Procurement - define LVP policy GSS & Latam Region - define strategy and T&E policy IT - implement IT Infrastructure Travel Agency - travel services | Leonardo Puccini Moreira | Not Started | 12-JAN-2016 - Not Started. |  |  | 02/28/16 |  |  | 04/30/16 |  | 03/31/16 |  | 2016-07-01 | [10 empty] | 2016-07-01 | [9 empty] | 04/30/16 | Banks | 6 | 0 | 0% | No Review |  |  | - | - | -
TN08 | 144 | GSS | Tania Nossa_Finance | Foreign Trade | Import and Export processes | Renegotiate Custom Broker contracts, setup import & export processes for both companies, slipt organization and provide trainings. | Brazil | Both | 2016-07-31 | 180 | 2016-02-02 | 15% | TRUE | Legal/Tax - Define Legal Entities Structure; IT - Systems Avaliability; Procurement - Negotiate Contracts (Custom Brokers) | Carlos Antonio Bonazzi | On Track | 18-Jan-2016 - Organization review in progress based on the 2016 volumes being reviewed with the Businesses |  | 02/29/16 |  | 02/29/16 |  | 04/30/16 |  |  |  | 04/30/16 | [10 empty] | 02/29/16 | [9 empty] | 04/30/16 | Softway (Foreign Trade System) | 4 | 0 | 0% | No Review |  |  | - | - | -
TN09 | 152 | GSS | Tania Nossa_Finance | Tax Services | Direct Taxes, Indirect Taxes and Tax Legal support | Work on new capital structure, setup systems, slipt organization and provide trainings. | Brazil | Both | 2016-07-31 | 210 | 2016-01-03 | 1% | TRUE | IT - implement IT Infrastructure Tax & Latam Region - define capital structure and legal entities Legal - Update the Company’s Minutes in the Public Agency | Leonardo Puccini Moreira | On Track | 01-12-2016 - Pending official document to be provided by legal department. And Tax department started the intial mapping for activities that requires technical training. |  | 12/31/15 |  | 02/28/16 |  | 04/30/16 |  |  |  | 2016-03-31 | [10 empty] | 12/31/15 | [9 empty] | 04/30/16 | Mastersaf (Tax Vendor) | 9 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN10 | 155 | GSS | Tania Nossa_Treasury | LA Treasury Backoffice | Cash Settlement, Headging and Treasury Accounting | Open banking accounts, system setup, slipt organization and train employees in order to be able to perform all activities needed (accounting, cash, hedging and controls) | Brazil | Both | 2016-07-01 | 180 | 2016-01-03 | 11% | TRUE | Tax - define capital structure and legal entities Treasury & Latam Region- define strategy and organization needed Intercam - provide FX services for both companies IT - implement IT Infrastructure | Leonardo Puccini Moreira | On Track | 08-JAN-2016- We are discussing new organization with Global Treasury; working on capital structure and openning new baking accounts. |  | 12/31/15 | 01/31/16 |  |  | 04/30/16 | [14 empty] | 01/31/16 | [9 empty] | 03/31/16 | Intercam (FX Broker) | 9 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN11 | 164 | GSS | Tania Nossa_Treasury | NA Treasury Backoffice | Cash Settlement, Headging and Treasury Accounting | Open banking accounts, system setup, slipt organization and train employees in order to be able to perform all activities needed (accounting, cash, hedging and controls) | US | Both | 2016-07-01 | 180 | 2016-01-03 | 12% | TRUE | Tax - define capital structure and legal entities Treasury, Trading Desks and GSS - define strategy and organization needed Intercam - provide FX services for both companies IT - implement IT Infrastructure | Leonardo Puccini Moreira | On Track | 08-JAN-2016- We are discussing new organization with Global Treasury; working on capital structure and separating derivatives strategies; |  | 12/31/15 | 01/31/16 |  |  | 04/30/16 |  | 01/31/16 | [22 empty] | 01/31/16 | Metal & Electricity Trading Desk (AMM) | 9 | 0 | 0% | No Review |  |  | REVIEW | - | -
TN12 | 137 | GSS | Tania Nossa_People Services | Payroll | Administrate all payments and discounts in payslip and Payroll vendor, Accouting and Bank deposits | Project to create payroll enviroment for New Co. | Brazil | Both | 2016-07-31 | 150 | 2016-03-03 | 5% | TRUE | Tax - define legal entity Finance - payroll accounting Treasury - open banking account Legal & Latam Region - Labor Relationship and Union Agreement IT - implement IT Infrastructure Apdata - provide payroll services | Luciana Traeger | On Track | 15-Feb-2016 Initial contact made with vendor explaining request and scope and asked to send estimate timeline for splitting system 12-JAN-2016 ¦ Awaiting for Procurement to start contract separation | 04/30/16 | 12/31/15 | 02/28/16 | 02/28/16 |  | 04/30/16 | [14 empty] | 02/28/16 | [9 empty] | 04/30/16 | Apdata (Vendor - Payroll) | 22 | 0 | 0% | No Review |  |  | - | - | -
TN13 | 138 | GSS | Tania Nossa_People Services | T&A | Manage time attandace for all employees, overtime, track, record and/or report employee absences | Project to create T&A enviroment for New Co. | Brazil | Both | 2016-07-31 | 60 | 2016-06-01 | 8% | TRUE | IT - implement IT Infrastructure Senior- provide T&A services Legal - Labor Relationship and Union Agreement | Luciana Traeger | Not Started | 15-Feb-2016 Initial contact made with vendor explaining request and scope and asked to send estimate timeline for splitting system |  |  |  | 02/28/16 |  | 04/30/16 | [24 empty] | 04/30/16 | Senior (Vendor - T&A) | 7 | 0 | 0% | No Review |  |  | - | - | -
TN14 | 139 | GSS | Tania Nossa_People Services | Benefits admin | Administrate health and dental insurance, loans, pharmacy, life insurance, meal ticket, transportation | Project to run all benefits for New Co. | Brazil | Both | 2016-07-31 | 150 | 2016-03-03 | 0% | TRUE | Procurement - renegotiate benefits contrats IT - implement IT Infrastructure Apdata - employee records Latam Region - benefits definition | Luciana Traeger | Not Started | 15-feb-2016 - Waiting for Comp & Benefits CoE to confirm that current benefits systems will be kept "as it is" for both companies 12-JAN-2016 ¦ Awaiting for Procurement to start contract separation | [5 empty] | 04/30/16 |  |  |  | 02/28/16 | [10 empty] | 01/31/16 | [9 empty] | 04/30/16 | Apdata (Vendor - Payroll) | 14 | 2 | 14.29% | No Review |  |  | - | - | -
TN15 | 140 | GSS | Tania Nossa_People Services | Global Mobility | Support in Visa process, start and finish Assignments in Payroll System and contact with Global Mobility oraganization | Define the global mobility policy for both companies. | Brazil | Both | 2016-07-31 | 120 | 2016-04-02 | 2% | TRUE | GSS & Latam Region - define global mobility policy for both companies | Luciana Traeger | On Track | [8 empty] | 02/28/16 | [12 empty] | 02/28/16 | [11 empty] | 8 | 0 | 0% | No Review |  |  | - | - | -
TN16 | 145 | GSS | Tania Nossa_People Services | Personnel Administration | Administrate all employee records, Vacation, Absences, Internship, Hire, Termination, Ratification and Retirement. | Create personnel adminitration for both companies. | Brazil | Both | 2016-07-31 | 150 | 2016-03-03 | 4% | TRUE | IT - implement IT Infrastructure Apdata - employee records Nexo - retirement support Legal - validate employee status (absence) | Luciana Traeger | On Track | 15-feb-2016 - Part of Personnel definition depends on GPS global strategy decision for borh companies |  |  |  | 02/28/16 |  | 04/30/16 | [24 empty] | 04/30/16 | Apdata (Vendor - Payroll); Nexo (Vendor- Healthy) | 15 | 0 | 0% | No Review |  |  | - | - | -
TN18 | 147 | GSS | Tania Nossa_People Services | Recruiting | Administrate all vacancies, reports and payments | Define recruiting policy and provide trainings. | Brazil | Both | 2016-07-31 | 120 | 2016-04-02 | 3% | TRUE | IT - implement IT Infrastructure Latam Region - recruiting policy | Luciana Traeger | On Track | 15-feb-2016 - R&S definition depends on GPS global strategy decision for borh companies | [5 empty] | 04/30/16 | [14 empty] | 02/28/16 | [11 empty] | 11 | 2 | 18.18% | No Review |  |  | - | - | -
TN19 | 148 | GSS | Tania Nossa_People Services | Compensation | Administrate local structures, promotions, variable compensation and changes of departments and Administrate the Private Pension Plan - Alcoa Previ | Project to create a compensation process for New Co. | Brazil | Both | 2016-07-31 | 150 | 2016-03-03 | 2% | TRUE | IT - implement IT Infrastructure Latam Region & GSS - Compensation policy | Luciana Traeger | On Track | 15-feb-2016 - definition depends on GPS global strategy decision for borh companies | [5 empty] | 04/30/16 |  | 02/28/16 | [12 empty] | 02/28/16 | [11 empty] | 13 | 2 | 15.38% | No Review |  |  | - | - | -
TN21 | 150, 162 | GSS | Tania Nossa_People Services | HR Global Services, HR Call Center & Performance | Administrate all Performance Cycle: Planning, Mid and End Cycle and Status Reports. Coordination of the HR Call Center (Support, Metrics and Tickets).; Global Voices, GPS, Talent reporting | Provide HR Global Services, HR Call center and Performance services for both companies. | Brazil; US | Both | 2016-07-31 | 150 | 2016-03-03 | 2% | TRUE | IT - implement IT Infrastructure Latam Region & GSS - reassure performance model GSS - reassure GVS, GPS and Talent Report models. Procurement - renegotiate call center contract. | Luciana Traeger | On Track | 15-feb-2016 - definition depends on GPS global strategy decision for borh companies | [5 empty] | 04/30/16 |  | 02/29/16 |  | 03/31/16 | [10 empty] | 02/29/16 | [9 empty] | 04/30/16 | Stefanini (Call Center) | 31 | 2 | 6.452% | No Review |  |  | - | - | -
TN22 | 142, 158, 161 | GSS | Tania Nossa_Compliance and Reporting | Compliance | Define Sample size, Perform ASAT (Alcoa Self Assessment Toll) tests, Re-tests, ASP (Compliance System) updating, ASAT reports and Tests Calendar Management | Define scope of services and organization needed to provide Compliance service, mainly related do ASAT. | Brazil;Europe; US | Both | 2016-07-31 | 120 | 2016-04-02 | 12.22% | TRUE | GSS - Strategy definition on activities and Customers to be attended by each hub (hub and spoke model) IT - implement IT Infrastructure - ASP and Sharepoint | Carlos Antonio Bonazzi | On Track | 18-jan-2016 - Lynne Ruff is visiting CoE ASAT on the week of Jan 18-22 to review strategy with EPS | [5 empty] | 04/30/16 |  | 02/29/16 | [24 empty] | 9 | 0 | 0% | No Review |  |  | - | - | -
TN23 | 143 | GSS | Tania Nossa_Other | Commercial Backoffice | Order Management and Customer Claims/ Data Management | Confirm with Extrusion, Wheels and GRP the scope of services to be provided by GSS | Brazil | V-A Co. | 2016-07-31 | 120 | 2016-04-02 | 20% | TRUE | IT - System availability Latam region - reassure scope of service for Commercial Backoffice | Carlos Antonio Bonazzi | On Track | 18-Jan-2016 - First discussion with LAE and GRP Leadership in Brazil to reassure scope for 2016 | [5 empty] | 04/30/16 | [14 empty] | 03/31/16 | [11 empty] | 3 | 0 | 0% | No Review |  |  | - | - | -
TN24 | 154 | GSS | Tania Nossa_Other | Other process (Communication;Controllership; People Services Business Partner) | Communication: • Internal Communications; • Communication vehicles managament; • Communication Consulting • Events organization Controllership: • Forecasting, Managerial reports, Budgeting, Chargeback, Accounting and Capital Expenditure Management for all GBS Functional Areas - Shared Services, Procurement, Information Technology and Transportation • Support to LA Regional and Global GBS Finance organization on the link to the LA GBS Financial Processes People Services Business Partner: • Ensure the execution of the HR processes from the BBHR perspective, HR program managament and Employees and Managers support | Define the common resources to support GBS in both companies (Controllership, HR BP, Communication and Gorvernment Affairs). | Brazil | Both | 2016-07-31 | 90 | 2016-05-02 | 9.444% | TRUE | IT - implement IT Infrastructure Branding - waiting for New Co. branding guidelines GSS & HR - define the common resources to support GBS in both companies (Controllership, HR BP, Communication and Gorvernment Affairs) | Tania Nossa | Not Started | 18-jan-2016 - No comments |  |  |  |  | 02/29/16 | 04/30/16 | 03/31/16 | 02/29/16 | [7 empty] | 03/31/16 | [16 empty] | 5 | 2 | 40% | Review |  |  | - | REVIEW | -
TN25 | 126, 153, 159, 163 | GSS | Tania Nossa_EHS | EHS | EHS Reporting and Analysis, Chemical Products Management, Waste Disposal Management, Supplier Pre Qualification, Contract Management and Industrial Hygiene | Reassure the scope of EHS service, split organization and provide trainings. | Australia, Brazil, Europe, US | Both | 2016-07-31 | 120 | 2016-04-02 | 9.444% | TRUE | IT - implement IT Infrastructure EHS & GSS- reassure the scope of services | Edson Reis | On Track | 15-FEB-2016 ¦ EHS leaders for new companies were announced. There are some EHS processes under evaluation to be considered as new EHS GSS services like Safety Pre Qualification of Supplier and SDS Management. The EHS Council met two weeks ago to define the EHS strategy. No changes for GBS from the last week. | [5 empty] | 04/30/16 |  | 02/29/16 |  |  | 02/29/16 | [21 empty] | 5 | 0 | 0% | No Review |  |  | - | - | -
TN26 | 151 | GSS | Tania Nossa_Records Management | Records Management | Record Storage | Split organization and renegotiate vendor contract. | Brazil | Both | 2016-07-31 | 120 | 2016-04-02 | 2% | TRUE | Legal - define temporality table and document which must be storaged GSS & Latam Region - define strategy IT - implement IT Infrastructure | Leonardo Puccini Moreira | On Track | 12-JAN-2016 - We started the discussion with Corporate Tax and Legal to determine if the documents currently archived onsite on downstream Bus should be transferred to Alcoa prior to separation process. |  |  |  | 03/31/16 |  | 04/30/16 |  | 03/31/16 |  | 03/31/16 | [10 empty] | 03/31/16 | [11 empty] | 5 | 0 | 0% | No Review |  |  | - | - | -
TN27 | 151, 157 | GSS | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Bridges; Monthly report; CEO/CFO presentations; Closing presentations; SRT Dashboard; Weekly and Monthly Forecast; QBR presentations; Hyperion support; Financial scorecards; Managerial reports | Reassure the scope of service to be provided after Day 1 | Brazil, Europe | Both | 2016-07-31 | 120 | 2016-04-02 | 12.22% | TRUE | Finance and Latam region - reassure scope of services IT - Provide system and infrastructure for FP&A and Reporting activites | Carlos Antonio Bonazzi | On Track | 18-jan-2016 - Project on track | 02/29/16 |  |  |  |  | 04/30/16 | [13 empty] | 02/29/16 | 02/29/16 | [11 empty] | 12 | 1 | 8.333% | No Review |  |  | - | - | -
TN28 | 160 | GSS | Tania Nossa_Compliance and Reporting | Reporting + FP&A | Bridges; Monthly report; CEO/CFO presentations; Closing presentations; SRT Dashboard; Weekly and Monthly Forecast; QBR presentations; Hyperion support; Financial scorecards; Managerial reports | Define with the Customers the scope of service to be provided after Day 1 | US | Both | 2016-07-31 | 120 | 2016-04-02 | 12.22% | TRUE | Finance and Latam Region - reassure scope of services IT - Provide system and infrastructure for FP&A and Reporting activites | Carlos Antonio Bonazzi | On Track | 18-jan-2016 - Project on track | 02/29/16 |  |  |  |  | 04/30/16 | [26 empty] | 0 | 0 | #DIV/0! | #DIV/0! |  |  | - |  | -
TN29 | N/A | GSS | Transformation_Facilities | Shared Facilities | Physical location of office and all supporting infrastructure | Project to address all infrastructure to support both orgs | Brazil | Both | 2016-07-31 | 210 | 2016-01-03 | 9.444% | TRUE | Define and split Facilitie office for both companies, including all GBS positions (Procurement, Transportation, IT and Shared Services) IT - Define and implement Infrastructure needed Procurement - Negotiate contract for Value Add office and IT infrastructure needed Tax - Legal Entity Structure | Tania Nossa | On Track | 11-Jan-2016 - Business Case for Value-Add and Upstream offices beig developed. |  | 03/31/16 |  |  |  | 05/31/16 |  |  |  | 04/30/16 | [22 empty] | 13 | 5 | 38.46% | Review |  |  | REVIEW | REVIEW | -
TN30 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN31 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN32 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN33 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN34 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN35 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN36 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN37 |  | GSS | [9 empty] | 9.444% | TRUE | [44 empty] | -
TN38 | [57 empty] | -
TN39 | [57 empty] | -
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Day 1 Project List_TN'!$[Required Completion Date]),"",'Day 1 Project List_TN'!$[Required Completion Date]-'Day 1 Project List_TN'!$[Days to Accomplish])
Project For GSS PMO Review? = IF(AND('Day 1 Project List_TN'!$[Status]<>"On Track",'Day 1 Project List_TN'!$[Start Date (Calculated)]<TODAY()+7),"Review",IF(OR('Day 1 Project List_TN'!$BA10>0.25),"Review","No Review"))
Start Date Review = IFERROR(IF([7]!ProjectsTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF([7]!ProjectsTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")

## Day 1 Project Costs_TN
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Project Costs
As Of | 2016-02-18 13:34
Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale

## Data Validation (hide) (hidden)
Master Function List | Sub-function list
Legal | Legal | HumanResources | FinanceandAccounting | OCIO | InvestorRelations | Communications | GPI | GlobalBilling | BusinessUnitFunctions | Yes/No | Day 1 Target State | TSA Feasibility | TSA Exit Activities
Human Resources | Benefits | HR Systems | Treasury | PMO | Investor Relations | Inc. PR | Business Office | Operational | Strategy | Yes | Replicate (Clone) | Possible - Low/Medium Complexity | Replicate (Clone)
Finance and Accounting | Stock Systems | GTA | FP&A | Facilities |  | Internal | Operations | Systems | Sales & Business Development | No | Give and Go | Possible - Very Complex | Give and Go
OCIO | Competition | MyHR | Tax | HR Systems |  | Brand / EVP | Tools |  | Marketing |  | New Build | Impossible | New Build
Investor Relations | Corporate | Comp/Ben/M&A | AP | Other Enabling Sys |  | Social Innovation | Services |  | Risk |  | Forward TSA | Not Required | Standalone
Communications | Employment | L&OD | Travel | Finance Systems |  |  | Platform |  | Trust & Safety |  | Reverse TSA |  | Discontinue
GPI | Compliance | Diversity | Purchasing | CS Systems |  |  | Data |  | CS |  | Standalone |  | Operating Agreement
Global Billing | Government Relations |  | Payroll | Traditional IT Systems |  |  | Infrastructure/Cloud |  | PD / Arch |  | Discontinue
Business Unit Functions | IP |  | Finance Separation |  |  |  | Data Center |  | Product |  | Operating Agreement
| Privacy |  | Accounting Policy | [5 empty] | Data
| Litigation |  | SEC Reporting | [5 empty] | Info Security
| Real Estate |  | SOX | [5 empty] | Regulatory
Finance Trans
Procurement

## Countries (hidden)
# | Location Country | Total Employees
1 | USA Total |  | USA | USA | FRA | GBR | CAN | DEU | IND | AUS | SWE | MEX | BEL | HKG | SGP | CHE | ARG | NLD | DNK | TWN | POL | NOR | THA | CZE | GRC | HUN | MCO | ESP | LUX | FIN | JPN | NZL | BRA | CHN | IRL | MYS | RUS
2 | FRA Total |  | FRA | USA: USA,FRA,GBR,CAN,DEU,IND,AUS,SWE,MEX,BEL,HKG,SGP,CHE,ARG,NLD,DNK,TWN,POL,NOR,THA,CZE,GRC,HUN,MCO,ESP,LUX,FIN,JPN,NZL,BRA,CHN,IRL,MYS,RUS
3 | GBR Total |  | GBR
4 | CAN Total |  | CAN
5 | DEU Total |  | DEU
6 | IND Total |  | IND
7 | AUS Total |  | AUS
8 | SWE Total |  | SWE
9 | MEX Total |  | MEX
10 | BEL Total |  | BEL
11 | HKG Total |  | HKG
12 | SGP Total |  | SGP
13 | CHE Total |  | CHE
14 | ARG Total |  | ARG
15 | NLD Total |  | NLD
16 | DNK Total |  | DNK
17 | TWN Total |  | TWN
18 | POL Total |  | POL
19 | NOR Total |  | NOR
20 | THA Total |  | THA
21 | CZE Total |  | CZE
22 | GRC Total |  | GRC
23 | HUN Total |  | HUN
24 | MCO Total |  | MCO
25 | ESP Total |  | ESP
26 | LUX Total |  | LUX
27 | FIN Total |  | FIN
28 | JPN Total |  | JPN
29 | NZL Total |  | NZL
30 | BRA Total |  | BRA
31 | CHN Total |  | CHN
32 | IRL Total |  | IRL
33 | MYS Total |  | MYS
34 | RUS Total |  | RUS
Grand Total

## Sheet1
General Ledger, Cost Accounting | TN01 | Tania Nossa_Finance
Accounts Payable | TN02 | Tania Nossa_Finance
FAPA | TN03 | Tania Nossa_Finance
Accounts Receivable & Credit | TN04 | Tania Nossa_Finance
PSC | TN05 | Tania Nossa_PSC
Finance System Support | TN06 | Tania Nossa_Finance
T&E | TN07 | Tania Nossa_Finance
Foreign Trade | TN08 | Tania Nossa_Finance
Tax Services | TN09 | Tania Nossa_Finance
LA Treasury Backoffice | TN10 | Tania Nossa_Treasury
NA Treasury Backoffice | TN11 | Tania Nossa_Treasury
Payroll | TN12 | Tania Nossa_People Services
T&A | TN13 | Tania Nossa_People Services
Benefits admin | TN14 | Tania Nossa_People Services
Global Mobility | TN15 | Tania Nossa_People Services
Personnel Administration | TN16 | Tania Nossa_People Services
#REF! | #REF! | #REF!
Recruiting | TN18 | Tania Nossa_People Services
Compensation | TN19 | Tania Nossa_People Services
#REF! | #REF! | #REF!
HR Global Services, HR Call Center & Performance | TN21 | Tania Nossa_People Services
Compliance | TN22 | Tania Nossa_Compliance and Reporting
Commercial Backoffice | TN23 | Tania Nossa_Other
Other process (Communication;Controllership; People Services Business Partner) | TN24 | Tania Nossa_Other
EHS | TN25 | Tania Nossa_EHS
Records Management | TN26 | Tania Nossa_Records Management
Reporting + FP&A | TN27 | Tania Nossa_Compliance and Reporting
Reporting + FP&A | TN28 | Tania Nossa_Compliance and Reporting
Shared Facilities | TN29 | Transformation_Facilities