## Instructions and Descriptions
Project Elevation
High-Level Separation Workplan - Instructions, Descriptions, and Examples
Below are instructions for the high-level separation workplan template
This template comprises of three tabs: one focused a list of Day 1 projects, the second focused on capturing the tasks and milestones required to complete those projects, and final focused on capturing project-associated costs
1) Follow the directions in the light grey rows of example tables below. There is an example table for each of the three tabs; example line items are provided in italics.
2) This template is designed to be modular - if you need to create multiple Project Plan tabs to break up workplanning, please do so. Indicate your tab divisions by renaming the tab where it says "{Project}"
3) Please refer any questions to your separation counterpart or contact. Leverage your contact for help with submission and plan consolidation
| Day 1 Project List Tab | Orange fields due for completion by 7 December 2015
| Activity-Level Description | [14 empty] | Dependency Resolution Checklist
| Project ID (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | Day 1 Project Description | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with a workstream-defined three letter code for WS & SWS and a unique 3 digit code for the activity within | List the name of the Resource Unit, Function, or division acting as a workstream with the separation | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Provide a detailed description (what, why and where) of the Day 1 Project | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Provide the date by which this project must be completed | Provide an estimate of the number of calendar days it will take to complete the entire project | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the project is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
x | HRD-LRL-001 | Human Resources | Labor Relations | French Works Council Approval | Adjusting organizations in France requires gaining approval from the Works Council via a formal proposal | Both | 2016-06-01 | 132 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Will require input from X, Y, and Z | [27 empty] | 2016-01-15
| HRD-LRL-002 | Human Resources | Labor Relations | German Works Council Approval | Adjusting organizations in Germany requires gaining approval from the Works Council via a series of formal meetings | Both | 2016-06-01 | 102 | 2016-02-20 | 0% | FALSE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Will require input from X, Y, and Z | [27 empty] | 2015-10-31
| Project Plan Tab | Fields due for completion by 17 December 2015
| Task-Level Description | [14 empty] | Dependency Resolution Checklist
| Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl)
| Assign a unique ID with workstream-defined three letter code for SWS, the unique 3 digit code for the activity, and a two digit code for the task | Provide the name of the sub-division within a workstream managing a related groups of activities | Identify the name of the Day 1 project (required for separation) | Identify the name of the task that must be done to complete the project. Only list one task per row | Use this field to indicate whether an activity applies to both future companies, or just a particular one | Mark whether or not this task is a milestone for a project. Milestones are the most critical tasks within a project, which are often time-sensitive. | Provide the date by which this task must be completed | Provide an estimate of the number of calendar days it will take to complete the entire task | A calculated field indicating approximately what day work must begin. May need to be moved from a weekend day due to nature of calcuation | Indicate the amount of the activity currently complete, as a percentage of the entire activity. Put 0% if no work has commenced | Mark this field true if the task is dependent on another project or function, and then: 1) describe the dependencies at right 2) mark the functions at right in the checklist area to categorize these dependencies | Provide a detailed description (what, why and where) of the dependencies for this project | Indicate who will be the SPA (single point of accountability) for completion of this activity | Indicate the current status of this activity (Not Started, On track, Off Track, At Risk, Completed). Provide justification/reasoning if the activity is Off Track or At Risk in the 'Comments / Notes' field | Write down any status explanations, important subtasks that must be captured, additional details and/or other data that cannot be captured in other fields | Use these fields to indicate dependencies with a specific function. If the date by which a dependency must be resolved is known, use that date to mark the appropriate column. If no required resolution date is yet known, put 10/31/15 as the date to highlight the cell red
| LRL-001-01 | Labor Relations | French Works Council Approval | -Draft Proposal | Both | FALSE | 2016-02-20 | 30 | 2016-01-21 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Dominique Bordeaux | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-001-02 | Labor Relations | French Works Council Approval | -Submit Proposal | Both | TRUE | 2016-03-01 | 10 | 2016-02-20 | 0% | FALSE |  | Dominique Bordeaux | Not Started
| LRL-001-03 | Labor Relations | French Works Council Approval | -Follow up after 3 months | Both | FALSE | 2016-06-01 | 90 | 2016-03-03 | 0% | FALSE |  | Dominique Bordeaux | Not Started
x | LRL-002-01 | Labor Relations | German Works Council Approval | -Draft Proposal | Both | FALSE | 2016-03-20 | 30 | 2016-02-19 | 5% | TRUE | All Org. Design work must be done before the proposal can be submitted, and no offical selections of talent for roles can occur until after approval is received | Petra Schmidt | Not Started | Dependency Desc: Nearly Complete Org Design must be Complete earlier than in most other countries Will require input from X, Y, and Z
| LRL-002-02 | Labor Relations | German Works Council Approval | -Submit Proposal | Both | TRUE | 2016-04-01 | 10 | 2016-03-22 | 0% | FALSE |  | Petra Schmidt | Not Started
| LRL-002-03 | Labor Relations | German Works Council Approval | -Follow up after 2 months | Both | FALSE | 2016-06-01 | 60 | 2016-04-02 | 0% | FALSE |  | Petra Schmidt | Not Started
Project Costs Tab
| Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale
| Provide the unique ID for the project defined on the Day 1 Projects tab | Provided the name of the Day 1 project defined on the Day 1 Projects tab | Provide a description of what the cost is and why it exists | Indicate if this cost is a dis-synergy (incl stranded cost) (True/False) | Indicate if this cost is a one-time cost (True/False) | Indicate who will own the plan to minimize and address this cost | Provide an estimated cost for all or part of this Day 1 Project | Briefly describe rationale (business case) for cost estimate
| HRD-LRL-002 | German Works Council Approval | Lobbying - Gaining approval often requires spending money to lobby key officials | No | Yes | Peter Schmidt | 10000 | Spending this money will reduce risk and speed transition for German Org
x
x
Formulas:
Start Date (Calculated) = IF(ISBLANK('Instructions and Descriptions'!$[Required Completion Date]),"",'Instructions and Descriptions'!$[Required Completion Date]-'Instructions and Descriptions'!$[Days to Accomplish])

## Day 1 Project List_TR
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Projects
| As Of | 2016-02-19 13:28
| Project-Level Description | [16 empty] | Dependency Resolution Checklist
Project Number | Project ID Blueprint # (WS-SWS-Activity) | Workstream (WS) | Sub-Workstream (SWS) | Day 1 Project Name | In scope sub processes | Day 1 Project Description | Country of Service Delivery | V-A Co, Up. Co, or Both | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Status explanations, additional details, etc.) PLEASE INSERT DATE BEFORE COMMENT DD-MON-YYYY (06-JAN-2016) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | Total # Tasks in Project | # of Tasks for Review | % Project Tasks For review | Project For GSS PMO Review? | Start Date Review | Completion Date Review | % Complete Progression Review | % Tasks for Review Flag | Off Track or at risk
TR01 | 165168 | GSS | Toine Raaymakers_HR | People Services Global HUB Europe | People Service system support, GPS&Alcoa Learn HR Reporting Data Management Hourly Recruitment Compliance | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | US/Global, Canada | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to understand future demand from GSS in the other regions to align delivery organization accordingly. Need to understand future system support strategies within GSS and GBS. Need to understand IT strategies related to AlcoaLearn and other shared systems for both companies. Need HR to support restructuring. | Ildiko Toth | On Track | 11-JAN-2016: project kicked off with European LT. Escalated missing tier 1 vendor selection to procurement. Reviewed critical vendor list with Europe procurement contact. |  |  |  |  | 2016-03-01 | 2016-02-01 |  | 2016-01-18 | [24 empty] | 14 | 1 | 7.143% | No Review |  |  | REVIEW | - | -
TR02 | 218 | GSS | Toine Raaymakers_HR | People Services Spain | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Spain | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Angel Garcia | On Track | 08-FEB-2016: initial discussions had with vendor regards payroll and future outsourced support for both companies. No issues envisaged, further discussions take place once Spain organisation known for both companies | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-03-01 | 2016-02-15 |  |  |  | 2016-02-01 | [22 empty] | 12 | 0 | 0% | No Review |  |  | REVIEW |  | -
TR03 | 219 | GSS | Toine Raaymakers_HR | People Services Switzerland | Payroll, HR reporting, Compliance, Administrative support, Pension and Savings Administration, Global Mobility | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Switzerland | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Emmanuelle Collet | On Track | 08-FEB-2016: initial discussions had with vendor regards payroll and future outsourced support for both companies. No issues envisaged, further discussions take place once CH organisation known for both companies | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-03-01 | 2016-02-15 |  |  |  | 2016-02-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | REVIEW |  | -
TR04 | 220 | GSS | Toine Raaymakers_HR | People Services Italy | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Italy | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Paolo Gasparini | On Track | 08-FEB-2016: initial communication provided to vendor regards payroll and future outsourced support for both companies. Follow up discussions to be organised once Italy organisation known for both companies | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-03-01 | 2016-02-15 |  |  |  | 2016-02-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | REVIEW |  | -
TR05 | 221 | GSS | Toine Raaymakers_HR | People Services France | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | France | V-A Co. | 2016-07-31 | 172 | 2016-02-10 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Maryline Jussiaume | On Track | 11-JAN-2016: project kicked off with European LT. Escalated missing tier 1 vendor selection to procurement. Reviewed critical vendor list with Europe procurement contact. | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-04-01 | 2016-03-14 |  |  |  | 2016-03-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | - |  | -
TR06 | 222 | GSS | Toine Raaymakers_HR | People Services Hungary | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support, Recruitment support and Training support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Hungary | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Ildiko Toth | On Track | 11-JAN-2016: project kicked off with European LT. Escalated missing tier 1 vendor selection to procurement. Reviewed critical vendor list with Europe procurement contact. | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-03-01 | 2016-02-15 |  |  |  | 2016-02-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | REVIEW |  | -
TR07 | 223 | GSS | Toine Raaymakers_HR | People Services North UK | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support and support to pensionairs | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | UK | V-A Co. | 2016-07-31 | 172 | 2016-02-10 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Mark Gregory | On Track | 08-FEB-2016: Payroll and TMS providers made aware of Alcoa split. Minimal impact in UK as all Added-Value. Further discussions with providers regards future testing from IT perspective. | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-04-01 | 2016-03-14 |  |  |  | 2016-03-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | - |  | -
TR08 | 224 | GSS | Toine Raaymakers_HR | People Services North NL/BE | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | NL/BE | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Mark Gregory | On Track | 08-FEB-2016: initial communication provided to Vendor regards payroll and future outsourced support for both companies. Await on Vendor to provide an SPA to discuss further details. | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-03-01 | 2016-02-15 |  |  |  | 2016-02-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | REVIEW |  | -
TR09 | 225 | GSS | Toine Raaymakers_HR | People Services North Norway | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Norway | Up. Co. | 2016-07-31 | 172 | 2016-02-10 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Mark Gregory | On Track | 08-FEB-2016: Payroll and TMS providers to be made aware of Alcoa split week ending 12th February. Minimal impact in NOR as all upstream. May require support from outsourced provider for IT testing perspective to ensure we continue have access to systems. | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-04-01 | 2016-03-14 |  |  |  | 2016-03-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | - |  | -
TR10 | 226 | GSS | Toine Raaymakers_HR | People Services North Iceland | Payroll, T&A, HR reporting, Compliance, Empl. Data Management, Administrative support | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Iceland | Up. Co. | 2016-07-31 | 172 | 2016-02-10 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Mark Gregory | On Track | 08-FEB-2016: Payroll and TMS providers made aware of Alcoa split. Minimal impact in ICE as all upstream. Further discussions with providers regards future testing from IT perspective. | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-04-01 | 2016-03-14 |  |  |  | 2016-03-01 | [22 empty] | 12 | 1 | 8.333% | No Review |  |  | - |  | -
TR11 |  | removed | [55 empty] | -
TR12 | 228 | GSS | Toine Raaymakers_ | People Services North Germany | GPS Helpdesk, PS centralized Compliance support, Europe Training administration, Expat Support and administrative support to Italy and Switzerland | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Europe | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to have in-country procurement support to renegotiate vendor contracts with payroll and other relevant (e.g. T&A) providers. Need IT to support any changes required in interfaces and configuration to support separation of systems. Need to align changes with legal, tax and treasury to determine impact and needs (e.g. new bank accounts). | Mark Gregory | On Track | 08-FEB-2016: Germany is a 'Added-Value' country. Payroll is with one provider and TMS each location have their own application. Notes applications/support not owned by People Services at present. |  |  |  |  | 2016-03-01 | 2016-02-01 |  | 2016-01-18 | [27 empty] | No Review |  |  | REVIEW |  | -
TR13 | 229 | GSS | Toine Raaymakers_ | People Services Small Countries | GPS Helpdesk, PS centralized Compliance support, Europe Training administration, Expat Support and administrative support to Italy and Switzerland | Define scope and level of services to be provided to both companies from Day 1 and establish associated organization structure, systems and procedures to be operational by August 1, 2016. Assume like-for-like services and consider people, contracts, SLA's, technology, training and validation in scope for this project. | Europe | Both | 2016-07-31 | 202 | 2016-01-11 | 7% | TRUE | Need to understand future demand from GSS in the regions to align delivery organization accordingly. Need to understand future system support strategies within GSS and GBS. Need to understand IT strategies related to AlcoaLearn and other shared systems for both companies. Need HR to support restructuring. | Ildiko Toth | On Track | 08-Feb-2016: Project tracked to ensure Payroll/TMS applications for small countries not missed, note services currently not supported by PS (decision required on who owns this seperation process activity) |  |  |  |  | 2016-03-01 | 2016-02-01 |  | 2016-01-18 | [27 empty] | No Review |  |  | REVIEW |  | -
-
-
-
-
-
-
-
-
-
-
-
-
x
Formulas:
Start Date (Calculated) = IF(ISBLANK(ProjectsTable[[#This Row],[Required Completion Date]]),"",ProjectsTable[[#This Row],[Required Completion Date]]-ProjectsTable[[#This Row],[Days to Accomplish]])
Project For GSS PMO Review? = IF(AND(ProjectsTable[[#This Row],[Status]]<>"On Track",ProjectsTable[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review",IF(OR(ProjectsTable[[#This Row],[% Project Tasks For review]]>0.25),"Review","No Review"))
Start Date Review = IFERROR(IF([8]!ProjectsTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF([8]!ProjectsTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")

## Risk Register_TR
Date risk recorded | Project Number | Day 1 Project Name | Sub-Workstream (SWS) | Related project Task ID(s) | Risk Title | Mitigating Action(s) | Probability of occurance (0-100%) 0% being less probable | Degree of Impact (1-10) 1 being low impact | Risk rating (Probability x Impact) | For discussion in GSS PMO? (Y/N) | Status | Weekly Status Comments (enter date DD-MON-YYYY (06-JAN-2016) then comment) | Person recording risk (Last name, First name) | Date Reviewed in PMO DD-MON-YYYY (06-JAN-2016) | Track in Deloitte tool? | SPO escalation?
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
|  | (risk register is a separate log in sharepoint) | [6 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>
[9 empty] | 0 | <Select> | <Select> |  |  |  | <Select> | <Select>

## TR01_Project Plan(HUB Europe)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours | Start Date Review | Completion Date Review | % Complete Progression Review
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Define/confirm scope for HUB provided services. | Both | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy and demand from other GSS PS and BBHR entities. | Raaymakers, Toine | Complete | Assume 'like-for-like' services to be provided. Consider any impact from dis-synergies and other changes to target condition. | [7 empty] | 2016-02-01 | [24 empty] | Review | 24 | PS | [5 empty] | REVIEW
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Define/confirm systems separation strategy for systems in use by HUB (e.g. AlcoaLearn, GPS etc.). | Both | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on GSS and IT strategies. | Toth, Ildiko | On Track | Assume 'like-for-like' services to be provided. Consider any impact from changes to target condition from IT strategy or other entities. | [5 empty] | 2016-02-01 |  | 2016-02-01 | [24 empty] | No Review | 36 | PS | [5 empty] | -
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Configuration of GPS for target condition. | Both | TRUE | MPS_10 | 2016-07-01 | 120 | 2016-03-03 | 0% | TRUE | Depends on GSS, GBS IS (GPS support) and HR (Janette Sterlitz). | Toth, Ildiko | Not Started | Assume Global HR will own overall configuration and align with IT. Consider significant testing activity within the HUB. |  |  |  |  | 2016-03-03 | 2016-03-03 |  | 2016-03-03 | [24 empty] | No Review | 200 | PS | [5 empty] | -
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | AlcoaLearn implementation according to target condition. | Both | TRUE | MPS_10 | 2016-07-01 | 150 | 2016-02-02 | 5% | TRUE |  |  | On Track | [33 empty] | No Review | 240 | PS |  |  | 240 |  |  | REVIEW
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Align reporting activities with target condition. Include any implications for Automate10 and any other tools. | Both | TRUE |  | 2016-07-01 | 150 | 2016-02-02 | 5% | TRUE |  |  | On Track | [33 empty] | No Review | 240 | PS | [5 empty] | REVIEW
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Define/confirm target organization for this area. | Both | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Toth, Ildiko | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 32 | PS | [5 empty] | REVIEW
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Implement target organization structure. | Both | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Toth, Ildiko | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 40 | PS | [5 empty] | -
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | SLA's, policies and procedures aligned with target condition. | Both | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Toth, Ildiko | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 160 | PS | [5 empty] | -
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Complete any knowledge transfer/training required for target condition. | Both | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Toth, Ildiko | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 200 | PS | [5 empty] | -
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Work with Legal on the Safe Harbor agreement - especially for the locations in Europe and US that have the services provided from the HUB | Both | TRUE | MPS_18 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE |  | Toth, Ildiko | Not Started | [33 empty] | No Review | 32 | PS | [5 empty] | -
TR01 | 165168 | Toine Raaymakers_HR | People Services Global HUB Europe | Employee data retention and archiving (US only). | Both | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Toth, Ildiko | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 40 | PS | [5 empty] | -
TR01 | 165169 | Toine Raaymakers_HR | People Services Global HUB Europe | Review and update ASAT process, and content. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Toth, Ildiko | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS | [5 empty] | -
TR01 | 165170 | Toine Raaymakers_HR | People Services Global HUB Europe | Testing and validation to be prepared for August 1 target condition. | Both | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Toth, Ildiko | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 200 | PS | [5 empty] | -
TR01 | 165171 | Toine Raaymakers_HR | People Services Global HUB Europe | Operational readiness checkpoint. | Both | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Toth, Ildiko | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 40 | PS | [5 empty] | -
u
x
Formulas:
Start Date (Calculated) = TasksTable[[#This Row],[Required Completion Date]]-TasksTable[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable[[#This Row],[Status]]<>"On Track",TasksTable[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Start Date Review = IFERROR(IF([8]!TasksTable[[#This Row],[Start Date (Calculated)]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Completion Date Review = IFERROR(IF([8]!TasksTable[[#This Row],[Required Completion Date]]-(TODAY()-WEEKDAY(TODAY())-1)>5,"REVIEW","-"),"")
Note on AZ12: raaymt: assume 10% of lead time
Note on AZ13: raaymt: depending startegy

## TR02_Project Plan(Spain)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Define/confirm PS scope for BU's in country. | Both | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Both | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Garcia, Angel | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Align Payroll contract and payroll system configuration with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Garcia, Angel | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 100 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Align T&A systems / contracts with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Garcia, Angel | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 80 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Define/confirm target organization for this area. | Both | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Garcia, Angel | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 32 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Implement target organization structure. | Both | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Garcia, Angel | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 48 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | SLA's, policies and procedures aligned with target condition. | Both | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Garcia, Angel | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 32 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Complete any knowledge transfer/training required for target condition. | Both | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Garcia, Angel | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 96 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Employee data retention and archiving. | Both | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Garcia, Angel | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 40 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Review and update ASAT process, and content. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Garcia, Angel | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Testing and validation to be prepared for August 1 target condition. | Both | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Garcia, Angel | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 160 | PS
TR02 | 223 | Toine Raaymakers_HR | People Services Spain | Operational readiness checkpoint. | Both | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Garcia, Angel | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable4910[[#This Row],[Required Completion Date]]-TasksTable4910[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable4910[[#This Row],[Status]]<>"On Track",TasksTable4910[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")

## TR03_Project Plan(Switzerland)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Define/confirm PS scope for BU's in country. | Both | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Both | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Collet, Emmanuelle | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Align Payroll contract and payroll system configuration with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Collet, Emmanuelle | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 100 | PS |  |  | 40
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Align T&A systems / contracts with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Collet, Emmanuelle | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 80 | PS |  |  | 40
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Define/confirm target organization for this area. | Both | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Collet, Emmanuelle | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 16 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Implement target organization structure. | Both | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Collet, Emmanuelle | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 40 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | SLA's, policies and procedures aligned with target condition. | Both | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Collet, Emmanuelle | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 32 | PS |  |  | 40
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Complete any knowledge transfer/training required for target condition. | Both | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Collet, Emmanuelle | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 80 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Employee data retention and archiving. | Both | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Collet, Emmanuelle | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 32 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Review and update ASAT process, and content. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Collet, Emmanuelle | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Testing and validation to be prepared for August 1 target condition. | Both | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Collet, Emmanuelle | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 80 | PS |  |  | 40
TR03 | 223 | Toine Raaymakers_HR | People Services Switzerland | Operational readiness checkpoint. | Both | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Collet, Emmanuelle | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable412[[#This Row],[Required Completion Date]]-TasksTable412[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable412[[#This Row],[Status]]<>"On Track",TasksTable412[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")

## TR04_Project Plan(Italy)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Define/confirm PS scope for BU's in country. | Both | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Both | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Gasparini, Paolo | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Align Payroll contract and payroll system configuration with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gasparini, Paolo | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 120 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Align T&A systems / contracts with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gasparini, Paolo | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 80 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Define/confirm target organization for this area. | Both | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Gasparini, Paolo | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 32 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Implement target organization structure. | Both | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Gasparini, Paolo | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 40 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | SLA's, policies and procedures aligned with target condition. | Both | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gasparini, Paolo | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 32 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Complete any knowledge transfer/training required for target condition. | Both | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gasparini, Paolo | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 80 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Employee data retention and archiving. | Both | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Gasparini, Paolo | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 32 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Review and update ASAT process, and content. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gasparini, Paolo | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Testing and validation to be prepared for August 1 target condition. | Both | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Gasparini, Paolo | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 160 | PS
TR04 | 223 | Toine Raaymakers_HR | People Services Italy | Operational readiness checkpoint. | Both | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Gasparini, Paolo | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable49[[#This Row],[Required Completion Date]]-TasksTable49[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable49[[#This Row],[Status]]<>"On Track",TasksTable49[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")

## TR05_Project Plan(France)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR05 | 223 | Toine Raaymakers_HR | People Services France | Define/confirm PS scope for BU's in country. | V-A Co. | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR05 | 223 | Toine Raaymakers_HR | People Services France | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | V-A Co. | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Jussiaume, Maryline | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR05 | 223 | Toine Raaymakers_HR | People Services France | Align Payroll contract with target condition. | V-A Co. | TRUE |  | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Jussiaume, Maryline | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 120 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Align T&A systems / contracts with target condition. | V-A Co. | TRUE |  | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Jussiaume, Maryline | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 80 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Define/confirm target organization for this area. | V-A Co. | TRUE |  | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Jussiaume, Maryline | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 24 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Implement target organization structure. | V-A Co. | TRUE |  | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Jussiaume, Maryline | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 40 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | SLA's, policies and procedures aligned with target condition. | V-A Co. | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Jussiaume, Maryline | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 32 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Complete any knowledge transfer/training required for target condition. | V-A Co. | TRUE |  | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Jussiaume, Maryline | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 96 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Employee data retention and archiving. | V-A Co. | TRUE |  | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Jussiaume, Maryline | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 40 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Review and update ASAT process, and content. | V-A Co. | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Jussiaume, Maryline | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Testing and validation to be prepared for August 1 target condition. | V-A Co. | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Jussiaume, Maryline | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 200 | PS |  |  | 80
TR05 | 223 | Toine Raaymakers_HR | People Services France | Operational readiness checkpoint. | V-A Co. | TRUE |  | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Jussiaume, Maryline | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable4[[#This Row],[Required Completion Date]]-TasksTable4[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable4[[#This Row],[Status]]<>"On Track",TasksTable4[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ17: raaymt: depends on any unexpected seperation activities.

## TR06_Project Plan(Hungary)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Define/confirm PS scope for BU's in country. | Both | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Both | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Toth, Ildiko | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 40 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Align Payroll contract and payroll system configuration with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Toth, Ildiko | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 200 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Align T&A systems / contracts with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Toth, Ildiko | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 200 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Define/confirm target organization for this area. | Both | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Toth, Ildiko | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 16 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Implement target organization structure. | Both | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Toth, Ildiko | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 16 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | SLA's, policies and procedures aligned with target condition. | Both | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Toth, Ildiko | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 20 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Complete any knowledge transfer/training required for target condition. | Both | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Toth, Ildiko | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 200 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Employee data retention and archiving. | Both | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Toth, Ildiko | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 40 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Review and update ASAT process, and content. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Toth, Ildiko | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Testing and validation to be prepared for August 1 target condition. | Both | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Toth, Ildiko | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 200 | PS
TR06 | 223 | Toine Raaymakers_HR | People Services Hungary | Operational readiness checkpoint. | Both | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Toth, Ildiko | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable41215[[#This Row],[Required Completion Date]]-TasksTable41215[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable41215[[#This Row],[Status]]<>"On Track",TasksTable41215[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ12: tothi3: includes also payroll systen configuration if as needed
Note on AZ18: tothi3: depending if old data needs to be split as well or only current employee information

## TR07_Project Plan(North UK)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Define/confirm PS scope for BU's in country. | V-A Co. | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | V-A Co. | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 100% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Gregory, Mark | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Align Payroll contract and payroll system configuration with target condition. | V-A Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 16 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Align T&A systems / contracts with target condition. | V-A Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 40 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Define/confirm target organization for this area. | V-A Co. | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Gregory, Mark | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 16 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Implement target organization structure. | V-A Co. | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Gregory, Mark | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 16 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | SLA's, policies and procedures aligned with target condition. | V-A Co. | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 16 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Complete any knowledge transfer/training required for target condition. | V-A Co. | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 60 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Employee data retention and archiving. | V-A Co. | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Gregory, Mark | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 16 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Review and update ASAT process, and content. | V-A Co. | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Testing and validation to be prepared for August 1 target condition. | V-A Co. | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Gregory, Mark | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 120 | PS
TR07 | 223 | Toine Raaymakers_HR | People Services North UK | Operational readiness checkpoint. | V-A Co. | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Gregory, Mark | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable413[[#This Row],[Required Completion Date]]-TasksTable413[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable413[[#This Row],[Status]]<>"On Track",TasksTable413[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ20: raaymt: assume 4 FTE for 3 days for testing.

## TR08_Project Plan(North NL_BE)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Define/confirm PS scope for BU's in country. | Both | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Both | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Gregory, Mark | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Align Payroll contract and payroll system configuration with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 80 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Align T&A systems / contracts with target condition. | Both | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 80 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Define/confirm target organization for this area. | Both | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Gregory, Mark | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 16 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Implement target organization structure. | Both | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Gregory, Mark | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 40 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | SLA's, policies and procedures aligned with target condition. | Both | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 32 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Complete any knowledge transfer/training required for target condition. | Both | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 80 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Employee data retention and archiving. | Both | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Gregory, Mark | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 32 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Review and update ASAT process, and content. | Both | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Testing and validation to be prepared for August 1 target condition. | Both | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Gregory, Mark | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 160 | PS
TR08 | 223 | Toine Raaymakers_HR | People Services North NL/BE | Operational readiness checkpoint. | Both | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Gregory, Mark | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable49101416[[#This Row],[Required Completion Date]]-TasksTable49101416[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable49101416[[#This Row],[Status]]<>"On Track",TasksTable49101416[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")

## TR09_Project Plan(North Norway)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Define/confirm PS scope for BU's in country. | Up. Co. | TRUE | MPS_1 | 2016-02-01 | 100% | 2016-01-31 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Up. Co. | TRUE | MPS_2 | 2016-02-29 | 100% | 2016-02-28 | 100% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Gregory, Mark | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Align Payroll contract and payroll system configuration with target condition. | Up. Co. | TRUE | MPS_10 | 2016-06-01 | 10% | 2016-05-31 21:36 | 5% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 16 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Align T&A systems / contracts with target condition. | Up. Co. | TRUE | MPS_10 | 2016-06-01 | 10% | 2016-05-31 21:36 | 5% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 40 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Define/confirm target organization for this area. | Up. Co. | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Gregory, Mark | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 16 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Implement target organization structure. | Up. Co. | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Gregory, Mark | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 16 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | SLA's, policies and procedures aligned with target condition. | Up. Co. | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 16 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Complete any knowledge transfer/training required for target condition. | Up. Co. | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 60 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Employee data retention and archiving. | Up. Co. | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Gregory, Mark | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 16 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Review and update ASAT process, and content. | Up. Co. | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Testing and validation to be prepared for August 1 target condition. | Up. Co. | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Gregory, Mark | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 120 | PS
TR09 | 223 | Toine Raaymakers_HR | People Services North Norway | Operational readiness checkpoint. | Up. Co. | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Gregory, Mark | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable49101417[[#This Row],[Required Completion Date]]-TasksTable49101417[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable49101417[[#This Row],[Status]]<>"On Track",TasksTable49101417[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ20: raaymt: assume 4 FTE for 3 days for testing.

## TR10Project Plan(North Iceland)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Define/confirm PS scope for BU's in country. | Up. Co. | TRUE | MPS_1 | 2016-02-01 | 20 | 2016-01-12 | 100% | TRUE | Depends on PS strategy provided by SPO or the BU leadership. | Raaymakers, Toine | Complete | Confirm scope of services to be delivered from Day 1. Validate 'like-for-like' assumption. |  |  |  |  | 2016-02-01 |  |  | 2016-02-01 | [24 empty] | Review | 24 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | Up. Co. | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 100% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Gregory, Mark | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Align Payroll contract and payroll system configuration with target condition. | Up. Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 16 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Align T&A systems / contracts with target condition. | Up. Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 40 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Define/confirm target organization for this area. | Up. Co. | TRUE | MPS_24 | 2016-04-01 | 120 | 2015-12-03 | 50% | TRUE | Depends on PS strategy and presence of future companies in the region (GSS LT). | Gregory, Mark | On Track | Define target organization structure assuming 'like-for-like' scope and services to start with and to be aligned with the final target condition thereafter. | [7 empty] | 2016-02-01 | [24 empty] | No Review | 16 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Implement target organization structure. | Up. Co. | TRUE | MPS_24 | 2016-06-01 | 90 | 2016-03-03 | 0% | TRUE | Depends on agreed upon target organization (GSS LT) and HR organization to implement changes (e.g. contractual impact). | Gregory, Mark | Not Started | Implement Defined organization structure. Align with HR and country organizations. |  |  |  |  | 2016-03-01 | [27 empty] | No Review | 16 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | SLA's, policies and procedures aligned with target condition. | Up. Co. | TRUE |  | 2016-07-01 | 90 | 2016-04-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 16 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Complete any knowledge transfer/training required for target condition. | Up. Co. | TRUE | MPS_25 | 2016-07-01 | 60 | 2016-05-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 60 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Employee data retention and archiving. | Up. Co. | TRUE | MPS_19 | 2016-07-20 | 120 | 2016-03-22 | 0% | TRUE | Depends on overall target condition but this is mainly GSS PS internal work to be completed. Consider to evaluate with legal. IT support. | Gregory, Mark | Not Started | Consider any in-country legal requirements. Work with IT on storage, migration (e.g. sharepoint). |  |  |  | 2016-02-11 |  | 2016-02-11 | [26 empty] | No Review | 16 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Review and update ASAT process, and content. | Up. Co. | TRUE |  | 2016-08-01 | 60 | 2016-06-02 | 0% | FALSE | This is mainly GSS PS internal work to be completed. | Gregory, Mark | Not Started | Allocate this work by means of subtasks to other employees and consider backfil when needed to assure continuation of operational processes. | [32 empty] | No Review | 40 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Testing and validation to be prepared for August 1 target condition. | Up. Co. | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Gregory, Mark | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 120 | PS
TR10 | 223 | Toine Raaymakers_HR | People Services North Iceland | Operational readiness checkpoint. | Up. Co. | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Gregory, Mark | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable491014[[#This Row],[Required Completion Date]]-TasksTable491014[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable491014[[#This Row],[Status]]<>"On Track",TasksTable491014[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ20: raaymt: assume 4 FTE for 3 days for testing.

## TR12Project Plan(Germany)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR11 | 228 | Toine Raaymakers_HR | People Services North Germany | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | V-A Co. | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Gregory, Mark | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR11 | 228 | Toine Raaymakers_HR | People Services North Germany | Align Payroll contract and payroll system configuration with target condition. | V-A Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 16 | PS
TR11 | 228 | Toine Raaymakers_HR | People Services North Germany | Align T&A systems / contracts with target condition. | V-A Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Gregory, Mark | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 40 | PS
TR11 | 228 | Toine Raaymakers_HR | People Services North Germany | Testing and validation to be prepared for August 1 target condition. | V-A Co. | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Gregory, Mark | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 120 | PS
TR11 | 228 | Toine Raaymakers_HR | People Services North Germany | Operational readiness checkpoint. | V-A Co. | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Gregory, Mark | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable49101411[[#This Row],[Required Completion Date]]-TasksTable49101411[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable49101411[[#This Row],[Status]]<>"On Track",TasksTable49101411[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ13: raaymt: assume 4 FTE for 3 days for testing.

## TR13Project Plan(SmallC)
Project Elevation
[Function] High-Level Separation Workplan - Project Plan(s) - [Project]
| As Of | 2016-02-19 13:28
| Task-Level Description | [15 empty] | Dependency Resolution Checklist
Project # | Task ID [SWS-Activity-Task] | Sub-Workstream (SWS) | Day 1 Project Name | Task Name | V-A Co, Up. Co, or Both | Milestone (True / False) | Common Milestone ID | Required Completion Date | Days to Accomplish | Start Date (Calculated) | % Complete | Dependencies (True / False) Flag Specifics -> | Dependencies Description | Owner | Status | Comments / Notes (Subtasks, status explanations, etc.) | Finance | Tax | Treasury | Legal | HR | IT | Branding | Global Shared Services (GSS) | Carve-out Financials / Form 10 | Procurement | EHS | IPAM | Quality | Growth & Market Strategy | Shared Sites / Real Estate | Gov't Affairs | Alcoa Technical Center (ATC) | China / Asia Region | Australia Region | Europe Region | LATAM Region | Canada | Investor Relations (IR) | Audit | Transportation | Aircraft / Security | Alcoa Ventures | Org Design and Selection | Communications | Corporate Affairs | Other | List Others (if appl) | For GSS PMO Review? | Internal Resource Work Hours Required (Team 1) | Internal Team 1 Description | Internal Resource Work Hours Required (Team 2) | Internal Team 2 Description | External Resource Work Hours
TR12 | 229 | Toine Raaymakers_HR | People Services Small Countries | Define/confirm Payroll, T&A and other (e.g. recruitment) systems strategy for the country. | V-A Co. | TRUE | MPS_2 | 2016-02-29 | 20 | 2016-02-09 | 90% | TRUE | Depends on potential business case to align with long term strategy (probably only for UpStream in Hungary, otherwise to confirm current strategy). Need GSS LT and potentially procurement. | Toth, Ildiko | On Track | Validate and confirm current systems strategy against target condition. Specially in case of shared countries. Include any benefits, pensions, medical schemes considerations and actions required (depending on specific country situation). | [7 empty] | 2016-02-01 |  | 2016-02-01 | [22 empty] | No Review | 32 | PS
TR12 | 229 | Toine Raaymakers_HR | People Services Small Countries | Align Payroll contract and payroll system configuration with target condition. | V-A Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Toth, Ildiko | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 16 | PS
TR12 | 229 | Toine Raaymakers_HR | People Services Small Countries | Align T&A systems / contracts with target condition. | V-A Co. | TRUE | MPS_10 | 2016-06-01 | 120 | 2016-02-02 | 10% | TRUE | Depends on legal regarding new legal entities and procurement to work with on contract changes and vendor negotiation. IT support. | Toth, Ildiko | On Track | For '1 on 1' countries it might only be a name change in the case of ValueAdd. For shared countries the contract needs to be separated across the two target companies. |  |  |  | 2016-02-01 |  | 2016-02-01 |  |  |  | 2016-02-02 | [22 empty] | No Review | 40 | PS
TR12 | 229 | Toine Raaymakers_HR | People Services Small Countries | Testing and validation to be prepared for August 1 target condition. | V-A Co. | TRUE | MPS_26 | 2016-08-01 | 60 | 2016-06-02 | 0% | TRUE | Other GSS and BBHR teams to assure E2E testing and validation. | Toth, Ildiko | Not Started | Unit testing to be considered in the earlier tasks. This activity considers integration testing of systems and procedures to assure E2E processes are meeting target requirements. | [32 empty] | No Review | 120 | PS
TR12 | 229 | Toine Raaymakers_HR | People Services Small Countries | Operational readiness checkpoint. | V-A Co. | TRUE | MPS_23 | 2016-08-01 | 5 | 2016-07-27 | 0% | TRUE | Evaluate across GSS and BBHR. | Toth, Ildiko | Not Started | Go/no go and/or sign-off/confirmation. | [7 empty] | 2016-07-01 | [24 empty] | No Review | 16 | PS
x
Formulas:
Start Date (Calculated) = TasksTable4910141118[[#This Row],[Required Completion Date]]-TasksTable4910141118[[#This Row],[Days to Accomplish]]
For GSS PMO Review? = IF(AND(TasksTable4910141118[[#This Row],[Status]]<>"On Track",TasksTable4910141118[[#This Row],[Start Date (Calculated)]]<TODAY()+7),"Review","No Review")
Note on AZ13: raaymt: assume 4 FTE for 3 days for testing.

## Day 1 Project Costs_TR
Project Elevation
[Function] High-Level Separation Workplan - Day 1 Project Costs
As Of | 2016-02-19 13:28
Project ID (WS-SWS-Activity) | Day 1 Project Name | Description | Dis-synergy | One-time | Owner | Estimated Value | Rationale

## Data Validation (hide) (hidden)
Master Function List | Sub-function list
Legal | Legal | HumanResources | FinanceandAccounting | OCIO | InvestorRelations | Communications | GPI | GlobalBilling | BusinessUnitFunctions | Yes/No | Day 1 Target State | TSA Feasibility | TSA Exit Activities
Human Resources | Benefits | HR Systems | Treasury | PMO | Investor Relations | Inc. PR | Business Office | Operational | Strategy | Yes | Replicate (Clone) | Possible - Low/Medium Complexity | Replicate (Clone)
Finance and Accounting | Stock Systems | GTA | FP&A | Facilities |  | Internal | Operations | Systems | Sales & Business Development | No | Give and Go | Possible - Very Complex | Give and Go
OCIO | Competition | MyHR | Tax | HR Systems |  | Brand / EVP | Tools |  | Marketing |  | New Build | Impossible | New Build
Investor Relations | Corporate | Comp/Ben/M&A | AP | Other Enabling Sys |  | Social Innovation | Services |  | Risk |  | Forward TSA | Not Required | Standalone
Communications | Employment | L&OD | Travel | Finance Systems |  |  | Platform |  | Trust & Safety |  | Reverse TSA |  | Discontinue
GPI | Compliance | Diversity | Purchasing | CS Systems |  |  | Data |  | CS |  | Standalone |  | Operating Agreement
Global Billing | Government Relations |  | Payroll | Traditional IT Systems |  |  | Infrastructure/Cloud |  | PD / Arch |  | Discontinue
Business Unit Functions | IP |  | Finance Separation |  |  |  | Data Center |  | Product |  | Operating Agreement
| Privacy |  | Accounting Policy | [5 empty] | Data
| Litigation |  | SEC Reporting | [5 empty] | Info Security
| Real Estate |  | SOX | [5 empty] | Regulatory
Finance Trans
Procurement

## Countries (hidden)
# | Location Country | Total Employees
1 | USA Total |  | USA | USA | FRA | GBR | CAN | DEU | IND | AUS | SWE | MEX | BEL | HKG | SGP | CHE | ARG | NLD | DNK | TWN | POL | NOR | THA | CZE | GRC | HUN | MCO | ESP | LUX | FIN | JPN | NZL | BRA | CHN | IRL | MYS | RUS
2 | FRA Total |  | FRA | USA: USA,FRA,GBR,CAN,DEU,IND,AUS,SWE,MEX,BEL,HKG,SGP,CHE,ARG,NLD,DNK,TWN,POL,NOR,THA,CZE,GRC,HUN,MCO,ESP,LUX,FIN,JPN,NZL,BRA,CHN,IRL,MYS,RUS
3 | GBR Total |  | GBR
4 | CAN Total |  | CAN
5 | DEU Total |  | DEU
6 | IND Total |  | IND
7 | AUS Total |  | AUS
8 | SWE Total |  | SWE
9 | MEX Total |  | MEX
10 | BEL Total |  | BEL
11 | HKG Total |  | HKG
12 | SGP Total |  | SGP
13 | CHE Total |  | CHE
14 | ARG Total |  | ARG
15 | NLD Total |  | NLD
16 | DNK Total |  | DNK
17 | TWN Total |  | TWN
18 | POL Total |  | POL
19 | NOR Total |  | NOR
20 | THA Total |  | THA
21 | CZE Total |  | CZE
22 | GRC Total |  | GRC
23 | HUN Total |  | HUN
24 | MCO Total |  | MCO
25 | ESP Total |  | ESP
26 | LUX Total |  | LUX
27 | FIN Total |  | FIN
28 | JPN Total |  | JPN
29 | NZL Total |  | NZL
30 | BRA Total |  | BRA
31 | CHN Total |  | CHN
32 | IRL Total |  | IRL
33 | MYS Total |  | MYS
34 | RUS Total |  | RUS
Grand Total

## Milestones_PS_Payroll
Updated as of 1 Feb 2016
|  |  | HUB Brazil | HUB Hungary | HUB Hungary | Spain | Switzerland | Italy | France | North UK | North N/L B/E | Germany | North Norway | North Iceland | US | CAN | MEX | AUS | RUS
|  |  | TN12, TN13, TN14, TN15, TN16 | TR01 | TR06 | TR02 | TR03 | TR04 | TR05 | TR07 | TR08 |  | TR09 | TR10 | HC08, HC09, HC10, HC11, HC12, HC13, HC19, HC20, HC21, HC22 | AT01,AT13,AT14,AT15, AT16, AT26 | AT07, AT25 | CAR05 | CAR02
|  | Payroll Model (Vendor or In-house) / System | ApData (Antares) | N/A | In-House/ Xber | Vendor/Conktia | Vendor/Applic8 | Vendor/Feinar | Vendor/Teams | Vendor/Nortgate | Vendor/ADP | Vendor/Datev | Vendor/Visma | Vendor/H3 | Hewitt/Peoplesoft | Desjardins | TRES | Vendor/inhouse | Boss Kadrovik (vendor)
|  | T&A Model (Vendor or In-house) | In-House (Ronda) | N/A | In-House/Winaccess | In-house/Spec | In-house | In-house/TPC&Join | In-house/Horoquartz | In-house/Mitrefinch | In-house/Pronet | In-house/various | In-house/Wintid | In-house/Vinnestund | Workbrain/Various | Kronos | TREs | na | In house
|  | UP Co # Employees | 2100 |  | 130 | 1950 | 14 | 17 | 0 | 0 | 20 | 0 | 1050 | 540 | 1500 Active/27500 est retirees | 2500 |  | 4000 | 0
|  | VA Co # Employees | 1900 |  | 2000 | 25 | 20 | 318 | 2900 | 2960 | 180 | 1530 | 0 | 0 | 20000 Active/50000 est retirees | 1000 | 2000 | 200 | 3058
APPLI | Common Milestone ID# | People Services Separation Strategy Milestone
y | MPS_1 | Define/confirm target GSS organization structures to support scope of services for both companies. | 2016-02-29 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-04-30 | 2016-02-12 | 2016-02-12 | 2016-02-12 | 2016-02-12
| # | IT System Separation Milestone
Y | MPS_2 | Determine IT system requirements and strategy by country | 2016-02-29 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-29 | 2016-02-28 | 2016-04-15 | 2016-02-29
| MPS_3 | Align IT systems strategy with IT organization | 2016-03-04 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-02-15 |  | 2016-03-30 | 2016-05-15 | 2016-03-15
| MPS_4 | Obtain system scope of work and timeline from vendor to stand- up second system | 2016-03-15 | 2016-03-01 | 1-Mar-2016 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-21 | 2016-04-15 | 2016-05-15
| MPS_5 | Obtain IT sign off for vendor owned system scope of work |  | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-15 | 2016-03-31 | 2016-05-01 | 2016-05-01
| MPS_6 | Procurement to execute vendor owned system scope of work for standing up second system | 2016-02-29 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 |  | 2016-03-31
| MPS_7 | Vendor commences work to stand-up separate system | 2016-05-01 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 2016-03-01 | 2016-04-01
| MPS_8 | Stakeholder Sign off on vendor completion of standing up second system | 2016-06-30 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 31-Mar-2016 | 2016-07-31 | 2016-05-01
| MPS_9 | Obtain final Value Add Co and Upstream organization structures to set up in People Services IT Systems | 2016-06-30 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-31 | 2016-03-01 |  | 2016-03-30
Y | MPS_10 | Complete IT system configuration with target condition in preparation for testing | 2016-07-31 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | TBD | 2016-04-01 |  | 2016-04-15
| MPS_11 | Participate in EBS Oracle- Test Test Event 1- 3/15- 4/15 | 2016-04-15 |  | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15 |  | 2016-04-15 | 2016-04-15 |  | 2016-04-15 | 2016-04-15 | 2016-04-15 | 2016-04-15
| MPS_12 | Participate in EBS Oracle - CRP testing 4/18 - 5/20 | 2016-05-20 |  | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20
| MPS_13 | Participate in EBS Oracle - UAT testing 5/23 - 7/8 | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08
| MPS_14 | Participate in GPS Testing- Test Test Event 1 | 2016-02-29: 2016-04-15 | TBD
| MPS_15 | Participate in GPS Testing - CRP testing | 2016-02-29: 2016-05-20 | TBD
| MPS_16 | Participate in GPS Testing - UAT testing | 2016-02-29: 2016-07-08 | TBD
| MPS_17 | Vendor owned IT System/Application testing | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 |  | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08 | 2016-07-08
| MPS_18 | Work with Legal on the Safe Harbor agreement - especially for the locations in Europe and US that have the services provided from the HUB | [12 empty] | 2016-04-30 | bar: 2016-02-29
| MPS_19 | Complete employee physical and electronic data purging | 2016-06-30 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
| MPS_20 | Complete the Testing of critical processes for Compensation (Hourly performance pay, compensation planning) and Talent Management (goal reporting, end cycle). | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
| MPS_21 | Single Sign on - Remediate Single Sign on and define a solution for external SSO that works for the 2 companies within GPS. Includes testing the solution with all 3rd party vendors and internal applications. | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
| MPS_22 | Participate in EBS Oracle - Cutover 7/15 - 7/31 - established live production system - if needed | 2016-02-29: 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-15
Y | MPS_23 | Operational readiness checkpoint completed with any gaps identified and action plans developed to ensure organizations, processes, and systems are ready for OD1. | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
| # | GSS People Services Organization Separation Milestones
Y | MPS_24 | Finalize the implementation of the new target GSS PS organizations for Value Add Co. and Upstream Co. | 2016-07-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 |  | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31
Y | MPS_25 | Complete GSS employee knowledge transfer/training required for the new GSS Value Add and Upstream organizations. | 2016-07-31 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 |  | 2016-06-30 | 2016-06-30 | 2016-07-31 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
| MPS_26 | Validate the Support Model is in place prior to the separation (Kiosks, HR Portal, HR Call Center and Escalation Level) | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 |  | 2016-06-30 | 2016-06-30 | 2016-08-01 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
Not applicable
On Track
Not started
At Risk
Off Track
Completed

## Sheet1
People Services Global HUB Europe | TR01
People Services Spain | TR02
People Services Switzerland | TR03
People Services Italy | TR04
People Services France | TR05
People Services Hungary | TR06
People Services North UK | TR07
People Services North NL/BE | TR08
People Services North Norway | TR09
People Services North Iceland | TR10
People Services Regional HUB Europe | TR11

## PMO Review
Tasks indicated for 'Review' by PMO
Day 1 Project List_TR tab (Overall view pf projects) |  | 0
People Services Global HUB Europe | TR01 | 1
People Services Spain | TR02 | 1
People Services Switzerland | TR03 | 1
People Services Italy | TR04 | 1
People Services France | TR05 | 1
People Services Hungary | TR06 | 1
People Services North UK | TR07 | 1
People Services North NL/BE | TR08 | 1
People Services North Norway | TR09 | 1
People Services North Iceland | TR10 | 1